## Utility Tracking Log
Today is: | 2015-08-05
[9 empty] | Bridge Data | [7 empty] | Utility Data
Calculated
Line Number | Early Completion (Y/N) | JV # | Bridge Key # | MPMS # | BMS # | District | County | Location | Feature Carried | Feature Intersected | Municipality Code | Latitude | Longitude | Pa One Call Serial No. | Utility Type | Utility Owner | Utility Owner Contact | Overhead or Underground | Size | D-419 Utility Relocation Classification | Anticipated Construction Start Date
1a | -- | 1 | 12879 | 97120 | 20000604100000 | 1 | Crawford | VERNON TOWNSHIP | SR 6,GRAND ARMY HY | OVER TR CONNEAUT LK OUT | 20/230 - VERNON | 41.6151 | -80.2379 | 20150351072 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2017-05-11
1b | -- | 1 | 12879 | 97120 | 20000604100000 | 1 | Crawford | VERNON TOWNSHIP | SR 6,GRAND ARMY HY | OVER TR CONNEAUT LK OUT | 20/230 - VERNON | 41.6151 | -80.2379 | 20150351072 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com |  |  |  | 2017-05-11
2a | -- | 2 | 12902 | 90155 | 20000608400273 | 1 | Crawford | CAMBRIDGE TOWNSHIP | SR 6,LAKES TO SEA | OVER FRENCH CREEK TRIB #3 | 20/204 - CAMBRIDGE | 41.7962 | -80.0781 | 20150341823 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2016-08-08
2b | -- | 2 | 12902 | 90155 | 20000608400273 | 1 | Crawford | CAMBRIDGE TOWNSHIP | SR 6,LAKES TO SEA | OVER FRENCH CREEK TRIB #3 | 20/204 - CAMBRIDGE | 41.7962 | -80.0781 | 20150341823 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com |  |  |  | 2016-08-08
2c | -- | 2 | 12902 | 90155 | 20000608400273 | 1 | Crawford | CAMBRIDGE TOWNSHIP | SR 6,LAKES TO SEA | OVER FRENCH CREEK TRIB #3 | 20/204 - CAMBRIDGE | 41.7962 | -80.0781 | 20150341823 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com |  |  |  | 2016-08-08
3 | -- | 3 | 13084 | 97121 | 20028501000629 | 1 | Crawford | NORTH SHENANGO TOWNSHIP | SR 285,LICKING ST | OVER BENNETT RUN | 20/213 - NORTH SHENANGO | 41.6021 | -80.4312 | 20151473198 |  | all facilities responded clear per one call |  |  |  |  | 2017-07-10
4a | -- | 4 | 13122 | 97117 | 20040801800428 | 1 | Crawford | RICHMOND TOWNSHIP | SR 408,CHURCH ST | OVER TEMPLE RUN | 20/217 - RICHMOND | 41.7483 | -79.9407 | 20143580160 | Gas | Laurel Mountain Midstream LLC | Delbert Woloski, 724-301-2499 , delbert.woloski@williams.com | UG |  |  | 2016-05-13
4b | -- | 4 | 13122 | 97117 | 20040801800428 | 1 | Crawford | RICHMOND TOWNSHIP | SR 408,CHURCH ST | OVER TEMPLE RUN | 20/217 - RICHMOND | 41.7483 | -79.9407 | 20143580160 |  | Richmond TWP | Charlie Hartman, 814-967-3822, richmondtwprc@windstream.net |  |  |  | 2016-05-13
4c | -- | 4 | 13122 | 97117 | 20040801800428 | 1 | Crawford | RICHMOND TOWNSHIP | SR 408,CHURCH ST | OVER TEMPLE RUN | 20/217 - RICHMOND | 41.7483 | -79.9407 | 20143580160 | Comm | Verizon North LLC | Eric Rodrigues, 814 871-2317, eric.rodrigues@verizon.com |  |  |  | 2016-05-13
4d | -- | 4 | 13122 | 97117 | 20040801800428 | 1 | Crawford | RICHMOND TOWNSHIP | SR 408,CHURCH ST | OVER TEMPLE RUN | 20/217 - RICHMOND | 41.7483 | -79.9407 | 20143580160 | Comm | Armstrong | Mike Schuwerk, 814-333-6731 X 224, mschuwerk@agoc.com |  |  |  | 2016-05-13
5a | -- | 5 | 13128 | 97118 | 20040805201643 | 1 | Crawford | HYDETOWN BOROUGH | SR 408,THOMPSON ST | OVER THOMPSON CREEK | 20/407 - HYDETOWN | 41.6514 | -79.7261 | 20150161005 | Storm | Hydetown Borough | Pat Myer, hydetownboro@yahoo.com | UG |  |  | 2016-05-23
5b | -- | 5 | 13128 | 97118 | 20040805201643 | 1 | Crawford | HYDETOWN BOROUGH | SR 408,THOMPSON ST | OVER THOMPSON CREEK | 20/407 - HYDETOWN | 41.6514 | -79.7261 | 20150161005 | Comm | Armstrong | Keith Smith, ksmith@agoc.com |  |  |  | 2016-05-23
5c | -- | 5 | 13128 | 97118 | 20040805201643 | 1 | Crawford | HYDETOWN BOROUGH | SR 408,THOMPSON ST | OVER THOMPSON CREEK | 20/407 - HYDETOWN | 41.6514 | -79.7261 | 20150161005 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2016-05-23
5d | -- | 5 | 13128 | 97118 | 20040805201643 | 1 | Crawford | HYDETOWN BOROUGH | SR 408,THOMPSON ST | OVER THOMPSON CREEK | 20/407 - HYDETOWN | 41.6514 | -79.7261 | 20150161005 |  | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com |  |  |  | 2016-05-23
6a | -- | 6 | 13027 | 89176 | 20088601600750 | 1 | Crawford | WOODCOCK BOROUGH | SR 886,MAIN STREET | OVER GRAVEL RUN | 20/414 - WOODCOCK | 41.7519 | -80.0878 | 20150350248 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2017-03-27
6b | -- | 6 | 13027 | 89176 | 20088601600750 | 1 | Crawford | WOODCOCK BOROUGH | SR 886,MAIN STREET | OVER GRAVEL RUN | 20/414 - WOODCOCK | 41.7519 | -80.0878 | 20150350248 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com |  |  |  | 2017-03-27
6c | -- | 6 | 13027 | 89176 | 20088601600750 | 1 | Crawford | WOODCOCK BOROUGH | SR 886,MAIN STREET | OVER GRAVEL RUN | 20/414 - WOODCOCK | 41.7519 | -80.0878 | 20150350248 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com |  |  |  | 2017-03-27
7a | -- | 7 | 13367 | 97124 | 20401100200000 | 1 | Crawford | HAYFIELD TOWNSHIP | SR 4011,MOSIERTOWN | OVER WOLF RUN TRIB | 20/212 - HAYFIELD | 41.7327 | -80.1616 | 20150340926 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2016-08-18
7b | -- | 7 | 13367 | 97124 | 20401100200000 | 1 | Crawford | HAYFIELD TOWNSHIP | SR 4011,MOSIERTOWN | OVER WOLF RUN TRIB | 20/212 - HAYFIELD | 41.7327 | -80.1616 | 20150340926 | Gas | KASTLE RESOURCES ENTERPRISES INC | Jesse Welcheck, 814-602-6231, jwelcheck25@gmail.com | UG |  |  | 2016-08-18
7c | -- | 7 | 13367 | 97124 | 20401100200000 | 1 | Crawford | HAYFIELD TOWNSHIP | SR 4011,MOSIERTOWN | OVER WOLF RUN TRIB | 20/212 - HAYFIELD | 41.7327 | -80.1616 | 20150340926 | sanitary | SAEGERTOWN AREA SEWER AUTHORITY | Matt Handley, 724-814-7503 | UG |  |  | 2016-08-18
8 | -- | 8 | 16373 | 1140 | 25401100800860 | 1 | Erie | MILL CREEK TOWNSHIP | SR 4011,GRUBB ROAD | OVER WALNUT CREEK | 25/213 - MILLCREEK | 42.0566 | -80.1481 | 20151473231 | Gas | National Fuel/National Fuel Supply Erie | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2017-09-08
9 | -- | 9 | 17195 | 74663 | 27006201302194 | 1 | Forest | TIONESTA BOROUGH | SR 62,ELM STREET | OVER TUBBS RUN | 27/401 - TIONESTA | 41.5088 | -79.4497 | 20150410270 | Comm | Armstrong | Keith Smith, ksmith@agoc.com |  |  |  | 2017-03-27
10a | -- | 10 | 17207 | 1370 | 27066600700000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5867 | -79.3548 | 20150161022 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2016-06-17
10b | -- | 10 | 17207 | 1370 | 27066600700000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5867 | -79.3548 | 20150161022 | Comm | Armstrong | Keith Smith, ksmith@agoc.com |  |  |  | 2016-06-17
10c | -- | 10 | 17207 | 1370 | 27066600700000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5867 | -79.3548 | 20150161022 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com |  |  |  | 2016-06-17
10d | -- | 10 | 17207 | 1370 | 27066600700000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5867 | -79.3548 | 20150161022 | Elect | Pennsylvania Electric Company | Charles Vroman, 814-676-7540, cvroman@firstenergycorp.com |  |  |  | 2016-06-17
10e | -- | 10 | 17207 | 1370 | 27066600700000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5867 | -79.3548 | 20150161022 |  | Hickory TWP | Nicholas Melnick, 814-676-5805, hickorytwp@verizon.net |  |  |  | 2016-06-17
11a | -- | 11 | 17208 | 93595 | 27066600900000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5858 | -79.3397 | 20151472691 | Comm | ARMSTRONG | Keith Smith, ksmith@agoc.com |  |  |  | 2017-06-05
11b | -- | 11 | 17208 | 93595 | 27066600900000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5858 | -79.3397 | 20151472691 |  | Hickory TWP | Nicholas Melnick, 814-676-5805, hickorytwp@verizon.net |  |  |  | 2017-06-05
11c | -- | 11 | 17208 | 93595 | 27066600900000 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5858 | -79.3397 | 20151472691 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com |  |  |  | 2017-06-05
12a | -- | 12 | 17209 | 1398 | 27066601100240 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5849 | -79.317 | 20150330199 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com |  |  |  | 2016-05-23
12b | -- | 12 | 17209 | 1398 | 27066601100240 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5849 | -79.317 | 20150330199 | Comm | Armstrong | Keith Smith, ksmith@agoc.com |  |  |  | 2016-05-23
12c | -- | 12 | 17209 | 1398 | 27066601100240 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5849 | -79.317 | 20150330199 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com |  |  |  | 2016-05-23
12d | -- | 12 | 17209 | 1398 | 27066601100240 | 1 | Forest | HICKORY TOWNSHIP | SR 666,D ZEIS HWY | OVER BEAVER RUN | 27/204 - HICKORY | 41.5849 | -79.317 | 20150330199 |  | Hickory TWP | Nicholas Melnick, 814-676-5805, hickorytwp@verizon.net |  |  |  | 2016-05-23
13a | -- | 13 | 25833 | 97328 | 43017304703518 | 1 | Mercer | NEW LEBANON BOROUGH | SR 173,COCHRANTON | OVER MILL CREEK | 43/408 - NEW LEBANON | 41.4087 | -80.0752 | 20151473445 | Comm | ARMSTRONG | Keith Smith, ksmith@agoc.com |  |  |  | 2017-08-21
13b | -- | 13 | 25833 | 97328 | 43017304703518 | 1 | Mercer | NEW LEBANON BOROUGH | SR 173,COCHRANTON | OVER MILL CREEK | 43/408 - NEW LEBANON | 41.4087 | -80.0752 | 20151473445 | Gas | Vista Resources Inc | 412-833-8884, info@vistaresources.com | UG |  |  | 2017-08-21
13c | -- | 13 | 25833 | 97328 | 43017304703518 | 1 | Mercer | NEW LEBANON BOROUGH | SR 173,COCHRANTON | OVER MILL CREEK | 43/408 - NEW LEBANON | 41.4087 | -80.0752 | 20151473445 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David (Dave) Ackerman, David.F.Ackerman@windstream.com, 319-790-1464 | Both |  |  | 2017-08-21
13d | -- | 13 | 25833 | 97328 | 43017304703518 | 1 | Mercer | NEW LEBANON BOROUGH | SR 173,COCHRANTON | OVER MILL CREEK | 43/408 - NEW LEBANON | 41.4087 | -80.0752 | 20151473445 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG |  |  | 2017-08-21
14a | -- | 14 | 25858 | 1686 | 43031801500622 | 1 | Mercer | LACKAWANNOCK TOWNSHIP | SR 318,W.MDLSX-MRC | OVER LT NESHANNOCK CK BR | 43/212 - LACKAWANNOCK | 41.1918 | -80.3903 | 20150330486 | GAS | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2017-02-24
14b | -- | 14 | 25858 | 1686 | 43031801500622 | 1 | Mercer | LACKAWANNOCK TOWNSHIP | SR 318,W.MDLSX-MRC | OVER LT NESHANNOCK CK BR | 43/212 - LACKAWANNOCK | 41.1918 | -80.3903 | 20150330486 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG |  |  | 2017-02-24
15 | -- | 15 | 26008 | 58092 | 43302001700000 | 1 | Mercer | JEFFERSON TOWNSHIP | SR 3020,LAMOR ROAD | OVER LACKAWANNOCK CREEK | 43/211 - JEFFERSON | 41.246 | -80.3028 | 20151472948 |  | all facilities responded clear per one call |  |  |  |  | 2017-05-30
16a | -- | 16 | 33765 | 93160 | 60042702200000 | 1 | Venango | PLUM TOWNSHIP | SR 427 | OVER SUGAR CREEK TRIB | 60/214 - PLUM | 41.5748 | -79.8654 | 20150330512 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com | UG |  |  | 2017-02-24
16b | -- | 16 | 33765 | 93160 | 60042702200000 | 1 | Venango | PLUM TOWNSHIP | SR 427 | OVER SUGAR CREEK TRIB | 60/214 - PLUM | 41.5748 | -79.8654 | 20150330512 | Gas | Range Resources | Brian Sprague, 814-425-3100, bsprague@rangeresources.com | UG |  |  | 2017-02-24
16c | -- | 16 | 33765 | 93160 | 60042702200000 | 1 | Venango | PLUM TOWNSHIP | SR 427 | OVER SUGAR CREEK TRIB | 60/214 - PLUM | 41.5748 | -79.8654 | 20150330512 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com |  |  |  | 2017-02-24
17a | -- | 17 | 33788 | 2251 | 60201301000000 | 1 | Venango | CRANBERRY TOWNSHIP | SR 2013,ROCKLAND R | OVER EAST SANDY CREEK | 60/206 - CRANBERRY | 41.3135 | -79.7238 | 20151471285, 20151471286 | Comm | ARMSTRONG | Keith Smith, ksmith@agoc.com |  |  |  | 2017-06-01
17b | -- | 17 | 33788 | 2251 | 60201301000000 | 1 | Venango | CRANBERRY TOWNSHIP | SR 2013,ROCKLAND R | OVER EAST SANDY CREEK | 60/206 - CRANBERRY | 41.3135 | -79.7238 | 20151471285, 20151471286 | Gas | UGI Central Penn Gas | Roy Carr (570) 829-8967 | UG |  |  | 2017-06-01
17c | -- | 17 | 33788 | 2251 | 60201301000000 | 1 | Venango | CRANBERRY TOWNSHIP | SR 2013,ROCKLAND R | OVER EAST SANDY CREEK | 60/206 - CRANBERRY | 41.3135 | -79.7238 | 20151471285, 20151471286 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David (Dave) Ackerman, David.F.Ackerman@windstream.com, 319-790-1464 | Both |  |  | 2017-06-01
17d | -- | 17 | 33788 | 2251 | 60201301000000 | 1 | Venango | CRANBERRY TOWNSHIP | SR 2013,ROCKLAND R | OVER EAST SANDY CREEK | 60/206 - CRANBERRY | 41.3135 | -79.7238 | 20151471285, 20151471286 |  | Rockland TWP | 814-498-2768 |  |  |  | 2017-06-01
17e | -- | 17 | 33788 | 2251 | 60201301000000 | 1 | Venango | CRANBERRY TOWNSHIP | SR 2013,ROCKLAND R | OVER EAST SANDY CREEK | 60/206 - CRANBERRY | 41.3135 | -79.7238 | 20151471285, 20151471286 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2017-06-01
18a | -- | 18 | 33956 | 97457 | 61000603502233 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 6,GRAND ARMY HY | OVER WINTROTH RUN | 61/201 - BROKENSTRAW | 41.8386 | -79.3614 | 20150411787 | sanitary | BROKENSTRAW VALLEY AREA AUTHORITY | Joel Turk, bvaa@verizon.net, Beverly Moore, 814-563-7681 | UG |  |  | 2017-02-21
18b | -- | 18 | 33956 | 97457 | 61000603502233 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 6,GRAND ARMY HY | OVER WINTROTH RUN | 61/201 - BROKENSTRAW | 41.8386 | -79.3614 | 20150411787 | GAS | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2017-02-21
19a | -- | 19 | 33957 | 2438 | 61000603900000 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 6,GRAND ARMY HY | OVER MEAD RUN | 61/201 - BROKENSTRAW | 41.8471 | -79.3363 | 20150340910 | GAS | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2017-03-08
19b | -- | 19 | 33957 | 2438 | 61000603900000 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 6,GRAND ARMY HY | OVER MEAD RUN | 61/201 - BROKENSTRAW | 41.8471 | -79.3363 | 20150340910 | sanitary | BROKENSTRAW VALLEY AREA AUTHORITY | Joel Turk, bvaa@verizon.net, Beverly Moore, 814-563-7681 | UG |  |  | 2017-03-08
19c | -- | 19 | 33957 | 2438 | 61000603900000 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 6,GRAND ARMY HY | OVER MEAD RUN | 61/201 - BROKENSTRAW | 41.8471 | -79.3363 | 20150340910 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com |  |  |  | 2017-03-08
20a | -- | 20 | 33982 | 2546 | 61000608200000 | 1 | Warren | SHEFFIELD TOWNSHIP | SR 6,GRAND ARMY HY | OVER FOUR MILE RUN | 61/218 - SHEFFIELD | 41.7256 | -79.0548 | 20151472392 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2017-06-02
20b | -- | 20 | 33982 | 2546 | 61000608200000 | 1 | Warren | SHEFFIELD TOWNSHIP | SR 6,GRAND ARMY HY | OVER FOUR MILE RUN | 61/218 - SHEFFIELD | 41.7256 | -79.0548 | 20151472392 | Gas | National Fuel/National Fuel Supply Roystone | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2017-06-02
20c | -- | 20 | 33982 | 2546 | 61000608200000 | 1 | Warren | SHEFFIELD TOWNSHIP | SR 6,GRAND ARMY HY | OVER FOUR MILE RUN | 61/218 - SHEFFIELD | 41.7256 | -79.0548 | 20151472392 | Gas | SLT Production LLC FRMLY Sheffield Land | 814-723-8650, 13 Six Mile Road Sheffield PA 16347 | UG |  |  | 2017-06-02
21a | -- | 21 | 34001 | 2580 | 61002705203359 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 27,NORTH MAIN | OVER HAZELTINE HOLLOW RUN | 61/201 - BROKENSTRAW | 41.904 | -79.3447 | 20150340945 | GAS | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2016-08-18
21b | -- | 21 | 34001 | 2580 | 61002705203359 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 27,NORTH MAIN | OVER HAZELTINE HOLLOW RUN | 61/201 - BROKENSTRAW | 41.904 | -79.3447 | 20150340945 | sanitary | BROKENSTRAW VALLEY AREA AUTHORITY | Joel Turk, bvaa@verizon.net, Beverly Moore, 814-563-7681 | UG |  |  | 2016-08-18
21c | -- | 21 | 34001 | 2580 | 61002705203359 | 1 | Warren | BROKENSTRAW TOWNSHIP | SR 27,NORTH MAIN | OVER HAZELTINE HOLLOW RUN | 61/201 - BROKENSTRAW | 41.904 | -79.3447 | 20150340945 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com |  |  |  | 2016-08-18
22a | -- | 22 | 34056 | 2548 | 61012700902381 | 1 | Warren | TRIUMPH TOWNSHIP | SR 127,BABLIN HILL | OVER GORDON RUN | 61/222 - TRIUMPH | 41.68 | -79.4221 | 20151473333, 20151473334 | Gas | National Fuel/National Fuel Supply Warren | James Kennedy, kennedyj@natfuel.com, 716-857-7368 | UG |  |  | 2017-08-21
22b | -- | 22 | 34056 | 2548 | 61012700902381 | 1 | Warren | TRIUMPH TOWNSHIP | SR 127,BABLIN HILL | OVER GORDON RUN | 61/222 - TRIUMPH | 41.68 | -79.4221 | 20151473333, 20151473334 | Gas | OZ Gas LTD | 814-484-0270 | UG |  |  | 2017-08-21
22c | -- | 22 | 34056 | 2548 | 61012700902381 | 1 | Warren | TRIUMPH TOWNSHIP | SR 127,BABLIN HILL | OVER GORDON RUN | 61/222 - TRIUMPH | 41.68 | -79.4221 | 20151473333, 20151473334 |  | Tidioute Boro/SW Warren County Municipal Auth | 814-484-7424, tboro@tidioute.org |  |  |  | 2017-08-21
23a | -- | 23 | 34077 | 84954 | 61095701700981 | 1 | Warren | FREEHOLD TOWNSHIP | SR 957 | OVER LITTLE BROKENSTRAW | 61/210 - FREEHOLD | 41.9515 | -79.4433 | 20151471561 | Gas | Enervest Operating LLC | 304-343-5505 | UG |  |  | 2017-05-18
23b | -- | 23 | 34077 | 84954 | 61095701700981 | 1 | Warren | FREEHOLD TOWNSHIP | SR 957 | OVER LITTLE BROKENSTRAW | 61/210 - FREEHOLD | 41.9515 | -79.4433 | 20151471561 | Gas | National Fuel/National Fuel Supply Warren | James Kennedy, kennedyj@natfuel.com, 716-857-7368 | UG |  |  | 2017-05-18
24a | -- | 24 | 34169 | 97452 | 61301000600428 | 1 | Warren | SPRING CREEK TOWNSHIP | SR 3010,SPRING CK | OVER WHITNEY RUN | 61/220 - SPRING CREEK | 41.846 | -79.5687 | 20143571624 | Comm | Verizon North LLC | Eric Rodrigues, 814-871-2317, eric.rodrigues@verizon.com | UG |  |  | 2016-05-12
24b | -- | 24 | 34169 | 97452 | 61301000600428 | 1 | Warren | SPRING CREEK TOWNSHIP | SR 3010,SPRING CK | OVER WHITNEY RUN | 61/220 - SPRING CREEK | 41.846 | -79.5687 | 20143571624 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com |  |  |  | 2016-05-12
25a | -- | 25 | 8831 | 85095 | 12012000400000 | 2 | Cameron | TRUMAN | SR 120-PA 120 | BIG RUN | 12/205 - SHIPPEN | 41.4708 | -78.3911 | 20150541259 | GAS | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2017-05-12
25b | -- | 25 | 8831 | 85095 | 12012000400000 | 2 | Cameron | TRUMAN | SR 120-PA 120 | BIG RUN | 12/205 - SHIPPEN | 41.4708 | -78.3911 | 20150541259 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com |  |  |  | 2017-05-12
26a | -- | 26 | 9265 | 88201 | 14004507902031 | 2 | Centre | WOODWARD | SR 45-PA 45 | PINE CREEK | 14/208 - HAINES | 40.899 | -77.3573 | 20150541283 | sanitary | Haines Woodward Mun Auth | Martha B. Futhey, Secretary, 814-349-8193 | UG |  |  | 2017-06-13
26b | -- | 26 | 9265 | 88201 | 14004507902031 | 2 | Centre | WOODWARD | SR 45-PA 45 | PINE CREEK | 14/208 - HAINES | 40.899 | -77.3573 | 20150541283 | Comm | Northeastern ITS | Nick Williams; John Bruce at (877) 601-7662; William Hosack, william.hosack@spreadnetworks.com |  |  |  | 2017-06-13
26c | -- | 26 | 9265 | 88201 | 14004507902031 | 2 | Centre | WOODWARD | SR 45-PA 45 | PINE CREEK | 14/208 - HAINES | 40.899 | -77.3573 | 20150541283 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com |  |  |  | 2017-06-13
26d | -- | 26 | 9265 | 88201 | 14004507902031 | 2 | Centre | WOODWARD | SR 45-PA 45 | PINE CREEK | 14/208 - HAINES | 40.899 | -77.3573 | 20150541283 | sanitary | Haines TWP | Martha B. Futhey, Secretary, 814-349-8193 | UG |  |  | 2017-06-13
27a | -- | 27 | 9360 | 88155 | 14014403400099 | 2 | Centre | BELLEFONTE | SR 144-PA 144 | YOCUM RUN | 14/221 - SPRING | 40.9243 | -77.78 | 20150541322 | sanitary | Bellefonte Borough | Ralph Stewart, 814-355-1501, rstewart@bellefonte.net | UG |  |  | 2017-02-13
27b | -- | 27 | 9360 | 88155 | 14014403400099 | 2 | Centre | BELLEFONTE | SR 144-PA 144 | YOCUM RUN | 14/221 - SPRING | 40.9243 | -77.78 | 20150541322 | Gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com | UG |  |  | 2017-02-13
27c | -- | 27 | 9360 | 88155 | 14014403400099 | 2 | Centre | BELLEFONTE | SR 144-PA 144 | YOCUM RUN | 14/221 - SPRING | 40.9243 | -77.78 | 20150541322 | sanitary | Spring Benner Walker Joint Auth | Warren Miller, wmiller@sbwja.com | UG |  |  | 2017-02-13
27d | -- | 27 | 9360 | 88155 | 14014403400099 | 2 | Centre | BELLEFONTE | SR 144-PA 144 | YOCUM RUN | 14/221 - SPRING | 40.9243 | -77.78 | 20150541322 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com |  |  |  | 2017-02-13
28 | -- | 28 | 9576 | 85135 | 14100200501555 | 2 | Centre | YARNELL | SR 1002 | LITTLE MARSH CREEK | 14/202 - BOGGS | 40.9992 | -77.8114 | 20150541685 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com |  |  |  | 2017-05-11
29a | -- | 29 | 9577 | 81359 | 14100200801726 | 2 | Centre | YARNELL | SR 1002 | BRANCH LITTLE MARSH CR | 14/202 - BOGGS | 41.0091 | -77.7908 | 20150541711 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com |  |  |  | 2017-08-01
29b | -- | 29 | 9577 | 81359 | 14100200801726 | 2 | Centre | YARNELL | SR 1002 | BRANCH LITTLE MARSH CR | 14/202 - BOGGS | 41.0091 | -77.7908 | 20150541711 | Gas | Dominion Transmission Inc Luthersburg | Charlie Muth, 814-583-5171 | UG |  |  | 2017-08-01
30 | -- | 30 | 9679 | 2893 | 14201300100000 | 2 | Centre | 2 MI NE COBURN | ON TSR 508 | PINE CREEK | 14/208 - HAINES | 40.8819 | -77.4198 | 20143580136 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com |  |  |  | 2017-08-03
31a | -- | 31 | 9431 | 85125 | 14304001301062 | 2 | Centre | PORT MATILDA | SR 220-US 220 | LAUREL RUN | 14/407 - PORT MATILDA | 40.8018 | -78.0516 | 20150541337 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com | OH |  |  | 2017-02-13
31b | -- | 31 | 9431 | 85125 | 14304001301062 | 2 | Centre | PORT MATILDA | SR 220-US 220 | LAUREL RUN | 14/407 - PORT MATILDA | 40.8018 | -78.0516 | 20150541337 | Comm | Need to Confirm Phone |  | OH |  |  | 2017-02-13
31c | -- | 31 | 9431 | 85125 | 14304001301062 | 2 | Centre | PORT MATILDA | SR 220-US 220 | LAUREL RUN | 14/407 - PORT MATILDA | 40.8018 | -78.0516 | 20150541337 | Comm | Comcast Cable Communications, Inc. or Country Cable - need to confirm | Brian Greene - Brian_Greene@cable.comcast.com | OH |  |  | 2017-02-13
31d | -- | 31 | 9431 | 85125 | 14304001301062 | 2 | Centre | PORT MATILDA | SR 220-US 220 | LAUREL RUN | 14/407 - PORT MATILDA | 40.8018 | -78.0516 | 20150541337 | wtr | Port Matilda Bourough | Vance Barndt, 814-692-0092, cell 814-441-7777 | UG |  |  | 2017-02-13
32a | -- | 32 | 9434 | 85128 | 14304001500701 | 2 | Centre | 1 MI E PORT MATILDA | SR 220-US 220 | SUNNYSIDE HOLLOW RUN | 14/225 - WORTH | 40.8126 | -78.0397 | 20150161081 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621 |  |  |  | 2016-04-07
32b | -- | 32 | 9434 | 85128 | 14304001500701 | 2 | Centre | 1 MI E PORT MATILDA | SR 220-US 220 | SUNNYSIDE HOLLOW RUN | 14/225 - WORTH | 40.8126 | -78.0397 | 20150161081 | sanitary | Port Matilda Borough Auth | Tim Estright (at the plant), 814-692-7513, 171 Bradford Drive, Port Matilda PA 16870; engineering consulant, Thomas Holleran, 814-574-0191, tholleran@hrg-inc.com | UG | 3" |  | 2016-04-07
32c | -- | 32 | 9434 | 85128 | 14304001500701 | 2 | Centre | 1 MI E PORT MATILDA | SR 220-US 220 | SUNNYSIDE HOLLOW RUN | 14/225 - WORTH | 40.8126 | -78.0397 | 20150161081 | Elect | West Penn Power | Jeff Miller, jmill20@firstenergy.com; engineering supervisor - Zach Reedy, 724-548-3578, zreedy@firstenergycorp.com | OH |  |  | 2016-04-07
32d | -- | 32 | 9434 | 85128 | 14304001500701 | 2 | Centre | 1 MI E PORT MATILDA | SR 220-US 220 | SUNNYSIDE HOLLOW RUN | 14/225 - WORTH | 40.8126 | -78.0397 | 20150161081 | Comm | Windstream | Jay Knight, Jay.Knight@windstream.com, 814-272-2648 | OH |  |  | 2016-04-07
32e | -- | 32 | 9434 | 85128 | 14304001500701 | 2 | Centre | 1 MI E PORT MATILDA | SR 220-US 220 | SUNNYSIDE HOLLOW RUN | 14/225 - WORTH | 40.8126 | -78.0397 | 20150161081 | Comm | Country Cable | Lee Dorman, 814-359-3161, dormanrep@aol.com |  |  |  | 2016-04-07
32f | -- | 32 | 9434 | 85128 | 14304001500701 | 2 | Centre | 1 MI E PORT MATILDA | SR 220-US 220 | SUNNYSIDE HOLLOW RUN | 14/225 - WORTH | 40.8126 | -78.0397 | 20150161081 | Comm | Nittany Media Inc. - Need to Confirm | Craig Yohn, 717-248-3733, cyohn@nmax.net |  |  |  | 2016-04-07
33a | -- | 33 | 9451 | 88199 | 14304003701668 | 2 | Centre | UNIONVILLE BORO | SR 3040 | DEWITT RUN | 14/411 - UNIONVILLE | 40.9064 | -77.8772 | 20150541356 | sanitary | Mid-Centre County Auth | Chad A. Bechdel, 814-355-8435, mccaio@hotmail.com | UG |  |  | 2017-02-13
33b | -- | 33 | 9451 | 88199 | 14304003701668 | 2 | Centre | UNIONVILLE BORO | SR 3040 | DEWITT RUN | 14/411 - UNIONVILLE | 40.9064 | -77.8772 | 20150541356 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com |  |  |  | 2017-02-13
33c | -- | 33 | 9451 | 88199 | 14304003701668 | 2 | Centre | UNIONVILLE BORO | SR 3040 | DEWITT RUN | 14/411 - UNIONVILLE | 40.9064 | -77.8772 | 20150541356 | sanitary | Unionville Borough | Sherry A. Lucas, 814-355-4837, uboro@vicon.net | UG |  |  | 2017-02-13
34a | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | 20150541697 | Gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com | UG |  |  | 2017-05-11
34b | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | 20150541697 | sanitary | Mountaintop Area Municipal Auth | Kenneth Hall, 814-387-4321, mama1993@verizon.net |  |  |  | 2017-05-11
34c | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | 20150541697 | Wtr | Mountaintop Regional Water Auth | Josh Cingle, 814-360-6362, mtrwa@verizon.net | UG |  |  | 2017-05-11
34d | -- | 34 | 9778 | 91413 | 14400200702338 | 2 | Centre | CLARENCE | SR 4002 | LITTLE SANDY RUN | 14/220 - SNOW SHOE | 41.0538 | -77.9439 | 20150541697 | sanitary | Snow Shoe TWP | 814-387-6012 | UG |  |  | 2017-05-11
35a | -- | 35 | 9790 | 3195 | 14400600100000 | 2 | Centre | CASANOVA | ON TSR 958 | MOSHANNON CREEK | 14/219 - RUSH | 40.955 | -78.1702 | 20150161095, 20150161097 | wtr | Cooper TWP Municipal Auth | Lisa Howe, 814-345-5673 | UG |  |  | 2016-06-08
35b | -- | 35 | 9790 | 3195 | 14400600100000 | 2 | Centre | CASANOVA | ON TSR 958 | MOSHANNON CREEK | 14/219 - RUSH | 40.955 | -78.1702 | 20150161095, 20150161097 | Elect | Pennsylvania Electric Company - need to confirm | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com | OH |  |  | 2016-06-08
35c | -- | 35 | 9790 | 3195 | 14400600100000 | 2 | Centre | CASANOVA | ON TSR 958 | MOSHANNON CREEK | 14/219 - RUSH | 40.955 | -78.1702 | 20150161095, 20150161097 | Comm | Verizon - Need to Confirm | Deborah D. Delia - 412-633-3810, deborah.d.delia@verizon.com | OH |  |  | 2016-06-08
35d | -- | 35 | 9790 | 3195 | 14400600100000 | 2 | Centre | CASANOVA | ON TSR 958 | MOSHANNON CREEK | 14/219 - RUSH | 40.955 | -78.1702 | 20150161095, 20150161097 | Comm | Tele-Media Company of Central PA - need to confirm | 814-353-2025 | OH |  |  | 2016-06-08
36a | -- | 36 | 11245 | 69443 | 17005306400000 | 2 | Clearfield | MORRISDALE | SR 53-PA 53 | EMIGH RUN | 17/224 - MORRIS | 40.9315 | -78.2242 | 20143580396 | Wtr | Pennsylvania American Water CO | Mark Rice, mark.rice@amwater.com, 814-342-0995 | UG |  |  | 2016-04-14
36b | -- | 36 | 11245 | 69443 | 17005306400000 | 2 | Clearfield | MORRISDALE | SR 53-PA 53 | EMIGH RUN | 17/224 - MORRIS | 40.9315 | -78.2242 | 20143580396 | sanitary | Municipal Auth of the Township of Morris | Vic Couturiaux, 814-574-5278, sewercat@msn.com, 135 Lil Troy Drive, Philipsburg, PA 16866 | UG |  |  | 2016-04-14
37a | -- | 37 | 11390 | 91508 | 17021902800000 | 2 | Clearfield | MCGEES MILLS | SR 219-US 219 | WHISKEY RUN | 17/202 - BELL | 40.8848 | -78.7566 | 20150712670 |  | all facilities responded clear per one call |  |  |  |  | 2017-02-13
37b | -- | 37 | 11390 | 91508 | 17021902800000 | 2 | Clearfield | MCGEES MILLS | SR 219-US 219 | WHISKEY RUN | 17/202 - BELL | 40.8848 | -78.7566 | 20150712670 | Elect | Need to Confirm Electric |  | OH |  |  | 2017-02-13
37c | -- | 37 | 11390 | 91508 | 17021902800000 | 2 | Clearfield | MCGEES MILLS | SR 219-US 219 | WHISKEY RUN | 17/202 - BELL | 40.8848 | -78.7566 | 20150712670 | Comm | Need to Confirm Phone |  | OH |  |  | 2017-02-13
38a | -- | 38 | 11399 | 85076 | 17021904201459 | 2 | Clearfield | CURRY RUN | SR 219-US 219 | CURRY RUN | 17/217 - GREENWOOD | 40.9094 | -78.6707 | 20150541754 |  | all facilities responded clear per one call |  |  |  |  | 2016-07-22
38b | -- | 38 | 11399 | 85076 | 17021904201459 | 2 | Clearfield | CURRY RUN | SR 219-US 219 | CURRY RUN | 17/217 - GREENWOOD | 40.9094 | -78.6707 | 20150541754 | Comm | Need to Confirm Cable |  | OH |  |  | 2016-07-22
38c | -- | 38 | 11399 | 85076 | 17021904201459 | 2 | Clearfield | CURRY RUN | SR 219-US 219 | CURRY RUN | 17/217 - GREENWOOD | 40.9094 | -78.6707 | 20150541754 | Comm | Verizon - Need to Confirm | Deborah D. Delia - 412-633-3810, deborah.d.delia@verizon.com | OH |  |  | 2016-07-22
39a | -- | 39 | 11403 | 85079 | 17021904602606 | 2 | Clearfield | BELLS LANDING | SR 219-US 219 | POPLAR RUN | 17/217 - GREENWOOD | 40.9303 | -78.6468 | 20150752974 | Gas | Alliance Petroleum Corp | 724-349-9070 | UG |  |  | 2017-02-13
39b | -- | 39 | 11403 | 85079 | 17021904602606 | 2 | Clearfield | BELLS LANDING | SR 219-US 219 | POPLAR RUN | 17/217 - GREENWOOD | 40.9303 | -78.6468 | 20150752974 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com |  |  |  | 2017-02-13
40a | -- | 40 | 11404 | 93323 | 17021904700185 | 2 | Clearfield | BELLS LANDING | SR 219-US 219 | BELL RUN | 17/217 - GREENWOOD | 40.9311 | -78.6461 | 20150752912 | Gas | Alliance Petroleum Corp | 724-349-9070 | UG |  |  | 2017-02-13
40b | -- | 40 | 11404 | 93323 | 17021904700185 | 2 | Clearfield | BELLS LANDING | SR 219-US 219 | BELL RUN | 17/217 - GREENWOOD | 40.9311 | -78.6461 | 20150752912 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com |  |  |  | 2017-02-13
41a | -- | 41 | 11454 | 93372 | 17025502200000 | 2 | Clearfield | 2 MI SW PENFIELD | SR 255-PA 255 | BENNETT BRANCH | 17/219 - HUSTON | 41.1896 | -78.6015 | 20150680973 | Elect | Pennsylvania Electric Company | Michael (Mike) Kephart, mkephart@firstenergycorp.com | OH |  |  | 2016-07-22
41b | -- | 41 | 11454 | 93372 | 17025502200000 | 2 | Clearfield | 2 MI SW PENFIELD | SR 255-PA 255 | BENNETT BRANCH | 17/219 - HUSTON | 41.1896 | -78.6015 | 20150680973 | Comm | Verizon | Steve Septak, steven.g.septak@one.verizon.com, 412-793-7126; Eric Rodrigues, eric.rodrigues@one.verizon.com, 814-871-2317 |  |  |  | 2016-07-22
41c | -- | 41 | 11454 | 93372 | 17025502200000 | 2 | Clearfield | 2 MI SW PENFIELD | SR 255-PA 255 | BENNETT BRANCH | 17/219 - HUSTON | 41.1896 | -78.6015 | 20150680973 | Comm | Zito Media | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com | OH |  |  | 2016-07-22
41d | -- | 41 | 11454 | 93372 | 17025502200000 | 2 | Clearfield | 2 MI SW PENFIELD | SR 255-PA 255 | BENNETT BRANCH | 17/219 - HUSTON | 41.1896 | -78.6015 | 20150680973 | Comm | Level3 | Stephen Putt, stephen.putt@level3.com, 412-728-6496 | OH |  |  | 2016-07-22
41e | -- | 41 | 11454 | 93372 | 17025502200000 | 2 | Clearfield | 2 MI SW PENFIELD | SR 255-PA 255 | BENNETT BRANCH | 17/219 - HUSTON | 41.1896 | -78.6015 | 20150680973 | Comm | Comcast Cable Communications, Inc. | Doug Olszewski, douglas_olszewski@cable.comcast.com | OH |  |  | 2016-07-22
41f | -- | 41 | 11454 | 93372 | 17025502200000 | 2 | Clearfield | 2 MI SW PENFIELD | SR 255-PA 255 | BENNETT BRANCH | 17/219 - HUSTON | 41.1896 | -78.6015 | 20150680973 | Comm | Windstream | Aldona (Ann) Pilarczyk, 319-790-6779, Aldona.Pilarczyk@windstream.com | OH |  |  | 2016-07-22
42a | -- | 42 | 11461 | 88626 | 17025503200000 | 2 | Clearfield | HOLLYWOOD | SR 255-PA 255 | MINE CAVE IN | 17/219 - HUSTON | 41.2422 | -78.5402 | 20150752439 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com |  |  |  | 2017-02-13
42b | -- | 42 | 11461 | 88626 | 17025503200000 | 2 | Clearfield | HOLLYWOOD | SR 255-PA 255 | MINE CAVE IN | 17/219 - HUSTON | 41.2422 | -78.5402 | 20150752439 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2017-02-13
43 | -- | 43 | 11658 |  |  | 2 | Clearfield | HAWK RUN | SR 1009 | HAWK RUN | 17/224 - MORRIS | 40.9375 | -78.2029 | 20150682136 | wtr | Pennsylvania American Water CO | Mark Rice, mark.rice@amwater.com, 814-342-0995 | UG |  |  | 2016-08-22
44a | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | 20143580324 | Comm | Comcast Cable Communications, Inc. | Jeffrey Walker, Jeffrey_Walker2@cable.comcast.com, 814-599-0621 | OH |  |  | 2016-06-06
44b | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | 20143580324 | wtr | Pennsylvania American Water CO | Mark Rice, mark.rice@amwater.com, 814-342-0995 | UG |  |  | 2016-06-06
44c | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | 20143580324 | GAS | UGI Central Penn Gas | Thomas (Tom) Shaffer, tshaffer@ugi.com, 814-577-6862 | UG |  |  | 2016-06-06
44d | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | 20143580324 | sanitary | Wallaceton-Boggs Municipal Auth | Denny Knepp, Gloria Knepp, 814-342-0725, 814-592-1600 (cell), 63 Apple Lane, West Decatur PA 16878 (home address) don’t call until after 10 am. | UG |  |  | 2016-06-06
44e | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | 20143580324 |  | Boggs TWP | 814-342-5243 |  |  |  | 2016-06-06
44f | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | 20143580324 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com | OH |  |  | 2016-06-06
44g | -- | 44 | 11698 | 3571 | 17200703101047 | 2 | Clearfield | WEST DECATUR | SR 2007 | LAUREL RUN | 17/205 - BOGGS | 40.9302 | -78.2797 | 20143580324 | comm | Verizon | Paul Deering, 814-231-6507, 250 S. Allen Street State College, PA 16801, paul.e.deering@verizon.com | OH |  |  | 2016-06-06
45a | -- | 45 | 11807 | 85119 | 17300902501042 | 2 | Clearfield | 2 MI SE TROUTVILLE | SR 3009 | E BR MAHONING CREEK | 17/207 - BRADY | 41.0036 | -78.7869 | 20150541736 | Elect | United Electric Coop Inc | Steve Long, 814-503-8509, slong@unitedpa.com | Both |  |  | 2016-07-12
45b | -- | 45 | 11807 | 85119 | 17300902501042 | 2 | Clearfield | 2 MI SE TROUTVILLE | SR 3009 | E BR MAHONING CREEK | 17/207 - BRADY | 41.0036 | -78.7869 | 20150541736 | sanitary | Brady TWP | 814-583-5652 | UG |  |  | 2016-07-12
45c | -- | 45 | 11807 | 85119 | 17300902501042 | 2 | Clearfield | 2 MI SE TROUTVILLE | SR 3009 | E BR MAHONING CREEK | 17/207 - BRADY | 41.0036 | -78.7869 | 20150541736 | wtr | Brady TWP Troutville Boro Water Assn Inc | 814-583-5554 | UG |  |  | 2016-07-12
45d | -- | 45 | 11807 | 85119 | 17300902501042 | 2 | Clearfield | 2 MI SE TROUTVILLE | SR 3009 | E BR MAHONING CREEK | 17/207 - BRADY | 41.0036 | -78.7869 | 20150541736 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Aldona (Ann) Pilarczyk, 319-790-6779, Aldona.Pilarczyk@windstream.com | UG |  |  | 2016-07-12
46a | -- | 46 | 12163 | 91510 | 18015000701624 | 2 | Clinton | 3 MILE EAST BEECH CREEK | SR 150-PA 150 | MASDEN RUN | 18/203 - BEECH CREEK | 41.09 | -77.5362 | 20150752547 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com |  |  |  | 2017-02-13
46b | -- | 46 | 12163 | 91510 | 18015000701624 | 2 | Clinton | 3 MILE EAST BEECH CREEK | SR 150-PA 150 | MASDEN RUN | 18/203 - BEECH CREEK | 41.09 | -77.5362 | 20150752547 | Comm | Comcast Cable Communications, Inc. | Dennis Treaster, 717-248-0193/0195 |  |  |  | 2017-02-13
46c | -- | 46 | 12163 | 91510 | 18015000701624 | 2 | Clinton | 3 MILE EAST BEECH CREEK | SR 150-PA 150 | MASDEN RUN | 18/203 - BEECH CREEK | 41.09 | -77.5362 | 20150752547 | Gas | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2017-02-13
46d | -- | 46 | 12163 | 91510 | 18015000701624 | 2 | Clinton | 3 MILE EAST BEECH CREEK | SR 150-PA 150 | MASDEN RUN | 18/203 - BEECH CREEK | 41.09 | -77.5362 | 20150752547 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com |  |  |  | 2017-02-13
47a | -- | 47 | 12239 | 69040 | 18047700300000 | 2 | Clinton | SALONA | SR 477-PA 477 | LONG RUN | 18/213 - LAMAR | 41.0855 | -77.4653 | 20143580327 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com | OH |  |  | 2016-06-27
47b | -- | 47 | 12239 | 69040 | 18047700300000 | 2 | Clinton | SALONA | SR 477-PA 477 | LONG RUN | 18/213 - LAMAR | 41.0855 | -77.4653 | 20143580327 | sanitary | East Nittany Valley Joint Municipal Auth | Ray Zwald, 570-726-6224, 200 Clintondale Hill Road Millhall, PA 17751, envjma@centurylink.net | UG |  |  | 2016-06-27
47c | -- | 47 | 12239 | 69040 | 18047700300000 | 2 | Clinton | SALONA | SR 477-PA 477 | LONG RUN | 18/213 - LAMAR | 41.0855 | -77.4653 | 20143580327 | Comm | TDS Telecom/Sugar Valley Telephone CO | Stewart Walker, 315-562-0091, stewart.walker@tdstelecom.com, 159 Main Street Edwards, NY 13635 |  |  |  | 2016-06-27
47d | -- | 47 | 12239 | 69040 | 18047700300000 | 2 | Clinton | SALONA | SR 477-PA 477 | LONG RUN | 18/213 - LAMAR | 41.0855 | -77.4653 | 20143580327 | Elect | West Penn Power | engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com; Robert Rhodes, rwrhodes@firstenergycorp.com | OH |  |  | 2016-06-27
47e | -- | 47 | 12239 | 69040 | 18047700300000 | 2 | Clinton | SALONA | SR 477-PA 477 | LONG RUN | 18/213 - LAMAR | 41.0855 | -77.4653 | 20143580327 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com | OH |  |  | 2016-06-27
48a | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | 20150161105 | air | Air Liquide | Rich Smitty, 814-781-6990, rich.smitty@airliquide.com | UG |  |  | 2016-07-18
48b | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | 20150161105 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com | UG | 6 and 2" |  | 2016-07-18
48c | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | 20150161105 | sanitary | City of Saint Marys | Tim Brennan, 814-781-1718 x234 or 235, tim@cityofstmarys.com, 11 Lafayette Street St. Marys PA 15857; Travis Skrzypek (GIS Tech), tskrzypek@cityofstmarys.com, 814-781-1718 x 235 | UG |  |  | 2016-07-18
48d | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | 20150161105 | Wtr | Saint Marys Area Water Authority | Dwight Hoare, 814-834-4362, stwaterdhoare@windstream.net (hours M-F 8-4:30) | UG |  |  | 2016-07-18
48e | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | 20150161105 | Elect | West Penn Power | Zach Reedy (engineering supervisor), zreedy@firstenergycorp.com, 724-548-3578; Cheryl Moore (distribution specialist), cmoore4@firstenergycorp.com, 814-781-5545 | OH |  |  | 2016-07-18
48f | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | 20150161105 | Comm | Windstream | Brian Cook, Brian.A.Cook@windstream.com | OH |  |  | 2016-07-18
48g | -- | 48 | 15531 | 85152 | 24012002801546 | 2 | Elk | CITY OF ST MARYS | SR 120-PA 120 | BRANCH ELK CREEK | 24/301 - SAINT MARYS | 41.428 | -78.5329 | 20150161105 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com | OH |  |  | 2016-07-18
49a | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | 20143580336 | Elect | Pennsylvania Electric Company | John Forbes, jforbes@firstenergycorp.com |  |  |  | 2016-07-08
49b | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | 20143580336 | Comm | Brockway Boro/BB Municipal Auth/BBSA/BTV | Laurie Wayne, 814-268-6565, brockway@broakwaytv.com | OH |  |  | 2016-07-08
49c | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | 20143580336 | Comm | Comcast Cable Communications, Inc. | Brian Greene, Brian_Greene@cable.comcast.com | OH |  |  | 2016-07-08
49d | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | 20143580336 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2016-07-08
49e | -- | 49 | 15535 | 69088 | 24021900201858 | 2 | Elk | BROCKPORT | SR 219-US 219 | MEAD RUN | 24/205 - HORTON | 41.2603 | -78.7261 | 20143580336 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com | OH |  |  | 2016-07-08
50a | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | 20150681014/ 20150681015 | Comm | Comcast Cable Communications, Inc. | Dennis Treaster, 717-248-0193/0195 | OH |  |  | 2016-07-22
50b | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | 20150681014/ 20150681015 |  | Johnsonburg Municipal Auth | Travis Long (Engineer with GD&F) 814-965-4218, jmawater@ncentral.com, 434 Center Street Johnsonburg, PA 15845 |  |  |  | 2016-07-22
50c | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | 20150681014/ 20150681015 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2016-07-22
50d | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | 20150681014/ 20150681015 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Aldona (Ann) Pilarczyk, 319-790-6779, Aldona.Pilarczyk@windstream.com | OH |  |  | 2016-07-22
50e | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | 20150681014/ 20150681015 | sanitary | Johnsonburg Borough | Mary Polasky, 814-965-5682, jbgboro@ncentral.com | UG |  |  | 2016-07-22
50f | -- | 50 | 15560 | 88185 | 24021904900000 | 2 | Elk | JOHNSONBURG | SR 219-US 219 | POWERS RUN | 24/401 - JOHNSONBURG | 41.4792 | -78.6697 | 20150681014/ 20150681015 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com | OH |  |  | 2016-07-22
51a | -- | 51 | 19992 | 88195 | 34003507200000 | 2 | Juniata | MCALISTERVILLE | SR 35-PA 35 | TRIB LOST CREEK | 34/203 - FAYETTE | 40.6347 | -77.2779 | 20150761133 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-02-13
51b | -- | 51 | 19992 | 88195 | 34003507200000 | 2 | Juniata | MCALISTERVILLE | SR 35-PA 35 | TRIB LOST CREEK | 34/203 - FAYETTE | 40.6347 | -77.2779 | 20150761133 | Comm | Nittany Media Inc | Jonathan Hain, 717-248-3733 |  |  |  | 2017-02-13
52 | -- | 52 | 20021 | 4194 | 34007502501504 | 2 | Juniata | EAST WATERFORD | SR 75-PA 75 | HORSE VALLEY RUN CREEK | 34/212 - TUSCARORA | 40.3722 | -77.6006 | 20151470384 | Comm | Comcast Cable Communications, Inc. | Dennis Treaster, 717-248-0193/0195 | UG |  |  | 2017-06-06
53a | -- | 53 | 20106 | 4214 | 34100200200000 | 2 | Juniata | 0.5 MI E CUBA MILLS | SR 1002 | LOST CREEK | 34/204 - FERMANAGH | 40.5937 | -77.3999 | 20151463303 | Comm | Nittany Media Inc | Jonathan Hain, 717-248-3733 |  |  |  | 2017-05-22
53b | -- | 53 | 20106 | 4214 | 34100200200000 | 2 | Juniata | 0.5 MI E CUBA MILLS | SR 1002 | LOST CREEK | 34/204 - FERMANAGH | 40.5937 | -77.3999 | 20151463303 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-05-22
54a | -- | 54 | 20118 | 4218 | 34100400300549 | 2 | Juniata | MCALISTERVILLE | SR 1004 | LITTLE LOST CREEK | 34/203 - FAYETTE | 40.637 | -77.2754 | 20151473006 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com |  |  |  | 2017-06-13
54b | -- | 54 | 20118 | 4218 | 34100400300549 | 2 | Juniata | MCALISTERVILLE | SR 1004 | LITTLE LOST CREEK | 34/203 - FAYETTE | 40.637 | -77.2754 | 20151473006 |  | McAlisterville Area Joint Authority | 717-463-3434 |  |  |  | 2017-06-13
54c | -- | 54 | 20118 | 4218 | 34100400300549 | 2 | Juniata | MCALISTERVILLE | SR 1004 | LITTLE LOST CREEK | 34/203 - FAYETTE | 40.637 | -77.2754 | 20151473006 | Comm | Nittany Media Inc | Jonathan Hain, 717-248-3733 |  |  |  | 2017-06-13
54d | -- | 54 | 20118 | 4218 | 34100400300549 | 2 | Juniata | MCALISTERVILLE | SR 1004 | LITTLE LOST CREEK | 34/203 - FAYETTE | 40.637 | -77.2754 | 20151473006 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-06-13
55a | -- | 55 | 20137 | 81508 | 34200601501696 | 2 | Juniata | VAN WERT | SR 2006 | DOE RUN | 34/213 - WALKER | 40.5835 | -77.2954 | 20150681042 | Comm | Nittany Media Inc | Craig Yohn, 717-248-3733, cyohn@nmax.net | OH |  |  | 2016-06-17
55b | -- | 55 | 20137 | 81508 | 34200601501696 | 2 | Juniata | VAN WERT | SR 2006 | DOE RUN | 34/213 - WALKER | 40.5835 | -77.2954 | 20150681042 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Both |  |  | 2016-06-17
55c | -- | 55 | 20137 | 81508 | 34200601501696 | 2 | Juniata | VAN WERT | SR 2006 | DOE RUN | 34/213 - WALKER | 40.5835 | -77.2954 | 20150681042 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com | OH |  |  | 2016-06-17
56a | -- | 56 | 20147 | 91518 | 34200701400000 | 2 | Juniata | OAKLAND MILLS | SR 2007 | LOST CREEK | 34/203 - FAYETTE | 40.6119 | -77.3132 | 20150781847 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-04-03
56b | -- | 56 | 20147 | 91518 | 34200701400000 | 2 | Juniata | OAKLAND MILLS | SR 2007 | LOST CREEK | 34/203 - FAYETTE | 40.6119 | -77.3132 | 20150781847 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com |  |  |  | 2017-04-03
56c | -- | 56 | 20147 | 91518 | 34200701400000 | 2 | Juniata | OAKLAND MILLS | SR 2007 | LOST CREEK | 34/203 - FAYETTE | 40.6119 | -77.3132 | 20150781847 | Comm | Nittany Media Inc | Jonathan Hain, 717-248-3733 |  |  |  | 2017-04-03
57a | -- | 57 | 25213 | 78606 | 42000605100562 | 2 | McKean | HAZELHURST | SR 6-US 6 | MARVIN CREEK | 42/208 - HAMLIN | 41.7052 | -78.5921 | 20150761183 | Comm | Comcast Cable Communications, Inc. | Dennis Treaster, 717-248-0193/0195 |  |  |  | 2017-03-21
57b | -- | 57 | 25213 | 78606 | 42000605100562 | 2 | McKean | HAZELHURST | SR 6-US 6 | MARVIN CREEK | 42/208 - HAMLIN | 41.7052 | -78.5921 | 20150761183 | sanitary | Hamlin TWP | 814-778-5855 | UG |  |  | 2017-03-21
57c | -- | 57 | 25213 | 78606 | 42000605100562 | 2 | McKean | HAZELHURST | SR 6-US 6 | MARVIN CREEK | 42/208 - HAMLIN | 41.7052 | -78.5921 | 20150761183 | Gas | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2017-03-21
57d | -- | 57 | 25213 | 78606 | 42000605100562 | 2 | McKean | HAZELHURST | SR 6-US 6 | MARVIN CREEK | 42/208 - HAMLIN | 41.7052 | -78.5921 | 20150761183 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2017-03-21
58a | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | 20150761206 | Comm | Comcast Cable Communications, Inc. | Dennis Treaster, 717-248-0193/0195 |  |  |  | 2017-03-21
58b | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | 20150761206 | sanitary | Hamlin TWP | 814-778-5855 | UG |  |  | 2017-03-21
58c | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | 20150761206 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2017-03-21
58d | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | 20150761206 | Elect | Pennsylvania Electric Company | Charles Vroman, 814-676-7540, cvroman@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com |  |  |  | 2017-03-21
58e | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | 20150761206 | Gas | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2017-03-21
58f | -- | 58 | 25216 | 78605 | 42000605800309 | 2 | McKean | MARVINDALE | SR 6-US 6 | WARNER BROOK | 42/208 - HAMLIN | 41.7302 | -78.5416 | 20150761206 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com |  |  |  | 2017-03-21
59 | -- | 59 | 25243 | 4344 | 42004600600000 | 2 | McKean | 3 MI SE BETULA | SR 46-PA 46 | HAVENS BROOK | 42/212 - NORWICH | 41.6341 | -78.3574 | 20150401604 |  | all facilities responded clear per one call |  |  |  |  | 2017-05-22
60a | -- | 60 | 25281 | 88664 | 42005904500000 | 2 | McKean | 1 MI W ORMSBY | SR 59-PA 59 | TRIB KINZUA CREEK | 42/209 - KEATING | 41.802 | -78.5643 | 20150640316 | Comm | Comcast Cable Communications, Inc. | Dennis Treaster, 717-248-0193/0195 |  |  |  | 2016-07-18
60b | -- | 60 | 25281 | 88664 | 42005904500000 | 2 | McKean | 1 MI W ORMSBY | SR 59-PA 59 | TRIB KINZUA CREEK | 42/209 - KEATING | 41.802 | -78.5643 | 20150640316 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com |  |  |  | 2016-07-18
60c | -- | 60 | 25281 | 88664 | 42005904500000 | 2 | McKean | 1 MI W ORMSBY | SR 59-PA 59 | TRIB KINZUA CREEK | 42/209 - KEATING | 41.802 | -78.5643 | 20150640316 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2016-07-18
60d | -- | 60 | 25281 | 88664 | 42005904500000 | 2 | McKean | 1 MI W ORMSBY | SR 59-PA 59 | TRIB KINZUA CREEK | 42/209 - KEATING | 41.802 | -78.5643 | 20150640316 |  | no visible OH facilities per site visit |  |  |  |  | 2016-07-18
61a | -- | 61 | 25297 | 88183 | 42015500200000 | 2 | McKean | LIBERTY | SR 155-PA 155 | PORTAGE CREEK | 42/211 - LIBERTY | 41.7083 | -78.2148 | 20150762216 | Elect | Tri-County Rural Electric Cooperative Inc. | Gerald Songster, 814-274-8740, trico@penn.com |  |  |  | 2017-03-06
61b | -- | 61 | 25297 | 88183 | 42015500200000 | 2 | McKean | LIBERTY | SR 155-PA 155 | PORTAGE CREEK | 42/211 - LIBERTY | 41.7083 | -78.2148 | 20150762216 | sanitary | Liberty TWP | Dominic Picarelli Sewage Enforcement Officer with KPI Technology) 717-339-0612, 143 Carlisle St Gettysburg, PA 17325 | UG |  |  | 2017-03-06
61c | -- | 61 | 25297 | 88183 | 42015500200000 | 2 | McKean | LIBERTY | SR 155-PA 155 | PORTAGE CREEK | 42/211 - LIBERTY | 41.7083 | -78.2148 | 20150762216 | Gas | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2017-03-06
62a | -- | 62 | 25308 | 85215 | 42015501900182 | 2 | McKean | 1 MI N PORT ALLEGHENY | SR 155-PA 155 | TWO MILE CREEK | 42/211 - LIBERTY | 41.8326 | -78.2963 | 20150401238 | Gas | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG | 8" |  | 2016-07-22
62b | -- | 62 | 25308 | 85215 | 42015501900182 | 2 | McKean | 1 MI N PORT ALLEGHENY | SR 155-PA 155 | TWO MILE CREEK | 42/211 - LIBERTY | 41.8326 | -78.2963 | 20150401238 | sanitary | Liberty TWP | Dominic Picarelli Sewage Enforcement Officer with KPI Technology) 717-339-0612, 143 Carlisle St Gettysburg, PA 17325 | UG |  |  | 2016-07-22
62c | -- | 62 | 25308 | 85215 | 42015501900182 | 2 | McKean | 1 MI N PORT ALLEGHENY | SR 155-PA 155 | TWO MILE CREEK | 42/211 - LIBERTY | 41.8326 | -78.2963 | 20150401238 | Comm | Verizon - Need to Confirm | Deborah D. Delia - 412-633-3810, deborah.d.delia@verizon.com | OH |  |  | 2016-07-22
63a | -- | 63 | 25313 | 4341 | 42015502701162 | 2 | McKean | 3 MI SE LARABEE | SR 155-PA 155 | ROCK RUN | 42/201 - ANNIN | 41.8788 | -78.349 | 20150401268 | comm | Verizon | Sue Hoover, 814-368-8404 | UG |  |  | 2017-05-18
63b | -- | 63 | 25313 | 4341 | 42015502701162 | 2 | McKean | 3 MI SE LARABEE | SR 155-PA 155 | ROCK RUN | 42/201 - ANNIN | 41.8788 | -78.349 | 20150401268 |  | Annin TWP | Robert Strait, 814-642-7959 |  |  |  | 2017-05-18
63c | -- | 63 | 25313 | 4341 | 42015502701162 | 2 | McKean | 3 MI SE LARABEE | SR 155-PA 155 | ROCK RUN | 42/201 - ANNIN | 41.8788 | -78.349 | 20150401268 | Gas | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2017-05-18
64a | -- | 64 | 25314 | 85259 | 42015502900238 | 2 | McKean | 2 MI SE LARABEE | SR 155-PA 155 | NEWELL CREEK | 42/205 - ELDRED | 41.8892 | -78.352 | 20150401536 | Comm | Comcast Cable Communications, Inc. | Dennis Treaster, 717-248-0193/0195 |  |  |  | 2017-06-19
64b | -- | 64 | 25314 | 85259 | 42015502900238 | 2 | McKean | 2 MI SE LARABEE | SR 155-PA 155 | NEWELL CREEK | 42/205 - ELDRED | 41.8892 | -78.352 | 20150401536 | sanitary | Eldred TWP | 814-225-4777, eldredboro@adelphia.net | UG |  |  | 2017-06-19
64c | -- | 64 | 25314 | 85259 | 42015502900238 | 2 | McKean | 2 MI SE LARABEE | SR 155-PA 155 | NEWELL CREEK | 42/205 - ELDRED | 41.8892 | -78.352 | 20150401536 |  | Annin TWP | Robert Strait, 814-642-7959 |  |  |  | 2017-06-19
64d | -- | 64 | 25314 | 85259 | 42015502900238 | 2 | McKean | 2 MI SE LARABEE | SR 155-PA 155 | NEWELL CREEK | 42/205 - ELDRED | 41.8892 | -78.352 | 20150401536 | Gas | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2017-06-19
65a | -- | 65 | 25418 | 85234 | 42034604101617 | 2 | McKean | 3 MI E BRADFORD | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5844 | 20150401631 | wtr | Bradford City Water Auth | Ken Bryan, 814-362-3004 | UG |  |  | 2017-03-21
65b | -- | 65 | 25418 | 85234 | 42034604101617 | 2 | McKean | 3 MI E BRADFORD | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5844 | 20150401631 | gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com | UG |  |  | 2017-03-21
65c | -- | 65 | 25418 | 85234 | 42034604101617 | 2 | McKean | 3 MI E BRADFORD | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5844 | 20150401631 | Comm | Comcast Cable Communications, Inc. | Dennis Treaster, 717-248-0193/0195 |  |  |  | 2017-03-21
66a | -- | 66 | 25420 | 4336 | 42034604201811 | 2 | McKean | DERRICK CITY | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5741 | 20150762617 | wtr | Bradford City Water Auth | Ken Bryan, 814-362-3004 | UG |  |  | 2017-03-21
66b | -- | 66 | 25420 | 4336 | 42034604201811 | 2 | McKean | DERRICK CITY | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5741 | 20150762617 | gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com | UG |  |  | 2017-03-21
66c | -- | 66 | 25420 | 4336 | 42034604201811 | 2 | McKean | DERRICK CITY | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5741 | 20150762617 | Comm | Comcast Cable Communications, Inc. | Dennis Treaster, 717-248-0193/0195 |  |  |  | 2017-03-21
66d | -- | 66 | 25420 | 4336 | 42034604201811 | 2 | McKean | DERRICK CITY | SR 346-PA 346 | FOSTER BROOK | 42/206 - FOSTER | 41.9716 | -78.5741 | 20150762617 | sanitary | Foster TWP | 814-362-4656, fostertownship@charter.net | UG |  |  | 2017-03-21
67a | -- | 67 | 25459 | 85237 | 42064602900000 | 2 | McKean | 1 MI N GILMORE | SR 646-PA 646 | PENNBROOK RUN | 42/206 - FOSTER | 41.9784 | -78.5575 | 20150401777 | wtr | Bradford City Water Auth | Ken Bryan, 814-362-3004 | UG |  |  | 2017-06-16
67b | -- | 67 | 25459 | 85237 | 42064602900000 | 2 | McKean | 1 MI N GILMORE | SR 646-PA 646 | PENNBROOK RUN | 42/206 - FOSTER | 41.9784 | -78.5575 | 20150401777 | gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com | UG |  |  | 2017-06-16
67c | -- | 67 | 25459 | 85237 | 42064602900000 | 2 | McKean | 1 MI N GILMORE | SR 646-PA 646 | PENNBROOK RUN | 42/206 - FOSTER | 41.9784 | -78.5575 | 20150401777 | Comm | Comcast Cable Communications, Inc. | Dennis Treaster, 717-248-0193/0195 |  |  |  | 2017-06-16
68a | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | 20150641226 | wtr | Bradford City Water Auth | Ken Bryan, 814-362-3004 | UG |  |  | 2016-08-12
68b | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | 20150641226 | sanitary | Bradford TWP | Ken Swanson, 814-331-7568 | UG |  |  | 2016-08-12
68c | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | 20150641226 | gas | National Fuel Supply/National Fuel BRDFD | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG | 2" |  | 2016-08-12
68d | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | 20150641226 | Elect | Pennsylvania Electric Company | Ed King, 814-726-5054, Eking@firstenergycorp.com | OH |  |  | 2016-08-12
68e | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | 20150641226 | Comm | Verizon - Need to Confirm | Deborah D. Delia - 412-633-3810, deborah.d.delia@verizon.com | OH |  |  | 2016-08-12
68f | -- | 68 | 25461 | 4340 | 42077001300784 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9044 | -78.6613 | 20150641226 | Comm | Atlantic Broadband | Dana Wells, 814-368-4541, dwells@atlanticbb.com | OH |  |  | 2016-08-12
69a | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | 20143580408 | wtr | Bradford City Water Auth | Kim Benjamin, 814-362-3004, watr@atlanticbb.net | UG |  |  | 2016-07-18
69b | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | 20143580408 | Gas | National Fuel Supply/National Fuel BRDFD | Matthew (Matt) Hovis, 814-871-8662, HovisM@natfuel.com; Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2016-07-18
69c | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | 20143580408 | Elect | Pennsylvania Electric Company | Edward (Ed) King, 814-726-5054, Eking@firstenergycorp.com | OH |  |  | 2016-07-18
69d | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | 20143580408 | sanitary | Bradford TWP | Ken Swanson, 814-362-4431, swanbagger@gmail.com | UG |  |  | 2016-07-18
69e | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | 20143580408 | Comm | Verizon | Susan Hoover, susan.a.hoover@verizon.com, 814-368-8404 | OH |  |  | 2016-07-18
69f | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | 20143580408 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com |  |  |  | 2016-07-18
69g | -- | 69 | 25462 | 88630 | 42077001400000 | 2 | McKean | CUSTER CITY | SR 770-PA 770 | SHEPPARD RUN | 42/202 - BRADFORD | 41.9055 | -78.6575 | 20143580408 | Comm | Atlantic Broadband | Dana Wells, 814-368-4541, dwells@atlanticbb.com | OH |  |  | 2016-07-18
70a | -- | 70 | 25489 | 68965 | 42101500100472 | 2 | McKean | WRIGHTS CORNERS | SR 1015 | NORTH BRANCH COLE CREEK | 42/209 - KEATING | 41.9248 | -78.4942 | 20150681611 | Comm | Comcast Cable Communications, Inc. | Dennis Treaster, 717-248-0193/0195 | OH |  |  | 2016-08-12
70b | -- | 70 | 25489 | 68965 | 42101500100472 | 2 | McKean | WRIGHTS CORNERS | SR 1015 | NORTH BRANCH COLE CREEK | 42/209 - KEATING | 41.9248 | -78.4942 | 20150681611 | GAS | UGI Central Penn Gas | Andrew Black, 570-829-8967 | UG |  |  | 2016-08-12
70c | -- | 70 | 25489 | 68965 | 42101500100472 | 2 | McKean | WRIGHTS CORNERS | SR 1015 | NORTH BRANCH COLE CREEK | 42/209 - KEATING | 41.9248 | -78.4942 | 20150681611 | Gas | Vineyard Oil & Gas CO | Skippy, 814-572-6010, Skippy33canfield@yahoo.com | UG |  |  | 2016-08-12
70d | -- | 70 | 25489 | 68965 | 42101500100472 | 2 | McKean | WRIGHTS CORNERS | SR 1015 | NORTH BRANCH COLE CREEK | 42/209 - KEATING | 41.9248 | -78.4942 | 20150681611 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com | OH |  |  | 2016-08-12
70e | -- | 70 | 25489 | 68965 | 42101500100472 | 2 | McKean | WRIGHTS CORNERS | SR 1015 | NORTH BRANCH COLE CREEK | 42/209 - KEATING | 41.9248 | -78.4942 | 20150681611 | Elect | Pennsylvania Electric Company - need to confirm | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com | OH |  |  | 2016-08-12
71a | -- | 71 | 25495 | 4486 | 42200100100806 | 2 | McKean | 6 MI SW CLERMONT | SR 2001 | SEVEN MILE RUN | 42/214 - SERGEANT | 41.6308 | -78.5754 | 20143580345 | Gas | Dominion Transmission Inc Luthersburg | Russell (Russ) Gregory, 814-583-1007, russell.l.gregory@dom.com; Andrew (Andy) Haag, Andrew.P.Haag@dom.com, 814-771-3590 | UG |  |  | 2016-07-08
71b | -- | 71 | 25495 | 4486 | 42200100100806 | 2 | McKean | 6 MI SW CLERMONT | SR 2001 | SEVEN MILE RUN | 42/214 - SERGEANT | 41.6308 | -78.5754 | 20143580345 |  | Sergeant TWP | 814-723-3775 |  |  |  | 2016-07-08
71c | -- | 71 | 25495 | 4486 | 42200100100806 | 2 | McKean | 6 MI SW CLERMONT | SR 2001 | SEVEN MILE RUN | 42/214 - SERGEANT | 41.6308 | -78.5754 | 20143580345 | Gas | UGI Central Penn Gas | Roy Carr 570-829-8967 |  |  |  | 2016-07-08
71d | -- | 71 | 25495 | 4486 | 42200100100806 | 2 | McKean | 6 MI SW CLERMONT | SR 2001 | SEVEN MILE RUN | 42/214 - SERGEANT | 41.6308 | -78.5754 | 20143580345 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com | UG |  |  | 2016-07-08
71e | -- | 71 | 25495 | 4486 | 42200100100806 | 2 | McKean | 6 MI SW CLERMONT | SR 2001 | SEVEN MILE RUN | 42/214 - SERGEANT | 41.6308 | -78.5754 | 20143580345 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Aldona (Ann) Pilarczyk, 319-790-6779, Aldona.Pilarczyk@windstream.com |  |  |  | 2016-07-08
71f | -- | 71 | 25495 | 4486 | 42200100100806 | 2 | McKean | 6 MI SW CLERMONT | SR 2001 | SEVEN MILE RUN | 42/214 - SERGEANT | 41.6308 | -78.5754 | 20143580345 |  | no visible OH facilities per site visit |  |  |  |  | 2016-07-08
72a | -- | 72 | 25500 | 78611 | 42200200320000 | 2 | McKean | BETULA | SR 2002 | WEST BRANCH POTATO CREEK | 42/212 - NORWICH | 41.6713 | -78.3998 | 20150401781 | GAS | UGI Central Penn Gas | Andrew Black, 570-829-8967 | UG |  |  | 2017-05-22
72b | -- | 72 | 25500 | 78611 | 42200200320000 | 2 | McKean | BETULA | SR 2002 | WEST BRANCH POTATO CREEK | 42/212 - NORWICH | 41.6713 | -78.3998 | 20150401781 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2017-05-22
73a | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | 20150682166 | wtr | Bradford City Water Auth | Ken Bryan, 814-362-3004 | UG |  |  | 2016-08-10
73b | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | 20150682166 | sanitary | Bradford TWP | Ken Swanson, 814-331-7568 | UG |  |  | 2016-08-10
73c | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | 20150682166 | gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com | UG |  |  | 2016-08-10
73d | -- | 73 | 25535 | 93322 | 42401100102339 | 2 | McKean | BRADFORD | SR 4011 | BENNETT BROOK | 42/202 - BRADFORD | 41.9658 | -78.6771 | 20150682166 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2016-08-10
74a | -- | 74 | 26468 | 4642 | 44065502201820 | 2 | Mifflin | KISHACOQUILLAS | SR 655-PA 655 | FROG HOLLOW RUN | 44/209 - UNION | 40.6278 | -77.6746 | 20150441409 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com |  |  |  | 2017-03-16
74b | -- | 74 | 26468 | 4642 | 44065502201820 | 2 | Mifflin | KISHACOQUILLAS | SR 655-PA 655 | FROG HOLLOW RUN | 44/209 - UNION | 40.6278 | -77.6746 | 20150441409 | wtr | Lewistown Borough Municipal Auth | Craig Bubb, 717-248-0165 | UG |  |  | 2017-03-16
74c | -- | 74 | 26468 | 4642 | 44065502201820 | 2 | Mifflin | KISHACOQUILLAS | SR 655-PA 655 | FROG HOLLOW RUN | 44/209 - UNION | 40.6278 | -77.6746 | 20150441409 | Comm | Zampelli Electronics | Joe Zampelli, 717-248-1544, joan@nmax.net |  |  |  | 2017-03-16
75a | -- | 75 | 26469 | 85297 | 44065502300022 | 2 | Mifflin | KISHACOQUILLAS | SR 655-PA 655 | ALEXANDER RUN | 44/209 - UNION | 40.6279 | -77.6742 | 20151473141 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com | UG |  |  | 2017-06-12
75b | -- | 75 | 26469 | 85297 | 44065502300022 | 2 | Mifflin | KISHACOQUILLAS | SR 655-PA 655 | ALEXANDER RUN | 44/209 - UNION | 40.6279 | -77.6742 | 20151473141 |  | Lewistown Borough Municipal Auth | Craig Bubb, 717-248-0165 | UG |  |  | 2017-06-12
75c | -- | 75 | 26469 | 85297 | 44065502300022 | 2 | Mifflin | KISHACOQUILLAS | SR 655-PA 655 | ALEXANDER RUN | 44/209 - UNION | 40.6279 | -77.6742 | 20151473141 | Comm | Zampelli Electronics | Joe Zampelli, 717-248-1544, joan@nmax.net |  |  |  | 2017-06-12
76a | -- | 76 | 26472 | 4676 | 44100200800896 | 2 | Mifflin | 3 MI NE REEDSVILLE | SR 1002 | HONEY CREEK | 44/201 - ARMAGH | 40.6888 | -77.5584 | 20151470677 |  | Armagh TWP Authority/Armagh TWP | 717-667-6260 | UG |  |  | 2017-05-26
76b | -- | 76 | 26472 | 4676 | 44100200800896 | 2 | Mifflin | 3 MI NE REEDSVILLE | SR 1002 | HONEY CREEK | 44/201 - ARMAGH | 40.6888 | -77.5584 | 20151470677 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com | UG |  |  | 2017-05-26
76c | -- | 76 | 26472 | 4676 | 44100200800896 | 2 | Mifflin | 3 MI NE REEDSVILLE | SR 1002 | HONEY CREEK | 44/201 - ARMAGH | 40.6888 | -77.5584 | 20151470677 |  | Lewistown Borough Municipal Auth | Craig Bubb, 717-248-0165 | UG |  |  | 2017-05-26
77 | -- | 77 | 26477 | 4677 | 44100201200618 | 2 | Mifflin | LOCKE MILLS | SR 1002 | HONEY CREEK | 44/201 - ARMAGH | 40.7052 | -77.5347 | 20151470863 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, jeremy.smith@centurylink.com | UG |  |  | 2017-06-01
78a | -- | 78 | 26595 | 85275 | 44401300500000 | 2 | Mifflin | 1 MI NW STRODES MILLS | SR 4013 | STRODES RUN | 44/206 - GRANVILLE | 40.5683 | -77.6762 | 20150401857 | Elect | Valley Rural Electric Coop Inc | Edward A. Dezich, 814-643-2650 | OH |  |  | 2016-07-22
78b | -- | 78 | 26595 | 85275 | 44401300500000 | 2 | Mifflin | 1 MI NW STRODES MILLS | SR 4013 | STRODES RUN | 44/206 - GRANVILLE | 40.5683 | -77.6762 | 20150401857 | Comm | Zampelli Electronics | Joe Zampelli, 717-248-1544, joan@nmax.net |  |  |  | 2016-07-22
78c | -- | 78 | 26595 | 85275 | 44401300500000 | 2 | Mifflin | 1 MI NW STRODES MILLS | SR 4013 | STRODES RUN | 44/206 - GRANVILLE | 40.5683 | -77.6762 | 20150401857 | Comm | Verizon - Need to Confirm | Deborah D. Delia - 412-633-3810, deborah.d.delia@verizon.com | OH |  |  | 2016-07-22
78d | -- | 78 | 26595 | 85275 | 44401300500000 | 2 | Mifflin | 1 MI NW STRODES MILLS | SR 4013 | STRODES RUN | 44/206 - GRANVILLE | 40.5683 | -77.6762 | 20150401857 | Comm | Nittany Media Inc - Need to Confirm | Jonathan Hain, 717-248-3733 | OH |  |  | 2016-07-22
79a | -- | 79 | 30090 | 88640 | 52000602300000 | 2 | Potter | COUDERSPORT BORO | SR 6-US 6 | DINGMANS RUN | 52/402 - COUDERSPORT | 41.7632 | -78.0383 | 20151472488 |  | Coudersport Area Municipal Auth | 814-274-9776, coudyboro@zitomedia.net | UG |  |  | 2017-05-30
79b | -- | 79 | 30090 | 88640 | 52000602300000 | 2 | Potter | COUDERSPORT BORO | SR 6-US 6 | DINGMANS RUN | 52/402 - COUDERSPORT | 41.7632 | -78.0383 | 20151472488 |  | Coudersport Borough Auth | 814-274-9776, coudyboro@zitomedia.net | UG |  |  | 2017-05-30
79c | -- | 79 | 30090 | 88640 | 52000602300000 | 2 | Potter | COUDERSPORT BORO | SR 6-US 6 | DINGMANS RUN | 52/402 - COUDERSPORT | 41.7632 | -78.0383 | 20151472488 |  | Coudersport Borough | 814-274-9776, coudyboro@zitomedia.net |  |  |  | 2017-05-30
79d | -- | 79 | 30090 | 88640 | 52000602300000 | 2 | Potter | COUDERSPORT BORO | SR 6-US 6 | DINGMANS RUN | 52/402 - COUDERSPORT | 41.7632 | -78.0383 | 20151472488 | gas | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2017-05-30
80a | -- | 80 | 30144 | 69501 | 52004402700000 | 2 | Potter | CARTER CAMP | SR 44-PA 44 | LITTLE KETTLE CREEK | 52/201 - ABBOTT | 41.625 | -77.7181 | 20150762632 | GAS | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2017-03-21
80b | -- | 80 | 30144 | 69501 | 52004402700000 | 2 | Potter | CARTER CAMP | SR 44-PA 44 | LITTLE KETTLE CREEK | 52/201 - ABBOTT | 41.625 | -77.7181 | 20150762632 | comm | Verizon | Cindy Oberholtzer, coberholtzer@usceng.com |  |  |  | 2017-03-21
81a | -- | 81 | 30156 | 93375 | 52004408101925 | 2 | Potter | 1 MI SE HEBRON CENTRE | SR 44-PA 44 | SOUTH BRANCH OSWAYO CR | 52/209 - HEBRON | 41.8694 | -78.002 | 20150640336 |  | Hebron TWP | Roger Bickleman 814-698-2457, hebrontwp@zitomedia.net, 786 Baker Creek Rd. Coudersport PA 16915 | UG |  |  | 2016-07-22
81b | -- | 81 | 30156 | 93375 | 52004408101925 | 2 | Potter | 1 MI SE HEBRON CENTRE | SR 44-PA 44 | SOUTH BRANCH OSWAYO CR | 52/209 - HEBRON | 41.8694 | -78.002 | 20150640336 | Elect | Tri-County Rural Electric Cooperative Inc. - need to confirm | Steve Salada, 570-662-8034 steves@ctenterprises.com | OH |  |  | 2016-07-22
81c | -- | 81 | 30156 | 93375 | 52004408101925 | 2 | Potter | 1 MI SE HEBRON CENTRE | SR 44-PA 44 | SOUTH BRANCH OSWAYO CR | 52/209 - HEBRON | 41.8694 | -78.002 | 20150640336 | Comm | Frontier Communications or Verizon - need to confirm | John Smithkors, john.smithkors@ftr.com, 570-924-0094 | OH |  |  | 2016-07-22
81d | -- | 81 | 30156 | 93375 | 52004408101925 | 2 | Potter | 1 MI SE HEBRON CENTRE | SR 44-PA 44 | SOUTH BRANCH OSWAYO CR | 52/209 - HEBRON | 41.8694 | -78.002 | 20150640336 | Comm | Cable - need to confirm |  | OH |  |  | 2016-07-22
81e | -- | 81 | 30156 | 93375 | 52004408101925 | 2 | Potter | 1 MI SE HEBRON CENTRE | SR 44-PA 44 | SOUTH BRANCH OSWAYO CR | 52/209 - HEBRON | 41.8694 | -78.002 | 20150640336 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION HEBRON and TENNESSEE GAS PIPELINE | Nick Allen, 814-274-3143 | UG | 16 |  | 2016-07-22
82a | -- | 82 | 30162 | 85309 | 52004409500000 | 2 | Potter | CLARA | SR 44-PA 44 | CLARA CREEK | 52/204 - CLARA | 41.9114 | -78.0977 | 20151471351 | Comm | Frontier | John Smithkors, john.smithkors@ftr.com, 570-924-0094 |  |  |  | 2017-04-10
82b | -- | 82 | 30162 | 85309 | 52004409500000 | 2 | Potter | CLARA | SR 44-PA 44 | CLARA CREEK | 52/204 - CLARA | 41.9114 | -78.0977 | 20151471351 | GAS | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2017-04-10
82c | -- | 82 | 30162 | 85309 | 52004409500000 | 2 | Potter | CLARA | SR 44-PA 44 | CLARA CREEK | 52/204 - CLARA | 41.9114 | -78.0977 | 20151471351 | GAS | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2017-04-10
83a | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | 20150640366 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2016-07-22
83b | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | 20150640366 | Gas | Alma Gas Inc | 814-225-3480 | UG |  |  | 2016-07-22
83c | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | 20150640366 | Gas | Maxson Gas Corp | 814-698-2194 | UG |  |  | 2016-07-22
83d | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | 20150640366 |  | Sharon TWP | 814-697-7316, 1972 SR 44 South, Shingleshouse, PA 16748 |  |  |  | 2016-07-22
83e | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | 20150640366 | GAS | UGI Central Penn Gas | Andrew Black, 570-829-8967 | UG |  |  | 2016-07-22
83f | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | 20150640366 | Elect | Pennsylvania Electric Company - need to confirm | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com | OH |  |  | 2016-07-22
83g | -- | 83 | 30166 | 4805 | 52004410100000 | 2 | Potter | SHARON CENTER | SR 44-PA 44 | SHARON CREEK | 52/218 - SHARON | 41.9392 | -78.1428 | 20150640366 | Comm | Frontier - Need to confirm | John Smithkors, john.smithkors@ftr.com, 570-924-0094 | OH |  |  | 2016-07-22
84a | -- | 84 | 30190 | 4897 | 52004904300530 | 2 | Potter | MILLS | SR 49-PA 49 | MARSH CREEK | 52/208 - HARRISON | 41.9463 | -77.6856 | 20143580428 | sanitary | Harrison TWP | Bonnie M. French, 814-334-5425, harrisontwp@verizon.net, 205 E. Main Street, Harrison Valley, PA 16927, Terry Meyers (sewer enforcement officer) with Ridgerunner SEO, 814-258-0301 | UG |  |  | 2016-06-27
84b | -- | 84 | 30190 | 4897 | 52004904300530 | 2 | Potter | MILLS | SR 49-PA 49 | MARSH CREEK | 52/208 - HARRISON | 41.9463 | -77.6856 | 20143580428 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com | OH |  |  | 2016-06-27
84c | -- | 84 | 30190 | 4897 | 52004904300530 | 2 | Potter | MILLS | SR 49-PA 49 | MARSH CREEK | 52/208 - HARRISON | 41.9463 | -77.6856 | 20143580428 | Gas | UGI Central Penn Gas | Roy Carr, 570-829-8967, rcarr@ugi.com | UG |  |  | 2016-06-27
84d | -- | 84 | 30190 | 4897 | 52004904300530 | 2 | Potter | MILLS | SR 49-PA 49 | MARSH CREEK | 52/208 - HARRISON | 41.9463 | -77.6856 | 20143580428 | Comm | Verizon | Jason Wagner, 570-327-7891, jason.e.wagner@verizon.com | OH |  |  | 2016-06-27
84e | -- | 84 | 30190 | 4897 | 52004904300530 | 2 | Potter | MILLS | SR 49-PA 49 | MARSH CREEK | 52/208 - HARRISON | 41.9463 | -77.6856 | 20143580428 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com | OH |  |  | 2016-06-27
85a | -- | 85 | 30191 | 4898 | 52004904400406 | 2 | Potter | MILLS | SR 49-PA 49 | BRANCH COWANESQUE CR | 52/208 - HARRISON | 41.9444 | -77.6732 | 20150161136 | sanitary | Harrison TWP | Bonnie M. French, 814-334-5425, harrisontwp@verizon.net, 205 E. Main Street, Harrison Valley, PA 16927, Terry Meyers (sewer enforcement officer) with Ridgerunner SEO, 814-258-0301 | UG |  |  | 2016-07-05
85b | -- | 85 | 30191 | 4898 | 52004904400406 | 2 | Potter | MILLS | SR 49-PA 49 | BRANCH COWANESQUE CR | 52/208 - HARRISON | 41.9444 | -77.6732 | 20150161136 | Elect | Pennsylvania Electric Company | Charles Vroman, 814-676-7540, cvroman@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com | OH |  |  | 2016-07-05
85c | -- | 85 | 30191 | 4898 | 52004904400406 | 2 | Potter | MILLS | SR 49-PA 49 | BRANCH COWANESQUE CR | 52/208 - HARRISON | 41.9444 | -77.6732 | 20150161136 | Gas | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2016-07-05
85d | -- | 85 | 30191 | 4898 | 52004904400406 | 2 | Potter | MILLS | SR 49-PA 49 | BRANCH COWANESQUE CR | 52/208 - HARRISON | 41.9444 | -77.6732 | 20150161136 | Comm | Verizon - Need to Confirm | Deborah D. Delia - 412-633-3810, deborah.d.delia@verizon.com | OH |  |  | 2016-07-05
85e | -- | 85 | 30191 | 4898 | 52004904400406 | 2 | Potter | MILLS | SR 49-PA 49 | BRANCH COWANESQUE CR | 52/208 - HARRISON | 41.9444 | -77.6732 | 20150161136 | Comm | Need to Confirm Cable |  | OH |  |  | 2016-07-05
86a | -- | 86 | 30233 | 4899 | 52044900501401 | 2 | Potter | 2 MI N WALTON | SR 449-PA 449 | BUCKSELLER RUN | 52/223 - ULYSSES | 41.8127 | -77.7879 | 20151473258 | GAS | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2017-06-15
86b | -- | 86 | 30233 | 4899 | 52044900501401 | 2 | Potter | 2 MI N WALTON | SR 449-PA 449 | BUCKSELLER RUN | 52/223 - ULYSSES | 41.8127 | -77.7879 | 20151473258 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com |  |  |  | 2017-06-15
87 | -- | 87 | 30348 | 93373 | 52200201302331 | 2 | Potter | 2 MI SW GERMANIA STATION | SR 2002 | LYMAN RUN | 52/224 - WEST BRANCH | 41.7032 | -77.7375 | 20151463369 | Gas | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2017-05-23
88a | -- | 88 | 30435 | 85402 | 52402600220000 | 2 | Potter | ROULETTE | ON TSR 404 | FISHING CREEK | 52/217 - ROULETTE | 41.7818 | -78.1651 | 20151471424 | gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Brent A. Hoover, PE, 814-871-8606, hooverb@natfuel.com | UG |  |  | 2017-05-25
88b | -- | 88 | 30435 | 85402 | 52402600220000 | 2 | Potter | ROULETTE | ON TSR 404 | FISHING CREEK | 52/217 - ROULETTE | 41.7818 | -78.1651 | 20151471424 |  | Roulette TWP | Terry Meyers, 814-544-7549, roulettetwp@gmail.com, 424 Railroad Ave, Roulette PA 16746 | UG |  |  | 2017-05-25
88c | -- | 88 | 30435 | 85402 | 52402600220000 | 2 | Potter | ROULETTE | ON TSR 404 | FISHING CREEK | 52/217 - ROULETTE | 41.7818 | -78.1651 | 20151471424 | Gas | UGI Central Penn Gas | Roy Carr 570-829-8967 | UG |  |  | 2017-05-25
88d | -- | 88 | 30435 | 85402 | 52402600220000 | 2 | Potter | ROULETTE | ON TSR 404 | FISHING CREEK | 52/217 - ROULETTE | 41.7818 | -78.1651 | 20151471424 | Comm | Zito Media LP | Todd McManus, 814-260-9575 x107, todd.mcmanus@zitomedia.com |  |  |  | 2017-05-25
89a | -- | 89 | 6074 | 83457 | 8001403400602 | 3 | Bradford | TROY BORO | SR-14 | FALL BROOK | 08/413 - TROY | 41.7765 | -76.7922 | 20150501485 | Wtr | Troy Borough | TINA WOODWARD PH: 570- 297-2966; DANIEL J. CLOSE MGR, 297-2966 | UG |  |  | 2016-06-13
89b | -- | 89 | 6074 | 83457 | 8001403400602 | 3 | Bradford | TROY BORO | SR-14 | FALL BROOK | 08/413 - TROY | 41.7765 | -76.7922 | 20150501485 | GAS | UGI Central Penn Gas | Andrew Black, 570-829-8967, Dave Fisher PH: 570-473-7464, dfisher@ugipng.com | UG |  |  | 2016-06-13
89c | -- | 89 | 6074 | 83457 | 8001403400602 | 3 | Bradford | TROY BORO | SR-14 | FALL BROOK | 08/413 - TROY | 41.7765 | -76.7922 | 20150501485 | Elect | Pennsylvania Electric Company - need to confirm | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | OH |  |  | 2016-06-13
89d | -- | 89 | 6074 | 83457 | 8001403400602 | 3 | Bradford | TROY BORO | SR-14 | FALL BROOK | 08/413 - TROY | 41.7765 | -76.7922 | 20150501485 | Comm | Frontier or North Penn Telephone Company - need to confirm | John Smithkors, john.smithkors@ftr.com, 570-924-0094 | OH |  |  | 2016-06-13
89e | -- | 89 | 6074 | 83457 | 8001403400602 | 3 | Bradford | TROY BORO | SR-14 | FALL BROOK | 08/413 - TROY | 41.7765 | -76.7922 | 20150501485 | Comm | Blue Ridge Cable Television Inc. - need to confirm | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675 | OH |  |  | 2016-06-13
90a | Y | 90 | 6104 | 99281 | 8018704000000 | 3 | Bradford | 1 MILE SOUTH OF DURELL | SR 0187 | DURELL CREEK | 08/203 - ASYLUM | 41.7171 | -76.3591 | 20140270636 | Comm | Frontier Communications | John Smithkors (570) 265-7775 | OH |  | Coordinated | 2015-07-16
90b | Y | 90 | 6104 | 99281 | 8018704000000 | 3 | Bradford | 1 MILE SOUTH OF DURELL | SR 0187 | DURELL CREEK | 08/203 - ASYLUM | 41.7171 | -76.3591 | 20140270636 | Elect | Claverack Rural Electric Cooperative, Inc. | Debbie Allyn (570) 268-1308 | OH |  | Not Affected | 2015-07-16
91a | -- | 91 | 6136 | 5038 | 8022001301099 | 3 | Bradford | VILLAGE OF STEVENSON | SR 0220 | SOUTH BRANCH TOWANDA CR | 08/201 - ALBANY | 41.6218 | -76.4392 | 20143580167 | wtr | Towanda WTR & SWR/Towanda Borough | FRED JOHNSON, 570-265-5151, FREDDJ@EPIX.NET | UG |  |  | 2016-06-17
91b | -- | 91 | 6136 | 5038 | 8022001301099 | 3 | Bradford | VILLAGE OF STEVENSON | SR 0220 | SOUTH BRANCH TOWANDA CR | 08/201 - ALBANY | 41.6218 | -76.4392 | 20143580167 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | OH |  |  | 2016-06-17
91c | -- | 91 | 6136 | 5038 | 8022001301099 | 3 | Bradford | VILLAGE OF STEVENSON | SR 0220 | SOUTH BRANCH TOWANDA CR | 08/201 - ALBANY | 41.6218 | -76.4392 | 20143580167 | Comm | Frontier | John Smithkors, john.smithkors@ftr.com, 570-924-0094 | OH |  |  | 2016-06-17
91d | -- | 91 | 6136 | 5038 | 8022001301099 | 3 | Bradford | VILLAGE OF STEVENSON | SR 0220 | SOUTH BRANCH TOWANDA CR | 08/201 - ALBANY | 41.6218 | -76.4392 | 20143580167 | Comm | Blue Ridge Cable Television Inc. | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675 | OH |  |  | 2016-06-17
91e | -- | 91 | 6136 | 5038 | 8022001301099 | 3 | Bradford | VILLAGE OF STEVENSON | SR 0220 | SOUTH BRANCH TOWANDA CR | 08/201 - ALBANY | 41.6218 | -76.4392 | 20143580167 | Elect | Claverack Rural Electric Cooperative, Inc. | Debbie Allyn, debbiea@ctenterprises.org, (570) 268-1308; Charles Goodwin (Field Tech), 1-800-326-9799 | OH |  |  | 2016-06-17
92a | Y | 92 | 6164 | 5093 | 8036700101794 | 3 | Bradford | 3.5 MI.SOUTH OF SILVARA | SR 0367 | FARGO CREEK | 08/230 - TUSCARORA | 41.6554 | -76.1377 | 20140231230 | Comm | Blue Ridge Cable Television Inc. | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675 | OH |  | Coordinated | 06-01-15 A
92b | Y | 92 | 6164 | 5093 | 8036700101794 | 3 | Bradford | 3.5 MI.SOUTH OF SILVARA | SR 0367 | FARGO CREEK | 08/230 - TUSCARORA | 41.6554 | -76.1377 | 20140231230 | Comm | Frontier Communications | Jeff Bolton (570) 406-5319 | OH |  | Coordinated | 06-01-15 A
92c | Y | 92 | 6164 | 5093 | 8036700101794 | 3 | Bradford | 3.5 MI.SOUTH OF SILVARA | SR 0367 | FARGO CREEK | 08/230 - TUSCARORA | 41.6554 | -76.1377 | 20140231230 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | OH |  | Coordinated | 06-01-15 A
93a | -- | 93 | 6191 | 79247 | 8041403800000 | 3 | Bradford | VILLAGE OF FRANKLINDALE | SR 414 | TRIB.TO TOWANDA CREEK | 08/209 - FRANKLIN | 41.7028 | -76.5568 | 20150501470 |  | Franklin TWP | 570-364-5713, franklin.township.bc@gmail.com |  |  |  | 2016-09-13
93b | -- | 93 | 6191 | 79247 | 8041403800000 | 3 | Bradford | VILLAGE OF FRANKLINDALE | SR 414 | TRIB.TO TOWANDA CREEK | 08/209 - FRANKLIN | 41.7028 | -76.5568 | 20150501470 | Elect | Pennsylvania Electric Company - need to confirm | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | OH |  |  | 2016-09-13
94a | Y | 94 | 6193 | 76863 | 8046700100052 | 3 | Bradford | 2 MILE SOUTH OF ROME BORO | SR 467 | WYSOX CREEK | 08/220 - ROME | 41.8304 | -76.3501 | 20121810773 | Comm | Beaver Valley TV | Doug Soden (570) 247-2512 | OH |  | Prior | 2015-10-05
94b | Y | 94 | 6193 | 76863 | 8046700100052 | 3 | Bradford | 2 MILE SOUTH OF ROME BORO | SR 467 | WYSOX CREEK | 08/220 - ROME | 41.8304 | -76.3501 | 20121810773 | Comm | Frontier Communications | Steve Lathrop (570) 278-0036 | OH |  | Prior | 2015-10-05
94c | Y | 94 | 6193 | 76863 | 8046700100052 | 3 | Bradford | 2 MILE SOUTH OF ROME BORO | SR 467 | WYSOX CREEK | 08/220 - ROME | 41.8304 | -76.3501 | 20121810773 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | OH |  | Coordinated | 2015-10-05
95a | Y | 95 | 6203 | 5210 | 8046702700000 | 3 | Bradford | PIKE TWP .4M S SR 1013 | SR 467 | OVER ROCKWELL CREEK | 08/218 - PIKE | 41.8231 | -76.1839 | 20123382078 | Comm | Frontier Communications | Steve Lathrop (570) 278-0036 | OH |  | Prior | 2015-07-22
95b | Y | 95 | 6203 | 5210 | 8046702700000 | 3 | Bradford | PIKE TWP .4M S SR 1013 | SR 467 | OVER ROCKWELL CREEK | 08/218 - PIKE | 41.8231 | -76.1839 | 20123382078 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | UG |  | Not Affected | 2015-07-22
96a | Y | 96 | 6216 | 5039 | 8051402000863 | 3 | Bradford | 2.5 MI.N.OF W.FRANKLIN | SR 0514 | N BR TOWANDA CREEK | 08/210 - GRANVILLE | 41.7132 | -76.6387 | 20102561704 | Comm | Frontier Communications | Jan Kapson (570) 673-7107 | OH |  | Prior | 2015-08-05
96b | Y | 96 | 6216 | 5039 | 8051402000863 | 3 | Bradford | 2.5 MI.N.OF W.FRANKLIN | SR 0514 | N BR TOWANDA CREEK | 08/210 - GRANVILLE | 41.7132 | -76.6387 | 20102561704 | Elect | Claverack Rural Electric Cooperative, Inc. | Charles Goodwin (570) 406-5992 | OH |  | Coordinated | 2015-08-05
96c | Y | 96 | 6216 | 5039 | 8051402000863 | 3 | Bradford | 2.5 MI.N.OF W.FRANKLIN | SR 0514 | N BR TOWANDA CREEK | 08/210 - GRANVILLE | 41.7132 | -76.6387 | 20102561704 | Elect | Claverack Rural Electric Cooperative, Inc. | Charles Goodwin (570) 406-5992 | OH |  | Coordinated | 2015-08-05
97a | Y | 97 | 6224 | 5208 | 8070601701340 | 3 | Bradford | 2 MI. NE. OF CAMPTOWN | SR 0706 | COLD CREEK | 08/226 - STEVENS | 41.7477 | -76.2075 | 20140230920 | Elect | Southwestern Energy Company | Steve Loop (570) 996-4259 | OH |  | Coordinated | 2016-03-16
97b | Y | 97 | 6224 | 5208 | 8070601701340 | 3 | Bradford | 2 MI. NE. OF CAMPTOWN | SR 0706 | COLD CREEK | 08/226 - STEVENS | 41.7477 | -76.2075 | 20140230920 | Water | Southwestern Energy Company | Steve Loop (570) 996-4259 | UG |  | Not Affected | 2016-03-16
98a | Y | 98 | 6227 | 5215 | 8070602601160 | 3 | Bradford | STEVENS TWP .1M E LR08034 | SR 0706 | OVER ROSS CREEK | 08/226 - STEVENS | 41.7808 | -76.1399 | 20140230925 | Comm | Frontier Communications | Steve Lathrop (570) 278-0036 | UG |  | Not Affected | 2016-04-18
98b | Y | 98 | 6227 | 5215 | 8070602601160 | 3 | Bradford | STEVENS TWP .1M E LR08034 | SR 0706 | OVER ROSS CREEK | 08/226 - STEVENS | 41.7808 | -76.1399 | 20140230925 | Elect | Southwestern Energy Company | Steve Loop (570) 996-4259 | UG |  | Not Affected | 2016-04-18
99 | -- | 99 | 6348 | 98535 | 8105900700582 | 3 | Bradford | 1 MI. W. OF WARREN CENTER | SR 1059 | OVER WAPPASENING CREEK | 08/232 - WARREN | 41.9375 | -76.1941 | 2015561535 |  | all facilities responded clear per one call |  |  |  |  | 2017-08-01
100a | -- | 100 | 6476 | 5218 | 8401302501496 | 3 | Bradford | 0.25 MI N.OF MIDDLETOWN | S.R.4013 | MILLER RUN | 08/219 - RIDGEBURY | 41.9308 | -76.7021 | 20150501494 |  | all facilities responded clear per one call |  |  |  |  | 2016-08-08
100b | -- | 100 | 6476 | 5218 | 8401302501496 | 3 | Bradford | 0.25 MI N.OF MIDDLETOWN | S.R.4013 | MILLER RUN | 08/219 - RIDGEBURY | 41.9308 | -76.7021 | 20150501494 | Elect | Pennsylvania Electric Company or Tri-County Rural Electric Coop - need to confirm | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | OH |  |  | 2016-08-08
100c | -- | 100 | 6476 | 5218 | 8401302501496 | 3 | Bradford | 0.25 MI N.OF MIDDLETOWN | S.R.4013 | MILLER RUN | 08/219 - RIDGEBURY | 41.9308 | -76.7021 | 20150501494 | Comm | Blue Ridge Cable Television Inc. or North Penn Telephone Company - Need to Confirm | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675 | OH |  |  | 2016-08-08
101a | -- | 101 | 12486 | 5589 | 19004402401397 | 3 | Columbia | 1.9 MI NW OF JERSEYTOWN | WHITE HALL ROAD | TRIB E BR CHILLISQUAQUE | 19/213 - MADISON | 41.1038 | -76.6084 | 20150510819 |  | all facilities responded clear per one call |  |  |  |  | 2016-08-11
101b | -- | 101 | 12486 | 5589 | 19004402401397 | 3 | Columbia | 1.9 MI NW OF JERSEYTOWN | WHITE HALL ROAD | TRIB E BR CHILLISQUAQUE | 19/213 - MADISON | 41.1038 | -76.6084 | 20150510819 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | OH |  |  | 2016-08-11
101c | -- | 101 | 12486 | 5589 | 19004402401397 | 3 | Columbia | 1.9 MI NW OF JERSEYTOWN | WHITE HALL ROAD | TRIB E BR CHILLISQUAQUE | 19/213 - MADISON | 41.1038 | -76.6084 | 20150510819 | Comm | Verizon - Need to Confirm | Robert (Rob) Jaworski - 570-387-3172, robert.m.jaworski@verizon.com | OH |  |  | 2016-08-11
101d | -- | 101 | 12486 | 5589 | 19004402401397 | 3 | Columbia | 1.9 MI NW OF JERSEYTOWN | WHITE HALL ROAD | TRIB E BR CHILLISQUAQUE | 19/213 - MADISON | 41.1038 | -76.6084 | 20150510819 | Comm | Need to Confirm Phone |  | OH |  |  | 2016-08-11
102a | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | 20140270413 | Comm | Metro Cast | Dave Richards (570) 802-5642 | OH |  | Coordinated | 2015-09-18
102b | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | 20140270413 | Comm | Metro Cast | Dave Richards (570) 802-5642 | OH |  | Coordinated | 2015-09-18
102c | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | 20140270413 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-09-18
102d | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | 20140270413 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-09-18
102e | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | 20140270413 | Comm | Verizon Pennsylvania LLC | Rob Jaworski (570) 387-3172 | OH |  | Coordinated | 2015-09-18
102f | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | 20140270413 | Comm | Verizon Pennsylvania LLC | Rob Jaworski (570) 387-3172 | OH |  | Coordinated | 2015-09-18
102g | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | 20140270413 | Comm | Frontier Communications | Rob Januszko (570) 542-7116 | OH |  | Coordinated | 2015-09-18
102h | Y | 102 | 12555 | 98939 | 19025402500486 | 3 | Columbia | 3.5 MI E OF MILLVILLE | SR 254 | TRIB TO MUD RUN | 19/209 - GREENWOOD | 41.1351 | -76.4583 | 20140270413 | Comm | Frontier Communications | Rob Januszko (570) 542-7116 | OH |  | Coordinated | 2015-09-18
103a | Y | 103 | 12592 | 5578 | 19048703700177 | 3 | Columbia | 1 MILE N OF LIGHTSTREET | SR 487 | STONY BROOK CREEK | 19/219 - ORANGE | 41.0524 | -76.4285 | 20140270447 | N/A | N/A | N/A | N/A |  | Not Affected | 2015-07-16
104a | Y | 104 | 12738 | 78822 | 19403101120000 | 3 | Columbia | 3 MI W OF WALLER | S.R. 4031 | OVER LITTLE FISHING CR. | 19/211 - JACKSON | 41.1988 | -76.4669 | 20140271013, 20140271014 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com |  |  | Coordinated | 2015-07-22
104b | Y | 104 | 12738 | 78822 | 19403101120000 | 3 | Columbia | 3 MI W OF WALLER | S.R. 4031 | OVER LITTLE FISHING CR. | 19/211 - JACKSON | 41.1988 | -76.4669 | 20140271013, 20140271014 | Comm | Verizon Pennsylvania LLC | Robert Jaworski (570) 387-3172 |  |  | Coordinated | 2015-07-22
| R | 105 | 12745 | #REF! | 19403600120000 | 3 | Columbia | TOWN OF BLOOMSBURG | #N/A | OVER HEMLOCK CREEK | 19/211 - JACKSON | 41.1988 | -76.4669 | [7 empty] | 2015-07-22
106a | -- | 106 | 24511 | 91436 | 41001500702198 | 3 | Lycoming | 8 MILES S OF WILLIAMSPORT | SR 0015 | OVER BLACK HOLE CREEK | 41/207 - CLINTON | 41.1781 | -76.9111 | 20150540536 | Gas | UGI Central Penn Gas | Sharon Reese, 570-829-8754, sreese1@ugi.com | UG |  |  | 2017-02-21
106b | -- | 106 | 24511 | 91436 | 41001500702198 | 3 | Lycoming | 8 MILES S OF WILLIAMSPORT | SR 0015 | OVER BLACK HOLE CREEK | 41/207 - CLINTON | 41.1781 | -76.9111 | 20150540536 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-02-21
107a | Y | 107 | 24566 | 6049 | 41004403440880 | 3 | Lycoming | 4.5 MI S OF JERSEY SHORE | SR 44 | OVER ANTES CREEK | 41/218 - LIMESTONE | 41.164 | -77.2209 | 20102520477 | Comm | Comcast Cable Communications, Inc. | Tim Creswell (570) 329-9821 | OH |  | Coordinated | 2015-07-20
107b | Y | 107 | 24566 | 6049 | 41004403440880 | 3 | Lycoming | 4.5 MI S OF JERSEY SHORE | SR 44 | OVER ANTES CREEK | 41/218 - LIMESTONE | 41.164 | -77.2209 | 20102520477 | Comm | Pennsylvania Telephone Company | Timothy Reinhard (570) 745-7101 | OH |  | Coordinated | 2015-07-20
107c | Y | 107 | 24566 | 6049 | 41004403440880 | 3 | Lycoming | 4.5 MI S OF JERSEY SHORE | SR 44 | OVER ANTES CREEK | 41/218 - LIMESTONE | 41.164 | -77.2209 | 20102520477 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-20
108a | -- | 108 | 24591 | 6023 | 41008700600000 | 3 | Lycoming | 0.1 MI N OF FARRAGUT | SR 0087 (LR 291) | OVER TRIB TO LOYALSOCK C | 41/238 - UPPER FAIRFIELD | 41.2972 | -76.906 | 20150510827 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-07-21
108b | -- | 108 | 24591 | 6023 | 41008700600000 | 3 | Lycoming | 0.1 MI N OF FARRAGUT | SR 0087 (LR 291) | OVER TRIB TO LOYALSOCK C | 41/238 - UPPER FAIRFIELD | 41.2972 | -76.906 | 20150510827 | Comm | Herr Cable CO | RALPH HERR, 570-435-2656 or 435-2780 |  |  |  | 2016-07-21
109a | -- | 109 | 24603 | 6145 | 41011801700622 | 3 | Lycoming | VILLAGE OF LAIRDSVILLE | 118/TWP.RD.INTERS. | OVER BIG RUN | 41/212 - FRANKLIN | 41.2321 | -76.6095 | 20150161147 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Both |  |  | 2016-05-31
109b | -- | 109 | 24603 | 6145 | 41011801700622 | 3 | Lycoming | VILLAGE OF LAIRDSVILLE | 118/TWP.RD.INTERS. | OVER BIG RUN | 41/212 - FRANKLIN | 41.2321 | -76.6095 | 20150161147 | Comm | Windstream | KEN STAHLNECKER, 570-546-9250, KENNETH.STAHLNECKER@WINDSTREAM.COM | OH |  |  | 2016-05-31
109c | -- | 109 | 24603 | 6145 | 41011801700622 | 3 | Lycoming | VILLAGE OF LAIRDSVILLE | 118/TWP.RD.INTERS. | OVER BIG RUN | 41/212 - FRANKLIN | 41.2321 | -76.6095 | 20150161147 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com | OH |  |  | 2016-05-31
110a | -- | 110 | 24748 | 6045 | 41041400100417 | 3 | Lycoming | 2 MI N OF WATERVILLE | SR 414 | OVER UPPER PINE BOT.R. | 41/209 - CUMMINGS | 41.3207 | -77.3864 | 20150510840 | Comm | Comcast Cable Communications, Inc. | Tim Criswell, 570-329-9821, timothy_criswell@cable.comcast.com; Keith Allridge, Keith_Allridge@cable.comcast.com |  |  |  | 2017-06-01
110b | -- | 110 | 24748 | 6045 | 41041400100417 | 3 | Lycoming | 2 MI N OF WATERVILLE | SR 414 | OVER UPPER PINE BOT.R. | 41/209 - CUMMINGS | 41.3207 | -77.3864 | 20150510840 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com, engineering supervisor - Zach Reedy, zreedy@firstenergycorp.com |  |  |  | 2017-06-01
111a | -- | 111 | 24751 | 6054 | 41041400800000 | 3 | Lycoming | VILLAGE OF JERSEY MILLS | SR 414 | OVER CALLAHAN RUN | 41/221 - MCHENRY | 41.36 | -77.4116 | 20150161160 | Elect | Tri-County Rural Electric Cooperative Inc. | Jess Kipferl, 570-6723-3160 jessk@ctenterprises.com | OH |  |  | 2016-07-08
111b | -- | 111 | 24751 | 6054 | 41041400800000 | 3 | Lycoming | VILLAGE OF JERSEY MILLS | SR 414 | OVER CALLAHAN RUN | 41/221 - MCHENRY | 41.36 | -77.4116 | 20150161160 | comm | Verizon | Jason Wagner, 570-327-7891, jason.e.wagner@verizon.com | OH |  |  | 2016-07-08
111c | -- | 111 | 24751 | 6054 | 41041400800000 | 3 | Lycoming | VILLAGE OF JERSEY MILLS | SR 414 | OVER CALLAHAN RUN | 41/221 - MCHENRY | 41.36 | -77.4116 | 20150161160 | Comm | Blue Ridge Cable Television Inc. | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675 |  |  |  | 2016-07-08
111d | -- | 111 | 24751 | 6054 | 41041400800000 | 3 | Lycoming | VILLAGE OF JERSEY MILLS | SR 414 | OVER CALLAHAN RUN | 41/221 - MCHENRY | 41.36 | -77.4116 | 20150161160 | Comm | Comcast Cable Communications, Inc. | Tim Cresswell, 570-329-9821, timothy_criswell@cable.comcast.com |  |  |  | 2016-07-08
111e | -- | 111 | 24751 | 6054 | 41041400800000 | 3 | Lycoming | VILLAGE OF JERSEY MILLS | SR 414 | OVER CALLAHAN RUN | 41/221 - MCHENRY | 41.36 | -77.4116 | 20150161160 | Comm | Cable - need to confirm | RALPH HERR, 570-435-2656 or 435-2780 | OH |  |  | 2016-07-08
112a | Y | 112 | 24850 | 6057 | 41200200320000 | 3 | Lycoming | 3 MI W OF ELIMSPORT | SR 2002 | OVER WHITE DEER HOLE CR | 41/239 - WASHINGTON | 41.1189 | -77.0668 | 20130590226 | Comm | Comcast Cable Communications, Inc. | Richard Roberts (570) 329-9818 | OH |  | Prior | 2015-08-31
112b | Y | 112 | 24850 | 6057 | 41200200320000 | 3 | Lycoming | 3 MI W OF ELIMSPORT | SR 2002 | OVER WHITE DEER HOLE CR | 41/239 - WASHINGTON | 41.1189 | -77.0668 | 20130590226 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | OH |  | Prior | 2015-08-31
112c | Y | 112 | 24850 | 6057 | 41200200320000 | 3 | Lycoming | 3 MI W OF ELIMSPORT | SR 2002 | OVER WHITE DEER HOLE CR | 41/239 - WASHINGTON | 41.1189 | -77.0668 | 20130590226 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Kenneth C. Stahlnecker (570) 546-9250 | OH |  | Prior | 2015-08-31
113a | -- | 113 | 24881 | 6052 | 41201501720000 | 3 | Lycoming | 1 MI NORTH OF LAIRDSVILLE | SR 2015 | OVER BIG RUN | 41/212 - FRANKLIN | 41.2445 | -76.6174 | 20150540567 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-06-27
113b | -- | 113 | 24881 | 6052 | 41201501720000 | 3 | Lycoming | 1 MI NORTH OF LAIRDSVILLE | SR 2015 | OVER BIG RUN | 41/212 - FRANKLIN | 41.2445 | -76.6174 | 20150540567 | Gas | Regency Energy Partners (PVR Marcellus) | 570-505-3700 | UG |  |  | 2017-06-27
114a | Y | 114 | 24928 | 74022 | 41205000120000 | 3 | Lycoming | 2.5 MI E OF LAIRDSVILLE | SR 2050 | OVER LITTLE MUNCY CREEK | 41/216 - JORDAN | 41.2428 | -76.561 | 20121721769, 20121721770 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-22
114b | Y | 114 | 24928 | 74022 | 41205000120000 | 3 | Lycoming | 2.5 MI E OF LAIRDSVILLE | SR 2050 | OVER LITTLE MUNCY CREEK | 41/216 - JORDAN | 41.2428 | -76.561 | 20121721769, 20121721770 | Comm | Verizon Pennsylvania LLC | Robert Jaworski (570) 387-3172 | OH |  | Coordinated | 2015-07-22
115a | -- | 115 | 24938 | 6144 | 41206101702204 | 3 | Lycoming | 3MI.E OF HUGHESVILLE | SR 2061 | OVER SUGAR RUN | 41/226 - MORELAND | 41.2432 | -76.6833 | 20150540589 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-08-01
115b | -- | 115 | 24938 | 6144 | 41206101702204 | 3 | Lycoming | 3MI.E OF HUGHESVILLE | SR 2061 | OVER SUGAR RUN | 41/226 - MORELAND | 41.2432 | -76.6833 | 20150540589 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Aldona (Ann) Pilarczyk, 319-790-6779, Aldona.Pilarczyk@windstream.com | OH |  |  | 2017-08-01
116a | -- | 116 | 28361 | 6387 | 47025400200000 | 3 | Montour | 4.5 M W OF LIMESTONEVILLE | SR 254 | OVER LIMESTONE RUN | 47/205 - LIMESTONE | 41.0322 | -76.7506 | 20143571637 | Comm | Verizon North LLC | Robert (Rob) Jaworski - 570-387-3172, robert.m.jaworski@verizon.com | UG |  |  | 2016-05-12
116b | -- | 116 | 28361 | 6387 | 47025400200000 | 3 | Montour | 4.5 M W OF LIMESTONEVILLE | SR 254 | OVER LIMESTONE RUN | 47/205 - LIMESTONE | 41.0322 | -76.7506 | 20143571637 | gas | UGI Central Penn Gas | Sharon Reese, 570-829-8754, sreese1@ugi.com | UG |  |  | 2016-05-12
116c | -- | 116 | 28361 | 6387 | 47025400200000 | 3 | Montour | 4.5 M W OF LIMESTONEVILLE | SR 254 | OVER LIMESTONE RUN | 47/205 - LIMESTONE | 41.0322 | -76.7506 | 20143571637 | Elect | Need to Confirm Electric |  | UG |  |  | 2016-05-12
117 | -- | 117 | 28387 | 6381 | 47100600100570 | 3 | Montour | 3 MI.N.WASHINGTONVILLE | SR 1006 | MCKEE CREEK | 47/201 - ANTHONY | 41.0928 | -76.7045 | 20150540599 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-08-01
118a | Y | 118 | 28389 | 74037 | 47100600500000 | 3 | Montour | 7MI NE OF WASHINGTOVILLE | SR 1006 | BR OF CHILLISQUAQUE CR. | 47/201 - ANTHONY | 41.0989 | -76.6614 | 20130310595 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-16
118b | Y | 118 | 28389 | 74037 | 47100600500000 | 3 | Montour | 7MI NE OF WASHINGTOVILLE | SR 1006 | BR OF CHILLISQUAQUE CR. | 47/201 - ANTHONY | 41.0989 | -76.6614 | 20130310595 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-16
118c | Y | 118 | 28389 | 74037 | 47100600500000 | 3 | Montour | 7MI NE OF WASHINGTOVILLE | SR 1006 | BR OF CHILLISQUAQUE CR. | 47/201 - ANTHONY | 41.0989 | -76.6614 | 20130310595 | Comm | Verizon Pennsylvania LLC | Robert Jaworski (570) 387-3172 | OH |  | Coordinated | 2015-07-16
118d | Y | 118 | 28389 | 74037 | 47100600500000 | 3 | Montour | 7MI NE OF WASHINGTOVILLE | SR 1006 | BR OF CHILLISQUAQUE CR. | 47/201 - ANTHONY | 41.0989 | -76.6614 | 20130310595 | Comm | Verizon Pennsylvania LLC | Robert Jaworski (570) 387-3172 | OH |  | Coordinated | 2015-07-16
119a | -- | 119 | 29174 | 97586 | 49102700400616 | 3 | Northumberland | VILLAGE OF POTTSGROVE | SR 1027 | OVER ROSS RUN | 49/203 - EAST CHILLISQUA | 40.9955 | -76.7899 | 20150510365 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-07-24
119b | -- | 119 | 29174 | 97586 | 49102700400616 | 3 | Northumberland | VILLAGE OF POTTSGROVE | SR 1027 | OVER ROSS RUN | 49/203 - EAST CHILLISQUA | 40.9955 | -76.7899 | 20150510365 | sanitary | Milton Regional Sewer Auth | GEORGE MYERS, 570-742-3424, gmyers@miltonwwtp.org | UG |  |  | 2017-07-24
120a | -- | 120 | 29178 | 6669 | 49200100200000 | 3 | Northumberland | 3 MI N OF ELYSBURG BORO | SR 2001 | LITTLE ROARING CREEK | 49/214 - RUSH | 40.8906 | -76.5581 | 20151412504 | Elect | PPL Electric Utilities Corporation | Denise Gray, 484-634-3756 | Both |  |  | 2016-08-11
120b | -- | 120 | 29178 | 6669 | 49200100200000 | 3 | Northumberland | 3 MI N OF ELYSBURG BORO | SR 2001 | LITTLE ROARING CREEK | 49/214 - RUSH | 40.8906 | -76.5581 | 20151412504 | Comm | Verizon | Robert (Rob) Jaworski - 570-387-3172, robert.m.jaworski@verizon.com | OH |  |  | 2016-08-11
120c | -- | 120 | 29178 | 6669 | 49200100200000 | 3 | Northumberland | 3 MI N OF ELYSBURG BORO | SR 2001 | LITTLE ROARING CREEK | 49/214 - RUSH | 40.8906 | -76.5581 | 20151412504 |  | Snydertown Borough | 570-672-2190 |  |  |  | 2016-08-11
121 | -- | 121 | 29303 | 79230 | 49402000301775 | 3 | Northumberland | 2.5 MI NW OF FISHERS FERRY | SR 4020 | HOLLOWING RUN | 49/208 - LOWER AUGUSTA | 40.7919 | -76.817 | 20150510353 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-08-01
122a | -- | 122 | 29306 | 6603 | 49402200101591 | 3 | Northumberland | .25 MI E OF FISHERS FERRY | SR 4022 | OVER BOILE RUN | 49/208 - LOWER AUGUSTA | 40.762 | -76.8353 | 20150161786 |  | all facilities responded clear per one call |  |  |  |  | 2016-06-14
122b | -- | 122 | 29306 | 6603 | 49402200101591 | 3 | Northumberland | .25 MI E OF FISHERS FERRY | SR 4022 | OVER BOILE RUN | 49/208 - LOWER AUGUSTA | 40.762 | -76.8353 | 20150161786 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | OH |  |  | 2016-06-14
122c | -- | 122 | 29306 | 6603 | 49402200101591 | 3 | Northumberland | .25 MI E OF FISHERS FERRY | SR 4022 | OVER BOILE RUN | 49/208 - LOWER AUGUSTA | 40.762 | -76.8353 | 20150161786 | Comm | Verizon | Jerry Van Buskirk, jerry.vanbuskirk@verizon.com | OH |  |  | 2016-06-14
123a | -- | 123 | 29311 | 88047 | 49402600100165 | 3 | Northumberland | 2 MI S OF AUGUSTAVILLE | SR 4026 | OVER LITTLE SHAMOKIN CR. | 49/213 - ROCKEFELLER | 40.7907 | -76.7248 | 20150540865 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-05-25
123b | -- | 123 | 29311 | 88047 | 49402600100165 | 3 | Northumberland | 2 MI S OF AUGUSTAVILLE | SR 4026 | OVER LITTLE SHAMOKIN CR. | 49/213 - ROCKEFELLER | 40.7907 | -76.7248 | 20150540865 | Comm | Service Electric Cablevision, Inc. | DWIGHT WALTER, 570-286-9662 |  |  |  | 2017-05-25
124a | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | 20150510372 | wtr | Aqua Pennsylvania | Josh Shoff, 570-443-7099 x55502, jpshoff@aquaamerica.com | UG |  |  | 2016-08-11
124b | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | 20150510372 | sanitary | Eastern Snyder Cnty Reg Auth | Scott Bailey, 570-374-1173, escra@verizon.net | UG | 10 and 16" |  | 2016-08-11
124c | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | 20150510372 |  | Hummels Wharf Municipal Auth | SANDI GILL, 570-743-1284, hummelswharfmunauth@hotmail.com |  |  |  | 2016-08-11
124d | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | 20150510372 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | Both |  |  | 2016-08-11
124e | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | 20150510372 | gas | UGI Central Penn Gas | Sharon Reese, 570-829-8754, sreese1@ugi.com | UG | 3" |  | 2016-08-11
124f | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | 20150510372 | Comm | Service Electric Cablevision, Inc. | DWIGHT WALTER, 570-286-9662 |  |  |  | 2016-08-11
124g | -- | 124 | 31169 | 88799 | 54102300401962 | 3 | Snyder | VILLAGE OF HUMMELS WHARF | OLD TRAIL | TRIB TO SUSQUEHANNA RVR | 54/208 - MONROE | 40.8299 | -76.8365 | 20150510372 | Comm | Verizon | Robert (Rob) Jaworski - 570-387-3172, robert.m.jaworski@verizon.com | OH |  |  | 2016-08-11
125a | -- | 125 | 31948 | 89977 | 56008701100148 | 3 | Sullivan | VILLAGE OF HILLSGROVE | SR 0087 | OVER MILL CREEK | 56/207 - HILLSGROVE | 41.4441 | -76.7066 | 20150510439 | Comm | Herr Cable CO | RALPH HERR, 570-435-2656 or 435-2780 | OH |  |  | 2016-12-12
125b | -- | 125 | 31948 | 89977 | 56008701100148 | 3 | Sullivan | VILLAGE OF HILLSGROVE | SR 0087 | OVER MILL CREEK | 56/207 - HILLSGROVE | 41.4441 | -76.7066 | 20150510439 | Elect | Sullivan County Rural Electric Coop Inc | Walter Tubach, wtubach@epix.net, 570-924-3381 |  |  |  | 2016-12-12
126a | Y | 126 | 31966 | 7021 | 56008705202440 | 3 | Sullivan | 0.25 MI W OF DUSHORE | SR 87 | OVER LITTLE LOYALSOCK CR | 56/201 - CHERRY | 41.5162 | -76.4103 | 20140621066 | Comm | Blue Ridge Cable Television Inc. | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675 | OH |  | Coordinated | 2015-08-03
126b | Y | 126 | 31966 | 7021 | 56008705202440 | 3 | Sullivan | 0.25 MI W OF DUSHORE | SR 87 | OVER LITTLE LOYALSOCK CR | 56/201 - CHERRY | 41.5162 | -76.4103 | 20140621066 | Comm | Frontier Communications | John Smithkors (570) 265-7775 | OH |  | Coordinated | 2015-08-03
126c | Y | 126 | 31966 | 7021 | 56008705202440 | 3 | Sullivan | 0.25 MI W OF DUSHORE | SR 87 | OVER LITTLE LOYALSOCK CR | 56/201 - CHERRY | 41.5162 | -76.4103 | 20140621066 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | OH |  | Coordinated | 2015-08-03
127 | -- | 127 | 31981 | 7009 | 56015401501564 | 3 | Tioga | 4 MI SE OF FORKSVILLE | SR154 | OVER DOUBLE RUN | 56/205 - FORKS | 41.466 | -76.579 | 20150540906 |  | all facilities responded clear per one call |  |  |  |  | 2016-11-28
128a | -- | 128 | 32822 | 7326 | 58004901400434 | 3 | Tioga | 0.5 MI E OF WESTFIELD | SR 49 | OVER CALIFORNIA BROOK | 58/230 - WESTFIELD | 41.9264 | -77.5213 | 20150540886 | gas | UGI Central Penn Gas | Sharon Reese, 570-829-8754, sreese1@ugi.com | UG |  |  | 2016-06-27
128b | -- | 128 | 32822 | 7326 | 58004901400434 | 3 | Tioga | 0.5 MI E OF WESTFIELD | SR 49 | OVER CALIFORNIA BROOK | 58/230 - WESTFIELD | 41.9264 | -77.5213 | 20150540886 |  | Westfield TWP | Tony Darslow, 814-367-2632 | UG |  |  | 2016-06-27
128c | -- | 128 | 32822 | 7326 | 58004901400434 | 3 | Tioga | 0.5 MI E OF WESTFIELD | SR 49 | OVER CALIFORNIA BROOK | 58/230 - WESTFIELD | 41.9264 | -77.5213 | 20150540886 | Elect | Pennsylvania Electric Company - need to confirm | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | OH |  |  | 2016-06-27
128d | -- | 128 | 32822 | 7326 | 58004901400434 | 3 | Tioga | 0.5 MI E OF WESTFIELD | SR 49 | OVER CALIFORNIA BROOK | 58/230 - WESTFIELD | 41.9264 | -77.5213 | 20150540886 | Comm | Westfield Community Antenna Assoc. Inc - need to confirm | 814-367-5190 | OH |  |  | 2016-06-27
129a | Y | 129 | 32843 | 7251 | 58024903220000 | 3 | Tioga | 3.5 MI E OF WESTFIELD | SR 249 | OVER JEMISON CREEK | 58/230 - WESTFIELD | 41.9334 | -77.4793 | 20120531621 | Comm | Westview TV | Sean, (814) 367-5190 | OH |  | Prior | 2015-07-13
129b | Y | 129 | 32843 | 7251 | 58024903220000 | 3 | Tioga | 3.5 MI E OF WESTFIELD | SR 249 | OVER JEMISON CREEK | 58/230 - WESTFIELD | 41.9334 | -77.4793 | 20120531621 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | OH |  | Prior | 2015-07-13
129c | Y | 129 | 32843 | 7251 | 58024903220000 | 3 | Tioga | 3.5 MI E OF WESTFIELD | SR 249 | OVER JEMISON CREEK | 58/230 - WESTFIELD | 41.9334 | -77.4793 | 20120531621 | Gas | UGI Central Penn Gas, Inc. | Roy Carr (570) 829-8967 | UG |  | Not Affected | 2015-07-13
129d | Y | 129 | 32843 | 7251 | 58024903220000 | 3 | Tioga | 3.5 MI E OF WESTFIELD | SR 249 | OVER JEMISON CREEK | 58/230 - WESTFIELD | 41.9334 | -77.4793 | 20120531621 | Comm | Verizon North LLC | Denny Vicary, 814-857-7613, dennis.m.vicary@one.verizon.com | OH |  | Prior | 2015-07-13
130a | -- | 130 | 32931 | 87929 | 58054902602539 | 3 | Tioga | 0.5 MI S OF JOBS CORNERS | SR 549 | OVER SEELY CREEK | 58/215 - JACKSON | 41.9301 | -76.9323 | 20150540876 |  | all facilities responded clear per one call |  |  |  |  | 2016-08-11
130b | -- | 130 | 32931 | 87929 | 58054902602539 | 3 | Tioga | 0.5 MI S OF JOBS CORNERS | SR 549 | OVER SEELY CREEK | 58/215 - JACKSON | 41.9301 | -76.9323 | 20150540876 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | OH |  |  | 2016-08-11
130c | -- | 130 | 32931 | 87929 | 58054902602539 | 3 | Tioga | 0.5 MI S OF JOBS CORNERS | SR 549 | OVER SEELY CREEK | 58/215 - JACKSON | 41.9301 | -76.9323 | 20150540876 | Comm | North Penn Telephone Company | 570-549-6736 | OH |  |  | 2016-08-11
131a | Y | 131 | 33080 | 79055 | 58300103901413 | 3 | Tioga | 1 MI S OF WATROUS | S.R.3001 | OVER ELK RUN | 58/213 - GAINES | 41.7352 | -77.5822 | 20102730430 | Comm | Gaines Watrous TV Company | Melvin Lowrey, 814-435-6578 | OH |  | Prior | 2015-08-06
131b | Y | 131 | 33080 | 79055 | 58300103901413 | 3 | Tioga | 1 MI S OF WATROUS | S.R.3001 | OVER ELK RUN | 58/213 - GAINES | 41.7352 | -77.5822 | 20102730430 | Comm | Verizon Pennsylvania LLC | Denny Vicary, 814-857-7613, dennis.m.vicary@one.verizon.com | OH |  | Not Affected | 2015-08-06
131c | Y | 131 | 33080 | 79055 | 58300103901413 | 3 | Tioga | 1 MI S OF WATROUS | S.R.3001 | OVER ELK RUN | 58/213 - GAINES | 41.7352 | -77.5822 | 20102730430 | Elect | Tri-County Rural Electric Cooperative Inc. | Steve Salada PH; 570-662-8034 steves@ctenterprises.com | OH |  | Prior | 2015-08-06
131d | Y | 131 | 33080 | 79055 | 58300103901413 | 3 | Tioga | 1 MI S OF WATROUS | S.R.3001 | OVER ELK RUN | 58/213 - GAINES | 41.7352 | -77.5822 | 20102730430 | Elect | Tri-County Rural Electric Cooperative Inc. | Steve Salada PH; 570-662-8034 steves@ctenterprises.com | OH |  | Coordinated | 2015-08-06
132a | Y | 132 | 33083 | 7136 | 58300500400000 | 3 | Tioga | VILLAGE OF DRAPER | SR 3005 | OVER STONY FORK CREEK | 58/208 - DELMAR | 41.6215 | -77.3662 | 20120531574 | ??? | Delmar Township | Shirley W. Borden (570) 724-5482 | UG |  | Not Affected | 2015-09-25
132b | Y | 132 | 33083 | 7136 | 58300500400000 | 3 | Tioga | VILLAGE OF DRAPER | SR 3005 | OVER STONY FORK CREEK | 58/208 - DELMAR | 41.6215 | -77.3662 | 20120531574 | Gas | UGI Central Penn Gas, Inc. | Roy Carr (570) 829-8967 | UG |  | Not Affected | 2015-09-25
132c | Y | 132 | 33083 | 7136 | 58300500400000 | 3 | Tioga | VILLAGE OF DRAPER | SR 3005 | OVER STONY FORK CREEK | 58/208 - DELMAR | 41.6215 | -77.3662 | 20120531574 | Comm | Frontier Communications | Jan Kapson (570) 673-7107 | OH |  | Prior | 2015-09-25
132d | Y | 132 | 33083 | 7136 | 58300500400000 | 3 | Tioga | VILLAGE OF DRAPER | SR 3005 | OVER STONY FORK CREEK | 58/208 - DELMAR | 41.6215 | -77.3662 | 20120531574 | Comm | Blue Ridge Cable Television Inc. | Richard (Rick) Hebda, rhebda@brctv.com, 610-826-9675 | OH |  | Prior | 2015-09-25
132e | Y | 132 | 33083 | 7136 | 58300500400000 | 3 | Tioga | VILLAGE OF DRAPER | SR 3005 | OVER STONY FORK CREEK | 58/208 - DELMAR | 41.6215 | -77.3662 | 20120531574 | Elect | Wellsboro Electric Company | Dave Kennedy (570) 724-3516 | OH |  | Prior | 2015-09-25
133a | Y | 133 | 33180 | 7347 | 58401702800000 | 3 | Tioga | 2 MI NW OF OSCEOLA | SR 4017 | HOLDEN CREEK | 58/221 - OSCEOLA | 41.9921 | -77.3798 | 20130461235 | Elect | Pennsylvania Electric Company | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com |  |  | Prior | 2015-07-30
133b | Y | 133 | 33180 | 7347 | 58401702800000 | 3 | Tioga | 2 MI NW OF OSCEOLA | SR 4017 | HOLDEN CREEK | 58/221 - OSCEOLA | 41.9921 | -77.3798 | 20130461235 | Comm | Verizon | Denny Vicary, 814-857-7613, dennis.m.vicary@one.verizon.com |  |  | Prior | 2015-07-30
134a | -- | 134 | 33209 | 83470 | 58403501300426 | 3 | Tioga | 3.5 MI NE OF WELLSBORO | SR 4035 | OVER CATLIN HOLLOW CREEK | 58/203 - CHARLESTON | 41.7979 | -77.2643 | 20150510450 | GAS | UGI Central Penn Gas | Andrew Black, 570-829-8967, Dave Fisher PH: 570-473-7464, dfisher@ugipng.com | UG |  |  | 2016-08-03
134b | -- | 134 | 33209 | 83470 | 58403501300426 | 3 | Tioga | 3.5 MI NE OF WELLSBORO | SR 4035 | OVER CATLIN HOLLOW CREEK | 58/203 - CHARLESTON | 41.7979 | -77.2643 | 20150510450 | Elect | Pennsylvania Electric Company or Wellsboro Electric Company - need to confirm | Steve Beers (570)-265-1237, sbeers@firstenergycorp.com Dan Dieffenbach, ddieffenbach@firstenergycorp.com | OH |  |  | 2016-08-03
135a | -- | 135 | 33469 | 7542 | 59100101101961 | 3 | Union | 2.5 MI W OF KELLY CROSSRD | SR 1001 | OVER SPRUCE RUN | 59/201 - BUFFALO | 41.0124 | -76.9825 | 20150161176, 20150161177 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Anthony "TJ" Seekins, 501-748-4447, anthony.seekins.jr@windstream.com | OH |  |  | 2016-07-11
135b | -- | 135 | 33469 | 7542 | 59100101101961 | 3 | Union | 2.5 MI W OF KELLY CROSSRD | SR 1001 | OVER SPRUCE RUN | 59/201 - BUFFALO | 41.0124 | -76.9825 | 20150161176, 20150161177 | Elect | Citizens Electric Company of Lewisburg - need to confirm | 570-524-2231 | OH |  |  | 2016-07-11
136a | -- | 136 | 33470 | 7542 | 59100101102058 | 3 | Union | 2.5 MI W OF KELLY CROSSRD | SR 1001 | OVER SPRUCE RUN | 59/205 - KELLY | 41.0124 | -76.9822 | 20150540916, 20150540917 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Dustin Velcoff, 501-748-4434, dustin.velcoff@windstream.com | OH |  |  | 2016-07-11
136b | -- | 136 | 33470 | 7542 | 59100101102058 | 3 | Union | 2.5 MI W OF KELLY CROSSRD | SR 1001 | OVER SPRUCE RUN | 59/205 - KELLY | 41.0124 | -76.9822 | 20150540916, 20150540917 | Elect | Citizens Electric Company of Lewisburg - need to confirm | 570-524-2231 | OH |  |  | 2016-07-11
137a | Y | 137 | 33478 | 83478 | 59100300200000 | 3 | Union | 2 MI NE BUFFALO CROSS RDS | SR 1003 | OVER BUFFALO CREEK | 59/201 - BUFFALO | 40.9734 | -76.9525 | 20113201954, 20113201955 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | OH |  | Not Affected | 2015-08-10
137b | Y | 137 | 33478 | 83478 | 59100300200000 | 3 | Union | 2 MI NE BUFFALO CROSS RDS | SR 1003 | OVER BUFFALO CREEK | 59/201 - BUFFALO | 40.9734 | -76.9525 | 20113201954, 20113201955 | Comm | Windstream | Jeremy Kennedy (570) 522-5707 | OH |  | Prior | 2015-08-10
137c | Y | 137 | 33478 | 83478 | 59100300200000 | 3 | Union | 2 MI NE BUFFALO CROSS RDS | SR 1003 | OVER BUFFALO CREEK | 59/201 - BUFFALO | 40.9734 | -76.9525 | 20113201954, 20113201955 | Elect | Citizens Electric | John Kelchner (570) 522-6143 | OH | Unk | Prior | 2015-08-10
138a | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | 20102451630 | Comm | Atlantic Broadband | Rich Fultz (814) 248-5338 | OH |  | Coordinated | 2016-06-20
138b | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | 20102451630 | Comm | Atlantic Broadband | Rich Fultz (814) 248-5338 | OH |  | Coordinated | 2016-06-20
138c | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | 20102451630 | ??? | Hartley Township Municipal Authority | Norm Strickler (570) 922-1310 | UG |  | Not Affected | 2016-06-20
138d | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | 20102451630 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2016-06-20
138e | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | 20102451630 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2016-06-20
138f | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | 20102451630 | Comm | Windstream | Jeremy Kennedy (570) 522-5707 | OH |  | Coordinated | 2016-06-20
138g | Y | 138 | 33543 | 74043 | 59300202000501 | 3 | Union | VILLAGE OF LAURELTON | SR 3002 | OVER LAUREL RUN | 59/204 - HARTLEY | 40.8831 | -77.1972 | 20102451630 | Comm | Windstream | Jeremy Kennedy (570) 522-5707 | OH |  | Coordinated | 2016-06-20
139a | -- | 139 | 20820 | 96689 | 35401900200731 | 4 | Lackawanna | S ABINGTON TP OVER I-81 | SR 4019 EDELLA RD | SR 0081 I-81 | 35/219 - SOUTH ABINGTON | 41.4894 | -75.6804 | 20143521244 | wtr | Pennsylvania American Water CO | Scott Reiner, Cell #570-840-8395, scott.reiner@amwater.com, JOE GRABOSKI (570) 586-6934 | UG |  |  | 2016-05-27
139b | -- | 139 | 20820 | 96689 | 35401900200731 | 4 | Lackawanna | S ABINGTON TP OVER I-81 | SR 4019 EDELLA RD | SR 0081 I-81 | 35/219 - SOUTH ABINGTON | 41.4894 | -75.6804 | 20143521244 | wtr | PENNSYLVANIA AMERICAN WATER CO Wilkes-Barre | Scott Reiner, Cell #570-840-8395, scott.reiner@amwater.com, PETE SARMONIS (570) 830-6540 | UG |  |  | 2016-05-27
139c | -- | 139 | 20820 | 96689 | 35401900200731 | 4 | Lackawanna | S ABINGTON TP OVER I-81 | SR 4019 EDELLA RD | SR 0081 I-81 | 35/219 - SOUTH ABINGTON | 41.4894 | -75.6804 | 20143521244 | sanitary & wtr | South Abington TWP | David G. O’Neill, #570-587-8717, davido01@comcast.net, MERLE HATFIELD (570) 586-2111 | UG | 12" san & 12" wtr |  | 2016-05-27
139d | -- | 139 | 20820 | 96689 | 35401900200731 | 4 | Lackawanna | S ABINGTON TP OVER I-81 | SR 4019 EDELLA RD | SR 0081 I-81 | 35/219 - SOUTH ABINGTON | 41.4894 | -75.6804 | 20143521244 | Elect | PPL Electric Utilities Corporation | CHARLOTTE KRUPA, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-05-27
139e | -- | 139 | 20820 | 96689 | 35401900200731 | 4 | Lackawanna | S ABINGTON TP OVER I-81 | SR 4019 EDELLA RD | SR 0081 I-81 | 35/219 - SOUTH ABINGTON | 41.4894 | -75.6804 | 20143521244 | gas | UGI Central Penn Gas | Sharon Reese, 570-829-8754, sreese1@ugi.com | UG | 4" |  | 2016-05-27
140a | -- | 140 | 23795 | 67364 | 40011501200000 | 4 | Luzerne | BEAR CR TW 1.2M S SR 2038 | SR 0115 TR 115 | SHADES CREEK | 40/201 - BEAR CREEK | 41.1809 | -75.6994 | 20150420607 | Elect | PPL Electric Utilities Corporation | CHARLOTTE KRUPA, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-06-17
140b | -- | 140 | 23795 | 67364 | 40011501200000 | 4 | Luzerne | BEAR CR TW 1.2M S SR 2038 | SR 0115 TR 115 | SHADES CREEK | 40/201 - BEAR CREEK | 41.1809 | -75.6994 | 20150420607 | Elect | Wind Park Bear Creek | Brandon Nehring, brandon.nehring@infigen-us.com; 570-821-8572; 570-820-7750 |  |  |  | 2016-06-17
141 | -- | 141 | 24493 | 97506 | 40800500201030 | 4 | Luzerne | BUTLER TWP OVER I-80 WB | SR 8005 RAMP E | SR 0080 I-80 WB | 40/204 - BUTLER | 41.0483 | -76.0083 | 20150420631 | Gas | Amerigas Propane LP | Brenda Pulse, brenda.pulse@amerigas.com, 570-253-2490 | UG |  |  | 2016-06-24
142a | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Comm | Blue Ridge Cable Television Inc. | Alice Muniz (610) 826-2551; Dwight Hunsicker (610) 826-9312 | OH |  | Coordinated | 06-29-15 A
142b | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Comm | Blue Ridge Cable Television Inc. | Alice Muniz (610) 826-2551; Dwight Hunsicker (610) 826-9312 | OH |  | Coordinated | 06-29-15 A
142c | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Comm | Blue Ridge Cable Television Inc. | Alice Muniz (610) 826-2551; Dwight Hunsicker (610) 826-9312 | OH |  | Coordinated | 06-29-15 A
142d | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Comm | Blue Ridge Cable Television Inc. | Alice Muniz (610) 826-2551; Dwight Hunsicker (610) 826-9312 | OH |  | Coordinated | 06-29-15 A
142e | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | OH |  | Coordinated | 06-29-15 A
142f | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | OH |  | Coordinated | 06-29-15 A
142g | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | OH |  | Coordinated | 06-29-15 A
142h | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | OH |  | Coordinated | 06-29-15 A
142i | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | OH |  | Coordinated | 06-29-15 A
142j | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | OH |  | Coordinated | 06-29-15 A
142k | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 06-29-15 A
142l | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 06-29-15 A
142m | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 06-29-15 A
142n | Y | 142 | 29947 | 96726 | 51100700301853 | 4 | Pike | SHOHOLA TWP 1.4M N SR1005 | SR 1007 | TWIN LAKES CREEK | 51/210 - SHOHOLA | 41.4116 | -74.8935 | 20140730431 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 06-29-15 A
143a | -- | 143 | 29982 | 67514 | 51200600100953 | 4 | Pike | DINGMAN TWP .2 M E TR 739 | SR 2006 | DWARFKILL CREEK | 51/203 - DINGMAN | 41.2992 | -74.9598 | 20143580171 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Brian Stoner, bstoner@firstenergycorp.com, 717-848-7181; GLENN SHOUP, PE, (610) 250-2815 |  |  |  | 2016-05-26
143b | -- | 143 | 29982 | 67514 | 51200600100953 | 4 | Pike | DINGMAN TWP .2 M E TR 739 | SR 2006 | DWARFKILL CREEK | 51/203 - DINGMAN | 41.2992 | -74.9598 | 20143580171 | Gas | Amerigas Propane LP | Brenda Pulse, brenda.pulse@amerigas.com, 570-253-2490 | UG |  |  | 2016-05-26
144a | -- | 144 | 32153 | 96737 | 57001104601461 | 4 | Susquehanna | N MILFRD TP .2M S SR 1018 | SR 0011 TR 11 | SALT LICK CREEK | 57/222 - NEW MILFORD | 41.8929 | -75.73 | 20150420639 | Comm | Sprint Nextel | Mike.brown@sprint.com, 304-283-5668 (Eastern PA); Wes.carpenter@sprint.com, 717-404-0899 (Western PA); JOSH PIERSON, 607-316-0566 |  |  |  | 2016-06-17
144b | -- | 144 | 32153 | 96737 | 57001104601461 | 4 | Susquehanna | N MILFRD TP .2M S SR 1018 | SR 0011 TR 11 | SALT LICK CREEK | 57/222 - NEW MILFORD | 41.8929 | -75.73 | 20150420639 | wtr | New Milford Municipal Auth | Sheila Shibley, munauth@nep.net, 570-465-7089; MR. V. STANTON, 570-465-3492 | UG |  |  | 2016-06-17
145 | -- | 145 | 32244 | 89023 | 57010601220638 | 4 | Susquehanna | LENOX TWP .1 M E TR 92 | SR 0106 TR 106 | TUNKHANNOCK CREEK | 57/219 - LENOX | 41.7101 | -75.6714 | 20143561405 | Elect | Pennsylvania Electric Company | Steve Beers, sbeers@firstenergycorp.com, 607-738-3120, Dan Dieffenbach, ddieffenbach@firstenergycorp.com, 607-738-3120 |  |  |  | 2016-03-25
146a | Y | 146 | 32307 | 9719 | 57026703200000 | 4 | Susquehanna | FORST LKE TP .8M N SR4012 | SR 0267 TR 267 | STONE STREET CREEK | 57/209 - FOREST LAKE | 41.8408 | -76.0292 | 20140701600 | Elect | Claverack Rural Electric Cooperative, Inc. | Charlie Goodwin (570) 265-2167 Ext.327, charlieg@ctenterprises.org | OH |  | Not Affected | 2015-08-07
146b | Y | 146 | 32307 | 9719 | 57026703200000 | 4 | Susquehanna | FORST LKE TP .8M N SR4012 | SR 0267 TR 267 | STONE STREET CREEK | 57/209 - FOREST LAKE | 41.8408 | -76.0292 | 20140701600 | Comm | Frontier Communications/CTSI, LLC | Steve Lathrop (570) 278-0036, steven.lathrop@ftr.com | OH |  | Coordinated | 2015-08-07
146c | Y | 146 | 32307 | 9719 | 57026703200000 | 4 | Susquehanna | FORST LKE TP .8M N SR4012 | SR 0267 TR 267 | STONE STREET CREEK | 57/209 - FOREST LAKE | 41.8408 | -76.0292 | 20140701600 | Comm | Frontier Communications/CTSI, LLC | Steve Lathrop (570) 278-0036, steven.lathrop@ftr.com | OH |  | Coordinated | 2015-08-07
146d | Y | 146 | 32307 | 9719 | 57026703200000 | 4 | Susquehanna | FORST LKE TP .8M N SR4012 | SR 0267 TR 267 | STONE STREET CREEK | 57/209 - FOREST LAKE | 41.8408 | -76.0292 | 20140701600 | Pole | Frontier Communications/CTSI, LLC | Steve Lathrop (570) 278-0036, steven.lathrop@ftr.com | OH |  | Coordinated | 2015-08-07
146e | Y | 146 | 32307 | 9719 | 57026703200000 | 4 | Susquehanna | FORST LKE TP .8M N SR4012 | SR 0267 TR 267 | STONE STREET CREEK | 57/209 - FOREST LAKE | 41.8408 | -76.0292 | 20140701600 | Pole | Frontier Communications/CTSI, LLC | Steve Lathrop (570) 278-0036, steven.lathrop@ftr.com | OH |  | Coordinated | 2015-08-07
147a | -- | 147 | 32308 | 79572 | 57026703202704 | 4 | Susquehanna | FRST LK TP 4.5M S SR 4014 | SR 0267 TR 267 | MIDDLE BR WYALUSING CR | 57/209 - FOREST LAKE | 41.8429 | -76.0189 | 20143580177 | Elect | Pennsylvania Electric Company | Steve Beers, sbeers@firstenergycorp.com, 607-738-3120, Dan Dieffenbach, ddieffenbach@firstenergycorp.com, 607-738-3120 |  |  |  | 2016-05-02
147b | -- | 147 | 32308 | 79572 | 57026703202704 | 4 | Susquehanna | FRST LK TP 4.5M S SR 4014 | SR 0267 TR 267 | MIDDLE BR WYALUSING CR | 57/209 - FOREST LAKE | 41.8429 | -76.0189 | 20143580177 | comm | Frontier | Steve Lathrop, 'Steven.Lathrop@FTR.com', 570-278-0036 |  |  |  | 2016-05-02
148 | -- | 148 | 32327 | 9656 | 57037400502476 | 4 | Susquehanna | LENOX TWP .5 M E SR 2016 | SR 0374 TR 374 | EAST BR TUNKHANNOCK CRK | 57/219 - LENOX | 41.6514 | -75.6917 | 20151410438 |  | all facilities responded clear per one call |  |  |  |  | 2017-05-30
149a | -- | 149 | 32365 | 96729 | 57070602700000 | 4 | Susquehanna | BRIDGWTR TP 2 M W TR 167 | SR 0706 TR 706 | PETTIS CREEK | 57/204 - BRIDGEWATER | 41.8248 | -75.9123 | 20143580198 |  | Bridgewater TWP | Mike Hester, Cell: 570-396-0275, 570-663-2625, mlhester1@yahoo.com |  |  |  | 2016-05-20
149b | -- | 149 | 32365 | 96729 | 57070602700000 | 4 | Susquehanna | BRIDGWTR TP 2 M W TR 167 | SR 0706 TR 706 | PETTIS CREEK | 57/204 - BRIDGEWATER | 41.8248 | -75.9123 | 20143580198 | Elect | Pennsylvania Electric Company | Steve Beers, sbeers@firstenergycorp.com, 607-738-3120, Dan Dieffenbach, ddieffenbach@firstenergycorp.com, 607-738-3120 |  |  |  | 2016-05-20
150 | -- | 150 | 32378 | 100550 | 57085800500000 | 4 | Susquehanna | RUSH TWP 2 M N TR 706 | SR 0858 TR 858 | GAYLORD CREEK | 57/224 - RUSH | 41.815 | -76.1057 | 20151411254 | Comm | Frontier | Jeffrey Bolton (Auburn TWP), 570-631-6710 |  |  |  | 2017-05-30
151a | Y | 151 | 32401 | 85782 | 57100700500000 | 4 | Susquehanna | THMPSN TWP 1.7M N SR 1004 | SR 1007 | SOUTH BR CANAWACTA CREEK | 57/227 - THOMPSON | 41.9134 | -75.5628 | 20140701622 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567 | OH |  | Not Affected | 2015-07-08
151b | Y | 151 | 32401 | 85782 | 57100700500000 | 4 | Susquehanna | THMPSN TWP 1.7M N SR 1004 | SR 1007 | SOUTH BR CANAWACTA CREEK | 57/227 - THOMPSON | 41.9134 | -75.5628 | 20140701622 | Comm | Northeastern Pennsylvania Telephone Company | Marlene Sample (570) 785-2219 | OH |  | Not Affected | 2015-07-08
152a | -- | 152 | 32437 | 96734 | 57101801302350 | 4 | Susquehanna | NEW MILFORD .6 M W TR 11 | SR 1018 | BEAVER CREEK | 57/222 - NEW MILFORD | 41.9045 | -75.7351 | 20143580483 |  | New Milford Municipal Auth | Sheila Shibley, munauth@nep.net, 570-465-7089; AMY HINE, 570-465-7089 / (570) 465-3394, nmboro@nep.net; AMY HINE, 570-465-7089 | UG |  |  | 2016-05-20
152b | -- | 152 | 32437 | 96734 | 57101801302350 | 4 | Susquehanna | NEW MILFORD .6 M W TR 11 | SR 1018 | BEAVER CREEK | 57/222 - NEW MILFORD | 41.9045 | -75.7351 | 20143580483 | Elect | Pennsylvania Electric Company | Steve Beers, sbeers@firstenergycorp.com, 607-738-3120, Dan Dieffenbach, ddieffenbach@firstenergycorp.com, 607-738-3120 |  |  |  | 2016-05-20
152c | -- | 152 | 32437 | 96734 | 57101801302350 | 4 | Susquehanna | NEW MILFORD .6 M W TR 11 | SR 1018 | BEAVER CREEK | 57/222 - NEW MILFORD | 41.9045 | -75.7351 | 20143580483 | Comm | Sprint Nextel | Mike.brown@sprint.com, 304-283-5668 (Eastern PA); Wes.carpenter@sprint.com 717-404-0899 (Western PA), 1-800-521-0579 |  |  |  | 2016-05-20
153a | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-20
153b | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-20
153c | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-20
153d | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-20
153e | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-20
153f | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-20
153g | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-20
153h | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-20
153i | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-20
153j | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Comm | Adams Cable Service | Dylan DeNike (570) 282-6121 Ext.203, dylandenike@echoes.net | OH |  | Coordinated | 2015-07-20
153k | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Comm | Adams Cable Service | Dylan DeNike (570) 282-6121 Ext.203, dylandenike@echoes.net | OH |  | Coordinated | 2015-07-20
153l | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Comm | Adams Cable Service | Dylan DeNike (570) 282-6121 Ext.203, dylandenike@echoes.net | OH |  | Coordinated | 2015-07-20
153m | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Comm | Northeastern Pennsylvania Telephone Company | Marlene Sample (570) 785-2219, msample@nep.net | OH |  | Coordinated | 2015-07-20
153n | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Comm | Northeastern Pennsylvania Telephone Company | Marlene Sample (570) 785-2219, msample@nep.net | OH |  | Coordinated | 2015-07-20
153o | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Comm | Northeastern Pennsylvania Telephone Company | Marlene Sample (570) 785-2219, msample@nep.net | OH |  | Coordinated | 2015-07-20
153p | Y | 153 | 32478 | 96727 | 57200800203639 | 4 | Susquehanna | CLIFFORD TWP 200'W TR 106 | SR 2008 | DUNDAFF CREEK | 57/207 - CLIFFORD | 41.6489 | -75.5995 | 20140730587 | Comm | Northeastern Pennsylvania Telephone Company | Marlene Sample (570) 785-2219, msample@nep.net | OH |  | Coordinated | 2015-07-20
154 | -- | 154 | 32507 | 9679 | 57202100501583 | 4 | Susquehanna | LENOX TWP OVER SR 0081 | SR 2021 | SR 0081 I-81 | 57/219 - LENOX | 41.6553 | -75.6602 | 20151411354 |  | all facilities responded clear per one call |  |  |  |  | 2017-05-30
155 | -- | 155 | 32647 | 96736 | 57400201300000 | 4 | Susquehanna | SILVER LK T 1.2M E SR4001 | SR 4002 | RHINEY CREEK | 57/225 - SILVER LAKE | 41.9715 | -75.9134 | 20150420650 |  | all facilities responded clear per one call |  |  |  |  | 2016-08-08
156a | -- | 156 | 35471 | 68876 | 63019106701296 | 4 | Wayne | OREGON TWP 1.5M N SR 4019 | SR 0191 TR 191 | BIG BROOK CREEK | 63/214 - OREGON | 41.6681 | -75.2546 | 20143580183 | Elect | PPL Electric Utilities Corporation | CHARLOTTE KRUPA, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-05-20
156b | -- | 156 | 35471 | 68876 | 63019106701296 | 4 | Wayne | OREGON TWP 1.5M N SR 4019 | SR 0191 TR 191 | BIG BROOK CREEK | 63/214 - OREGON | 41.6681 | -75.2546 | 20143580183 | Gas | UGI Central Penn Gas | Sharon Reese, 570-829-8754, sreese1@ugi.com; Scott Kinter, 570-893-6600 | UG |  |  | 2016-05-20
156c | -- | 156 | 35471 | 68876 | 63019106701296 | 4 | Wayne | OREGON TWP 1.5M N SR 4019 | SR 0191 TR 191 | BIG BROOK CREEK | 63/214 - OREGON | 41.6681 | -75.2546 | 20143580183 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com, Dan Blodnikar, 570-253-0048 |  |  |  | 2016-05-20
157a | -- | 157 | 35508 | 9969 | 63029601800000 | 4 | Wayne | CANAAN TWP 1 M S SR 3028 | TR 296 EASTON TPK | BRANCH OF MIDDLE CREEK | 63/203 - CANAAN | 41.5542 | -75.4081 | 20150420657 | Elect | PPL Electric Utilities Corporation | CHARLOTTE KRUPA, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-08-25
157b | -- | 157 | 35508 | 9969 | 63029601800000 | 4 | Wayne | CANAAN TWP 1 M S SR 3028 | TR 296 EASTON TPK | BRANCH OF MIDDLE CREEK | 63/203 - CANAAN | 41.5542 | -75.4081 | 20150420657 |  | Western Wayne School District | LaCoe, Clay; clacoe@westernwayne.org |  |  |  | 2016-08-25
158a | Y | 158 | 35624 | 68917 | 63101801602046 | 4 | Wayne | MANCHSTR TP 3.7M E TR 191 | SR 1018 | BR LITTLE EQUINUNK CREEK | 63/212 - MANCHESTER | 41.8244 | -75.1497 | 20140730520 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | OH |  | Coordinated | 2015-08-17
158b | Y | 158 | 35624 | 68917 | 63101801602046 | 4 | Wayne | MANCHSTR TP 3.7M E TR 191 | SR 1018 | BR LITTLE EQUINUNK CREEK | 63/212 - MANCHESTER | 41.8244 | -75.1497 | 20140730520 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | OH |  | Coordinated | 2015-08-17
158c | Y | 158 | 35624 | 68917 | 63101801602046 | 4 | Wayne | MANCHSTR TP 3.7M E TR 191 | SR 1018 | BR LITTLE EQUINUNK CREEK | 63/212 - MANCHESTER | 41.8244 | -75.1497 | 20140730520 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | OH |  | Not Affected | 2015-08-17
159a | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | 20140730487 | Comm | Blue Ridge Cable Television Inc. | Alice Muniz (610) 826-2551, amuniz@pencor.com | OH |  | Not Affected | 2015-08-13
159b | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | 20140730487 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-08-13
159c | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | 20140730487 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-08-13
159d | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | 20140730487 | Pole | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-08-13
159e | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | 20140730487 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-08-13
159f | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | 20140730487 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-08-13
159g | Y | 159 | 35654 | 68927 | 63200700301844 | 4 | Wayne | BERLIN TWP @ JCT SR 2009 | SR 2007 | HOLBERT CREEK | 63/201 - BERLIN | 41.5696 | -75.2254 | 20140730487 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | OH |  | Not Affected | 2015-08-13
160a | -- | 160 | 35675 | 67584 | 63300601600000 | 4 | Wayne | SALEM TWP .6 M N SR 3008 | SR3006 LEDGEDLE RD | ARIEL CREEK | 63/218 - SALEM | 41.4041 | -75.3364 | 20140872316 | Elect | PPL Electric Utilities Corporation | CHARLOTTE KRUPA, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-08-01
160b | -- | 160 | 35675 | 67584 | 63300601600000 | 4 | Wayne | SALEM TWP .6 M N SR 3008 | SR3006 LEDGEDLE RD | ARIEL CREEK | 63/218 - SALEM | 41.4041 | -75.3364 | 20140872316 |  | Western Wayne School District | LaCoe, Clay; clacoe@westernwayne.org |  |  |  | 2016-08-01
161a | Y | 161 | 35765 | 56752 | 63401401300733 | 4 | Wayne | SCOTT TWP .5 M E SR 4037 | SR 4014 | BALLS CREEK | 63/219 - SCOTT | 41.9429 | -75.3848 | 20150271472 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | OH |  | Not Affected | 2015-08-13
161b | Y | 161 | 35765 | 56752 | 63401401300733 | 4 | Wayne | SCOTT TWP .5 M E SR 4037 | SR 4014 | BALLS CREEK | 63/219 - SCOTT | 41.9429 | -75.3848 | 20150271472 | Comm | Verizon North LLC | Dan Blodnikar (570) 253-0048 | OH |  | Not Affected | 2015-08-13
162a | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | OH |  | Coordinated | 2015-07-01
162b | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | OH |  | Coordinated | 2015-07-01
162c | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | OH |  | Coordinated | 2015-07-01
162d | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | OH |  | Coordinated | 2015-07-01
162e | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | OH |  | Coordinated | 2015-07-01
162f | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | OH |  | Coordinated | 2015-07-01
162g | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | OH |  | Coordinated | 2015-07-01
162h | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | OH |  | Coordinated | 2015-07-01
162i | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com | OH |  | Coordinated | 2015-07-01
162j | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Comm | Hancock Telephone Company | Dave Niles (607) 637-9944, dniles@hancock.net | OH |  | Coordinated | 2015-07-01
162k | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Comm | Hancock Telephone Company | Dave Niles (607) 637-9944, dniles@hancock.net | OH |  | Coordinated | 2015-07-01
162l | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Comm | Hancock Telephone Company | Dave Niles (607) 637-9944, dniles@hancock.net | OH |  | Coordinated | 2015-07-01
162m | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Pole | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | OH |  | Coordinated | 2015-07-01
162n | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | OH |  | Coordinated | 2015-07-01
162o | Y | 162 | 35802 | 79580 | 63403302600090 | 4 | Wayne | BUCKINGHAM TWP 90'N TR370 | SR 4033 STRLGHT RD | SHEHAWKEN CREEK | 63/202 - BUCKINGHAM | 41.8907 | -75.3364 | 20140730634 | Comm | Verizon North LLC | Danny Blodnikar (570) 253-0048, dan.blodnikar@verizon.com | OH |  | Coordinated | 2015-07-01
163 | -- | 163 | 35810 | 9978 | 63403703303161 | 4 | Wayne | SCOTT TWP .2 M S SR 4043 | SR 4037 | OQUAGA CREEK | 63/219 - SCOTT | 41.9976 | -75.4019 | 20151671802 |  | all facilities responded clear per one call |  |  |  |  | 2016-07-05
164a | -- | 164 | 37163 | 10230 | 65026700100659 | 4 | Wyoming | MESHOPPEN BOR .1 M N TR 6 | SR 0267 TR 267 | LITTLE MESHOPPEN CREEK | 65/403 - MESHOPPEN | 41.6145 | -76.0478 | 20150682207 | sanitary | Meshoppen Borough | Carlton Shupp, 570-836-1700 | UG |  |  | 2016-08-18
164b | -- | 164 | 37163 | 10230 | 65026700100659 | 4 | Wyoming | MESHOPPEN BOR .1 M N TR 6 | SR 0267 TR 267 | LITTLE MESHOPPEN CREEK | 65/403 - MESHOPPEN | 41.6145 | -76.0478 | 20150682207 |  | Peoples Financial Services Corp | 570-879-2175 |  |  |  | 2016-08-18
165 | -- | 165 | 37172 | 10243 | 65029201500354 | 4 | Wyoming | N MORELND TP .1M W SR2009 | SR 0292 TR 292 | BR WHITELOCK CREEK | 65/213 - NORTHMORELAND | 41.4142 | -75.9074 | 20150701251 |  | UGI Energy Services | Kurt Zielaskowski, 610-736-5571, kzielaskowski@ugi.com; 717-795-1180 |  |  |  | 2016-08-15
166a | Y | 166 | 37192 | 68786 | 65100100500000 | 4 | Wyoming | TUNKHANNOCK TP JCT SR1002 | SR 1001 | OUTLET LAKE CAREY | 65/216 - TUNKHANNOCK | 41.58 | -75.9166 | 20140701940 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com; Construction Contact - Gary Cluster (570) 278-5562 | OH |  | Coordinated | 2015-08-06
166b | Y | 166 | 37192 | 68786 | 65100100500000 | 4 | Wyoming | TUNKHANNOCK TP JCT SR1002 | SR 1001 | OUTLET LAKE CAREY | 65/216 - TUNKHANNOCK | 41.58 | -75.9166 | 20140701940 | Elect | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com; Construction Contact - Gary Cluster (570) 278-5562 | OH |  | Coordinated | 2015-08-06
166c | Y | 166 | 37192 | 68786 | 65100100500000 | 4 | Wyoming | TUNKHANNOCK TP JCT SR1002 | SR 1001 | OUTLET LAKE CAREY | 65/216 - TUNKHANNOCK | 41.58 | -75.9166 | 20140701940 | Pole | Pennsylvania Electric Company | Kurt Durland (570) 278-5567, kdurland@firstenergycorp.com; Construction Contact - Gary Cluster (570) 278-5562 | OH |  | Coordinated | 2015-08-06
166d | Y | 166 | 37192 | 68786 | 65100100500000 | 4 | Wyoming | TUNKHANNOCK TP JCT SR1002 | SR 1001 | OUTLET LAKE CAREY | 65/216 - TUNKHANNOCK | 41.58 | -75.9166 | 20140701940 | Comm | Blue Ridge Cable Television Inc. | Rick Hebda (570) 836-0919, rhebda@pencor.com | OH |  | Not Affected | 2015-08-06
166e | Y | 166 | 37192 | 68786 | 65100100500000 | 4 | Wyoming | TUNKHANNOCK TP JCT SR1002 | SR 1001 | OUTLET LAKE CAREY | 65/216 - TUNKHANNOCK | 41.58 | -75.9166 | 20140701940 | Comm | Frontier Communications | Jeff Bolton (570) 631-6710, Jeff.Bolton@ftr.com | OH |  | Not Affected | 2015-08-06
167a | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | 20140701917 | Elect | Claverack Rural Electric Cooperative, Inc. | Charles Goodwin (570) 265-2167 Ext.327 | OH |  | Not Affected | 2015-08-03
167b | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | 20140701917 | Comm | Blue Ridge Cable Television Inc. | Dwight (Skip) M. Hunsicker, Chief Plant Engr (610) 826-2551 Ext.314; Construction Contact - Rick Hebda (570) 836-0919 | OH |  | Coordinated | 2015-08-03
167c | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | 20140701917 | Comm | Blue Ridge Cable Television Inc. | Dwight (Skip) M. Hunsicker, Chief Plant Engr (610) 826-2551 Ext.314; Construction Contact - Rick Hebda (570) 836-0919 | OH |  | Coordinated | 2015-08-03
167d | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | 20140701917 | Pole | Frontier Communications | Jeff Bolton (570) 631-6710, Jeff.Bolton@ftr.com | OH |  | Coordinated | 2015-08-03
167e | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | 20140701917 | Comm | Frontier Communications | Jeff Bolton (570) 631-6710, Jeff.Bolton@ftr.com | OH |  | Coordinated | 2015-08-03
167f | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | 20140701917 | Comm | Frontier Communications | Jeff Bolton (570) 631-6710, Jeff.Bolton@ftr.com | OH |  | Coordinated | 2015-08-03
167g | Y | 167 | 37222 | 68806 | 65200100500596 | 4 | Wyoming | MONROE TWP .2 M S SR 2002 | SR 2001 | SOUTH RUN CREEK | 65/210 - MONROE | 41.4076 | -76.0296 | 20140701917 | Comm | Frontier Communications | Jeff Bolton (570) 631-6710, Jeff.Bolton@ftr.com | OH |  | Coordinated | 2015-08-03
168a | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | 20150271473 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325, Rick Moslen, 412-999-0590 |  |  |  | 2016-08-01
168b | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | 20150271473 | sanitary | Cumru TWP WW Dept | Jeanne Johnston, jjohnston@cumrutowship.org, 610-777-1343; James Sigworth, 610-777-1343, bocandpc@cumrutownship.com | UG |  |  | 2016-08-01
168c | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | 20150271473 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Charlie Roberts, charoberts@firstenergycorp.com, 610-921-6229; Allen Rino, Ancrino@firstenergycorp.com, 610-921-6157; Michele Heckman, 610-921-6695, mheckman@gpu.com |  |  |  | 2016-08-01
168d | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | 20150271473 | wtr | Reading Area Water Auth | Renee S. Watt, Renee.Watt@readingareawater.com, 610-406-6321 | UG | 8" |  | 2016-08-01
168e | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | 20150271473 | Comm | Service Electric Cablevision, Inc. | Darryl Reccek, 610-868-0902, rec@sectv.com |  |  |  | 2016-08-01
168f | -- | 168 | 4900 | 79078 | 6062501301318 | 5 | Berks | NEW HOLLAND ROAD | LR518 (PA625) | ANGELICA CREEK | 06/103 - CUMRU | 40.2902 | -75.9472 | 20150271473 | gas | UGI Utilities, Inc. | Kurt Zielaskowski, 610-736-5571, kzielaskowski@ugi.com | UG |  |  | 2016-08-01
169a | -- | 169 | 4946 | 78877 | 6100400100619 | 5 | Berks | WILLOW CREEK BRIDGE | SR 1004(LR 06201) | WILLOW CREEK | 06/228 - ONTELAUNEE | 40.427 | -75.934 | 20150161804 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325, Rick Moslen, 412-999-0590 |  |  |  | 2016-06-20
169b | -- | 169 | 4946 | 78877 | 6100400100619 | 5 | Berks | WILLOW CREEK BRIDGE | SR 1004(LR 06201) | WILLOW CREEK | 06/228 - ONTELAUNEE | 40.427 | -75.934 | 20150161804 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Charlie Roberts, charoberts@firstenergycorp.com, 610-921-6229; Allen Rino, Ancrino@firstenergycorp.com Tel: 610-921-6157 ; Michele Heckman, 610-921-6695, mheckman@gpu.com |  |  |  | 2016-06-20
169c | -- | 169 | 4946 | 78877 | 6100400100619 | 5 | Berks | WILLOW CREEK BRIDGE | SR 1004(LR 06201) | WILLOW CREEK | 06/228 - ONTELAUNEE | 40.427 | -75.934 | 20150161804 |  | Ontelaunee TWP Municipal Auth | William Mcmullen, Arrow group 570-366-9534. bill.mcmullen@thearrowgroup.com. 610-916-3445; Marie Piehel (Retired), 610-926-2812 | UG |  |  | 2016-06-20
170a | -- | 170 | 4953 | 78889 | 6100601100107 | 5 | Berks | CRYSTALCAVE RD,VIRGINVLLE | SR 1006 (LR 06135) | SACONY CREEK | 06/215 - GREENWICH | 40.5255 | -75.875 | 20143571648, 20151561632 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Charlie Roberts, charoberts@firstenergycorp.com, 610-921-6229; Allen Rino, Ancrino@firstenergycorp.com, 610-921-6157; Michele Heckman, 610-921-6695, mheckman@gpu.com |  |  |  | 2016-08-22
170b | -- | 170 | 4953 | 78889 | 6100601100107 | 5 | Berks | CRYSTALCAVE RD,VIRGINVLLE | SR 1006 (LR 06135) | SACONY CREEK | 06/215 - GREENWICH | 40.5255 | -75.875 | 20143571648, 20151561632 | Sanitary | Richmond TWP Municipal Authority | Gary Jenkins, docgj2003@yahoo.com, 607-329-5820; Joe Welch (Secretary), rtma@ptd.net 570-662-7316, cell: 570-662-5019 ; NANCY BRAY, 570-662-3774 |  |  |  | 2016-08-22
170c | -- | 170 | 4953 | 78889 | 6100601100107 | 5 | Berks | CRYSTALCAVE RD,VIRGINVLLE | SR 1006 (LR 06135) | SACONY CREEK | 06/215 - GREENWICH | 40.5255 | -75.875 | 20143571648, 20151561632 | Comm | Service Electric Cablevision, Inc. | Chris Shunk, birdsborooffice@secv.coml ; (610) 582-5317. ROBERT TRENTLY (N/A), 570-453-2586 |  |  |  | 2016-08-22
170d | -- | 170 | 4953 | 78889 | 6100601100107 | 5 | Berks | CRYSTALCAVE RD,VIRGINVLLE | SR 1006 (LR 06135) | SACONY CREEK | 06/215 - GREENWICH | 40.5255 | -75.875 | - | Comm | Verizon Pennsylvania LLC | Cynthia Oberholtzer, Coberholtzer@ucseng.com, 570-387-3175 |  |  |  | 2016-08-22
171a | -- | 171 | 4957 | 85635 | 6100800300000 | 5 | Berks | .5 MI.SOUTH OF HAMBURG | SR 1008 (LR 06125) | WINDSOR CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | 20150682225 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325 ; Rick Moslen, 412-999-0590 |  |  |  | 2016-08-15
171b | -- | 171 | 4957 | 85635 | 6100800300000 | 5 | Berks | .5 MI.SOUTH OF HAMBURG | SR 1008 (LR 06125) | WINDSOR CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | 20150682225 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Charlie Roberts, charoberts@firstenergycorp.com, 610-921-6229; Allen Rino, Ancrino@firstenergycorp.com, 610-921-6157; Michele Heckman, 610-921-6695, mheckman@gpu.com |  |  |  | 2016-08-15
172a | -- | 172 | 5147 | 79081 | 6300900701675 | 5 | Berks | W.WYOMISSING AVE. | SR 3009 (LR 660) | WYOMISSING CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | 20150161811 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325, Rick Moslen, 412-999-0590 |  |  |  | 2016-06-01
172b | -- | 172 | 5147 | 79081 | 6300900701675 | 5 | Berks | W.WYOMISSING AVE. | SR 3009 (LR 660) | WYOMISSING CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | 20150161811 | sanitary | Cumru TWP WW Dept | Robert McNichols, bmcnichols@cumrutownship.org, 610-777-1343; James Sigworth (inactive), bocandpc@cumrutownship.com | UG |  |  | 2016-06-01
172c | -- | 172 | 5147 | 79081 | 6300900701675 | 5 | Berks | W.WYOMISSING AVE. | SR 3009 (LR 660) | WYOMISSING CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | 20150161811 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Charlie Roberts, charoberts@firstenergycorp.com, 610-921-6229; Allen Rino, Ancrino@firstenergycorp.com, 610-921-6157; Michele Heckman, 610-921-6695, mheckman@gpu.com |  |  |  | 2016-06-01
172d | -- | 172 | 5147 | 79081 | 6300900701675 | 5 | Berks | W.WYOMISSING AVE. | SR 3009 (LR 660) | WYOMISSING CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | 20150161811 | Comm | Service Electric Cablevision, Inc. | Darryl Reccek, 610-868-0902, rec@sectv.com |  |  |  | 2016-06-01
172e | -- | 172 | 5147 | 79081 | 6300900701675 | 5 | Berks | W.WYOMISSING AVE. | SR 3009 (LR 660) | WYOMISSING CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | 20150161811 |  | Shillington Borough | Michael Montz, 610-777-1338, info@shillingtonborough.net; Mark S. Reed, 610-777-1338 | UG |  |  | 2016-06-01
172f | -- | 172 | 5147 | 79081 | 6300900701675 | 5 | Berks | W.WYOMISSING AVE. | SR 3009 (LR 660) | WYOMISSING CREEK | 06/244 - WINDSOR | 40.5493 | -75.9633 | 20150161811 | gas | UGI Utilities, Inc. | Kurt Zielaskowski, 610-736-5571, kzielaskowski@ugi.com | UG |  |  | 2016-06-01
173a | Y | 173 | 8994 | 85764 | 13020902602676 | 5 | Carbon | PACKERTON HOLLOW | US 209 (LR 163) | BEAVER RUN | 13/208 - MAHONING | 40.8514 | -75.7132 | 20140660634, 20140761455 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Prior | 2016-03-07
173b | Y | 173 | 8994 | 85764 | 13020902602676 | 5 | Carbon | PACKERTON HOLLOW | US 209 (LR 163) | BEAVER RUN | 13/208 - MAHONING | 40.8514 | -75.7132 | 20140660634, 20140761455 | Sewer | Mahoning Township Municipal Authority | Gregory Haas (570) 645-9545, carbonei@ptd.net | UG |  | Not Affected | 2016-03-07
173c | Y | 173 | 8994 | 85764 | 13020902602676 | 5 | Carbon | PACKERTON HOLLOW | US 209 (LR 163) | BEAVER RUN | 13/208 - MAHONING | 40.8514 | -75.7132 | 20140660634, 20140761455 | Water | Lehighton Water Authority | Nicole Nothstein (610) 377-1912, waterlwa@ptd.net; Armen Galasso (610) 377-5585 | UG |  | Not Affected | 2016-03-07
173d | Y | 173 | 8994 | 85764 | 13020902602676 | 5 | Carbon | PACKERTON HOLLOW | US 209 (LR 163) | BEAVER RUN | 13/208 - MAHONING | 40.8514 | -75.7132 | 20140660634, 20140761455 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | OH |  | Prior | 2016-03-07
173e | Y | 173 | 8994 | 85764 | 13020902602676 | 5 | Carbon | PACKERTON HOLLOW | US 209 (LR 163) | BEAVER RUN | 13/208 - MAHONING | 40.8514 | -75.7132 | 20140660634, 20140761455 | Comm | Verizon Pennsylvania, LLC | Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com | OH |  | Prior | 2016-03-07
173f | Y | 173 | 8994 | 85764 | 13020902602676 | 5 | Carbon | PACKERTON HOLLOW | US 209 (LR 163) | BEAVER RUN | 13/208 - MAHONING | 40.8514 | -75.7132 | 20140660634, 20140761455 | Gas | UGI Central Penn Gas | Taylor Bet (610) 807-3140, tbet@ugi.com | UG |  | Prior | 2016-03-07
174a | -- | 174 | 9104 | 85762 | 13401000501489 | 5 | Carbon | GERHARDS, QUAKAKE RD. | SR 4010(LR 13025) | QUAKAKE CREEK | 13/210 - PACKER | 40.8892 | -75.9184 | 20150762133 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-06-05
174b | -- | 174 | 9104 | 85762 | 13401000501489 | 5 | Carbon | GERHARDS, QUAKAKE RD. | SR 4010(LR 13025) | QUAKAKE CREEK | 13/210 - PACKER | 40.8892 | -75.9184 | 20150762133 | wtr | Hazleton City Auth Water Dept | 570-454-2401 | UG |  |  | 2017-06-05
175a | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | 20150261292, 20150261293 | Comm | RCN Telecom Services Inc | Bill Reese, 610-443-2956, bill.reese@rcn.net |  |  |  | 2016-11-01
175b | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | 20150261292, 20150261293 |  | City of Allentown | Brian Borzak, 610-437-7574 | UG |  |  | 2016-11-01
175c | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | 20150261292, 20150261293 | comm | AT&T Atlanta | 404-249-9052 |  |  |  | 2016-11-01
175d | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | 20150261292, 20150261293 |  | Lehigh Cnty Auth | Frank Leist, 610-398-2503, frankleist@lehighcountyauthority.org | UG |  |  | 2016-11-01
175e | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | 20150261292, 20150261293 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-11-01
175f | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | 20150261292, 20150261293 |  | South Whitehall TWP | Gerald Gasda, 610-398-0401 | UG |  |  | 2016-11-01
175g | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | 20150261292, 20150261293 | gas | UGI Utilities, Inc. | Luke Lichtenwalner, 610-807-3107 llichtenwalneri@ugi.com, 610-736-5571 | UG |  |  | 2016-11-01
175h | -- | 175 | 23144 | 85693 | 39022202103224 | 5 | Lehigh | HAMILTON ST. | US 222(LR 157) | CEDAR CREEK | 39/301 - ALLENTOWN | 40.5942 | -75.5007 | 20150261292, 20150261293 | Comm | Verizon Pennsylvania LLC | Cynthia Oberholtzer, Coberholtzer@ucseng.com, 570-387-3175 | UG |  |  | 2016-11-01
176a | -- | 176 | 23228 | 89633 | 39100400202044 | 5 | Lehigh | 1600'E.OF RACE ST.BRIDGE | LR 39032(RACE ST.) | CATASAUQUA CREEK | 39/402 - CATASAUQUA | 40.6504 | -75.4656 | 20150751362 |  | Catasauqua Borough | 610-264-0571, manager@catasauqua.org | UG |  |  | 2017-03-09
176b | -- | 176 | 23228 | 89633 | 39100400202044 | 5 | Lehigh | 1600'E.OF RACE ST.BRIDGE | LR 39032(RACE ST.) | CATASAUQUA CREEK | 39/402 - CATASAUQUA | 40.6504 | -75.4656 | 20150751362 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-03-09
176c | -- | 176 | 23228 | 89633 | 39100400202044 | 5 | Lehigh | 1600'E.OF RACE ST.BRIDGE | LR 39032(RACE ST.) | CATASAUQUA CREEK | 39/402 - CATASAUQUA | 40.6504 | -75.4656 | 20150751362 | Comm | RCN Telecom Services Inc | Bill Reese, 610-443-2956, bill.reese@rcn.net |  |  |  | 2017-03-09
176d | -- | 176 | 23228 | 89633 | 39100400202044 | 5 | Lehigh | 1600'E.OF RACE ST.BRIDGE | LR 39032(RACE ST.) | CATASAUQUA CREEK | 39/402 - CATASAUQUA | 40.6504 | -75.4656 | 20150751362 | gas | UGI Utilities, Inc. | Luke Lichtenwalner, 610-807-3107 llichtenwalneri@ugi.com, 610-736-5571 | UG |  |  | 2017-03-09
176e | -- | 176 | 23228 | 89633 | 39100400202044 | 5 | Lehigh | 1600'E.OF RACE ST.BRIDGE | LR 39032(RACE ST.) | CATASAUQUA CREEK | 39/402 - CATASAUQUA | 40.6504 | -75.4656 | 20150751362 | comm | Verizon Pennsylvania LLC | Cynthia Oberholtzer, Coberholtzer@ucseng.com, 570-387-3175; Deborah D. Deila, 412-633-3810, deborah.d.deila@verizon.com |  |  |  | 2017-03-09
177a | -- | 177 | 23330 | 85683 | 39204900302189 | 5 | Lehigh | CAMP MEETING ROAD | SR 2049 (LR 39081) | SAUCON CREEK | 39/211 - UPPER SAUCON | 40.5508 | -75.4054 | 20143580203 | comm | Verizon Pennsylvania LLC | Cynthia Oberholtzer, Coberholtzer@ucseng.com, 570-387-3175 | UG |  |  | 2017-05-22
177b | -- | 177 | 23330 | 85683 | 39204900302189 | 5 | Lehigh | CAMP MEETING ROAD | SR 2049 (LR 39081) | SAUCON CREEK | 39/211 - UPPER SAUCON | 40.5508 | -75.4054 | 20143580203 | wtr | Bethlehem City Dept of Wtr/Swr Resources | Robert Taylor, Rtaylor@bethlehem-pa.gov, 610-997-7947 | UG |  |  | 2017-05-22
177c | -- | 177 | 23330 | 85683 | 39204900302189 | 5 | Lehigh | CAMP MEETING ROAD | SR 2049 (LR 39081) | SAUCON CREEK | 39/211 - UPPER SAUCON | 40.5508 | -75.4054 | 20143580203 | Elect | PPL Electric Utilities Corporation | Jennifer Perdick, 1-800-342-5775, jperdick@pplweb.com, Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-05-22
177d | -- | 177 | 23330 | 85683 | 39204900302189 | 5 | Lehigh | CAMP MEETING ROAD | SR 2049 (LR 39081) | SAUCON CREEK | 39/211 - UPPER SAUCON | 40.5508 | -75.4054 | 20143580203 | gas | UGI Utilities, Inc. | Luke Lichtenwalner, 610-807-3107 llichtenwalneri@ugi.com, 610-736-5571 |  |  |  | 2017-05-22
177e | -- | 177 | 23330 | 85683 | 39204900302189 | 5 | Lehigh | CAMP MEETING ROAD | SR 2049 (LR 39081) | SAUCON CREEK | 39/211 - UPPER SAUCON | 40.5508 | -75.4054 | 20143580203 |  | Upper Saucon TWP Wtr Swr Dept | 610-694-8680 | UG |  |  | 2017-05-22
178a | -- | 178 | 23136 | 89639 | 39622200303519 | 5 | Lehigh | TREXLERTOWN NEAR RT.100 | US 222(LR 157) | IRON RUN | 39/209 - UPPER MACUNGIE | 40.5475 | -75.6073 | 20150681064 | comm | AT&T Atlanta | 404-249-9052 |  |  |  | 2016-06-17
178b | -- | 178 | 23136 | 89639 | 39622200303519 | 5 | Lehigh | TREXLERTOWN NEAR RT.100 | US 222(LR 157) | IRON RUN | 39/209 - UPPER MACUNGIE | 40.5475 | -75.6073 | 20150681064 |  | Lehigh Cnty Auth | Frank Leist, 610-398-2503, frankleist@lehighcountyauthority.org | UG |  |  | 2016-06-17
178c | -- | 178 | 23136 | 89639 | 39622200303519 | 5 | Lehigh | TREXLERTOWN NEAR RT.100 | US 222(LR 157) | IRON RUN | 39/209 - UPPER MACUNGIE | 40.5475 | -75.6073 | 20150681064 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-06-17
178d | -- | 178 | 23136 | 89639 | 39622200303519 | 5 | Lehigh | TREXLERTOWN NEAR RT.100 | US 222(LR 157) | IRON RUN | 39/209 - UPPER MACUNGIE | 40.5475 | -75.6073 | 20150681064 | gas | UGI Utilities, Inc. | Luke Lichtenwalner, 610-807-3107 llichtenwalneri@ugi.com, 610-736-5571 | UG |  |  | 2016-06-17
178e | -- | 178 | 23136 | 89639 | 39622200303519 | 5 | Lehigh | TREXLERTOWN NEAR RT.100 | US 222(LR 157) | IRON RUN | 39/209 - UPPER MACUNGIE | 40.5475 | -75.6073 | 20150681064 | comm | Verizon Pennsylvania LLC | Cynthia Oberholtzer, Coberholtzer@ucseng.com, 570-387-3175; Deborah D. Deila, 412-633-3810, deborah.d.deila@verizon.com | UG |  |  | 2016-06-17
178f | -- | 178 | 23136 | 89639 | 39622200303519 | 5 | Lehigh | TREXLERTOWN NEAR RT.100 | US 222(LR 157) | IRON RUN | 39/209 - UPPER MACUNGIE | 40.5475 | -75.6073 | - |  | LEC TRO |  |  |  |  | 2016-06-17
179a | -- | 179 | 26785 | 85811 | 45020900401748 | 5 | Monroe | KRESGEVILLE | SR 209(LR 164) | MIDDLE CREEK | 45/210 - POLK | 40.901 | -75.497 | 20143561422 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-05-26
179b | -- | 179 | 26785 | 85811 | 45020900401748 | 5 | Monroe | KRESGEVILLE | SR 209(LR 164) | MIDDLE CREEK | 45/210 - POLK | 40.901 | -75.497 | 20143561422 | GAS | Amerigas Propane LP | Brenda Pulse, brenda.pulse@amerigas.com, 570-253-2490 | UG |  |  | 2016-05-26
179c | -- | 179 | 26785 | 85811 | 45020900401748 | 5 | Monroe | KRESGEVILLE | SR 209(LR 164) | MIDDLE CREEK | 45/210 - POLK | 40.901 | -75.497 | 20143561422 | Comm | Blue Ridge Cable Television Inc. | Dawn Shoemaker, 610-826-2551, dshoemaker@pencor.com |  |  |  | 2016-05-26
179d | -- | 179 | 26785 | 85811 | 45020900401748 | 5 | Monroe | KRESGEVILLE | SR 209(LR 164) | MIDDLE CREEK | 45/210 - POLK | 40.901 | -75.497 | 20143561422 |  | Commonwealth Telephone | Steve Lathrop, 570-278-0036 |  |  |  | 2016-05-26
179e | -- | 179 | 26785 | 85811 | 45020900401748 | 5 | Monroe | KRESGEVILLE | SR 209(LR 164) | MIDDLE CREEK | 45/210 - POLK | 40.901 | -75.497 | 20143561422 |  | Palmerton Telephone | 610-826-6650 |  |  |  | 2016-05-26
180a | Y | 180 | 26795 | 91680 | 45020903110000 | 5 | Monroe | AT JUNCT. WITH PA33 SB | SR 209 & SR 33SB | APPENZELL CREEK | 45/205 - HAMILTON | 40.9557 | -75.2876 | 20140730675 | N/A | N/A | N/A | N/A | N/A | Not Affected | 2016-03-08
181a | Y | 181 | 26811 | 79157 | 45031401101750 | 5 | Monroe | 2.5 M. S.OF SWIFTWATER | PA 314(LR45025) | SWIFTWATER CREEK | 45/208 - PARADISE | 41.0911 | -75.288 | 20140310616, 20140630216 | N/A | N/A | N/A | N/A |  | Not Affected | 2015-07-23
182a | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | 20140281453, 20140691002 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-08-03
182b | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | 20140281453, 20140691002 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-08-03
182c | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | 20140281453, 20140691002 | Comm | Verizon Pennsylvania, LLC | Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com; William Wojcik (construction) (570) 424-0058, william.wojcik@verizon.com | OH |  | Coordinated | 2015-08-03
182d | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | 20140281453, 20140691002 | Comm | Verizon Pennsylvania, LLC | Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com; William Wojcik (construction) (570) 424-0058, william.wojcik@verizon.com | OH |  | Coordinated | 2015-08-03
182e | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | 20140281453, 20140691002 | Comm | Verizon Pennsylvania, LLC | Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com; William Wojcik (construction) (570) 424-0058, william.wojcik@verizon.com | OH |  | Coordinated | 2015-08-03
182f | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | 20140281453, 20140691002 | Comm | Verizon Pennsylvania, LLC | Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com; William Wojcik (construction) (570) 424-0058, william.wojcik@verizon.com | UG |  | Not Affected | 2015-08-03
182g | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | 20140281453, 20140691002 | Water | Aqua Pennsylvania | Jennifer Cathers (610) 525-1400 jccathers@aquaamerica.com | UG |  | Not Affected | 2015-08-03
182h | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | 20140281453, 20140691002 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | OH |  | Coordinated | 2015-08-03
182i | Y | 182 | 26832 | 79158 | 45039000300932 | 5 | Monroe | MOUNTAIN HOME | SR 390(LR 324) | MILL CREEK | 45/201 - BARRETT | 41.1684 | -75.2733 | 20140281453, 20140691002 | Comm | SUNESYS, INC. | James O’Brien (610) 884-1395, jobrien@sunesys.com | OH |  | Coordinated | 2015-08-03
183a | Y | 183 | 26887 | 11649 | 45061105100000 | 5 | Monroe | TOBYHANNA | SR 611(LR 168) | TOBYHANNA CREEK | 45/203 - COOLBAUGH | 41.1732 | -75.4152 | 20140240189, 20140691204 | N/A | N/A | N/A | N/A |  | Not Affected | 2015-07-16
184a | Y | 184 | 26888 | 11730 | 45071500201751 | 5 | Monroe | 1 M. N.OF BRODHEADSVILLE | SR 715 (LR45041) | MCMICHAELS CREEK | 45/202 - CHESTNUTHILL | 40.9377 | -75.3928 | 20140281480 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-24
184b | Y | 184 | 26888 | 11730 | 45071500201751 | 5 | Monroe | 1 M. N.OF BRODHEADSVILLE | SR 715 (LR45041) | MCMICHAELS CREEK | 45/202 - CHESTNUTHILL | 40.9377 | -75.3928 | 20140281480 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-24
184c | Y | 184 | 26888 | 11730 | 45071500201751 | 5 | Monroe | 1 M. N.OF BRODHEADSVILLE | SR 715 (LR45041) | MCMICHAELS CREEK | 45/202 - CHESTNUTHILL | 40.9377 | -75.3928 | 20140281480 | Comm | Frontier Communications | Pat Galli (570) 208-6458, Patrick.Galli@FTR.com | OH |  | Coordinated | 2015-07-24
184d | Y | 184 | 26888 | 11730 | 45071500201751 | 5 | Monroe | 1 M. N.OF BRODHEADSVILLE | SR 715 (LR45041) | MCMICHAELS CREEK | 45/202 - CHESTNUTHILL | 40.9377 | -75.3928 | 20140281480 | Comm | Frontier Communications | Pat Galli (570) 208-6458, Patrick.Galli@FTR.com | OH |  | Concurrent | 2015-07-24
184e | Y | 184 | 26888 | 11730 | 45071500201751 | 5 | Monroe | 1 M. N.OF BRODHEADSVILLE | SR 715 (LR45041) | MCMICHAELS CREEK | 45/202 - CHESTNUTHILL | 40.9377 | -75.3928 | 20140281480 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | OH |  | Coordinated | 2015-07-24
184f | Y | 184 | 26888 | 11730 | 45071500201751 | 5 | Monroe | 1 M. N.OF BRODHEADSVILLE | SR 715 (LR45041) | MCMICHAELS CREEK | 45/202 - CHESTNUTHILL | 40.9377 | -75.3928 | 20140281480 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | OH |  | Concurrent | 2015-07-24
185a | Y | 185 | 26901 | 96445 | 45090300200000 | 5 | Monroe | 0.33 MI.W.OF PA 115 | SR 903 (LR 550) | TRIB.TO TUNKHANNOCK CK. | 45/216 - TUNKHANNOCK | 41.0528 | -75.5539 | 20140240157 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-08-26
185b | Y | 185 | 26901 | 96445 | 45090300200000 | 5 | Monroe | 0.33 MI.W.OF PA 115 | SR 903 (LR 550) | TRIB.TO TUNKHANNOCK CK. | 45/216 - TUNKHANNOCK | 41.0528 | -75.5539 | 20140240157 | Comm | Frontier Communications | Pat Galli (570) 208-6458, Patrick.Galli@FTR.com | OH |  | Coordinated | 2015-08-26
186a | Y | 186 | 26904 | 85879 | 45094000701313 | 5 | Monroe | 2 MI.E.OF BLAKESLEE | SR 940 (LR 169) | DAVEY RUN | 45/215 - TOBYHANNA | 41.1118 | -75.5609 | 20140170608, 20140691602 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Not Affected | 2015-07-20
186b | Y | 186 | 26904 | 85879 | 45094000701313 | 5 | Monroe | 2 MI.E.OF BLAKESLEE | SR 940 (LR 169) | DAVEY RUN | 45/215 - TOBYHANNA | 41.1118 | -75.5609 | 20140170608, 20140691602 | Comm | Frontier Communications Solutions | Melissa Sorber (570) 631-3060, Melissa.Sorber@FTR.com | OH |  | Not Affected | 2015-07-20
186c | Y | 186 | 26904 | 85879 | 45094000701313 | 5 | Monroe | 2 MI.E.OF BLAKESLEE | SR 940 (LR 169) | DAVEY RUN | 45/215 - TOBYHANNA | 41.1118 | -75.5609 | 20140170608, 20140691602 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | OH |  | Not Affected | 2015-07-20
186d | Y | 186 | 26904 | 85879 | 45094000701313 | 5 | Monroe | 2 MI.E.OF BLAKESLEE | SR 940 (LR 169) | DAVEY RUN | 45/215 - TOBYHANNA | 41.1118 | -75.5609 | 20140170608, 20140691602 | Gas | UGI Utilities, Inc. | Luke Lichtenwalner (610) 807-3140, lichtenwalner@ugi.com | UG |  | Prior | 2015-07-20
187a | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | 20140691482, 20140691602, 20140720024, 20140170626 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-24
187b | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | 20140691482, 20140691602, 20140720024, 20140170626 | Comm | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-24
187c | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | 20140691482, 20140691602, 20140720024, 20140170626 | Comm | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-24
187d | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | 20140691482, 20140691602, 20140720024, 20140170626 | Comm | Frontier Communications Solutions | Melissa Sorber (570) 631-3060, Melissa.Sorber@FTR.com | OH |  | Coordinated | 2015-07-24
187e | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | 20140691482, 20140691602, 20140720024, 20140170626 | Comm | Frontier Communications Solutions | Melissa Sorber (570) 631-3060, Melissa.Sorber@FTR.com | OH |  | Coordinated | 2015-07-24
187f | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | 20140691482, 20140691602, 20140720024, 20140170626 | Comm | Frontier Communications Solutions | Melissa Sorber (570) 631-3060, Melissa.Sorber@FTR.com | OH |  | Coordinated | 2015-07-24
187g | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | 20140691482, 20140691602, 20140720024, 20140170626 | Comm | Level 3 | Kou Yang (570) 300-2910, Kou.yang@Level3.com | OH |  | Coordinated | 2015-07-24
187h | Y | 187 | 26907 | 89628 | 45094001400882 | 5 | Monroe | 5 MI.E.OF BLAKESLEE | SR 940 (LR 169) | TOBYHANNA CK.(POCONO LKE | 45/215 - TOBYHANNA | 41.1117 | -75.5065 | 20140691482, 20140691602, 20140720024, 20140170626 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | OH |  | Coordinated | 2015-07-24
188a | Y | 188 | 26914 | 79204 | 45094003900000 | 5 | Monroe | 2 MI.E. OF MT.POCONO | SR 940 (LR 169) | PARADISE CREEK | 45/208 - PARADISE | 41.1271 | -75.308 | 20140170663, 20140680050 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2016-03-08
188b | Y | 188 | 26914 | 79204 | 45094003900000 | 5 | Monroe | 2 MI.E. OF MT.POCONO | SR 940 (LR 169) | PARADISE CREEK | 45/208 - PARADISE | 41.1271 | -75.308 | 20140170663, 20140680050 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2016-03-08
188c | Y | 188 | 26914 | 79204 | 45094003900000 | 5 | Monroe | 2 MI.E. OF MT.POCONO | SR 940 (LR 169) | PARADISE CREEK | 45/208 - PARADISE | 41.1271 | -75.308 | 20140170663, 20140680050 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | OH |  | Coordinated | 2016-03-08
188d | Y | 188 | 26914 | 79204 | 45094003900000 | 5 | Monroe | 2 MI.E. OF MT.POCONO | SR 940 (LR 169) | PARADISE CREEK | 45/208 - PARADISE | 41.1271 | -75.308 | 20140170663, 20140680050 | Comm | Verizon Pennsylvania, Inc. | Deborah Delia (412) 237-2285, deborah.d.delia@verizon.com; Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com | OH |  | Coordinated | 2016-03-08
189a | Y | 189 | 26924 | 79170 | 45100400300941 | 5 | Monroe | 1.2 M. E. OF PA 314 | SR 1004(LR 45027) | PARADISE CREEK | 45/208 - PARADISE | 41.1018 | -75.2696 | 20140630317 | N/A | N/A | N/A | N/A |  | Not Affected | 2016-06-08
190a | Y | 190 | 26962 | 76368 | 45200900101729 | 5 | Monroe | BRIDGE ST. | SR 2009(LR 45050) | POCONO CREEK | 45/214 - STROUD | 40.9854 | -75.2254 | 20130561832, 20130561993 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Prior | 2015-12-09
190b | Y | 190 | 26962 | 76368 | 45200900101729 | 5 | Monroe | BRIDGE ST. | SR 2009(LR 45050) | POCONO CREEK | 45/214 - STROUD | 40.9854 | -75.2254 | 20130561832, 20130561993 | Comm | Frontier Communications | Pat Galli (570) 208-6458, Patrick.Galli@FTR.com | OH |  | Prior | 2015-12-09
190c | Y | 190 | 26962 | 76368 | 45200900101729 | 5 | Monroe | BRIDGE ST. | SR 2009(LR 45050) | POCONO CREEK | 45/214 - STROUD | 40.9854 | -75.2254 | 20130561832, 20130561993 | Comm | Verizon Pennsylvania LLC | Deborah Delia (412) 633-3810, deborah.d.delia@verizon.com | OH |  | Prior | 2015-12-09
190d | Y | 190 | 26962 | 76368 | 45200900101729 | 5 | Monroe | BRIDGE ST. | SR 2009(LR 45050) | POCONO CREEK | 45/214 - STROUD | 40.9854 | -75.2254 | 20130561832, 20130561993 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | OH |  | Prior | 2015-12-09
190e | Y | 190 | 26962 | 76368 | 45200900101729 | 5 | Monroe | BRIDGE ST. | SR 2009(LR 45050) | POCONO CREEK | 45/214 - STROUD | 40.9854 | -75.2254 | 20130561832, 20130561993 | Gas | UGI Central Penn Gas | Tom O'Neill (610) 807-3701, to'neill@ugi.com | UG |  | Not Affected | 2015-12-09
190f | Y | 190 | 26962 | 76368 | 45200900101729 | 5 | Monroe | BRIDGE ST. | SR 2009(LR 45050) | POCONO CREEK | 45/214 - STROUD | 40.9854 | -75.2254 | 20130561832, 20130561993 | Water | Brodhead Creek Regional Authority | Chris Borger (570) 421-3232, cborger@ptd.net | UG |  | Not Affected | 2015-12-09
191a | Y | 191 | 27011 | 96447 | 45300900220000 | 5 | Monroe | T-939 S.OF MERWINSBURG | SR3009(45066)T-939 | POHOPOCO CREEK | 45/202 - CHESTNUTHILL | 40.951 | -75.4473 | 20140511410 | N/A | N/A | N/A | N/A |  | Not Affected | 2015-10-07
192a | Y | 192 | 27017 | 11758 | 45301100300000 | 5 | Monroe | SUGAR HOLLOW ROAD | SR 3011(LR 45042) | SUGAR HOLLOW CREEK | 45/202 - CHESTNUTHILL | 40.9634 | -75.4306 | 20140310593 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-08-07
192b | Y | 192 | 27017 | 11758 | 45301100300000 | 5 | Monroe | SUGAR HOLLOW ROAD | SR 3011(LR 45042) | SUGAR HOLLOW CREEK | 45/202 - CHESTNUTHILL | 40.9634 | -75.4306 | 20140310593 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-08-07
192c | Y | 192 | 27017 | 11758 | 45301100300000 | 5 | Monroe | SUGAR HOLLOW ROAD | SR 3011(LR 45042) | SUGAR HOLLOW CREEK | 45/202 - CHESTNUTHILL | 40.9634 | -75.4306 | 20140310593 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-08-07
192d | Y | 192 | 27017 | 11758 | 45301100300000 | 5 | Monroe | SUGAR HOLLOW ROAD | SR 3011(LR 45042) | SUGAR HOLLOW CREEK | 45/202 - CHESTNUTHILL | 40.9634 | -75.4306 | 20140310593 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | OH |  | Coordinated | 2015-08-07
192e | Y | 192 | 27017 | 11758 | 45301100300000 | 5 | Monroe | SUGAR HOLLOW ROAD | SR 3011(LR 45042) | SUGAR HOLLOW CREEK | 45/202 - CHESTNUTHILL | 40.9634 | -75.4306 | 20140310593 | Comm | Verizon Pennsylvania LLC | Deborah Delia (412) 237-2285, deborah.d.delia@verizon.com; Joseph Snyder (570) 424-0902, e-mail j.anthony.snyder@verizon.com; Bill Wojcik (570) 424-0058, william.wojcik@verizon.com | OH |  | Coordinated | 2015-08-07
| R | 193 | 27022 | #REF! | 45301500201644 | 5 | Monroe | ROLLING HILLS ROAD | #N/A | AQUASHICOLA CREEK | 45/202 - CHESTNUTHILL | 40.9634 | -75.4306 | [7 empty] | 2015-08-07
194a | Y | 194 | 27042 | 79185 | 45302301202040 | 5 | Monroe | RIM ROCK DRIVE | SR 3023(LR 45033) | POCONO CREEK | 45/205 - HAMILTON | 41.0036 | -75.2796 | 20092382122 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-21
194b | Y | 194 | 27042 | 79185 | 45302301202040 | 5 | Monroe | RIM ROCK DRIVE | SR 3023(LR 45033) | POCONO CREEK | 45/205 - HAMILTON | 41.0036 | -75.2796 | 20092382122 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-21
194c | Y | 194 | 27042 | 79185 | 45302301202040 | 5 | Monroe | RIM ROCK DRIVE | SR 3023(LR 45033) | POCONO CREEK | 45/205 - HAMILTON | 41.0036 | -75.2796 | 20092382122 | Comm | Verizon Pennsylvania LLC | Deborah Delia (412) 237-2285, deborah.d.delia@verizon.com; Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com | OH |  | Coordinated | 2015-07-21
194d | Y | 194 | 27042 | 79185 | 45302301202040 | 5 | Monroe | RIM ROCK DRIVE | SR 3023(LR 45033) | POCONO CREEK | 45/205 - HAMILTON | 41.0036 | -75.2796 | 20092382122 | Comm | Verizon Pennsylvania LLC | Deborah Delia (412) 237-2285, deborah.d.delia@verizon.com; Joseph Snyder (570) 424-0902, j.anthony.snyder@verizon.com | OH |  | Coordinated | 2015-07-21
194e | Y | 194 | 27042 | 79185 | 45302301202040 | 5 | Monroe | RIM ROCK DRIVE | SR 3023(LR 45033) | POCONO CREEK | 45/205 - HAMILTON | 41.0036 | -75.2796 | 20092382122 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | OH |  | Coordinated | 2015-07-21
195a | Y | 195 | 27055 | 85849 | 45400300702976 | 5 | Monroe | LOCUST RIDGE ROAD | SR 4003(LR45039) | TROUT CREEK | 45/215 - TOBYHANNA | 41.1528 | -75.5799 | 20140240144, 20140720024 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2016-04-28
195b | Y | 195 | 27055 | 85849 | 45400300702976 | 5 | Monroe | LOCUST RIDGE ROAD | SR 4003(LR45039) | TROUT CREEK | 45/215 - TOBYHANNA | 41.1528 | -75.5799 | 20140240144, 20140720024 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2016-04-28
195c | Y | 195 | 27055 | 85849 | 45400300702976 | 5 | Monroe | LOCUST RIDGE ROAD | SR 4003(LR45039) | TROUT CREEK | 45/215 - TOBYHANNA | 41.1528 | -75.5799 | 20140240144, 20140720024 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2016-04-28
195d | Y | 195 | 27055 | 85849 | 45400300702976 | 5 | Monroe | LOCUST RIDGE ROAD | SR 4003(LR45039) | TROUT CREEK | 45/215 - TOBYHANNA | 41.1528 | -75.5799 | 20140240144, 20140720024 | Comm | Frontier Communications Solutions | Melissa Sorber (570) 631-3060, Melissa.Sorber@FTR.com | OH |  | Coordinated | 2016-04-28
195e | Y | 195 | 27055 | 85849 | 45400300702976 | 5 | Monroe | LOCUST RIDGE ROAD | SR 4003(LR45039) | TROUT CREEK | 45/215 - TOBYHANNA | 41.1528 | -75.5799 | 20140240144, 20140720024 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | OH |  | Coordinated | 2016-04-28
196a | Y | 196 | 27059 | 79187 | 45400600200000 | 5 | Monroe | .7 M. W.OF LR 45024 | SR 4006(LR45024SP) | POCONO CREEK | 45/209 - POCONO | 41.0538 | -75.3403 | 20140240265 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Prior | 2016-03-08
196b | Y | 196 | 27059 | 79187 | 45400600200000 | 5 | Monroe | .7 M. W.OF LR 45024 | SR 4006(LR45024SP) | POCONO CREEK | 45/209 - POCONO | 41.0538 | -75.3403 | 20140240265 | Comm | Verizon Pennsylvania LLC | Deborah Delia (412) 231-2285, deborah.d.delia@verizon.com | OH |  | Prior | 2016-03-08
196c | Y | 196 | 27059 | 79187 | 45400600200000 | 5 | Monroe | .7 M. W.OF LR 45024 | SR 4006(LR45024SP) | POCONO CREEK | 45/209 - POCONO | 41.0538 | -75.3403 | 20140240265 | Comm | Blue Ridge Cable Television Inc. | Dwight Hunsicker, 610-826-9312, 484-547-1364, dhunsicker@pencor.com | OH |  | Prior | 2016-03-08
197a | -- | 197 | 28493 | 99555 | 48003300200000 | 5 | Northampton | US22/PA33 INTERCHANGE | SR 33(LR 1098NB) | SR 22(LR772) | 48/101 - BETHLEHEM | 40.6828 | -75.289 | 20150161793 | GAS | Amerigas Propane LP | Brenda Pulse, brenda.pulse@amerigas.com, 570-253-2490 | UG |  |  | 2016-06-06
197b | -- | 197 | 28493 | 99555 | 48003300200000 | 5 | Northampton | US22/PA33 INTERCHANGE | SR 33(LR 1098NB) | SR 22(LR772) | 48/101 - BETHLEHEM | 40.6828 | -75.289 | 20150161793 |  | Bethlehem TWP Municipal Auth/Bethlehem TWP | Matthew Dorner, Chief of Engineering, 610-865-7067, mdorner@bethlehem-pa.gov | UG |  |  | 2016-06-06
197c | -- | 197 | 28493 | 99555 | 48003300200000 | 5 | Northampton | US22/PA33 INTERCHANGE | SR 33(LR 1098NB) | SR 22(LR772) | 48/101 - BETHLEHEM | 40.6828 | -75.289 | 20150161793 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-06-06
197d | -- | 197 | 28493 | 99555 | 48003300200000 | 5 | Northampton | US22/PA33 INTERCHANGE | SR 33(LR 1098NB) | SR 22(LR772) | 48/101 - BETHLEHEM | 40.6828 | -75.289 | 20150161793 | Comm | RCN Telecom Services Inc | Bill Reese, 610-443-2956, bill.reese@rcn.net |  |  |  | 2016-06-06
198a | -- | 198 | 28494 | 104632 | 48003300210000 | 5 | Northampton | US22/PA33 INTERCHANGE | SR 33(LR 1098NB) | SR 22(LR772) | 48/101 - BETHLEHEM | 40.6828 | -75.289 | 20151412643 | GAS | Amerigas Propane LP | Gary, 484-426-7265; Brenda Pulse, brenda.pulse@amerigas.com, 570-253-2490 | UG |  |  | 2017-03-06
198b | -- | 198 | 28494 | 104632 | 48003300210000 | 5 | Northampton | US22/PA33 INTERCHANGE | SR 33(LR 1098NB) | SR 22(LR772) | 48/101 - BETHLEHEM | 40.6828 | -75.289 | 20151412643 | wtr | Bethlehem TWP Municipal Auth/Bethlehem TWP | Steven Hunsberger, steven@bethlehemtwp.com, 610-814-6400 | UG |  |  | 2017-03-06
| R | 199 | 42278 | #REF! | 48003301200000 | 5 | Northampton | 0.5 MI S OF PA 191 EXIT | #N/A | BUSHKILL CREEK | 48/101 - BETHLEHEM | 40.6828 | -75.289 | [7 empty] | 2017-03-06
| R | 200 | 42446 | #REF! | 48003301210000 | 5 | Northampton | 0.5MI S OF PA 191 EXIT | #N/A | BUSHKILL CREEK | 48/101 - BETHLEHEM | 40.6828 | -75.289 | [7 empty] | 2017-03-06
201 | -- | 201 | 28606 | 85947 | 48051202101582 | 5 | Northampton | W.MOORESTOWN RD.@ HEYER | SR 512 (LR 752) | BUSHKILL CR. | 48/203 - BUSHKILL | 40.789 | -75.3658 | 20150681634 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-06-17
202a | -- | 202 | 28660 | 67256 | 48100400601655 | 5 | Northampton | 3 MI.W.OF RIVERTON | SR 1004 (LR 48025) | OUGHOUGHTON CREEK | 48/208 - LOWER MT BETHEL | 40.8027 | -75.126 | 20150261297 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-06-27
202b | -- | 202 | 28660 | 67256 | 48100400601655 | 5 | Northampton | 3 MI.W.OF RIVERTON | SR 1004 (LR 48025) | OUGHOUGHTON CREEK | 48/208 - LOWER MT BETHEL | 40.8027 | -75.126 | 20150261297 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Brian Stoner, bstoner@firstenergycorp.com, 717-848-7181; Michele Heckman, 610-921-6695, mheckman@gpu.com |  |  |  | 2016-06-27
203a | -- | 203 | 28672 | 12098 | 48101500801677 | 5 | Northampton | @ INT. WITH T-604 | SR 1015 (LR 165) | WALTZ CREEK | 48/216 - WASHINGTON | 40.8248 | -75.2031 | 20150781905 | GAS | Amerigas Propane LP | Brenda Pulse, brenda.pulse@amerigas.com, 570-253-2490 | UG |  |  | 2017-05-11
203b | -- | 203 | 28672 | 12098 | 48101500801677 | 5 | Northampton | @ INT. WITH T-604 | SR 1015 (LR 165) | WALTZ CREEK | 48/216 - WASHINGTON | 40.8248 | -75.2031 | 20150781905 |  | Bangor Borough Auth | Luke Lichtenwalner, 610-807-3107 llichtenwalneri@ugi.com, 610-736-5571 | UG |  |  | 2017-05-11
203c | -- | 203 | 28672 | 12098 | 48101500801677 | 5 | Northampton | @ INT. WITH T-604 | SR 1015 (LR 165) | WALTZ CREEK | 48/216 - WASHINGTON | 40.8248 | -75.2031 | 20150781905 |  | East Bangor Municipal Auth | 610-588-4656, info@eastbangorborough.org |  |  |  | 2017-05-11
203d | -- | 203 | 28672 | 12098 | 48101500801677 | 5 | Northampton | @ INT. WITH T-604 | SR 1015 (LR 165) | WALTZ CREEK | 48/216 - WASHINGTON | 40.8248 | -75.2031 | 20150781905 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Brian Stoner, bstoner@firstenergycorp.com, 717-848-7181; Michele Heckman, 610-921-6695, mheckman@gpu.com |  |  |  | 2017-05-11
203e | -- | 203 | 28672 | 12098 | 48101500801677 | 5 | Northampton | @ INT. WITH T-604 | SR 1015 (LR 165) | WALTZ CREEK | 48/216 - WASHINGTON | 40.8248 | -75.2031 | 20150781905 |  | Washington TWP Northampton | 610-588-1524 |  |  |  | 2017-05-11
204a | Y | 204 | 30678 | 12717 | 53033902000276 | 5 | Schuylkill | VILLAGE OF ZIONS GROVE | PA 339 | CATAWISSA CREEK | 53/219 - NORTH UNION | 40.9031 | -76.21 | 20140690621, 20140761583 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-14
204b | Y | 204 | 30678 | 12717 | 53033902000276 | 5 | Schuylkill | VILLAGE OF ZIONS GROVE | PA 339 | CATAWISSA CREEK | 53/219 - NORTH UNION | 40.9031 | -76.21 | 20140690621, 20140761583 | Comm | Frontier Communications | John Bugdonovitch (570) 788-1777, John.Bugdonovitch@FTR.com | OH |  | Coordinated | 2015-07-14
205a | Y | 205 | 30679 | 99559 | 53033902400902 | 5 | Schuylkill | CATAWISSA CREEK ROAD | PA 339 (LR 53091) | CATAWISSA CREEK | 53/219 - NORTH UNION | 40.9212 | -76.2264 | 20140690644 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-09-15
205b | Y | 205 | 30679 | 99559 | 53033902400902 | 5 | Schuylkill | CATAWISSA CREEK ROAD | PA 339 (LR 53091) | CATAWISSA CREEK | 53/219 - NORTH UNION | 40.9212 | -76.2264 | 20140690644 | Comm | Frontier Communications | John Bugdonovitch (570) 788-1777, John.Bugdonovitch@FTR.com | OH |  | Coordinated | 2015-09-15
206a | Y | 206 | 30680 | 12710 | 53033902401098 | 5 | Schuylkill | CATAWISSA CREEK ROAD | SR 339(LR 53091) | TRIB.TO CATAWISSA CREEK | 53/219 - NORTH UNION | 40.9217 | -76.2265 | 20140690673 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-09-14
206b | Y | 206 | 30680 | 12710 | 53033902401098 | 5 | Schuylkill | CATAWISSA CREEK ROAD | SR 339(LR 53091) | TRIB.TO CATAWISSA CREEK | 53/219 - NORTH UNION | 40.9217 | -76.2265 | 20140690673 | Comm | Frontier Communications | John Bugdonovitch (570) 788-1777, John.Bugdonovitch@FTR.com | OH |  | Coordinated | 2015-09-14
207a | Y | 207 | 30730 | 85810 | 53092400702725 | 5 | Schuylkill | SOUTH SHENANDOAH | PA 924 (LR 464) | REMOVED RR & KEHLY RUN | 53/427 - SHENANDOAH | 40.8153 | -76.1995 | 20140761698 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Prior | 2016-02-17
207b | Y | 207 | 30730 | 85810 | 53092400702725 | 5 | Schuylkill | SOUTH SHENANDOAH | PA 924 (LR 464) | REMOVED RR & KEHLY RUN | 53/427 - SHENANDOAH | 40.8153 | -76.1995 | 20140761698 | Comm | Verizon Pennsylvania LLC | Ronald Silinski (570) 826-4263, ronald.w.silinskie@verizon.com; Kevin Brown (570) 826-4033, kevin.j.brown@verizon.com | OH |  | Prior | 2016-02-17
207c | Y | 207 | 30730 | 85810 | 53092400702725 | 5 | Schuylkill | SOUTH SHENANDOAH | PA 924 (LR 464) | REMOVED RR & KEHLY RUN | 53/427 - SHENANDOAH | 40.8153 | -76.1995 | 20140761698 | Comm | Service Electric Cablevision, Inc. | William Brayford (570) 773-2585, mahanoycity@secv.com | OH |  | Prior | 2016-02-17
207d | Y | 207 | 30730 | 85810 | 53092400702725 | 5 | Schuylkill | SOUTH SHENANDOAH | PA 924 (LR 464) | REMOVED RR & KEHLY RUN | 53/427 - SHENANDOAH | 40.8153 | -76.1995 | 20140761698 | Sewer | Borough of Shenandoah | Joe Palubinsky (570) 462-1918 | UG |  | Not Affected | 2016-02-17
207e | Y | 207 | 30730 | 85810 | 53092400702725 | 5 | Schuylkill | SOUTH SHENANDOAH | PA 924 (LR 464) | REMOVED RR & KEHLY RUN | 53/427 - SHENANDOAH | 40.8153 | -76.1995 | 20140761698 | Water | Shenendoah Municipal Authority | Rich **** (570) 233-5319 | UG |  | Not Affected | 2016-02-17
208a | Y | 208 | 30832 | 85724 | 53401600100000 | 5 | Schuylkill | VILLAGE OF KLINGERSTOWN | SR 4016 (LR 53047) | MAHANTANGO CREEK | 53/231 - UPPER MAHANTANG | 40.6616 | -76.6866 | 20130300901, 20140131742, 20140761803 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Coordinated | 2015-07-20
208b | Y | 208 | 30832 | 85724 | 53401600100000 | 5 | Schuylkill | VILLAGE OF KLINGERSTOWN | SR 4016 (LR 53047) | MAHANTANGO CREEK | 53/231 - UPPER MAHANTANG | 40.6616 | -76.6866 | 20130300901, 20140131742, 20140761803 | Comm | Comcast Cable Communications, Inc. | Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com; Gary Kissinger (610) 589-1415, Gary_Kissinger@cable.comcast.com | OH |  | Coordinated | 2015-07-20
208c | Y | 208 | 30832 | 85724 | 53401600100000 | 5 | Schuylkill | VILLAGE OF KLINGERSTOWN | SR 4016 (LR 53047) | MAHANTANGO CREEK | 53/231 - UPPER MAHANTANG | 40.6616 | -76.6866 | 20130300901, 20140131742, 20140761803 | Comm | TDS Telcom | Stewart Walker (315) 562-0091, stewart.walker@tdstelecom.com | OH |  | Coordinated | 2015-07-20
209a | Y | 209 | 30856 | 47695 | 53403600300000 | 5 | Schuylkill | 0.75 MI.E.OF COLUMBIA CO. | SR 4036(LR 53064) | TREXLER RUN | 53/230 - UNION | 40.8525 | -76.2805 | 20140161218, 20140761890 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Not Affected | 2015-08-24
209b | Y | 209 | 30856 | 47695 | 53403600300000 | 5 | Schuylkill | 0.75 MI.E.OF COLUMBIA CO. | SR 4036(LR 53064) | TREXLER RUN | 53/230 - UNION | 40.8525 | -76.2805 | 20140161218, 20140761890 | Comm | Frontier Communications | John Bugdonovitch (570) 788-1777, John.Bugdonovitch@FTR.com | OH |  | Coordinated | 2015-08-24
209c | Y | 209 | 30856 | 47695 | 53403600300000 | 5 | Schuylkill | 0.75 MI.E.OF COLUMBIA CO. | SR 4036(LR 53064) | TREXLER RUN | 53/230 - UNION | 40.8525 | -76.2805 | 20140161218, 20140761890 | Comm | Frontier Communications | John Bugdonovitch (570) 788-1777, John.Bugdonovitch@FTR.com | OH |  | Coordinated | 2015-08-24
209d | Y | 209 | 30856 | 47695 | 53403600300000 | 5 | Schuylkill | 0.75 MI.E.OF COLUMBIA CO. | SR 4036(LR 53064) | TREXLER RUN | 53/230 - UNION | 40.8525 | -76.2805 | 20140161218, 20140761890 | Comm | Service Electric Cablevision, Inc. | Robert Trently (570) 454-3841, robert.trently@secv.com | OH |  | Coordinated | 2015-08-24
210a | Y | 210 | 30862 | 12522 | 53403900200000 | 5 | Schuylkill | VILLAGE OF HAAS | SR 4039 (LR 53055) | MAHANTANGO CREEK | 53/210 - ELDRED | 40.7038 | -76.4901 | 20140131714, 20140761993 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa (610) 774-6287, cakrupa@pplweb.com | OH |  | Restrictive | 2015-07-20
210b | Y | 210 | 30862 | 12522 | 53403900200000 | 5 | Schuylkill | VILLAGE OF HAAS | SR 4039 (LR 53055) | MAHANTANGO CREEK | 53/210 - ELDRED | 40.7038 | -76.4901 | 20140131714, 20140761993 | Comm | Verizon Pennsylvania, LLC | Jerry Van Buskirk (570) 374-0412, jerry.vanbuskirk@verizon.com | OH |  | Coordinated | 2015-07-20
211a | -- | 211 | 7262 | 56830 | 9203701900000 | 6 | Bucks | BILLBOARD 38C08 (3151E10) | LINCOLN HIGHWAY | EAST BR.QUEEN ANNE CREEK | 09/208 - FALLS | 40.1878 | -74.8468 | 20143580217 |  | TWP of Falls Authority | 215-946-6062, info@tofa-pa.com | UG |  |  | 2017-04-03
211b | -- | 211 | 7262 | 56830 | 9203701900000 | 6 | Bucks | BILLBOARD 38C08 (3151E10) | LINCOLN HIGHWAY | EAST BR.QUEEN ANNE CREEK | 09/208 - FALLS | 40.1878 | -74.8468 | 20143580217 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 |  |  |  | 2017-04-03
212 | -- | 212 | 10497 | 81284 | 15304401300000 | 6 | Chester | NEAR WEST GROVE 45F06 (3799E7) | EWING ROAD | MIDDLE BR WHITE CLAY CR | 15/222 - LONDON GROVE | 39.8326 | -75.8452 | 20150712604 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 |  |  |  | 2017-03-06
213 | -- | 213 | 10599 | 86306 | 15400800402407 | 6 | Chester | BRANDYWINE MANOR 19E02 (3360E09) | INDIAN RUN DRIVE | INDIAN RUN | 15/241 - WALLACE | 40.0722 | -75.7863 | 20150682247 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 |  |  |  | 2016-08-31
214a | -- | 214 | 15002 | 15232 | 23042000701072 | 6 | Delaware | FOLSOM, NR MACDADE 35D09/3697K07 | KEDRON AVENUE | STONY CREEK / 3697-K6 | 23/107 - RIDLEY | 39.8979 | -75.3162 | 20150271475 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 |  |  |  | 2016-08-04
214b | -- | 214 | 15002 | 15232 | 23042000701072 | 6 | Delaware | FOLSOM, NR MACDADE 35D09/3697K07 | KEDRON AVENUE | STONY CREEK / 3697-K6 | 23/107 - RIDLEY | 39.8979 | -75.3162 | 20150271475 | wtr | Aqua Pennsylvania | William A. Zahn, 610-645-4203, wazahn@aquaamerica.com | UG |  |  | 2016-08-04
214c | -- | 214 | 15002 | 15232 | 23042000701072 | 6 | Delaware | FOLSOM, NR MACDADE 35D09/3697K07 | KEDRON AVENUE | STONY CREEK / 3697-K6 | 23/107 - RIDLEY | 39.8979 | -75.3162 | 20150271475 | sanitary | Central Delaware County Auth | Phillip Dossou, Pdossou@cataniaengineering.com | UG | 30" |  | 2016-08-04
214d | -- | 214 | 15002 | 15232 | 23042000701072 | 6 | Delaware | FOLSOM, NR MACDADE 35D09/3697K07 | KEDRON AVENUE | STONY CREEK / 3697-K6 | 23/107 - RIDLEY | 39.8979 | -75.3162 | 20150271475 | wtr | Township of Ridley | Margaret Keegan, 610-534-4806, pkeegan@mail.twp.ridley.pa.us | UG |  |  | 2016-08-04
215a | -- | 215 | 27513 | 102315 | 46066302700894 | 6 | Montgomery | PERKIOMEN HEIGHTS 02D13 | LAYFIELD ROAD | BRCH PERKIOMEN CR/2916H1 | 46/219 - UPPER HANOVER | 40.3734 | -75.5184 | 20150751388 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 |  |  |  | 2017-03-24
215b | -- | 215 | 27513 | 102315 | 46066302700894 | 6 | Montgomery | PERKIOMEN HEIGHTS 02D13 | LAYFIELD ROAD | BRCH PERKIOMEN CR/2916H1 | 46/219 - UPPER HANOVER | 40.3734 | -75.5184 | 20150751388 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-03-24
216a | -- | 216 | 27605 | 102218 | 46201300320000 | 6 | Montgomery | 1.5MI.WEST PHILA. 33C07 | PHILMONT AVENUE | VALLEY CR. 3372B1 | 46/105 - LOWER MORELAND | 40.1219 | -75.0515 | 20150751415 | wtr | Aqua Pennsylvania | William A. Zahn, 610-645-4203, wazahn@aquaamerica.com | UG |  |  | 2017-03-08
216b | -- | 216 | 27605 | 102218 | 46201300320000 | 6 | Montgomery | 1.5MI.WEST PHILA. 33C07 | PHILMONT AVENUE | VALLEY CR. 3372B1 | 46/105 - LOWER MORELAND | 40.1219 | -75.0515 | 20150751415 | sanitary | Lower Moreland TWP | 215-947-3100 | UG |  |  | 2017-03-08
216c | -- | 216 | 27605 | 102218 | 46201300320000 | 6 | Montgomery | 1.5MI.WEST PHILA. 33C07 | PHILMONT AVENUE | VALLEY CR. 3372B1 | 46/105 - LOWER MORELAND | 40.1219 | -75.0515 | 20150751415 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 |  |  |  | 2017-03-08
217a | -- | 217 | 27643 | 86343 | 46202700500209 | 6 | Montgomery | SPRINGFIELD TWP. 31B07 | PENNSYLVANIA AVE. | SANDY RUN | 46/108 - SPRINGFIELD | 40.1232 | -75.1915 | 20150751452 | wtr | Aqua Pennsylvania | William A. Zahn, 610-645-4203, wazahn@aquaamerica.com | UG |  |  | 2017-03-24
217b | -- | 217 | 27643 | 86343 | 46202700500209 | 6 | Montgomery | SPRINGFIELD TWP. 31B07 | PENNSYLVANIA AVE. | SANDY RUN | 46/108 - SPRINGFIELD | 40.1232 | -75.1915 | 20150751452 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 |  |  |  | 2017-03-24
217c | -- | 217 | 27643 | 86343 | 46202700500209 | 6 | Montgomery | SPRINGFIELD TWP. 31B07 | PENNSYLVANIA AVE. | SANDY RUN | 46/108 - SPRINGFIELD | 40.1232 | -75.1915 | 20150751452 | wtr | Philadelphia City Water Dept | Charles H. Sawyer, 215-686-3410 | UG |  |  | 2017-03-24
217d | -- | 217 | 27643 | 86343 | 46202700500209 | 6 | Montgomery | SPRINGFIELD TWP. 31B07 | PENNSYLVANIA AVE. | SANDY RUN | 46/108 - SPRINGFIELD | 40.1232 | -75.1915 | 20150751452 | sanitary | Bucks County Water and Sewer Auth | James Napoleon, jimnapoleon@bcwsa.net | UG |  |  | 2017-03-24
218a | -- | 218 | 27757 | 67373 | 46304400500389 | 6 | Montgomery | WYNNEWOOD;WOODSIDE 3478H10 | WYNNWOOD ROAD | BRANCH INDIAN CREEK | 46/412 - NARBERTH | 40.0033 | -75.2683 | 20150701229 | wtr | Aqua Pennsylvania | William A. Zahn, 610-645-4203, wazahn@aquaamerica.com | UG |  |  | 2016-08-31
218b | -- | 218 | 27757 | 67373 | 46304400500389 | 6 | Montgomery | WYNNEWOOD;WOODSIDE 3478H10 | WYNNWOOD ROAD | BRANCH INDIAN CREEK | 46/412 - NARBERTH | 40.0033 | -75.2683 | 20150701229 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 |  |  |  | 2016-08-31
218c | -- | 218 | 27757 | 67373 | 46304400500389 | 6 | Montgomery | WYNNEWOOD;WOODSIDE 3478H10 | WYNNWOOD ROAD | BRANCH INDIAN CREEK | 46/412 - NARBERTH | 40.0033 | -75.2683 | 20150701229 | Comm | Verizon Pennsylvania LLC | Cindy Oberholtzer, 570-387-3175, coberholtzer@usceng.com.; Norman Parrish, 610-280-2152, norman.l.parrish@verizon.net | UG |  |  | 2016-08-31
219a | -- | 219 | 27868 | 81290 | 46404200341011 | 6 | Montgomery | NW POTTSTOWN 11B6/3026C8 | GROSSTOWN ROAD | MANATAWNY CREEK | 46/112 - WEST POTTSGROVE | 40.267 | -75.6728 | 20143571505 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ,Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com; Nicole L. LeVine, Assoc. Engr. 610-380-2537 |  |  |  | 2016-07-05
219b | -- | 219 | 27868 | 81290 | 46404200341011 | 6 | Montgomery | NW POTTSTOWN 11B6/3026C8 | GROSSTOWN ROAD | MANATAWNY CREEK | 46/112 - WEST POTTSGROVE | 40.267 | -75.6728 | 20143571505 | Comm | Verizon Pennsylvania LLC | Cindy Oberholtzer, coberholtzer@usceng.com , 570-387-3175 | UG |  |  | 2016-07-05
220a | -- | 220 | 47 | 87428 | 1003003000000 | 8 | Adams | GETTYSBURG | US 30; SR 0030 | ROCK CREEK | 01/407 - GETTYSBURG | 39.8346 | -77.2199 | 20150681661/ 20150681662 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2017-04-03
220b | -- | 220 | 47 | 87428 | 1003003000000 | 8 | Adams | GETTYSBURG | US 30; SR 0030 | ROCK CREEK | 01/407 - GETTYSBURG | 39.8346 | -77.2199 | 20150681661/ 20150681662 | GAS | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com, rian K. Shomper, 717-849-0137, bshomper@nisource.com | UG |  |  | 2017-04-03
220c | -- | 220 | 47 | 87428 | 1003003000000 | 8 | Adams | GETTYSBURG | US 30; SR 0030 | ROCK CREEK | 01/407 - GETTYSBURG | 39.8346 | -77.2199 | 20150681661/ 20150681662 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-04-03
220d | -- | 220 | 47 | 87428 | 1003003000000 | 8 | Adams | GETTYSBURG | US 30; SR 0030 | ROCK CREEK | 01/407 - GETTYSBURG | 39.8346 | -77.2199 | 20150681661/ 20150681662 | sanitary | Gettysburg Borough | 717-334-1160 | UG |  |  | 2017-04-03
220e | -- | 220 | 47 | 87428 | 1003003000000 | 8 | Adams | GETTYSBURG | US 30; SR 0030 | ROCK CREEK | 01/407 - GETTYSBURG | 39.8346 | -77.2199 | 20150681661/ 20150681662 | sanitary | Gettysburg Municipal Auth | Mark Guise, 717-334-6738 | UG |  |  | 2017-04-03
220f | -- | 220 | 47 | 87428 | 1003003000000 | 8 | Adams | GETTYSBURG | US 30; SR 0030 | ROCK CREEK | 01/407 - GETTYSBURG | 39.8346 | -77.2199 | 20150681661/ 20150681662 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-04-03
221a | -- | 221 | 71 | 87427 | 1003402200745 | 8 | Adams | N. OF BIGLERVILLE | PA 34; SR 0034 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9812 | -77.2343 | 20150261301 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com |  |  |  | 2016-08-15
221b | -- | 221 | 71 | 87427 | 1003402200745 | 8 | Adams | N. OF BIGLERVILLE | PA 34; SR 0034 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9812 | -77.2343 | 20150261301 | sanitary | Bendersville Borough | Andrea Rivera, secretary@bendersvilleborough.net, 717-677-8112. Ken McKee, 717-677-7857 | UG |  |  | 2016-08-15
221c | -- | 221 | 71 | 87427 | 1003402200745 | 8 | Adams | N. OF BIGLERVILLE | PA 34; SR 0034 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9812 | -77.2343 | 20150261301 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2016-08-15
221d | -- | 221 | 71 | 87427 | 1003402200745 | 8 | Adams | N. OF BIGLERVILLE | PA 34; SR 0034 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9812 | -77.2343 | 20150261301 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | UG |  |  | 2016-08-15
221e | -- | 221 | 71 | 87427 | 1003402200745 | 8 | Adams | N. OF BIGLERVILLE | PA 34; SR 0034 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9812 | -77.2343 | 20150261301 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-08-15
221f | -- | 221 | 71 | 87427 | 1003402200745 | 8 | Adams | N. OF BIGLERVILLE | PA 34; SR 0034 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9812 | -77.2343 | 20150261301 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2016-08-15
222a | -- | 222 | 75 | 87417 | 1003402700000 | 8 | Adams | IDAVILLE | PA 34; SR 0034 | BERMUDIAN CREEK | 01/220 - TYRONE | 40.0131 | -77.2029 | 20150261305, 20150261306 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2016-07-11
222b | -- | 222 | 75 | 87417 | 1003402700000 | 8 | Adams | IDAVILLE | PA 34; SR 0034 | BERMUDIAN CREEK | 01/220 - TYRONE | 40.0131 | -77.2029 | 20150261305, 20150261306 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-07-11
222c | -- | 222 | 75 | 87417 | 1003402700000 | 8 | Adams | IDAVILLE | PA 34; SR 0034 | BERMUDIAN CREEK | 01/220 - TYRONE | 40.0131 | -77.2029 | 20150261305, 20150261306 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2016-07-11
223a | -- | 223 | 87 | 87673 | 1009701000240 | 8 | Adams | 1 MI. N. OF LITTLESTOWN | PA 97; SR 0097 | ALLOWAY CREEK | 01/215 - MOUNT JOY | 39.7588 | -77.124 | 20150712635/ 20150712636 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2017-03-21
223b | -- | 223 | 87 | 87673 | 1009701000240 | 8 | Adams | 1 MI. N. OF LITTLESTOWN | PA 97; SR 0097 | ALLOWAY CREEK | 01/215 - MOUNT JOY | 39.7588 | -77.124 | 20150712635/ 20150712636 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | UG |  |  | 2017-03-21
223c | -- | 223 | 87 | 87673 | 1009701000240 | 8 | Adams | 1 MI. N. OF LITTLESTOWN | PA 97; SR 0097 | ALLOWAY CREEK | 01/215 - MOUNT JOY | 39.7588 | -77.124 | 20150712635/ 20150712636 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-03-21
223d | -- | 223 | 87 | 87673 | 1009701000240 | 8 | Adams | 1 MI. N. OF LITTLESTOWN | PA 97; SR 0097 | ALLOWAY CREEK | 01/215 - MOUNT JOY | 39.7588 | -77.124 | 20150712635/ 20150712636 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-03-21
224a | -- | 224 | 98 | 18051 | 1011601100000 | 8 | Adams | 1 MI N E OF FAIRFIELD | PA 116; SR 0116 | MUDDY RUN | 01/210 - HIGHLAND | 39.8002 | -77.3497 | 20150161850 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com |  |  |  | 2016-06-17
224b | -- | 224 | 98 | 18051 | 1011601100000 | 8 | Adams | 1 MI N E OF FAIRFIELD | PA 116; SR 0116 | MUDDY RUN | 01/210 - HIGHLAND | 39.8002 | -77.3497 | 20150161850 | Comm | Centurylink formerly Embarq | Perry Byers (until December 2016), 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com, Matt 814-935-5365 |  |  |  | 2016-06-17
224c | -- | 224 | 98 | 18051 | 1011601100000 | 8 | Adams | 1 MI N E OF FAIRFIELD | PA 116; SR 0116 | MUDDY RUN | 01/210 - HIGHLAND | 39.8002 | -77.3497 | 20150161850 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-06-17
224d | -- | 224 | 98 | 18051 | 1011601100000 | 8 | Adams | 1 MI N E OF FAIRFIELD | PA 116; SR 0116 | MUDDY RUN | 01/210 - HIGHLAND | 39.8002 | -77.3497 | 20150161850 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2016-06-17
224e | -- | 224 | 98 | 18051 | 1011601100000 | 8 | Adams | 1 MI N E OF FAIRFIELD | PA 116; SR 0116 | MUDDY RUN | 01/210 - HIGHLAND | 39.8002 | -77.3497 | 20150161850 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2016-06-17
225a | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | 20150170124 | sanitary | Abbottstown Borough | Loreen Greer, abbottstwon@comcast.net, 717-259-0965 | UG |  |  | 2016-06-16
225b | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | 20150170124 | sanitary | Abbottstown Paradise Joint Sewer Auth | Amy E. Perry, 717-259-9120, aperry@apjsawwtf.comcastbiz.net; P. O. Box 505, Abbottstown, PA 17301 | UG |  |  | 2016-06-16
225c | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | 20150170124 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-92; Alan W. Mains, 717-334-2171, alanm@adamsec.com |  |  |  | 2016-06-16
225d | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | 20150170124 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2016-06-16
225e | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | 20150170124 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-06-16
225f | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | 20150170124 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2016-06-16
225g | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | 20150170124 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | UG |  |  | 2016-06-16
225h | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | 20150170124 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com |  |  |  | 2016-06-16
225i | -- | 225 | 128 | 99774 | 1019402401689 | 8 | Adams | ABBOTTSTOWN | PA 194; SR 0194 | BRANCH OF BEAVER CREEK | 01/401 - ABBOTTSTOWN | 39.8838 | -76.9831 | 20150170124 | wtr | York Water CO | Kent K. Croman, 717-718-7541, kentc@yorkwater.com | UG |  |  | 2016-06-16
226a | -- | 226 | 135 | 87436 | 1023401202343 | 8 | Adams | CULPS CORNERS | PA 234; SR 0234 | CONEWAGO CREEK | 01/205 - FRANKLIN | 39.9462 | -77.3403 | 20150762657/ 20150762658 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2017-08-01
226b | -- | 226 | 135 | 87436 | 1023401202343 | 8 | Adams | CULPS CORNERS | PA 234; SR 0234 | CONEWAGO CREEK | 01/205 - FRANKLIN | 39.9462 | -77.3403 | 20150762657/ 20150762658 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-08-01
226c | -- | 226 | 135 | 87436 | 1023401202343 | 8 | Adams | CULPS CORNERS | PA 234; SR 0234 | CONEWAGO CREEK | 01/205 - FRANKLIN | 39.9462 | -77.3403 | 20150762657/ 20150762658 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-08-01
226d | -- | 226 | 135 | 87436 | 1023401202343 | 8 | Adams | CULPS CORNERS | PA 234; SR 0234 | CONEWAGO CREEK | 01/205 - FRANKLIN | 39.9462 | -77.3403 | 20150762657/ 20150762658 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2017-08-01
226e | -- | 226 | 135 | 87436 | 1023401202343 | 8 | Adams | CULPS CORNERS | PA 234; SR 0234 | CONEWAGO CREEK | 01/205 - FRANKLIN | 39.9462 | -77.3403 | 20150762657/ 20150762658 | sanitary | Bendersville Borough | Andrea Rivera, secretary@bendersvilleborough.net, 717-677-8112. Ken McKee, 717-677-7857 | UG |  |  | 2017-08-01
227 | -- | 227 | 148 | 87434 | 1023403100000 | 8 | Adams | 2 MI.N.E. OF BIGLERVILLE | PA 234; SR 0234 | OPOSSUM CREEK | 01/202 - BUTLER | 39.9411 | -77.2045 | 20150170126 |  | all facilities responded clear per one call |  |  |  |  | 2016-06-17
228a | -- | 228 | 160 | 18146 | 1039400600526 | 8 | Adams | VILLAGE OF TABLE ROCK | PA 394; SR 0394 | CONEWAGO CREEK | 01/202 - BUTLER | 39.9154 | -77.2217 | 20151412879 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | UG |  |  | 2017-06-05
228b | -- | 228 | 160 | 18146 | 1039400600526 | 8 | Adams | VILLAGE OF TABLE ROCK | PA 394; SR 0394 | CONEWAGO CREEK | 01/202 - BUTLER | 39.9154 | -77.2217 | 20151412879 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | UG |  |  | 2017-06-05
228c | -- | 228 | 160 | 18146 | 1039400600526 | 8 | Adams | VILLAGE OF TABLE ROCK | PA 394; SR 0394 | CONEWAGO CREEK | 01/202 - BUTLER | 39.9154 | -77.2217 | 20151412879 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-06-05
229a | -- | 229 | 185 | 87676 | 1101400501701 | 8 | Adams | VILLAGE OF LIMEROCK MILL | SR 1014 | BERMUDIAN CREEK | 01/211 - HUNTINGTON | 39.9825 | -77.1646 | 20150261308, 20150261307 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com |  |  |  | 2016-06-22
229b | -- | 229 | 185 | 87676 | 1101400501701 | 8 | Adams | VILLAGE OF LIMEROCK MILL | SR 1014 | BERMUDIAN CREEK | 01/211 - HUNTINGTON | 39.9825 | -77.1646 | 20150261308, 20150261307 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2016-06-22
229c | -- | 229 | 185 | 87676 | 1101400501701 | 8 | Adams | VILLAGE OF LIMEROCK MILL | SR 1014 | BERMUDIAN CREEK | 01/211 - HUNTINGTON | 39.9825 | -77.1646 | 20150261308, 20150261307 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-06-22
230 | -- | 230 | 198 | 87671 | 1101601101587 | 8 | Adams | GARDNERS | SR 1016 | UPPER BERMUDIAN CREEK | 01/211 - HUNTINGTON | 40.0031 | -77.1924 | 20150762107/ 20150762108 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-03-06
231a | -- | 231 | 229 | 74951 | 1200600400591 | 8 | Adams | 2 MI. S.E. HUNTERSTOWN | SR 2006 | CSX; WESTERN MARYLAND RR | 01/219 - STRABAN | 39.8612 | -77.136 | 20143580152 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2016-05-25
231b | -- | 231 | 229 | 74951 | 1200600400591 | 8 | Adams | 2 MI. S.E. HUNTERSTOWN | SR 2006 | CSX; WESTERN MARYLAND RR | 01/219 - STRABAN | 39.8612 | -77.136 | 20143580152 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325, Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-05-25
231c | -- | 231 | 229 | 74951 | 1200600400591 | 8 | Adams | 2 MI. S.E. HUNTERSTOWN | SR 2006 | CSX; WESTERN MARYLAND RR | 01/219 - STRABAN | 39.8612 | -77.136 | 20143580152 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | UG |  |  | 2016-05-25
231d | -- | 231 | 229 | 74951 | 1200600400591 | 8 | Adams | 2 MI. S.E. HUNTERSTOWN | SR 2006 | CSX; WESTERN MARYLAND RR | 01/219 - STRABAN | 39.8612 | -77.136 | 20143580152 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2016-05-25
231e | -- | 231 | 229 | 74951 | 1200600400591 | 8 | Adams | 2 MI. S.E. HUNTERSTOWN | SR 2006 | CSX; WESTERN MARYLAND RR | 01/219 - STRABAN | 39.8612 | -77.136 | 20143580152 | GAS | Sunoco Pipeline LP | sxldesignreviews@sunocologistics.com; Tracy Hoffman, 610-670-3256, tlhoffman@sunocologistics.com | UG |  |  | 2016-05-25
232a | -- | 232 | 319 | 87675 | 1301301000061 | 8 | Adams | KNOXLYN | SR 3013 | MARSH CREEK | 01/210 - HIGHLAND | 39.8305 | -77.3177 | 20151412034 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com |  |  |  | 2017-05-30
232b | -- | 232 | 319 | 87675 | 1301301000061 | 8 | Adams | KNOXLYN | SR 3013 | MARSH CREEK | 01/210 - HIGHLAND | 39.8305 | -77.3177 | 20151412034 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-05-30
232c | -- | 232 | 319 | 87675 | 1301301000061 | 8 | Adams | KNOXLYN | SR 3013 | MARSH CREEK | 01/210 - HIGHLAND | 39.8305 | -77.3177 | 20151412034 |  | Highland TWP | 717-642-8410, highlandtownship@comcast.net, hours M-Th 8:30-2:30pm |  |  |  | 2017-05-30
232d | -- | 232 | 319 | 87675 | 1301301000061 | 8 | Adams | KNOXLYN | SR 3013 | MARSH CREEK | 01/210 - HIGHLAND | 39.8305 | -77.3177 | 20151412034 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-05-30
233a | -- | 233 | 362 | 87437 | 1400500101339 | 8 | Adams | 1/4 MI.N. OF BENDERSVILLE | SR 4005 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9899 | -77.2529 | 20151411415 |  | Bendersville Borough | Andrea Rivera, secretary@bendersvilleborough.net, 717-677-8112. Ken McKee, 717-677-7857 |  |  |  | 2017-06-01
233b | -- | 233 | 362 | 87437 | 1400500101339 | 8 | Adams | 1/4 MI.N. OF BENDERSVILLE | SR 4005 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9899 | -77.2529 | 20151411415 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | UG |  |  | 2017-06-01
233c | -- | 233 | 362 | 87437 | 1400500101339 | 8 | Adams | 1/4 MI.N. OF BENDERSVILLE | SR 4005 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9899 | -77.2529 | 20151411415 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-06-01
233d | -- | 233 | 362 | 87437 | 1400500101339 | 8 | Adams | 1/4 MI.N. OF BENDERSVILLE | SR 4005 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.9899 | -77.2529 | 20151411415 |  | Menallen TWP | 717-677-6635, menallentwp@centurylink.net |  |  |  | 2017-06-01
234 | -- | 234 | 364 | 87438 | 1400601202897 | 8 | Adams | ASPERS | SR 4006 | OPOSSUM CREEK | 01/214 - MENALLEN | 39.977 | -77.2255 | 20150161834 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | UG |  |  | 2017-05-26
235a | -- | 235 | 381 | 90784 | 1401100101013 | 8 | Adams | NEAR ADAMS & FRANK.LINE | SR 4011 | CARBAUGH RUN | 01/205 - FRANKLIN | 39.9014 | -77.4676 | 20150712651 | Gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | UG |  |  | 2017-05-30
235b | -- | 235 | 381 | 90784 | 1401100101013 | 8 | Adams | NEAR ADAMS & FRANK.LINE | SR 4011 | CARBAUGH RUN | 01/205 - FRANKLIN | 39.9014 | -77.4676 | 20150712651 | Gas | Texas Eastern/Spectra | Michael Beer, 717-709-4201 | UG |  |  | 2017-05-30
236a | -- | 236 | 13564 | 90694 | 21001105202844 | 8 | Cumberland | 1 MI EAST OF MIDDLESEX | US 11; SR 0011 | LETORT SPRING CREEK | 21/203 - HOPEWELL | 40.2338 | -77.1388 | 20150721703 |  | Carlisle Borough/Carlisle Borough Municipal Auth | Mark Malarich, 717-249-6932, Mmalarich@carlislepa.org | UG |  |  | 2017-03-13
236b | -- | 236 | 13564 | 90694 | 21001105202844 | 8 | Cumberland | 1 MI EAST OF MIDDLESEX | US 11; SR 0011 | LETORT SPRING CREEK | 21/203 - HOPEWELL | 40.2338 | -77.1388 | 20150721703 | Comm | Centurylink formerly Embarq | Perry Byers (until December 2016), 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com, Matt 814-935-5365 |  |  |  | 2017-03-13
236c | -- | 236 | 13564 | 90694 | 21001105202844 | 8 | Cumberland | 1 MI EAST OF MIDDLESEX | US 11; SR 0011 | LETORT SPRING CREEK | 21/203 - HOPEWELL | 40.2338 | -77.1388 | 20150721703 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-03-13
236d | -- | 236 | 13564 | 90694 | 21001105202844 | 8 | Cumberland | 1 MI EAST OF MIDDLESEX | US 11; SR 0011 | LETORT SPRING CREEK | 21/203 - HOPEWELL | 40.2338 | -77.1388 | 20150721703 |  | Middlesex TWP Municipal Auth | Rory Morrison, 717-243-0674 | UG |  |  | 2017-03-13
236d | -- | 236 | 13564 | 90694 | 21001105202844 | 8 | Cumberland | 1 MI EAST OF MIDDLESEX | US 11; SR 0011 | LETORT SPRING CREEK | 21/203 - HOPEWELL | 40.2338 | -77.1388 | 20150721703 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-03-13
236e | -- | 236 | 13564 | 90694 | 21001105202844 | 8 | Cumberland | 1 MI EAST OF MIDDLESEX | US 11; SR 0011 | LETORT SPRING CREEK | 21/203 - HOPEWELL | 40.2338 | -77.1388 | 20150721703 | Gas | UGI Utilities, Inc. | Tom Witt, twitt@ugi.com, 717-255-1425; Barry Lieberman, 717-299-7281 | UG |  |  | 2017-03-13
237a | -- | 237 | 13616 | 87424 | 21003400700827 | 8 | Cumberland | HUNTERS RUN | PA 34; SR 0034 | HUNTERS RUN | 21/213 - SOUTH MIDDLETON | 40.0794 | -77.1932 | 20150721733 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2017-03-21
237b | -- | 237 | 13616 | 87424 | 21003400700827 | 8 | Cumberland | HUNTERS RUN | PA 34; SR 0034 | HUNTERS RUN | 21/213 - SOUTH MIDDLETON | 40.0794 | -77.1932 | 20150721733 | Comm | Comcast Cable Communications, Inc. | Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-03-21
237c | -- | 237 | 13616 | 87424 | 21003400700827 | 8 | Cumberland | HUNTERS RUN | PA 34; SR 0034 | HUNTERS RUN | 21/213 - SOUTH MIDDLETON | 40.0794 | -77.1932 | 20150721733 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-03-21
238a | -- | 238 | 13735 | 90695 | 21023300900266 | 8 | Cumberland | PINE GROVE FURNACE | PA 233; SR 0233 | TOMS RUN | 21/201 - COOKE | 40.0338 | -77.304 | 20151671682 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-08-21
238b | -- | 238 | 13735 | 90695 | 21023300900266 | 8 | Cumberland | PINE GROVE FURNACE | PA 233; SR 0233 | TOMS RUN | 21/201 - COOKE | 40.0338 | -77.304 | 20151671682 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2017-08-21
239a | -- | 239 | 13741 | 89274 | 21023303801454 | 8 | Cumberland | NORTH OF NEWVILLE | PA 233; SR 0233 | CONODOQUINET CREEK | 21/209 - NORTH NEWTON | 40.1842 | -77.406 | 20150721759 / 20150721760 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2017-02-10
239b | -- | 239 | 13741 | 89274 | 21023303801454 | 8 | Cumberland | NORTH OF NEWVILLE | PA 233; SR 0233 | CONODOQUINET CREEK | 21/209 - NORTH NEWTON | 40.1842 | -77.406 | 20150721759 / 20150721760 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-02-10
239c | -- | 239 | 13741 | 89274 | 21023303801454 | 8 | Cumberland | NORTH OF NEWVILLE | PA 233; SR 0233 | CONODOQUINET CREEK | 21/209 - NORTH NEWTON | 40.1842 | -77.406 | 20150721759 / 20150721760 | sanitary | North Newton TWP | 717-532-5372 | UG |  |  | 2017-02-10
239d | -- | 239 | 13741 | 89274 | 21023303801454 | 8 | Cumberland | NORTH OF NEWVILLE | PA 233; SR 0233 | CONODOQUINET CREEK | 21/209 - NORTH NEWTON | 40.1842 | -77.406 | 20150721759 / 20150721760 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-02-10
240a | -- | 240 | 13824 | 74054 | 21099702601555 | 8 | Cumberland | MCCREA | PA 997; SR 0997 | DOUBLING GAP CREEK | 21/205 - LOWER MIFFLIN | 40.2381 | -77.4452 | 20150781279 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com |  |  |  | 2017-05-11
240b | -- | 240 | 13824 | 74054 | 21099702601555 | 8 | Cumberland | MCCREA | PA 997; SR 0997 | DOUBLING GAP CREEK | 21/205 - LOWER MIFFLIN | 40.2381 | -77.4452 | 20150781279 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2017-05-11
240c | -- | 240 | 13824 | 74054 | 21099702601555 | 8 | Cumberland | MCCREA | PA 997; SR 0997 | DOUBLING GAP CREEK | 21/205 - LOWER MIFFLIN | 40.2381 | -77.4452 | 20150781279 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-05-11
241 | -- | 241 | 13896 | 90739 | 21203100100000 | 8 | Cumberland | Spanglers Mill over Yellow Breeches Ck | 2031 Spanglers Mil | YELLOW BREECHES CREEK | 21/102 - LOWER ALLEN | 40.212 | -76.9065 | 20150762150 /20150762160 |  | all facilities responded clear per one call |  |  |  |  | 2017-05-31
242a | -- | 242 | 13946 | 74055 | 21301900100000 | 8 | Cumberland | MONTSERA | SR 3019; T-544 | YELLOW BREECHES CREEK | 21/202 - DICKINSON | 40.1118 | -77.2847 | 20151411466 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | UG |  |  | 2017-05-30
242b | -- | 242 | 13946 | 74055 | 21301900100000 | 8 | Cumberland | MONTSERA | SR 3019; T-544 | YELLOW BREECHES CREEK | 21/202 - DICKINSON | 40.1118 | -77.2847 | 20151411466 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-05-30
242c | -- | 242 | 13946 | 74055 | 21301900100000 | 8 | Cumberland | MONTSERA | SR 3019; T-544 | YELLOW BREECHES CREEK | 21/202 - DICKINSON | 40.1118 | -77.2847 | 20151411466 | Comm | Sprint Nextel | 1-800-521-0579 | UG |  |  | 2017-05-30
242d | -- | 242 | 13946 | 74055 | 21301900100000 | 8 | Cumberland | MONTSERA | SR 3019; T-544 | YELLOW BREECHES CREEK | 21/202 - DICKINSON | 40.1118 | -77.2847 | 20151411466 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Gail Schmitz, Gail.Schmitz@windstream.com, 1-800-289-1901 | UG |  |  | 2017-05-30
243 | -- | 243 | 13948 | 90769 | 21400100200000 | 8 | Cumberland | 2 MI.N. OF SHIPPENSBURG | SR 4001; TWP. RD. | MIDDLE SPRING CR. | 21/215 - SOUTHAMPTON | 40.0834 | -77.5432 | 20151412188, 20151412224 | wtr | Southern Cumberland Water Association | 717-530-0703 | UG |  |  | 2017-05-30
244a | -- | 244 | 13961 | 90770 | 21400800302148 | 8 | Cumberland | WASHINGTON | SR 4008 | BACK CREEK | 21/205 - LOWER MIFFLIN | 40.2091 | -77.4366 | 20151420686 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com |  |  |  | 2017-08-14
244b | -- | 244 | 13961 | 90770 | 21400800302148 | 8 | Cumberland | WASHINGTON | SR 4008 | BACK CREEK | 21/205 - LOWER MIFFLIN | 40.2091 | -77.4366 | 20151420686 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | UG |  |  | 2017-08-14
244c | -- | 244 | 13961 | 90770 | 21400800302148 | 8 | Cumberland | WASHINGTON | SR 4008 | BACK CREEK | 21/205 - LOWER MIFFLIN | 40.2091 | -77.4366 | 20151420686 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-08-14
244d | -- | 244 | 13961 | 90770 | 21400800302148 | 8 | Cumberland | WASHINGTON | SR 4008 | BACK CREEK | 21/205 - LOWER MIFFLIN | 40.2091 | -77.4366 | 20151420686 | Comm | Kuhn Communications Inc | 717-532-8857 |  |  |  | 2017-08-14
245a | -- | 245 | 14441 | 100078 | 22101800101692 | 8 | Dauphin | 3 MI. N W GRATZ | SR 1018 | DEEP CREEK | 22/210 - LYKENS | 40.628 | -76.778 | 20150701189 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-08-18
245b | -- | 245 | 14441 | 100078 | 22101800101692 | 8 | Dauphin | 3 MI. N W GRATZ | SR 1018 | DEEP CREEK | 22/210 - LYKENS | 40.628 | -76.778 | 20150701189 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-08-18
245c | -- | 245 | 14441 | 100078 | 22101800101692 | 8 | Dauphin | 3 MI. N W GRATZ | SR 1018 | DEEP CREEK | 22/210 - LYKENS | 40.628 | -76.778 | 20150701189 | Comm | TDS Telcom | Gregory Michael, 570-758-6911, gregory.michael@tdstelecom.com |  |  |  | 2016-08-18
246a | -- | 246 | 14481 | 47519 | 22201200100356 | 8 | Dauphin | .5 MI. N. OF HERSHEY | SR 2012 | NS RAILROAD (PENN EAST) | 22/202 - DERRY | 40.2995 | -76.6385 | 20150271477 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | UG |  |  | 2016-08-01
246b | -- | 246 | 14481 | 47519 | 22201200100356 | 8 | Dauphin | .5 MI. N. OF HERSHEY | SR 2012 | NS RAILROAD (PENN EAST) | 22/202 - DERRY | 40.2995 | -76.6385 | 20150271477 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-08-01
246c | -- | 246 | 14481 | 47519 | 22201200100356 | 8 | Dauphin | .5 MI. N. OF HERSHEY | SR 2012 | NS RAILROAD (PENN EAST) | 22/202 - DERRY | 40.2995 | -76.6385 | 20150271477 | wtr | Pennsylvania American Water CO | Linda Taflinger, 717-531-3294, linda.taflinger@amwater.com | UG |  |  | 2016-08-01
246d | -- | 246 | 14481 | 47519 | 22201200100356 | 8 | Dauphin | .5 MI. N. OF HERSHEY | SR 2012 | NS RAILROAD (PENN EAST) | 22/202 - DERRY | 40.2995 | -76.6385 | 20150271477 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-08-01
246e | -- | 246 | 14481 | 47519 | 22201200100356 | 8 | Dauphin | .5 MI. N. OF HERSHEY | SR 2012 | NS RAILROAD (PENN EAST) | 22/202 - DERRY | 40.2995 | -76.6385 | 20150271477 | Gas | UGI Utilities, Inc. | Tom Witt, twitt@ugi.com, 717-255-1425; Barry Lieberman, 717-299-7281 | UG |  |  | 2016-08-01
247a | -- | 247 | 14578 | 87457 | 22400400202505 | 8 | Dauphin | 2 MI. W. ENDERS | SR 4004 | ARMSTRONG CREEK | 22/205 - JACKSON | 40.4805 | -76.8825 | 20150261309 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-07-05
247b | -- | 247 | 14578 | 87457 | 22400400202505 | 8 | Dauphin | 2 MI. W. ENDERS | SR 4004 | ARMSTRONG CREEK | 22/205 - JACKSON | 40.4805 | -76.8825 | 20150261309 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-07-05
248a | -- | 248 | 17407 | 87686 | 28023302000092 | 8 | Franklin | AT CALEDONIA STATE PARK | PA 233; SR 0233 | CARBAUGH RUN | 28/203 - GREENE | 39.9054 | -77.4783 | 20150781288 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2017-08-07
248b | -- | 248 | 17407 | 87686 | 28023302000092 | 8 | Franklin | AT CALEDONIA STATE PARK | PA 233; SR 0233 | CARBAUGH RUN | 28/203 - GREENE | 39.9054 | -77.4783 | 20150781288 | GAS | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; Brian K. Shomper, 717-849-0137, bshomper@nisource.com | UG | 3" |  | 2017-08-07
248c | -- | 248 | 17407 | 87686 | 28023302000092 | 8 | Franklin | AT CALEDONIA STATE PARK | PA 233; SR 0233 | CARBAUGH RUN | 28/203 - GREENE | 39.9054 | -77.4783 | 20150781288 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-08-07
248d | -- | 248 | 17407 | 87686 | 28023302000092 | 8 | Franklin | AT CALEDONIA STATE PARK | PA 233; SR 0233 | CARBAUGH RUN | 28/203 - GREENE | 39.9054 | -77.4783 | 20150781288 | Gas | Sunoco Pipeline LP | sxldesignreviews@sunocologistics.com; Tracy Hoffman, 610-670-3256, tlhoffman@sunocologistics.com | UG |  |  | 2017-08-07
248e | -- | 248 | 17407 | 87686 | 28023302000092 | 8 | Franklin | AT CALEDONIA STATE PARK | PA 233; SR 0233 | CARBAUGH RUN | 28/203 - GREENE | 39.9054 | -77.4783 | 20150781288 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2017-08-07
249 | -- | 249 | 17408 | 63173 | 28027400200000 | 8 | Franklin | 1 ML. N. OF DOYLESBURG | PA 274; SR 0274 | BR. TUSCARORA CREEK | 28/202 - FANNETT | 40.2257 | -77.6928 | 20143580224 |  | all facilities responded clear per one call |  |  |  |  | 2016-05-17
250a | -- | 250 | 17471 | 87683 | 28099706500000 | 8 | Franklin | TOWNSHIP LINE LURG.& LETT | PA 997; SR 0997 | CONODOGUINET CREEK | 28/206 - LETTERKENNY | 40.0916 | -77.6481 | 20150781297/ 20150781298 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-05-11
250b | -- | 250 | 17471 | 87683 | 28099706500000 | 8 | Franklin | TOWNSHIP LINE LURG.& LETT | PA 997; SR 0997 | CONODOGUINET CREEK | 28/206 - LETTERKENNY | 40.0916 | -77.6481 | 20150781297/ 20150781298 | Elect | Pennsylvania Electric Company | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com |  |  |  | 2017-05-11
250c | -- | 250 | 17471 | 87683 | 28099706500000 | 8 | Franklin | TOWNSHIP LINE LURG.& LETT | PA 997; SR 0997 | CONODOGUINET CREEK | 28/206 - LETTERKENNY | 40.0916 | -77.6481 | 20150781297/ 20150781298 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2017-05-11
250d | -- | 250 | 17471 | 87683 | 28099706500000 | 8 | Franklin | TOWNSHIP LINE LURG.& LETT | PA 997; SR 0997 | CONODOGUINET CREEK | 28/206 - LETTERKENNY | 40.0916 | -77.6481 | 20150781297/ 20150781298 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com |  |  |  | 2017-05-11
250e | -- | 250 | 17471 | 87683 | 28099706500000 | 8 | Franklin | TOWNSHIP LINE LURG.& LETT | PA 997; SR 0997 | CONODOGUINET CREEK | 28/206 - LETTERKENNY | 40.0916 | -77.6481 | 20150781297/ 20150781298 | sanitary | Lurgan TWP | 717-532-7460 | UG |  |  | 2017-05-11
251 | -- | 251 | 17592 | 78710 | 28400801900060 | 8 | Franklin | 2 MI. NE OF EDENVILLE | SR 4008 | DENNIS RUN | 28/205 - HAMILTON | 39.9768 | -77.7583 | 20151411926 |  | all facilities responded clear per one call |  |  |  |  | 2017-06-08
252a | -- | 252 | 17593 | 78708 | 28400802301142 | 8 | Franklin | 3 MI E OF EDENVILLE | SR 4008 | ROCKY SPRING CREEK | 28/205 - HAMILTON | 39.9649 | -77.7302 | 20150261312 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2016-07-11
252b | -- | 252 | 17593 | 78708 | 28400802301142 | 8 | Franklin | 3 MI E OF EDENVILLE | SR 4008 | ROCKY SPRING CREEK | 28/205 - HAMILTON | 39.9649 | -77.7302 | 20150261312 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2016-07-11
252c | -- | 252 | 17593 | 78708 | 28400802301142 | 8 | Franklin | 3 MI E OF EDENVILLE | SR 4008 | ROCKY SPRING CREEK | 28/205 - HAMILTON | 39.9649 | -77.7302 | 20150261312 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-07-11
253a | -- | 253 | 20976 | 19965 | 36002300301231 | 8 | Lancaster | 1.5 MI.E. of Marietta | PA 23; SR 0023 | Chickies Creek | 36/239 - WEST HEMPFIELD | 40.0629 | -76.5162 | 20143580433, 20143580434 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-06-07
253b | -- | 253 | 20976 | 19965 | 36002300301231 | 8 | Lancaster | 1.5 MI.E. of Marietta | PA 23; SR 0023 | Chickies Creek | 36/239 - WEST HEMPFIELD | 40.0629 | -76.5162 | 20143580433, 20143580434 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-06-07
253c | -- | 253 | 20976 | 19965 | 36002300301231 | 8 | Lancaster | 1.5 MI.E. of Marietta | PA 23; SR 0023 | Chickies Creek | 36/239 - WEST HEMPFIELD | 40.0629 | -76.5162 | 20143580433, 20143580434 | wtr | Columbia Water Company | Dave Lewis, dlewis@pa.net, 717-684-2188 ;Charles Gohn (retired),columbiawater@pa.net | UG |  |  | 2016-06-07
253d | -- | 253 | 20976 | 19965 | 36002300301231 | 8 | Lancaster | 1.5 MI.E. of Marietta | PA 23; SR 0023 | Chickies Creek | 36/239 - WEST HEMPFIELD | 40.0629 | -76.5162 | 20143580433, 20143580434 | Gas | Sunoco Pipeline LP | sxldesignreviews@sunocologistics.com; Tracy Hoffman, 610-670-3256, tlhoffman@sunocologistics.com | UG |  |  | 2016-06-07
254a | -- | 254 | 21043 | 87315 | 36003004802322 | 8 | Lancaster | LEAMAN PLACE | US 30; SR 0030 | ESHELMAN'S RUN | 36/226 - PARADISE | 40.006 | -76.1108 | 20150721780 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-03-21
254b | -- | 254 | 21043 | 87315 | 36003004802322 | 8 | Lancaster | LEAMAN PLACE | US 30; SR 0030 | ESHELMAN'S RUN | 36/226 - PARADISE | 40.006 | -76.1108 | 20150721780 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-03-21
255a | -- | 255 | 21196 | 87316 | 36032201500954 | 8 | Lancaster | VILLAGE OF CLAY | US 322; SR 0322 | MIDDLE CREEK | 36/204 - CLAY | 40.2191 | -76.2577 | 20150681684/ 20150681685 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-06-17
255b | -- | 255 | 21196 | 87316 | 36032201500954 | 8 | Lancaster | VILLAGE OF CLAY | US 322; SR 0322 | MIDDLE CREEK | 36/204 - CLAY | 40.2191 | -76.2577 | 20150681684/ 20150681685 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-06-17
255c | -- | 255 | 21196 | 87316 | 36032201500954 | 8 | Lancaster | VILLAGE OF CLAY | US 322; SR 0322 | MIDDLE CREEK | 36/204 - CLAY | 40.2191 | -76.2577 | 20150681684/ 20150681685 | Comm | WINDSTREAM | Glen Esenwein, 610-582-6239, gesenwein@ceni.com |  |  |  | 2016-06-17
256a | -- | 256 | 21237 | 87536 | 36034003700000 | 8 | Lancaster | 1 MI. W. OF CAIN | PA 340; SR 0340 | PEQUEA CREEK | 36/232 - SALISBURY | 40.0289 | -75.967 | 20150781953 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-05-30
256b | -- | 256 | 21237 | 87536 | 36034003700000 | 8 | Lancaster | 1 MI. W. OF CAIN | PA 340; SR 0340 | PEQUEA CREEK | 36/232 - SALISBURY | 40.0289 | -75.967 | 20150781953 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-05-30
256c | -- | 256 | 21237 | 87536 | 36034003700000 | 8 | Lancaster | 1 MI. W. OF CAIN | PA 340; SR 0340 | PEQUEA CREEK | 36/232 - SALISBURY | 40.0289 | -75.967 | 20150781953 |  | Salisbury TWP | 717-768-8059 | UG |  |  | 2017-05-30
257a | -- | 257 | 21238 | 87554 | 36034003801674 | 8 | Lancaster | CAINS | PA 340; SR 0340 | MILLER'S RUN | 36/232 - SALISBURY | 40.0249 | -75.9487 | 20150271480 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-08-18
257b | -- | 257 | 21238 | 87554 | 36034003801674 | 8 | Lancaster | CAINS | PA 340; SR 0340 | MILLER'S RUN | 36/232 - SALISBURY | 40.0249 | -75.9487 | 20150271480 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-08-18
258a | -- | 258 | 21251 | 19915 | 36037204240000 | 8 | Lancaster | Christiana Borough | PA 372; Water St | Williams Run | 36/403 - CHRISTIANA | 39.9533 | -75.9967 | 20151462579 |  | Christiana Boro/Christiana B W&S Auth | Laverne Rettew (secy), 610-593-5199, christianaboro@comcast.net | UG |  |  | 2017-05-11
258b | -- | 258 | 21251 | 19915 | 36037204240000 | 8 | Lancaster | Christiana Borough | PA 372; Water St | Williams Run | 36/403 - CHRISTIANA | 39.9533 | -75.9967 | 20151462579 | Comm | Comcast Cable Communications, Inc. | Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2017-05-11
258c | -- | 258 | 21251 | 19915 | 36037204240000 | 8 | Lancaster | Christiana Borough | PA 372; Water St | Williams Run | 36/403 - CHRISTIANA | 39.9533 | -75.9967 | 20151462579 | Elect | PECO Energy | Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com |  |  |  | 2017-05-11
258d | -- | 258 | 21251 | 19915 | 36037204240000 | 8 | Lancaster | Christiana Borough | PA 372; Water St | Williams Run | 36/403 - CHRISTIANA | 39.9533 | -75.9967 | 20151462579 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-05-11
259a | -- | 259 | 21277 | 87505 | 36046202200000 | 8 | Lancaster | Columbia Ave over Little Conestoga Creek | 462 Columbia Ave | LITTLE CONESTOGA CREEK | 36/220 - LANCASTER | 40.0379 | -76.343 | 20150722077 /20150722078/ 20150722079 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-03-08
259b | -- | 259 | 21277 | 87505 | 36046202200000 | 8 | Lancaster | Columbia Ave over Little Conestoga Creek | 462 Columbia Ave | LITTLE CONESTOGA CREEK | 36/220 - LANCASTER | 40.0379 | -76.343 | 20150722077 /20150722078/ 20150722079 | sanitary | City of Lancaster/Lanc SA/Lanc Auth | Michael Kyle, 717-299-4843 | UG |  |  | 2017-03-08
259c | -- | 259 | 21277 | 87505 | 36046202200000 | 8 | Lancaster | Columbia Ave over Little Conestoga Creek | 462 Columbia Ave | LITTLE CONESTOGA CREEK | 36/220 - LANCASTER | 40.0379 | -76.343 | 20150722077 /20150722078/ 20150722079 | wtr | Lancaster TWP | Robert J. Ruth, PE, 717-291-4729, rruth@cityoflancasterpa.com | UG |  |  | 2017-03-08
259d | -- | 259 | 21277 | 87505 | 36046202200000 | 8 | Lancaster | Columbia Ave over Little Conestoga Creek | 462 Columbia Ave | LITTLE CONESTOGA CREEK | 36/220 - LANCASTER | 40.0379 | -76.343 | 20150722077 /20150722078/ 20150722079 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-03-08
259e | -- | 259 | 21277 | 87505 | 36046202200000 | 8 | Lancaster | Columbia Ave over Little Conestoga Creek | 462 Columbia Ave | LITTLE CONESTOGA CREEK | 36/220 - LANCASTER | 40.0379 | -76.343 | 20150722077 /20150722078/ 20150722079 | wtr | East Hempfield TWP | Rod Ray, 717-898-8231 | UG |  |  | 2017-03-08
259f | -- | 259 | 21277 | 87505 | 36046202200000 | 8 | Lancaster | Columbia Ave over Little Conestoga Creek | 462 Columbia Ave | LITTLE CONESTOGA CREEK | 36/220 - LANCASTER | 40.0379 | -76.343 | 20150722077 /20150722078/ 20150722079 |  | Manor TWP | 717-397-4769 | UG |  |  | 2017-03-08
260 | -- | 260 | 21292 | 91194 | 36062501302573 | 8 | Lancaster | 1 MI. S. OF BOWMANSVILLE | PA 625; SR 0625 | MUDDY CREEK | 36/202 - BRECKNOCK | 40.1893 | -76.0169 | 20150761153 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-05-31
261a | -- | 261 | 21326 | 78868 | 36077204500174 | 8 | Lancaster | 1.5 MI. S.E. OF LITITZ | PA 772; SR 0772 | LITITZ RUN | 36/235 - WARWICK | 40.1476 | -76.2715 | 20143580443 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-06-22
261b | -- | 261 | 21326 | 78868 | 36077204500174 | 8 | Lancaster | 1.5 MI. S.E. OF LITITZ | PA 772; SR 0772 | LITITZ RUN | 36/235 - WARWICK | 40.1476 | -76.2715 | 20143580443 |  | Warwick TWP Municipal Auth | Carl Haws / Claudia Watt, 717-627-2379, chaws@warwicktownship.org | UG |  |  | 2016-06-22
261c | -- | 261 | 21326 | 78868 | 36077204500174 | 8 | Lancaster | 1.5 MI. S.E. OF LITITZ | PA 772; SR 0772 | LITITZ RUN | 36/235 - WARWICK | 40.1476 | -76.2715 | 20143580443 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David F. Ackerman. David.F.Ackerman@windstream.com, 319-790-1464 | OH |  |  | 2016-06-22
262a | -- | 262 | 21403 | 91266 | 36101900500000 | 8 | Lancaster | 1.5 MI. S.E. CHURCHTOWN | Shirktown Rd | Conestoga River | 36/203 - CAERNARVON | 40.1328 | -75.9367 | 20143571514 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-04-03
262b | -- | 262 | 21403 | 91266 | 36101900500000 | 8 | Lancaster | 1.5 MI. S.E. CHURCHTOWN | Shirktown Rd | Conestoga River | 36/203 - CAERNARVON | 40.1328 | -75.9367 | 20143571514 |  | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-04-03
262c | -- | 262 | 21403 | 91266 | 36101900500000 | 8 | Lancaster | 1.5 MI. S.E. CHURCHTOWN | Shirktown Rd | Conestoga River | 36/203 - CAERNARVON | 40.1328 | -75.9367 | 20143571514 | Comm | Service Electric Cablevision, Inc. | Darryl Reccek, 610-868-0902, rec@sectv.com |  |  |  | 2017-04-03
262d | -- | 262 | 21403 | 91266 | 36101900500000 | 8 | Lancaster | 1.5 MI. S.E. CHURCHTOWN | Shirktown Rd | Conestoga River | 36/203 - CAERNARVON | 40.1328 | -75.9367 | 20143571514 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David F. Ackerman. David.F.Ackerman@windstream.com, 319-790-1464 | UG & OH |  |  | 2017-04-03
263a | -- | 263 | 21409 | 87521 | 36102100420000 | 8 | Lancaster | S. OF UNION GROVE | SR 1021; TWP. RD. | Conestoga River | 36/213 - EAST EARL | 40.1437 | -76.0207 | 20151671723 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-05-30
263b | -- | 263 | 21409 | 87521 | 36102100420000 | 8 | Lancaster | S. OF UNION GROVE | SR 1021; TWP. RD. | Conestoga River | 36/213 - EAST EARL | 40.1437 | -76.0207 | 20151671723 | Comm | Frontier Communications | James Zionkowski, 610-926-4747, james.zionkowski@frontiercorp.com |  |  |  | 2017-05-30
263c | -- | 263 | 21409 | 87521 | 36102100420000 | 8 | Lancaster | S. OF UNION GROVE | SR 1021; TWP. RD. | Conestoga River | 36/213 - EAST EARL | 40.1437 | -76.0207 | 20151671723 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-05-30
264 | -- | 264 | 21415 | 74958 | 36102402100000 | 8 | Lancaster | WEST OF SPRINGVILLE | SR 1024 | INDIAN RUN | 36/218 - EPHRATA | 40.2039 | -76.1822 | 20150261320 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-07-11
265a | -- | 265 | 21417 | 19927 | 36102500801639 | 8 | Lancaster | 0.75 mi NW of Farmersville | N Farmersville Rd | Conestoga River | 36/238 - WEST EARL | 40.1348 | -76.1741 | 20150271482 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-08-03
265b | -- | 265 | 21417 | 19927 | 36102500801639 | 8 | Lancaster | 0.75 mi NW of Farmersville | N Farmersville Rd | Conestoga River | 36/238 - WEST EARL | 40.1348 | -76.1741 | 20150271482 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-08-03
265c | -- | 265 | 21417 | 19927 | 36102500801639 | 8 | Lancaster | 0.75 mi NW of Farmersville | N Farmersville Rd | Conestoga River | 36/238 - WEST EARL | 40.1348 | -76.1741 | 20150271482 | sanitary | West Earl TWP | James Houser, 717-859-3201 | UG |  |  | 2016-08-03
266a | -- | 266 | 21439 | 100523 | 36103400200000 | 8 | Lancaster | 1MI NE DENVER | S.R. 1034 | SWAMP CREEK | 36/210 - EAST COCALICO | 40.2441 | -76.1136 | 20151471484 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-07-10
266b | -- | 266 | 21439 | 100523 | 36103400200000 | 8 | Lancaster | 1MI NE DENVER | S.R. 1034 | SWAMP CREEK | 36/210 - EAST COCALICO | 40.2441 | -76.1136 | 20151471484 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David Ackerman, David.F.Ackerman@windstream.com, 319-790-1464 | OH |  |  | 2017-07-10
267a | -- | 267 | 21446 | 63230 | 36103501500846 | 8 | Lancaster | 0.75 MILE N. OF NEWTOWN | SR 1035 | MIDDLE CREEK | 36/204 - CLAY | 40.2452 | -76.2489 | 20151472602 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-08-31
267b | -- | 267 | 21446 | 63230 | 36103501500846 | 8 | Lancaster | 0.75 MILE N. OF NEWTOWN | SR 1035 | MIDDLE CREEK | 36/204 - CLAY | 40.2452 | -76.2489 | 20151472602 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-08-31
268a | -- | 268 | 21454 | 20124 | 36103702100000 | 8 | Lancaster | Speedwell Forge Rd/Hammer Creek | SR 1037 | HAMMER CREEK | 36/217 - ELIZABETH | 40.2276 | -76.335 | 20150271484 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Joseph Green, Joseph.Green@windstream.com, 319-790-7510 | OH |  |  | 2016-08-03
269a | -- | 269 | 21459 | 87706 | 36103900500000 | 8 | Lancaster | 1.5 MI.N. OF MILLWAY | SR 1039 | MIDDLE CREEK | 36/218 - EPHRATA | 40.1772 | -76.2417 | 20151470444 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-08-01
269b | -- | 269 | 21459 | 87706 | 36103900500000 | 8 | Lancaster | 1.5 MI.N. OF MILLWAY | SR 1039 | MIDDLE CREEK | 36/218 - EPHRATA | 40.1772 | -76.2417 | 20151470444 | Comm | WINDSTREAM | Glen Esenwein, 610-582-6239, gesenwein@ceni.com; gesenwein@decommunications.com; |  |  |  | 2017-08-01
270 | -- | 270 | 21474 | 91323 | 36104800500000 | 8 | Lancaster | 1.25 MI.E. OF TERRE HILL | SR 1048 | BLACK CREEK | 36/213 - EAST EARL | 40.1656 | -76.0222 | 20151470509, 20151470510 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-08-01
271a | -- | 271 | 21482 | 87515 | 36105300200000 | 8 | Lancaster | 0.5 MI. W. DENVER BORO | SR 1053 | COCALICO CREEK | 36/236 - WEST COCALICO | 40.2413 | -76.1414 | 20150271485 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-08-03
271b | -- | 271 | 21482 | 87515 | 36105300200000 | 8 | Lancaster | 0.5 MI. W. DENVER BORO | SR 1053 | COCALICO CREEK | 36/236 - WEST COCALICO | 40.2413 | -76.1414 | 20150271485 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-08-03
271c | -- | 271 | 21482 | 87515 | 36105300200000 | 8 | Lancaster | 0.5 MI. W. DENVER BORO | SR 1053 | COCALICO CREEK | 36/236 - WEST COCALICO | 40.2413 | -76.1414 | 20150271485 | GAS | UGI Utilities, Inc. | Tom Witt, twitt@ugi.com, 717-255-1425; Barry Lieberman, 717-299-7281 | UG |  |  | 2016-08-03
271d | -- | 271 | 21482 | 87515 | 36105300200000 | 8 | Lancaster | 0.5 MI. W. DENVER BORO | SR 1053 | COCALICO CREEK | 36/236 - WEST COCALICO | 40.2413 | -76.1414 | 20150271485 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com |  |  |  | 2016-08-03
271e | -- | 271 | 21482 | 87515 | 36105300200000 | 8 | Lancaster | 0.5 MI. W. DENVER BORO | SR 1053 | COCALICO CREEK | 36/236 - WEST COCALICO | 40.2413 | -76.1414 | 20150271485 | Comm | WINDSTREAM | Glen Esenwein, 610-582-6239, gesenwein@ceni.com; gesenwein@decommunications.com; | UG |  |  | 2016-08-03
272a | -- | 272 | 21487 | 87566 | 36105500202673 | 8 | Lancaster | Reinholds Rd over Swamp Ck (N of i76) | SR 1055 | SWAMP CREEK | 36/210 - EAST COCALICO | 40.243 | -76.123 | 20143561430 |  | Ephrata Borough/Ephrata Joint Auth | David Burkholder, dburkholder@ephrataboro.org, 717-738-9202 (x135) ; Ryan Coulson, 717-738-9222 |  |  |  | 2016-05-17
272b | -- | 272 | 21487 | 87566 | 36105500202673 | 8 | Lancaster | Reinholds Rd over Swamp Ck (N of i76) | SR 1055 | SWAMP CREEK | 36/210 - EAST COCALICO | 40.243 | -76.123 | 20143561430 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com |  |  |  | 2016-05-17
273a | -- | 273 | 21514 | 91324 | 36200200602329 | 8 | Lancaster | KIRKS MILL | Twp Road | REYNOLDS RUN | 36/222 - LITTLE BRITAIN | 39.7552 | -76.1071 | 20150762193 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2017-06-12
273b | -- | 273 | 21514 | 91324 | 36200200602329 | 8 | Lancaster | KIRKS MILL | Twp Road | REYNOLDS RUN | 36/222 - LITTLE BRITAIN | 39.7552 | -76.1071 | 20150762193 | Comm | Neon Transcom | Brian Loucks, 508-439-2406 |  |  |  | 2017-06-12
273c | -- | 273 | 21514 | 91324 | 36200200602329 | 8 | Lancaster | KIRKS MILL | Twp Road | REYNOLDS RUN | 36/222 - LITTLE BRITAIN | 39.7552 | -76.1071 | 20150762193 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-06-12
274a | -- | 274 | 21518 | 87516 | 36200500300000 | 8 | Lancaster | 1MI NOF NEW TEXAS | SR 2005; TWP ROAD | LITTLE CONOWINGO CRK | 36/219 - FULTON | 39.7625 | -76.1542 | 20150641242 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias, 717-453-7434, jack_tobias@cable.comcast.com |  |  |  | 2016-08-03
274b | -- | 274 | 21518 | 87516 | 36200500300000 | 8 | Lancaster | 1MI NOF NEW TEXAS | SR 2005; TWP ROAD | LITTLE CONOWINGO CRK | 36/219 - FULTON | 39.7625 | -76.1542 | 20150641242 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-08-03
275a | -- | 275 | 21533 | 20123 | 36201000560000 | 8 | Lancaster | PUSEYVILLE | SR 2010 | W BR OCTORARO | 36/205 - COLERAIN | 39.8481 | -76.1136 | 20150781883 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-07-31
276 | -- | 276 | 21536 | 87562 | 36201200320000 | 8 | Lancaster | 1 MI.N. OF UNION | SR 2012; TWP RD | TRIB W.BR.OCTORARO | 36/205 - COLERAIN | 39.8517 | -76.0433 | 20151470950 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-08-01
277 | -- | 277 | 21545 | 91108 | 36201500400000 | 8 | Lancaster | 2 MI E OF COLLINS | SR 2015 | WEST BRANCH OCTORARO CR | 36/205 - COLERAIN | 39.8806 | -76.1047 | 20151463220 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-06-01
278a | -- | 278 | 21558 | 19964 | 36202000100000 | 8 | Lancaster | CAMARGO | SR 2020 | BEAVER CREEK | 36/216 - EDEN | 39.9171 | -76.1749 | 20143571656 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2016-05-12
278b | -- | 278 | 21558 | 19964 | 36202000100000 | 8 | Lancaster | CAMARGO | SR 2020 | BEAVER CREEK | 36/216 - EDEN | 39.9171 | -76.1749 | 20143571656 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-05-12
279a | -- | 279 | 21559 | 87518 | 36202000200000 | 8 | Lancaster | 1 MI.N. CAMARGO | SR 2020 | BOWEY RUN | 36/216 - EDEN | 39.9172 | -76.1748 | 20150641265 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2016-10-19
279b | -- | 279 | 21559 | 87518 | 36202000200000 | 8 | Lancaster | 1 MI.N. CAMARGO | SR 2020 | BOWEY RUN | 36/216 - EDEN | 39.9172 | -76.1748 | 20150641265 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-10-19
280 | -- | 280 | 21595 | 87501 | 36204500700000 | 8 | Lancaster | North of Bird In Hand | 2045 Monterrey Rd | Mill Creek | 36/234 - UPPER LEACOCK | 40.0549 | -76.1706 | 20143571667, 20143571668 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2016-08-05
281a | -- | 281 | 21601 | 19812 | 36300400200000 | 8 | Lancaster | DRUMORE | SR 3004; (TWP RD) | FISHING CREEK | 36/208 - DRUMORE | 39.7943 | -76.2593 | 20150752891 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2017-06-26
281b | -- | 281 | 21601 | 19812 | 36300400200000 | 8 | Lancaster | DRUMORE | SR 3004; (TWP RD) | FISHING CREEK | 36/208 - DRUMORE | 39.7943 | -76.2593 | 20150752891 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-06-26
281c | -- | 281 | 21601 | 19812 | 36300400200000 | 8 | Lancaster | DRUMORE | SR 3004; (TWP RD) | FISHING CREEK | 36/208 - DRUMORE | 39.7943 | -76.2593 | 20150752891 | GAS | UGI Utilities, Inc. | Tom Witt, twitt@ugi.com, 717-255-1425; Barry Lieberman, 717-299-7281 | UG |  |  | 2017-06-26
282a | -- | 282 | 21637 | 63229 | 36301702401388 | 8 | Lancaster | 0.5 MI.NORTH OF LETORT | SR 3017 | W.BR.CONESTOGA CREEK | 36/233 - STRASBURG | 39.9843 | -76.4059 | 20150420402 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2016-08-03
282b | -- | 282 | 21637 | 63229 | 36301702401388 | 8 | Lancaster | 0.5 MI.NORTH OF LETORT | SR 3017 | W.BR.CONESTOGA CREEK | 36/233 - STRASBURG | 39.9843 | -76.4059 | 20150420402 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-08-03
282c | -- | 282 | 21637 | 63229 | 36301702401388 | 8 | Lancaster | 0.5 MI.NORTH OF LETORT | SR 3017 | W.BR.CONESTOGA CREEK | 36/233 - STRASBURG | 39.9843 | -76.4059 | 20150420402 | sanitary | Lancaster Area Sewer Auth | John Vilga, 717-344-5819, Jvilga@lasa.org | UG |  |  | 2016-08-03
283a | -- | 283 | 21662 | 20151 | 36303201100000 | 8 | Lancaster | Letort Road over Little Conestoga Creek | 3032 LeTort Rd | LITTLE CONESTOGA CREEK | 36/223 - MANOR | 39.9922 | -76.3802 | 20150762649 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2017-06-08
283b | -- | 283 | 21662 | 20151 | 36303201100000 | 8 | Lancaster | Letort Road over Little Conestoga Creek | 3032 LeTort Rd | LITTLE CONESTOGA CREEK | 36/223 - MANOR | 39.9922 | -76.3802 | 20150762649 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-06-08
284 | -- | 284 | 22812 | 91352 | 38402000800000 | 8 | Lebanon | INDIANTOWN GAP | SR 4020 | AIRE RUN | 38/215 - UNION | 40.4373 | -76.542 | 20143571525 |  | all facilities responded clear per one call |  |  |  |  | 2017-04-03
285a | -- | 285 | 29426 | 87462 | 50001100300893 | 8 | Perry | MARYSVILLE BORO | US 11&15; STATE.RD | FISHING CREEK | 50/406 - MARYSVILLE | 40.3377 | -76.9276 | 20150752474 | Comm | AT&T Atlanta | 404-249-9052 |  |  |  | 2017-04-14
285b | -- | 285 | 29426 | 87462 | 50001100300893 | 8 | Perry | MARYSVILLE BORO | US 11&15; STATE.RD | FISHING CREEK | 50/406 - MARYSVILLE | 40.3377 | -76.9276 | 20150752474 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2017-04-14
285c | -- | 285 | 29426 | 87462 | 50001100300893 | 8 | Perry | MARYSVILLE BORO | US 11&15; STATE.RD | FISHING CREEK | 50/406 - MARYSVILLE | 40.3377 | -76.9276 | 20150752474 |  | Marysville Borough | 717-957-3110, boro17053@comcast.net |  |  |  | 2017-04-14
285d | -- | 285 | 29426 | 87462 | 50001100300893 | 8 | Perry | MARYSVILLE BORO | US 11&15; STATE.RD | FISHING CREEK | 50/406 - MARYSVILLE | 40.3377 | -76.9276 | 20150752474 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-04-14
285e | -- | 285 | 29426 | 87462 | 50001100300893 | 8 | Perry | MARYSVILLE BORO | US 11&15; STATE.RD | FISHING CREEK | 50/406 - MARYSVILLE | 40.3377 | -76.9276 | 20150752474 | Comm | WINDSTREAM | Glen Esenwein, 610-582-6239, gesenwein@ceni.com; gesenwein@decommunications.com; |  |  |  | 2017-04-14
286 | -- | 286 | 29451 | 93582 | 50001701101051 | 8 | Perry | 2 MILES WEST OF KISTLER | PA 17; SR 0017 | BIXLERS RUN | 50/210 - NORTHEAST MADIS | 40.3821 | -77.4535 | 20151410849 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | UG |  |  | 2017-05-26
287a | -- | 287 | 29468 | 79054 | 50001707600000 | 8 | Perry | LIVERPOOL BORO | PA 17; SR 0017 | TRIB TO SUSQUEHANNA | 50/405 - LIVERPOOL | 40.5752 | -76.9961 | 20151410975 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | UG |  |  | 2017-05-26
287b | -- | 287 | 29468 | 79054 | 50001707600000 | 8 | Perry | LIVERPOOL BORO | PA 17; SR 0017 | TRIB TO SUSQUEHANNA | 50/405 - LIVERPOOL | 40.5752 | -76.9961 | 20151410975 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-05-26
287c | -- | 287 | 29468 | 79054 | 50001707600000 | 8 | Perry | LIVERPOOL BORO | PA 17; SR 0017 | TRIB TO SUSQUEHANNA | 50/405 - LIVERPOOL | 40.5752 | -76.9961 | 20151410975 | Comm | Zampelli Electronics | Joe Zampelli, 717-248-1544, joan@nmax.net |  |  |  | 2017-05-26
288a | -- | 288 | 29518 | 73961 | 50007401900530 | 8 | Perry | GREEN PARK | PA 74; SR 0074 | MONTOUR CREEK | 50/219 - TYRONE | 40.3831 | -77.3077 | 20150751481 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2017-05-25
288b | -- | 288 | 29518 | 73961 | 50007401900530 | 8 | Perry | GREEN PARK | PA 74; SR 0074 | MONTOUR CREEK | 50/219 - TYRONE | 40.3831 | -77.3077 | 20150751481 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-05-25
289a | -- | 289 | 29565 | 87465 | 50085002201839 | 8 | Perry | 1MI NO OF FORT ROBINSON | PA 850; SR 0850 | BIXLERS RUN | 50/210 - NORTHEAST MADIS | 40.371 | -77.4011 | 20151410885 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | UG |  |  | 2017-05-30
289b | -- | 289 | 29565 | 87465 | 50085002201839 | 8 | Perry | 1MI NO OF FORT ROBINSON | PA 850; SR 0850 | BIXLERS RUN | 50/210 - NORTHEAST MADIS | 40.371 | -77.4011 | 20151410885 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-05-30
290a | -- | 290 | 29566 | 90716 | 50085002501777 | 8 | Perry | FORT ROBINSON | PA 850; SR 0850 | BIXLERS RUN | 50/210 - NORTHEAST MADIS | 40.3591 | -77.381 | 20150161237 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2016-05-31
290b | -- | 290 | 29566 | 90716 | 50085002501777 | 8 | Perry | FORT ROBINSON | PA 850; SR 0850 | BIXLERS RUN | 50/210 - NORTHEAST MADIS | 40.3591 | -77.381 | 20150161237 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-05-31
291a | -- | 291 | 29605 | 87491 | 50101502002360 | 8 | Perry | 2 MI.S. OF MILLERSTOWN | W.JUNIATA PARKWAY | WILD CAT RUN | 50/204 - GREENWOOD | 40.5142 | -77.1297 | 20150420413 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2016-08-03
291b | -- | 291 | 29605 | 87491 | 50101502002360 | 8 | Perry | 2 MI.S. OF MILLERSTOWN | W.JUNIATA PARKWAY | WILD CAT RUN | 50/204 - GREENWOOD | 40.5142 | -77.1297 | 20150420413 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-08-03
292 | -- | 292 | 29651 | 101098 | 50300600100014 | 8 | Perry | 4 MI SW OF BLAIN | SR 3006 | SHAEFFER'S RUN | 50/206 - JACKSON | 40.2982 | -77.5129 | 20151421242 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | UG |  |  | 2017-07-24
293a | -- | 293 | 29673 | 79042 | 50301700100000 | 8 | Perry | AT BRIDGEPORT | SR 3017; TWP RD | TRIB SHERMANS CREEK | 50/216 - SPRING | 40.3291 | -77.2846 | 20150420431 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2016-08-03
293b | -- | 293 | 29673 | 79042 | 50301700100000 | 8 | Perry | AT BRIDGEPORT | SR 3017; TWP RD | TRIB SHERMANS CREEK | 50/216 - SPRING | 40.3291 | -77.2846 | 20150420431 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-08-03
293c | -- | 293 | 29673 | 79042 | 50301700100000 | 8 | Perry | AT BRIDGEPORT | SR 3017; TWP RD | TRIB SHERMANS CREEK | 50/216 - SPRING | 40.3291 | -77.2846 | 20150420431 | comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2016-08-03
294a | -- | 294 | 29693 | 79047 | 50400701001472 | 8 | Perry | DONNALLY'S MILLS | CREEK RD. | RACCOON CREEK | 50/218 - TUSCARORA | 40.5159 | -77.2365 | 20151412690 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com | UG |  |  | 2017-05-30
294b | -- | 294 | 29693 | 79047 | 50400701001472 | 8 | Perry | DONNALLY'S MILLS | CREEK RD. | RACCOON CREEK | 50/218 - TUSCARORA | 40.5159 | -77.2365 | 20151412690 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-05-30
295a | -- | 295 | 37488 | 91353 | 66012401400000 | 8 | York | 1.5 W OF DELROY | PA 124; SR 0124 | KREUTZ CREEK | 66/233 - WINDSOR | 39.9677 | -76.5979 | 20150752367 | gas | Columbia Gas of PA Design | Brian K. Shomper, 717-849-0137, bshomper@nisource.com | UG |  |  | 2017-03-20
295b | -- | 295 | 37488 | 91353 | 66012401400000 | 8 | York | 1.5 W OF DELROY | PA 124; SR 0124 | KREUTZ CREEK | 66/233 - WINDSOR | 39.9677 | -76.5979 | 20150752367 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2017-03-20
295c | -- | 295 | 37488 | 91353 | 66012401400000 | 8 | York | 1.5 W OF DELROY | PA 124; SR 0124 | KREUTZ CREEK | 66/233 - WINDSOR | 39.9677 | -76.5979 | 20150752367 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-03-20
296a | -- | 296 | 37491 | 87693 | 66012402502532 | 8 | York | 1 MILE N OF CRALEY | PA 124; SR 0124 | CABIN CREEK | 66/216 - LOWER WINDSOR | 39.9621 | -76.5144 | 20143571677 | Comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 |  |  |  | 2016-08-05
296b | -- | 296 | 37491 | 87693 | 66012402502532 | 8 | York | 1 MILE N OF CRALEY | PA 124; SR 0124 | CABIN CREEK | 66/216 - LOWER WINDSOR | 39.9621 | -76.5144 | 20143571677 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2016-08-05
296c | -- | 296 | 37491 | 87693 | 66012402502532 | 8 | York | 1 MILE N OF CRALEY | PA 124; SR 0124 | CABIN CREEK | 66/216 - LOWER WINDSOR | 39.9621 | -76.5144 | 20143571677 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-08-05
297a | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | 20151463749, 20151463750 | Comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 |  |  |  | 2017-06-08
297b | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | 20151463749, 20151463750 |  | Lower Windsor TWP | 717-244-6813, GeneraLInfo@LowerWindsor.com |  |  |  | 2017-06-08
297c | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | 20151463749, 20151463750 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-06-08
297d | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | 20151463749, 20151463750 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2017-06-08
297e | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | 20151463749, 20151463750 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com |  |  |  | 2017-06-08
297f | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | 20151463749, 20151463750 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 |  |  |  | 2017-06-08
297g | -- | 297 | 37590 | 91191 | 66042504600314 | 8 | York | 1.2 MI.S.E. OF CRALEY | PA 425; SR 0425 | FISHING CREEK | 66/202 - CHANCEFORD | 39.9398 | -76.4871 | 20151463749, 20151463750 | Elect | PECO Energy | Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com |  |  |  | 2017-06-08
298a | -- | 298 | 37607 | 78860 | 66061601000255 | 8 | York | .5 MI. N.W. OF GLEN ROCK | PA 616; SR 0616 | TRIB TO S BR CODORUS CR | 66/226 - SHREWSBURY | 39.8005 | -76.7392 | 20150752392 | Comm | ARMSTRONG | Aaron Dierdorff, 800-762-0592, aarondierdorff@usicinc.com; Mike Greer, 800-572-1038 |  |  |  | 2017-05-25
298b | -- | 298 | 37607 | 78860 | 66061601000255 | 8 | York | .5 MI. N.W. OF GLEN ROCK | PA 616; SR 0616 | TRIB TO S BR CODORUS CR | 66/226 - SHREWSBURY | 39.8005 | -76.7392 | 20150752392 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2017-05-25
298c | -- | 298 | 37607 | 78860 | 66061601000255 | 8 | York | .5 MI. N.W. OF GLEN ROCK | PA 616; SR 0616 | TRIB TO S BR CODORUS CR | 66/226 - SHREWSBURY | 39.8005 | -76.7392 | 20150752392 |  | Glen Rock Water and Sewer Auth | DALE GETZ, 717-235-2082; Garth Green, 717-235-2082, grwsa@nfdc.net | UG |  |  | 2017-05-25
298d | -- | 298 | 37607 | 78860 | 66061601000255 | 8 | York | .5 MI. N.W. OF GLEN ROCK | PA 616; SR 0616 | TRIB TO S BR CODORUS CR | 66/226 - SHREWSBURY | 39.8005 | -76.7392 | 20150752392 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-05-25
298e | -- | 298 | 37607 | 78860 | 66061601000255 | 8 | York | .5 MI. N.W. OF GLEN ROCK | PA 616; SR 0616 | TRIB TO S BR CODORUS CR | 66/226 - SHREWSBURY | 39.8005 | -76.7392 | 20150752392 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com |  |  |  | 2017-05-25
299a | -- | 299 | 37608 | 87551 | 66061601001014 | 8 | York | 1.0 MI. NW GLEN ROCK | SEVEN VALLEYS RD. | CENTERVILLE CREEK | 66/226 - SHREWSBURY | 39.8008 | -76.7417 | 20150781928/ 20150781929 | Comm | ARMSTRONG | Aaron Dierdorff, 800-762-0592, aarondierdorff@usicinc.com; Mike Greer, 800-572-1038 |  |  |  | 2017-07-24
299b | -- | 299 | 37608 | 87551 | 66061601001014 | 8 | York | 1.0 MI. NW GLEN ROCK | SEVEN VALLEYS RD. | CENTERVILLE CREEK | 66/226 - SHREWSBURY | 39.8008 | -76.7417 | 20150781928/ 20150781929 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2017-07-24
299c | -- | 299 | 37608 | 87551 | 66061601001014 | 8 | York | 1.0 MI. NW GLEN ROCK | SEVEN VALLEYS RD. | CENTERVILLE CREEK | 66/226 - SHREWSBURY | 39.8008 | -76.7417 | 20150781928/ 20150781929 |  | Glen Rock Water and Sewer Auth | Garth Green, 717-235-2082, grwsa@nfdc.net | UG |  |  | 2017-07-24
299d | -- | 299 | 37608 | 87551 | 66061601001014 | 8 | York | 1.0 MI. NW GLEN ROCK | SEVEN VALLEYS RD. | CENTERVILLE CREEK | 66/226 - SHREWSBURY | 39.8008 | -76.7417 | 20150781928/ 20150781929 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-07-24
300a | -- | 300 | 37641 | 78878 | 66092100900000 | 8 | York | 3 MI.E. OF DOVER | PA 921; SR 0921 | TRIB TO LITTLE CONEWAGO | 66/204 - CONEWAGO | 40.0343 | -76.7871 | 20150161784 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2016-05-31
300b | -- | 300 | 37641 | 78878 | 66092100900000 | 8 | York | 3 MI.E. OF DOVER | PA 921; SR 0921 | TRIB TO LITTLE CONEWAGO | 66/204 - CONEWAGO | 40.0343 | -76.7871 | 20150161784 | sanitary | Conewago TWP Sewer Auth | Caroline Kern, Admin Asst. 717-266-5518, Fax: 717-266-0474; 600 Locust Point Rd , York PA 17406 | UG |  |  | 2016-05-31
300c | -- | 300 | 37641 | 78878 | 66092100900000 | 8 | York | 3 MI.E. OF DOVER | PA 921; SR 0921 | TRIB TO LITTLE CONEWAGO | 66/204 - CONEWAGO | 40.0343 | -76.7871 | 20150161784 | comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com |  |  |  | 2016-05-31
300d | -- | 300 | 37641 | 78878 | 66092100900000 | 8 | York | 3 MI.E. OF DOVER | PA 921; SR 0921 | TRIB TO LITTLE CONEWAGO | 66/204 - CONEWAGO | 40.0343 | -76.7871 | 20150161784 | wtr | York Water CO | Kent K. Croman, 717-718-7541, kentc@yorkwater.com | UG |  |  | 2016-05-31
300e | -- | 300 | 37641 | 78878 | 66092100900000 | 8 | York | 3 MI.E. OF DOVER | PA 921; SR 0921 | TRIB TO LITTLE CONEWAGO | 66/204 - CONEWAGO | 40.0343 | -76.7871 | 20150161784 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147 |  |  |  | 2016-05-31
301a | -- | 301 | 37725 | 78896 | 66202800800249 | 8 | York | DELTA BORO | SR 2028 | SCOTT'S RUN | 66/403 - DELTA | 39.7217 | -76.3374 | 20150420444, 20150420445 | Comm | ARMSTRONG | Aaron Dierdorff, 800-762-0592, aarondierdorff@usicinc.com; Mike Greer, 800-572-1038 |  |  |  | 2016-08-01
301b | -- | 301 | 37725 | 78896 | 66202800800249 | 8 | York | DELTA BORO | SR 2028 | SCOTT'S RUN | 66/403 - DELTA | 39.7217 | -76.3374 | 20150420444, 20150420445 | wtr | Delta Borough | Sam Maiter, waterman3989@gmail.com, 717-405-0663. Patricia Koehler, deltabilling@yahoo.com, 717-456-6248. EDNA JANE CROTHERS, 717-456-6248. Cindy Dennis Singh Operations Services Inc 8 Rees Drive Willow Street PA 17584 | UG |  |  | 2016-08-01
301c | -- | 301 | 37725 | 78896 | 66202800800249 | 8 | York | DELTA BORO | SR 2028 | SCOTT'S RUN | 66/403 - DELTA | 39.7217 | -76.3374 | 20150420444, 20150420445 | Elect | PECO Energy | Bill Hensil, 610-725-7129, bill.hensil@exeloncorp.com; Luis Figueroa, 610-725-7157, Luis.Figueroa@exeloncorp.com ; Matt Sweeney, 610-490-3153, matt.sweeney@exeloncorp.com |  |  |  | 2016-08-01
301d | -- | 301 | 37725 | 78896 | 66202800800249 | 8 | York | DELTA BORO | SR 2028 | SCOTT'S RUN | 66/403 - DELTA | 39.7217 | -76.3374 | 20150420444, 20150420445 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com |  |  |  | 2016-08-01
302a | -- | 302 | 37726 | 87695 | 66202900902536 | 8 | York | 5 MILE NE OF RED LION | SR 2029 | CABIN CREEK | 66/216 - LOWER WINDSOR | 39.9603 | -76.5536 | 20150681692 | comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 |  |  |  | 2016-08-01
302b | -- | 302 | 37726 | 87695 | 66202900902536 | 8 | York | 5 MILE NE OF RED LION | SR 2029 | CABIN CREEK | 66/216 - LOWER WINDSOR | 39.9603 | -76.5536 | 20150681692 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2016-08-01
303a | -- | 303 | 37878 | 91367 | 66304500800853 | 8 | York | JACOBS MILLS | SR 3045 | OIL CREEK | 66/211 - HEIDELBERG | 39.8317 | -76.9275 | 201514200645 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com |  |  |  | 2017-08-04
303b | -- | 303 | 37878 | 91367 | 66304500800853 | 8 | York | JACOBS MILLS | SR 3045 | OIL CREEK | 66/211 - HEIDELBERG | 39.8317 | -76.9275 | 201514200645 | Comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 |  |  |  | 2017-08-04
303c | -- | 303 | 37878 | 91367 | 66304500800853 | 8 | York | JACOBS MILLS | SR 3045 | OIL CREEK | 66/211 - HEIDELBERG | 39.8317 | -76.9275 | 201514200645 | Comm | Centurylink formerly Embarq | Perry Byers, 610-547-0705, Perry.Byers@centurylink.com, Thomas F. Chambers, 610-405-7050, Thomas.Chambers@centurylink.com |  |  |  | 2017-08-04
303d | -- | 303 | 37878 | 91367 | 66304500800853 | 8 | York | JACOBS MILLS | SR 3045 | OIL CREEK | 66/211 - HEIDELBERG | 39.8317 | -76.9275 | 201514200645 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-08-04
304a | -- | 304 | 37890 | 87596 | 66305100200000 | 8 | York | 1 MI.W. OF JEFFERSON | SR 3051 | CODORUS CREEK | 66/218 - MANHEIM | 39.8104 | -76.8732 | 20150261323, 20150261324 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com |  |  |  | 2016-06-17
304b | -- | 304 | 37890 | 87596 | 66305100200000 | 8 | York | 1 MI.W. OF JEFFERSON | SR 3051 | CODORUS CREEK | 66/218 - MANHEIM | 39.8104 | -76.8732 | 20150261323, 20150261324 | comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 |  |  |  | 2016-06-17
304c | -- | 304 | 37890 | 87596 | 66305100200000 | 8 | York | 1 MI.W. OF JEFFERSON | SR 3051 | CODORUS CREEK | 66/218 - MANHEIM | 39.8104 | -76.8732 | 20150261323, 20150261324 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2016-06-17
305a | -- | 305 | 37921 | 87595 | 66307100100000 | 8 | York | 1 MILE S.W. OF PA 94 | SR 3071; T-513 | SOUTH BR CONEWAGO CREEK | 66/232 - WEST MANHEIM | 39.731 | -76.9479 | 20151420309 | Comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 |  |  |  | 2017-07-28
305b | -- | 305 | 37921 | 87595 | 66307100100000 | 8 | York | 1 MILE S.W. OF PA 94 | SR 3071; T-513 | SOUTH BR CONEWAGO CREEK | 66/232 - WEST MANHEIM | 39.731 | -76.9479 | 20151420309 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-07-28
305c | -- | 305 | 37921 | 87595 | 66307100100000 | 8 | York | 1 MILE S.W. OF PA 94 | SR 3071; T-513 | SOUTH BR CONEWAGO CREEK | 66/232 - WEST MANHEIM | 39.731 | -76.9479 | 20151420309 | Wtr | York Water CO | Kent K. Croman, 717-718-7541, kentc@yorkwater.com | UG |  |  | 2017-07-28
306a | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | 20150261329, 20150261330 | gas | Columbia Gas of PA Design | Chris Lovell, 800-440-6111, clovell@nisource.com; SHANNON GRIEST, sgriest@nisource.com | UG | 8" |  | 2016-07-22
306b | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | 20150261329, 20150261330 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2016-07-22
306c | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | 20150261329, 20150261330 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2016-07-22
306d | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | 20150261329, 20150261330 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com |  |  |  | 2016-07-22
306e | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | 20150261329, 20150261330 | sanitary | Dover TWP | Chuck Farley, 717-292-3634, cfarley@dovertownship.org | UG |  |  | 2016-07-22
306f | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | 20150261329, 20150261330 | comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 |  |  |  | 2016-07-22
306g | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | 20150261329, 20150261330 | sanitary | Conewago TWP Sewer Auth | Caroline Kern, Admin Asst. ,ctsa600@comcast.net; 717-266-5518; 717-533-6643 | UG |  |  | 2016-07-22
306h | -- | 306 | 37946 | 74944 | 66400102102301 | 8 | York | 2 MILES E. OF DOVER | SR 4001 | FOX RUN | 66/205 - DOVER | 40.0106 | -76.8066 | 20150261329, 20150261330 | wtr | York Water CO | Kent K. Croman, 717-718-7541, kentc@yorkwater.com | UG |  |  | 2016-07-22
307a | -- | 307 | 37976 | 83428 | 66401200602478 | 8 | York | 0.5 MI.E. OF KRALLTOWN | SR 4012 | DOE RUN | 66/230 - WASHINGTON | 40.0176 | -76.9748 | 20150420589 | Elect | Adams Electric Coop Inc | Dave Gring, daveg@adamsec.coop, 717-334-9211; Alan W. Mains, 717-334-2171, alanm@adamsec.com |  |  |  | 2016-08-03
307b | -- | 307 | 37976 | 83428 | 66401200602478 | 8 | York | 0.5 MI.E. OF KRALLTOWN | SR 4012 | DOE RUN | 66/230 - WASHINGTON | 40.0176 | -76.9748 | 20150420589 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2016-08-03
307c | -- | 307 | 37976 | 83428 | 66401200602478 | 8 | York | 0.5 MI.E. OF KRALLTOWN | SR 4012 | DOE RUN | 66/230 - WASHINGTON | 40.0176 | -76.9748 | 20150420589 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2016-08-03
307d | -- | 307 | 37976 | 83428 | 66401200602478 | 8 | York | 0.5 MI.E. OF KRALLTOWN | SR 4012 | DOE RUN | 66/230 - WASHINGTON | 40.0176 | -76.9748 | 20150420589 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com |  |  |  | 2016-08-03
308a | -- | 308 | 38007 | 90222 | 66403300403136 | 8 | York | 1.0 MI.N.E. ANDERSONTOWN | SR 4033 | YELLOW BREECHES CREEK | 66/208 - FAIRVIEW | 40.162 | -76.9218 | 20150271466, 20150271467, 20150271468, 20150271469 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Dave McLuckie, Dave_McLuckie@cable.comcast.co, | OH |  |  | 2016-07-18
308b | -- | 308 | 38007 | 90222 | 66403300403136 | 8 | York | 1.0 MI.N.E. ANDERSONTOWN | SR 4033 | YELLOW BREECHES CREEK | 66/208 - FAIRVIEW | 40.162 | -76.9218 | 20150271466, 20150271467, 20150271468, 20150271469 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2016-07-18
308c | -- | 308 | 38007 | 90222 | 66403300403136 | 8 | York | 1.0 MI.N.E. ANDERSONTOWN | SR 4033 | YELLOW BREECHES CREEK | 66/208 - FAIRVIEW | 40.162 | -76.9218 | 20150271466, 20150271467, 20150271468, 20150271469 | Elect | PPL Electric Utilities Corporation | Charlotte Krupa, 610-774-6287, cakrupa@pplweb.com | UG |  |  | 2016-07-18
309a | -- | 309 | 38023 | 91192 | 66405100300581 | 8 | York | 1 MI. N.E. FARMERS | BIG MOUNT RD. | PARADISE CREEK | 66/223 - PARADISE | 39.9307 | -76.9034 | 20151420609, 20151420610 | Comm | Comcast Cable Communications, Inc. | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; Jack Tobias (717) 202-8442, Jack_Tobias@cable.comcast.com |  |  |  | 2017-07-28
309b | -- | 309 | 38023 | 91192 | 66405100300581 | 8 | York | 1 MI. N.E. FARMERS | BIG MOUNT RD. | PARADISE CREEK | 66/223 - PARADISE | 39.9307 | -76.9034 | 20151420609, 20151420610 | Comm | Comcast of Southeastern Pennsylvania | Harold Holt, 717-752-0829, harold_holt@cable.comcast.com, 2720 Baltimore Pike, Gettysburg PA 17325; 717-273-8511 |  |  |  | 2017-07-28
309c | -- | 309 | 38023 | 91192 | 66405100300581 | 8 | York | 1 MI. N.E. FARMERS | BIG MOUNT RD. | PARADISE CREEK | 66/223 - PARADISE | 39.9307 | -76.9034 | 20151420609, 20151420610 | Elect | METROPOLITAN EDISON CO/FIRSTENERGY | Steve Ward, sward@firstenergycorp.com, 717-848-7147; Al Nerino, 610-921-6157, anerino@gpu.com |  |  |  | 2017-07-28
309d | -- | 309 | 38023 | 91192 | 66405100300581 | 8 | York | 1 MI. N.E. FARMERS | BIG MOUNT RD. | PARADISE CREEK | 66/223 - PARADISE | 39.9307 | -76.9034 | 20151420609, 20151420610 | Comm | Verizon North LLC | David Newmister, 717-771-5298, dave.newmister@verizon.com |  |  |  | 2017-07-28
310a | -- | 310 | 3954 | 88114 | 5003001000907 | 9 | Bedford | 2.8 MI.W. OF SHELLSBURG | US 30 | BURNS CREEK | 05/210 - JUNIATA | 40.0394 | -78.6882 | 20150161798 | Comm | Centurylink formerly Embarq | Don Hubbard, 717-633-8285, don.g.hubbard@embarq.com | OH |  |  | 2016-05-23
310b | -- | 310 | 3954 | 88114 | 5003001000907 | 9 | Bedford | 2.8 MI.W. OF SHELLSBURG | US 30 | BURNS CREEK | 05/210 - JUNIATA | 40.0394 | -78.6882 | 20150161798 | Elect | Pennsylvania Electric Company | Joe Ritter, 814-269-6709, jritter@firstenergycorp.com, Dale Shaner, 814-768-4148, dshaner@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-05-23
311 | -- | 311 | 3955 | 21558 | 5003001100000 | 9 | Bedford | 2.3 MI.W.OF SHELLSBURG | US 30 | SHAWNEE CREEK | 05/218 - NAPIER | 40.0418 | -78.6799 | 20150380175 | Comm | Centurylink formerly Embarq | Don Hubbard, 717-633-8285, don.g.hubbard@embarq.com | OH |  |  | 2016-06-17
312a | -- | 312 | 4010 | 21563 | 5005600901305 | 9 | Bedford | 1.68 MILE WEST FROM PA 96 | PA 56 | BAREFOOT RUN | 05/227 - WEST ST CLAIR | 40.1906 | -78.6379 | 20143561437 | Elect | Pennsylvania Electric Company | Timothy (Tim) Frye, tfrye@firstenergycorp.com, 814-949-4652; engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2016-03-25
312b | -- | 312 | 4010 | 21563 | 5005600901305 | 9 | Bedford | 1.68 MILE WEST FROM PA 96 | PA 56 | BAREFOOT RUN | 05/227 - WEST ST CLAIR | 40.1906 | -78.6379 | 20143561437 | Elect | Bedford Rural Electric Company | Troy Mock, tmock@bedfordrec.com, 814-977-6906; Jim Seymour, jseymour@bedfordrec.com | OH |  |  | 2016-03-25
312c | -- | 312 | 4010 | 21563 | 5005600901305 | 9 | Bedford | 1.68 MILE WEST FROM PA 96 | PA 56 | BAREFOOT RUN | 05/227 - WEST ST CLAIR | 40.1906 | -78.6379 | 20143561437 | Comm | Centurylink formerly Embarq | June Smith, june.i.smith@centurylink.com, 814-623-3624, 317 South Richard Street, Bedford, PA 15522 | OH |  |  | 2016-03-25
313a | -- | 313 | 4044 | 21455 | 5009602600000 | 9 | Bedford | MADLEY | PA 96 | WOLF CAMP RUN | 05/215 - LONDONDERRY | 39.8966 | -78.672 | 20143561445 | comm | Centurylink formerly Embarq | Don Hubbard, 717-633-8285, don.g.hubbard@embarq.com | OH |  |  | 2016-04-15
313b | -- | 313 | 4044 | 21455 | 5009602600000 | 9 | Bedford | MADLEY | PA 96 | WOLF CAMP RUN | 05/215 - LONDONDERRY | 39.8966 | -78.672 | 20143561445 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-04-15
313c | -- | 313 | 4044 | 21455 | 5009602600000 | 9 | Bedford | MADLEY | PA 96 | WOLF CAMP RUN | 05/215 - LONDONDERRY | 39.8966 | -78.672 | 20143561445 | Comm | Comcast Cable Communications, Inc. | Jeffrey (Jeff) Gilliland, 717-752-5036, Jeffrey_Gilliland@cable.comcast.com | OH |  |  | 2016-04-15
314a | -- | 314 | 4122 | 88121 | 5086901201328 | 9 | Bedford | 3.16 MILE WEST FROM PA 96 | PA 869 | BOBS CREEK | 05/222 - PAVIA | 40.2541 | -78.583 | 20143561454 |  | Pavia TWP | George Porle, 814-276-9345, 1850 Birdshouse Rd. Imler, PA 16655 |  |  |  | 2016-05-23
314b | -- | 314 | 4122 | 88121 | 5086901201328 | 9 | Bedford | 3.16 MILE WEST FROM PA 96 | PA 869 | BOBS CREEK | 05/222 - PAVIA | 40.2541 | -78.583 | 20143561454 | Elect | Pennsylvania Electric Company | Joe Ritter, 814-269-6709, jritter@firstenergycorp.com, Dale Shaner, 814-768-4148, dshaner@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2016-05-23
314c | -- | 314 | 4122 | 88121 | 5086901201328 | 9 | Bedford | 3.16 MILE WEST FROM PA 96 | PA 869 | BOBS CREEK | 05/222 - PAVIA | 40.2541 | -78.583 | 20143561454 | Comm | Sprint | Wesley Carpenter, wesley.a.carpenter@sprint.com |  |  |  | 2016-05-23
314d | -- | 314 | 4122 | 88121 | 5086901201328 | 9 | Bedford | 3.16 MILE WEST FROM PA 96 | PA 869 | BOBS CREEK | 05/222 - PAVIA | 40.2541 | -78.583 | 20143561454 | Elect | Bedford Rural Electric Company | Troy Mock, tmock@bedfordrec.com, 814-977-6906; Jim Seymour, jseymour@bedfordrec.com | OH |  |  | 2016-05-23
314e | -- | 314 | 4122 | 88121 | 5086901201328 | 9 | Bedford | 3.16 MILE WEST FROM PA 96 | PA 869 | BOBS CREEK | 05/222 - PAVIA | 40.2541 | -78.583 | 20143561454 | Comm | Centurylink formerly Embarq | June Smith, june.i.smith@centurylink.com, 814-623-3624, 317 South Richard Street, Bedford, PA 15522 | OH |  |  | 2016-05-23
315a | -- | 315 | 4174 | 21596 | 5101100400000 | 9 | Bedford | 2 MI.N.OF BREEZEWOOD | SR 1011 | TUB MILL RUN | 05/206 - EAST PROVIDENCE | 40.0192 | -78.2589 | 20150411932 |  | all facilities responded clear per one call |  |  |  |  | 2017-05-30
315b | -- | 315 | 4174 | 21596 | 5101100400000 | 9 | Bedford | 2 MI.N.OF BREEZEWOOD | SR 1011 | TUB MILL RUN | 05/206 - EAST PROVIDENCE | 40.0192 | -78.2589 | 20150411932 | Elect | Need to Confirm Electric |  | OH |  |  | 2017-05-30
316a | -- | 316 | 4177 | 21552 | 5101200400000 | 9 | Bedford | 1.73 MILE EAST FROM SR 1009 | SR 1012 | RAYSTOWN BR JUNIATA RIV. | 05/226 - WEST PROVIDENCE | 40.0528 | -78.3252 | 20150411927 | Comm | Centurylink formerly Embarq | Don Hubbard, 717-633-8285, don.g.hubbard@embarq.com | OH |  |  | 2016-07-05
316b | -- | 316 | 4177 | 21552 | 5101200400000 | 9 | Bedford | 1.73 MILE EAST FROM SR 1009 | SR 1012 | RAYSTOWN BR JUNIATA RIV. | 05/226 - WEST PROVIDENCE | 40.0528 | -78.3252 | 20150411927 | Elect | Bedford REC or Penelec - Need to confirm | Troy Mock, tmock@bedfordrec.com, 814-977-6906; Jim Seymour, jseymour@bedfordrec.com | OH |  |  | 2016-07-05
317a | -- | 317 | 4196 | 21600 | 5102000500880 | 9 | Bedford | 0.16 MILE EAST FROM SR 1009 | SR 1020 | PIPERS RUN | 05/209 - HOPEWELL | 40.0978 | -78.3167 | 20143580298 | comm | Centurylink formerly Embarq | Kim Grauel, Kim.L.Grauel@centurylink.com | Both |  |  | 2016-05-31
317b | -- | 317 | 4196 | 21600 | 5102000500880 | 9 | Bedford | 0.16 MILE EAST FROM SR 1009 | SR 1020 | PIPERS RUN | 05/209 - HOPEWELL | 40.0978 | -78.3167 | 20143580298 | Elect | Bedford REC or Penelec - Need to confirm | Troy Mock, tmock@bedfordrec.com, 814-977-6906; Jim Seymour, jseymour@bedfordrec.com | OH |  |  | 2016-05-31
318a | -- | 318 | 4386 | 74424 | 5403101601407 | 9 | Bedford | VILLAGE OF QUEEN | SR 4031 | BEAVERDAM CREEK | 05/211 - KIMMEL | 40.2599 | -78.4888 | 20150411937 |  | all facilities responded clear per one call |  |  |  |  | 2017-05-30
318b | -- | 318 | 4386 | 74424 | 5403101601407 | 9 | Bedford | VILLAGE OF QUEEN | SR 4031 | BEAVERDAM CREEK | 05/211 - KIMMEL | 40.2599 | -78.4888 | 20150411937 | Elect | Need to Confirm Electric |  | OH |  |  | 2017-05-30
318c | -- | 318 | 4386 | 74424 | 5403101601407 | 9 | Bedford | VILLAGE OF QUEEN | SR 4031 | BEAVERDAM CREEK | 05/211 - KIMMEL | 40.2599 | -78.4888 | 20150411937 | Comm | Need to Confirm Phone |  | OH |  |  | 2017-05-30
319a | -- | 319 | 5699 | 22107 | 7101302400000 | 9 | Blair | .75 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5864 | -78.2457 | 20150411944 | Elect | Valley Rural Electric Coop Inc | Jeff Garner, 814-793-2609 |  |  |  | 2017-07-11
319b | -- | 319 | 5699 | 22107 | 7101302400000 | 9 | Blair | .75 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5864 | -78.2457 | 20150411944 | Comm | Need to Confirm Phone |  | OH |  |  | 2017-07-11
320a | -- | 320 | 5702 | 74376 | 7101302500908 | 9 | Blair | 1.5 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5912 | -78.2365 | 20143580307 | Elect | Pennsylvania Electric Company | Richard Fink, rfink@firstenergycorp.com |  |  |  | 2016-06-28
320b | -- | 320 | 5702 | 74376 | 7101302500908 | 9 | Blair | 1.5 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5912 | -78.2365 | 20143580307 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667 | OH |  |  | 2016-06-28
320c | -- | 320 | 5702 | 74376 | 7101302500908 | 9 | Blair | 1.5 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5912 | -78.2365 | 20143580307 | Comm | Verizon - Need to Confirm | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com | OH |  |  | 2016-06-28
320d | -- | 320 | 5702 | 74376 | 7101302500908 | 9 | Blair | 1.5 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5912 | -78.2365 | 20143580307 | Elect | REA Energy Coop | Chris Yahner, cyahner@reaenergy.com, 814-472-8570 |  |  |  | 2016-06-28
320e | -- | 320 | 5702 | 74376 | 7101302500908 | 9 | Blair | 1.5 MI.NE.OF CULP | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.5912 | -78.2365 | 20143580307 | Comm | Zayo Bandwidth (ACC) | John Lynch, john.lynch@zayo.com, 724-972-5667; Ricci Blakeley, ricci.blakeley@zayo.com | OH |  |  | 2016-06-28
321a | -- | 321 | 5709 | 21957 | 7101303601234 | 9 | Blair | 0.23 MILE NORTH FROM PA 453 | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.616 | -78.1704 | 20150411939 |  | all facilities responded clear per one call |  |  |  |  | 2017-03-20
321b | -- | 321 | 5709 | 21957 | 7101303601234 | 9 | Blair | 0.23 MILE NORTH FROM PA 453 | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.616 | -78.1704 | 20150411939 | Elect | Need to Confirm Electric |  | OH |  |  | 2017-03-20
321c | -- | 321 | 5709 | 21957 | 7101303601234 | 9 | Blair | 0.23 MILE NORTH FROM PA 453 | SR 1013 | SINKING RUN | 07/214 - TYRONE | 40.616 | -78.1704 | 20150411939 | Comm | Need to Confirm Phone |  | OH |  |  | 2017-03-20
322 | -- | 322 | 5763 | 21961 | 7300500100050 | 9 | Blair | .5 MI.W.OF SPROUL | SR 3005 | BEAVERDAM CREEK | 07/207 - GREENFIELD | 40.2673 | -78.4716 | 20150491178 | Comm | Centurylink formerly Embarq | Don Hubbard, 717-633-8285, don.g.hubbard@embarq.com |  |  |  | 2017-07-13
323a | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | 20150161831 | Comm | Comcast Cable Communications, Inc. | Dan Cramer, 800-219-9103, dan.cramer@adelphia.com | OH |  |  | 2016-06-17
323b | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | 20150161831 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com | OH |  |  | 2016-06-17
323c | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | 20150161831 | gas | Peoples Gas Altoona Division | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-06-17
323d | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | 20150161831 | gas | Peoples Gas Design Altoona | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-06-17
323e | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | 20150161831 | wtr | Tyrone Borough Auth Water | 814-684-1330, info@tyroneboropa.com | UG |  |  | 2016-06-17
323f | -- | 323 | 5883 | 21967 | 7403100301171 | 9 | Blair | TYRONE BOROUGH | SR 4031 | DECKER RUN | 07/407 - TYRONE | 40.6893 | -78.2362 | 20150161831 | sanitary | Tyrone Borough Auth Sewer | 814-684-1330, info@tyroneboropa.com | UG |  |  | 2016-06-17
324a | -- | 324 | 8424 | 22626 | 11016002000862 | 9 | Cambria | 0.2 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3312 | -78.7402 | 20150161836 | gas | Amerigas Propane LP | 814-487-7651 | UG |  |  | 2016-06-17
324b | -- | 324 | 8424 | 22626 | 11016002000862 | 9 | Cambria | 0.2 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3312 | -78.7402 | 20150161836 | Elect | Pennsylvania Electric Company | Joe Ritter, 814-269-6709, jritter@firstenergycorp.com, Dale Shaner, 814-768-4148, dshaner@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-06-17
324c | -- | 324 | 8424 | 22626 | 11016002000862 | 9 | Cambria | 0.2 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3312 | -78.7402 | 20150161836 | Comm | Verizon | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com | OH |  |  | 2016-06-17
325a | -- | 325 | 8425 | 22627 | 11016002200000 | 9 | Cambria | 1.0 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3331 | -78.7246 | 20143561462 | GAS | Amerigas Propane LP | Ray Veroli, 814-445-6591 | UG |  |  | 2016-05-23
325b | -- | 325 | 8425 | 22627 | 11016002200000 | 9 | Cambria | 1.0 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3331 | -78.7246 | 20143561462 | Elect | Pennsylvania Electric Company | Joe Ritter, 814-269-6709, jritter@firstenergycorp.com; Dale Shaner, 814-768-4148, dshaner@firstenergycorp.com |  |  |  | 2016-05-23
325c | -- | 325 | 8425 | 22627 | 11016002200000 | 9 | Cambria | 1.0 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3331 | -78.7246 | 20143561462 | Comm | Verizon | Barbara Witkowski, barb.witkowski@verizon.com, 814-871-2275; Robert Preston, 304-670-9999, robert.preston@cyient.com | Both |  |  | 2016-05-23
325d | -- | 325 | 8425 | 22627 | 11016002200000 | 9 | Cambria | 1.0 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3331 | -78.7246 | 20143561462 | wtr | Tri-Township Water Auth | Janet, 814-487-7056 |  |  |  | 2016-05-23
325e | -- | 325 | 8425 | 22627 | 11016002200000 | 9 | Cambria | 1.0 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3331 | -78.7246 | 20143561462 | Elect | REA Energy Coop | Chris Yahner, cyahner@reaenergy.com, 814-472-8570 |  |  |  | 2016-05-23
325f | -- | 325 | 8425 | 22627 | 11016002200000 | 9 | Cambria | 1.0 MILE NORTH OF TR 869E | PA 160 | LAUREL RUN | 11/210 - CROYLE | 40.3331 | -78.7246 | 20143561462 | Comm | Comcast Cable Communications, Inc. | John Radeshak, John_Radeshak@cable.comcast.com, 412-352-5769 | OH |  |  | 2016-05-23
326a | -- | 326 | 8580 | 22444 | 11102601101804 | 9 | Cambria | 0.18 MILE WEST FROM PA 53 | SR 1026 | CLEARFIELD CREEK | 11/229 - WHITE | 40.6534 | -78.4967 | 20150491142 |  | all facilities responded clear per one call |  |  |  |  | 2016-07-08
326b | -- | 326 | 8580 | 22444 | 11102601101804 | 9 | Cambria | 0.18 MILE WEST FROM PA 53 | SR 1026 | CLEARFIELD CREEK | 11/229 - WHITE | 40.6534 | -78.4967 | 20150491142 | Elect | Pennsylvania Electric Company - need to confirm | Joe Ritter, 814-269-6709, jritter@firstenergycorp.com, Dale Shaner, 814-768-4148, dshaner@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-07-08
326c | -- | 326 | 8580 | 22444 | 11102601101804 | 9 | Cambria | 0.18 MILE WEST FROM PA 53 | SR 1026 | CLEARFIELD CREEK | 11/229 - WHITE | 40.6534 | -78.4967 | 20150491142 | Comm | Verizon - Need to Confirm | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com | OH |  |  | 2016-07-08
326d | -- | 326 | 8580 | 22444 | 11102601101804 | 9 | Cambria | 0.18 MILE WEST FROM PA 53 | SR 1026 | CLEARFIELD CREEK | 11/229 - WHITE | 40.6534 | -78.4967 | 20150491142 | Comm | Need to Confirm Cable |  | OH |  |  | 2016-07-08
327a | -- | 327 | 17813 | 22797 | 29048400101102 | 9 | Fulton | 0.2 MILE EAST OF TR 26 | PA 484 | SIDELING HILL CREEK | 29/210 - UNION | 39.743 | -78.3593 | 20150501070 | gas | Columbia Gas of PA Design | Brad Snyder, 717-676-7831, brsnyder@nisource.com | UG |  |  | 2017-05-11
327b | -- | 327 | 17813 | 22797 | 29048400101102 | 9 | Fulton | 0.2 MILE EAST OF TR 26 | PA 484 | SIDELING HILL CREEK | 29/210 - UNION | 39.743 | -78.3593 | 20150501070 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2017-05-11
328a | -- | 328 | 17826 | 22798 | 29052201401573 | 9 | Fulton | NEEDMORE | US 522 | BARNETT RUN | 29/202 - BELFAST | 39.8439 | -78.1487 | 20150500720/20151811319 | wtr | Needmore Water Supply Co Inc | 717-573-2318; Donny Gordan 717-816-6460 | UG |  |  | 2016-08-22
328b | -- | 328 | 17826 | 22798 | 29052201401573 | 9 | Fulton | NEEDMORE | US 522 | BARNETT RUN | 29/202 - BELFAST | 39.8439 | -78.1487 | 20150500720/20151811319 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-08-22
328c | -- | 328 | 17826 | 22798 | 29052201401573 | 9 | Fulton | NEEDMORE | US 522 | BARNETT RUN | 29/202 - BELFAST | 39.8439 | -78.1487 | 20150500720/20151811319 | Comm | Frontier | Craig (Kip) Pletz, Craig.Pletz@ftr.com, 717-587-9740 | OH |  |  | 2016-08-22
329a | -- | 329 | 17827 | 22825 | 29052201600330 | 9 | Fulton | 3/4 MILE N. OF NEEDMORE | US 522 | PALMER RUN | 29/202 - BELFAST | 39.854 | -78.1398 | 20143561474 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-03-25
329b | -- | 329 | 17827 | 22825 | 29052201600330 | 9 | Fulton | 3/4 MILE N. OF NEEDMORE | US 522 | PALMER RUN | 29/202 - BELFAST | 39.854 | -78.1398 | 20143561474 | Comm | Frontier | Craig (Kip) Pletz, Craig.Pletz@ftr.com, 717-587-9740 | OH |  |  | 2016-03-25
330a | -- | 330 | 17828 | 22826 | 29052201601370 | 9 | Fulton | 1 MILE NORTH OF NEEDMORE | US 522 | LITTLE TONOLOWAY CREEK | 29/202 - BELFAST | 39.8549 | -78.1363 | 20143571735 | Comm | Frontier | Craig (Kip) Pletz, Craig.Pletz@ftr.com, 717-587-9740 | OH |  |  | 2016-03-25
330b | -- | 330 | 17828 | 22826 | 29052201601370 | 9 | Fulton | 1 MILE NORTH OF NEEDMORE | US 522 | LITTLE TONOLOWAY CREEK | 29/202 - BELFAST | 39.8549 | -78.1363 | 20143571735 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-03-25
330c | -- | 330 | 17828 | 22826 | 29052201601370 | 9 | Fulton | 1 MILE NORTH OF NEEDMORE | US 522 | LITTLE TONOLOWAY CREEK | 29/202 - BELFAST | 39.8549 | -78.1363 | 20143571735 | Elect | Valley Rural Electric Coop Inc | Patrick Lichner, 814-793-2609 | OH |  |  | 2016-03-25
331a | -- | 331 | 17832 | 22827 | 29052202901545 | 9 | Fulton | 0.47 MILE NORTH FROM PA 928 | US 522 | BIG COVE CREEK | 29/201 - AYR | 39.8563 | -78.0451 | 20143571746 | Comm | Centurylink formerly Embarq | Bradley (Brad) Benson, Bradley.J.Benson1@centurylink.com, 717-267-4724 | OH |  |  | 2016-05-23
331b | -- | 331 | 17832 | 22827 | 29052202901545 | 9 | Fulton | 0.47 MILE NORTH FROM PA 928 | US 522 | BIG COVE CREEK | 29/201 - AYR | 39.8563 | -78.0451 | 20143571746 | Comm | Comcast Cable Communications, Inc. | Jeff Gilliland, 717-752-5036, Jeffrey_Gilliland@cable.comcast.com, Dennis Thomas, Dennis_Thomas@cable.comcast.com | OH |  |  | 2016-05-23
331c | -- | 331 | 17832 | 22827 | 29052202901545 | 9 | Fulton | 0.47 MILE NORTH FROM PA 928 | US 522 | BIG COVE CREEK | 29/201 - AYR | 39.8563 | -78.0451 | 20143571746 | sanitary | McConnellsburg Sewerage Auth | Craig Strait, 717-485-4728, 20789 Great Cove Road McConnellsburg, PA 17233 | UG |  |  | 2016-05-23
331d | -- | 331 | 17832 | 22827 | 29052202901545 | 9 | Fulton | 0.47 MILE NORTH FROM PA 928 | US 522 | BIG COVE CREEK | 29/201 - AYR | 39.8563 | -78.0451 | 20143571746 | Elect | Valley Rural Electric Coop Inc | Patrick Lichner, 814-793-2609 |  |  |  | 2016-05-23
331e | -- | 331 | 17832 | 22827 | 29052202901545 | 9 | Fulton | 0.47 MILE NORTH FROM PA 928 | US 522 | BIG COVE CREEK | 29/201 - AYR | 39.8563 | -78.0451 | 20143571746 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-05-23
332a | -- | 332 | 17850 | 22832 | 29065503900454 | 9 | Fulton | .1 M N TR30,HARRISONVILLE | PA 655 | SINDELDECKER BRANCH | 29/206 - LICKING CREEK | 39.9886 | -78.0596 | 20150501099 | Comm | Centurylink formerly Embarq | Don Hubbard, 717-633-8285, don.g.hubbard@embarq.com |  |  |  | 2017-04-05
332b | -- | 332 | 17850 | 22832 | 29065503900454 | 9 | Fulton | .1 M N TR30,HARRISONVILLE | PA 655 | SINDELDECKER BRANCH | 29/206 - LICKING CREEK | 39.9886 | -78.0596 | 20150501099 |  | Licking Creek TWP | 717-485-5670 |  |  |  | 2017-04-05
332c | -- | 332 | 17850 | 22832 | 29065503900454 | 9 | Fulton | .1 M N TR30,HARRISONVILLE | PA 655 | SINDELDECKER BRANCH | 29/206 - LICKING CREEK | 39.9886 | -78.0596 | 20150501099 | Elect | Valley Rural Electric Coop Inc | Patrick Lichner, 814-793-2609 |  |  |  | 2017-04-05
332d | -- | 332 | 17850 | 22832 | 29065503900454 | 9 | Fulton | .1 M N TR30,HARRISONVILLE | PA 655 | SINDELDECKER BRANCH | 29/206 - LICKING CREEK | 39.9886 | -78.0596 | 20150501099 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2017-04-05
333a | -- | 333 | 17853 | 88142 | 29065504501203 | 9 | Fulton | 1.4 MI. SOUTH OF TURNPIKE | PA 655 | FORTUNE TELLER CREEK | 29/205 - DUBLIN | 40.0275 | -78.0282 | 20150500707 | Elect | Valley Rural Electric Coop Inc | Patrick Lichner, 814-793-2609 | OH |  |  | 2016-08-11
333b | -- | 333 | 17853 | 88142 | 29065504501203 | 9 | Fulton | 1.4 MI. SOUTH OF TURNPIKE | PA 655 | FORTUNE TELLER CREEK | 29/205 - DUBLIN | 40.0275 | -78.0282 | 20150500707 | Comm | Comcast Cable Communications, Inc. | Dan Cramer, 800-219-9103, dan.cramer@adelphia.com | OH |  |  | 2016-08-11
333c | -- | 333 | 17853 | 88142 | 29065504501203 | 9 | Fulton | 1.4 MI. SOUTH OF TURNPIKE | PA 655 | FORTUNE TELLER CREEK | 29/205 - DUBLIN | 40.0275 | -78.0282 | 20150500707 | sanitary | Hustontown Sewage Auth | 717-987-3185, uncleclem@embarqmail.com | UG |  |  | 2016-08-11
334a | -- | 334 | 17873 | 22837 | 29100100100266 | 9 | Fulton | WEBSTER MILLS | SR 1001 | SPRING RUN | 29/201 - AYR | 39.8596 | -78.0346 | 20150500694 | Elect | Valley Rural Electric Coop Inc | Patrick Lichner, 814-793-2609 |  |  |  | 2016-07-08
334b | -- | 334 | 17873 | 22837 | 29100100100266 | 9 | Fulton | WEBSTER MILLS | SR 1001 | SPRING RUN | 29/201 - AYR | 39.8596 | -78.0346 | 20150500694 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2016-07-08
334c | -- | 334 | 17873 | 22837 | 29100100100266 | 9 | Fulton | WEBSTER MILLS | SR 1001 | SPRING RUN | 29/201 - AYR | 39.8596 | -78.0346 | 20150500694 | Comm | Centurylink formerly Embarq | Don Hubbard, 717-633-8285, don.g.hubbard@embarq.com | OH |  |  | 2016-07-08
334d | -- | 334 | 17873 | 22837 | 29100100100266 | 9 | Fulton | WEBSTER MILLS | SR 1001 | SPRING RUN | 29/201 - AYR | 39.8596 | -78.0346 | 20150500694 | Comm | Comcast Cable Communications, Inc. | Dan Cramer, 800-219-9103, dan.cramer@adelphia.com | OH |  |  | 2016-07-08
335a | -- | 335 | 18576 | 74433 | 31002202300000 | 9 | Huntingdon | OVER TR 26 | US 22 | PA 0026 | 31/221 - SMITHFIELD | 40.4912 | -78.0388 | 20150501134 | Gas | UGI Central Penn Gas | Clarence Krepps, 717-248-6488, ckrepps@ugi.com | UG |  |  | 2017-03-21
335b | -- | 335 | 18576 | 74433 | 31002202300000 | 9 | Huntingdon | OVER TR 26 | US 22 | PA 0026 | 31/221 - SMITHFIELD | 40.4912 | -78.0388 | 20150501134 |  | Huntingdon B/H Area Water & Sewer Auth | Karen Brown (secy), 814-643-2644, kbrown@huntingdonboro.com | UG |  |  | 2017-03-21
336a | -- | 336 | 18601 | 23030 | 31002604900654 | 9 | Huntingdon | .1 MI N SR1011,CNTR UNION | PA 26 | MURRAY RUN | 31/217 - ONEIDA | 40.5401 | -77.9603 | 20143571761 | Elect | Pennsylvania Electric Company | Richard (Rick) Fink, rfink@firstenergycorp.com, 814-949-4641 | OH |  |  | 2016-04-25
336b | -- | 336 | 18601 | 23030 | 31002604900654 | 9 | Huntingdon | .1 MI N SR1011,CNTR UNION | PA 26 | MURRAY RUN | 31/217 - ONEIDA | 40.5401 | -77.9603 | 20143571761 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667 | OH |  |  | 2016-04-25
336c | -- | 336 | 18601 | 23030 | 31002604900654 | 9 | Huntingdon | .1 MI N SR1011,CNTR UNION | PA 26 | MURRAY RUN | 31/217 - ONEIDA | 40.5401 | -77.9603 | 20143571761 | Comm | Verizon | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com | OH |  |  | 2016-04-25
337a | -- | 337 | 18603 | 22980 | 31002605100972 | 9 | Huntingdon | 0.2 MILE NORTH OF SR 1009 | PA 26 | HORN RUN | 31/217 - ONEIDA | 40.5574 | -77.9527 | 20150501356 | comm | Comcast Cable Communications, Inc. | Barry Savage, 301-895-4375 |  |  |  | 2017-03-21
337b | -- | 337 | 18603 | 22980 | 31002605100972 | 9 | Huntingdon | 0.2 MILE NORTH OF SR 1009 | PA 26 | HORN RUN | 31/217 - ONEIDA | 40.5574 | -77.9527 | 20150501356 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667 |  |  |  | 2017-03-21
338a | -- | 338 | 18703 | 23039 | 31065505400533 | 9 | Huntingdon | .7 MI.N.SR 1005,FOUSETOWN | PA 655 | SADDLERS RUN | 31/202 - BRADY | 40.4508 | -77.9036 | 20143580417 | Elect | Valley Rural Electric Coop Inc | Mike Lansberry, mlansberry@valleyrec.com, 814-506-1667 | OH |  |  | 2016-06-08
338b | -- | 338 | 18703 | 23039 | 31065505400533 | 9 | Huntingdon | .7 MI.N.SR 1005,FOUSETOWN | PA 655 | SADDLERS RUN | 31/202 - BRADY | 40.4508 | -77.9036 | 20143580417 | wtr and sanitary | Mill Creek Area Municipal Auth | 814-643-5666 (main office); Keith (operator), 814-386-4167, Main Street Mill Creek, PA 17060 (verified that address has no number), only open until noon M-F | UG |  |  | 2016-06-08
338c | -- | 338 | 18703 | 23039 | 31065505400533 | 9 | Huntingdon | .7 MI.N.SR 1005,FOUSETOWN | PA 655 | SADDLERS RUN | 31/202 - BRADY | 40.4508 | -77.9036 | 20143580417 | Comm | Verizon | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com | OH |  |  | 2016-06-08
338d | -- | 338 | 18703 | 23039 | 31065505400533 | 9 | Huntingdon | .7 MI.N.SR 1005,FOUSETOWN | PA 655 | SADDLERS RUN | 31/202 - BRADY | 40.4508 | -77.9036 | 20143580417 | Comm | Centurylink formerly Embarq | Jeremy Smith, 717-436-5211, Jeremy.Smith1@centurylink.com | OH |  |  | 2016-06-08
339a | -- | 339 | 18742 | 23038 | 31091301901896 | 9 | Huntingdon | 0.4 MILE EAST FROM SR 3019, ROBERTSDALE | PA 913 | GREAT TROUGH CREEK | 31/230 - WOOD | 40.1826 | -78.1152 | 20143580425 | Elect | Pennsylvania Electric Company | Marti Kerch, 814-269-6773, mkerch@firstenergycorp.com; Timothy (Tim) Frye, 814-949-4652, tfrye@firstenergycorp.com | OH |  |  | 2016-05-19
339b | -- | 339 | 18742 | 23038 | 31091301901896 | 9 | Huntingdon | 0.4 MILE EAST FROM SR 3019, ROBERTSDALE | PA 913 | GREAT TROUGH CREEK | 31/230 - WOOD | 40.1826 | -78.1152 | 20143580425 | wtr and sanitary | Wood Broad Top Wells JT Muni Auth | Fred Myers, 814-635-2354, watera1@comcast.net | UG |  |  | 2016-05-19
339c | -- | 339 | 18742 | 23038 | 31091301901896 | 9 | Huntingdon | 0.4 MILE EAST FROM SR 3019, ROBERTSDALE | PA 913 | GREAT TROUGH CREEK | 31/230 - WOOD | 40.1826 | -78.1152 | 20143580425 |  | Wood TWP | Norman L. McClain (secy) 814-635-2440 |  |  |  | 2016-05-19
339d | -- | 339 | 18742 | 23038 | 31091301901896 | 9 | Huntingdon | 0.4 MILE EAST FROM SR 3019, ROBERTSDALE | PA 913 | GREAT TROUGH CREEK | 31/230 - WOOD | 40.1826 | -78.1152 | 20143580425 | Comm | Verizon | Richard (Rich) Lampenfeld, richard.m.lampenfeld@verizon.com, 814-946-5909, 1119 16th Street Altoona, PA 16601 | OH |  |  | 2016-05-19
339e | -- | 339 | 18742 | 23038 | 31091301901896 | 9 | Huntingdon | 0.4 MILE EAST FROM SR 3019, ROBERTSDALE | PA 913 | GREAT TROUGH CREEK | 31/230 - WOOD | 40.1826 | -78.1152 | 20143580425 | Comm | Comcast Cable Communications, Inc. - need to confirm | Jeffrey (Jeff) Gilliland, 717-752-5036, Jeffrey_Gilliland@cable.comcast.com | OH |  |  | 2016-05-19
340 | -- | 340 | 18773 | 23058 | 31100800400000 | 9 | Huntingdon | 1 MI.E.OF COTTAGE | SR 1008 | SHAVERS CREEK | 31/229 - WEST | 40.6178 | -77.9684 | 20150501378 | Elect | Valley Rural Electric Coop Inc | Jeff Garner, 814-793-2609 |  |  |  | 2017-05-31
341a | -- | 341 | 18784 | 23114 | 31101900100185 | 9 | Huntingdon | 0.03 MILE NORTH FROM PA 26 | SR 1019 | STANDING STONE CREEK | 31/215 - MILLER | 40.5957 | -77.862 | 20150501112 | Elect | Valley Rural Electric Coop Inc | Jeff Garner, 814-793-2609 | OH |  |  | 2016-06-20
341b | -- | 341 | 18784 | 23114 | 31101900100185 | 9 | Huntingdon | 0.03 MILE NORTH FROM PA 26 | SR 1019 | STANDING STONE CREEK | 31/215 - MILLER | 40.5957 | -77.862 | 20150501112 | Comm | Verizon - Need to Confirm | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com | OH |  |  | 2016-06-20
342 | -- | 342 | 18785 | 74449 | 31101900600000 | 9 | Huntingdon | 1.75 MILE NORTH FROM PA 26 | SR 1019 | E BR STANDING STONE CRK | 31/211 - JACKSON | 40.6009 | -77.8322 | 20150501361 | Elect | Valley Rural Electric Coop Inc | Jeff Garner, 814-793-2609 |  |  |  | 2017-05-11
343 | -- | 343 | 18881 | 23116 | 31400900200000 | 9 | Huntingdon | 0.24 MILE NORTH FROM PA 305 | SR 4009 | SHAVERS CREEK | 31/214 - LOGAN | 40.5824 | -78.0459 | 20150501372 |  | all facilities responded clear per one call |  |  |  |  | 2017-05-11
344a | -- | 344 | 45123 | 88158 | 55003003602574 | 9 | Somerset | 2.44 MILE WEST FROM PA 160 | US 30 | TRIB CALENDAR RUN | 55/223 - STONYCREEK | 40.0744 | -78.8699 | 20150161848, 20150161849 |  | Shade TWP | Lillian Feathers (secy), 814-754-4622 | UG |  |  | 2016-06-17
344b | -- | 344 | 45123 | 88158 | 55003003602574 | 9 | Somerset | 2.44 MILE WEST FROM PA 160 | US 30 | TRIB CALENDAR RUN | 55/223 - STONYCREEK | 40.0744 | -78.8699 | 20150161848, 20150161849 | Elect | Pennsylvania Electric Company | Joe Ritter, 814-269-6709, jritter@firstenergycorp.com, Dale Shaner, 814-768-4148, dshaner@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-06-17
344c | -- | 344 | 45123 | 88158 | 55003003602574 | 9 | Somerset | 2.44 MILE WEST FROM PA 160 | US 30 | TRIB CALENDAR RUN | 55/223 - STONYCREEK | 40.0744 | -78.8699 | 20150161848, 20150161849 | Comm | Verizon - Need to Confirm | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com | OH |  |  | 2016-06-17
344d | -- | 344 | 45123 | 88158 | 55003003602574 | 9 | Somerset | 2.44 MILE WEST FROM PA 160 | US 30 | TRIB CALENDAR RUN | 55/223 - STONYCREEK | 40.0744 | -78.8699 | 20150161848, 20150161849 |  | Upper Stonycreek JT Muni Auth | John Toth, 814-893-5668 | UG |  |  | 2016-06-17
345a | -- | 345 | 41517 | 92698 | 55003003702626 | 9 | Somerset | 1.74 MILE WEST FROM PA 160 | US 30 | CALENDAR RUN | 55/223 - STONYCREEK | 40.075 | -78.8667 | 20150170057, 20150170058 | Elect | Pennsylvania Electric Company | Joe Ritter, 814-269-6709, jritter@firstenergycorp.com, Dale Shaner, 814-768-4148, dshaner@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2016-06-17
345b | -- | 345 | 41517 | 92698 | 55003003702626 | 9 | Somerset | 1.74 MILE WEST FROM PA 160 | US 30 | CALENDAR RUN | 55/223 - STONYCREEK | 40.075 | -78.8667 | 20150170057, 20150170058 |  | Shade TWP | Lillian Feathers (secy), 814-754-4622 | UG |  |  | 2016-06-17
345c | -- | 345 | 41517 | 92698 | 55003003702626 | 9 | Somerset | 1.74 MILE WEST FROM PA 160 | US 30 | CALENDAR RUN | 55/223 - STONYCREEK | 40.075 | -78.8667 | 20150170057, 20150170058 |  | Upper Stonycreek JT Muni Auth | John Toth, 814-893-5668 | UG |  |  | 2016-06-17
345d | -- | 345 | 41517 | 92698 | 55003003702626 | 9 | Somerset | 1.74 MILE WEST FROM PA 160 | US 30 | CALENDAR RUN | 55/223 - STONYCREEK | 40.075 | -78.8667 | 20150170057, 20150170058 | Comm | Verizon - Need to Confirm | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com | OH |  |  | 2016-06-17
346 | -- | 346 | 31343 | 23517 | 55003104200000 | 9 | Somerset | 0.5 MILE EAST OF SR 1005 | PA 31 | SANDY HOLLOW CREEK | 55/223 - STONYCREEK | 39.9649 | -78.9481 | 20150501388, 20150501389 |  | all facilities responded clear per one call |  |  |  |  | 2017-03-21
347a | -- | 347 | 31469 | 23586 | 55052300301840 | 9 | Somerset | LISTONBURG | PA 523 | WHITES CREEK | 55/201 - ADDISON | 39.7544 | -79.3142 | 20143580432 |  | all facilities responded clear per one call |  |  |  |  | 2016-07-06
347b | -- | 347 | 31469 | 23586 | 55052300301840 | 9 | Somerset | LISTONBURG | PA 523 | WHITES CREEK | 55/201 - ADDISON | 39.7544 | -79.3142 | 20143580432 | Elect | Pennsylvania Electric Company or Somerset County Rural Electric Coop - need to confirm | Joe Ritter, 814-269-6709, jritter@firstenergycorp.com, Dale Shaner, 814-768-4148, dshaner@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-07-06
347c | -- | 347 | 31469 | 23586 | 55052300301840 | 9 | Somerset | LISTONBURG | PA 523 | WHITES CREEK | 55/201 - ADDISON | 39.7544 | -79.3142 | 20143580432 | Comm | Verizon - Need to Confirm | Joseph (Joe) Schoch, 814-231-6565, joseph.l.schoch.jr@verizon.com | OH |  |  | 2016-07-06
348a | -- | 348 | 31470 | 23410 | 55052300701200 | 9 | Somerset | BEACHLY | PA 523 | LAUREL RUN | 55/201 - ADDISON | 39.7766 | -79.3107 | 20143571775 | comm | Verizon North LLC | Eric Rodrigues, eric.rodrigues@verizon.com, 814-490-0176; Robert Preston (field engineer) Robert.Preston@cyient.com, 304-670-9999 | OH |  |  | 2016-05-23
348b | -- | 348 | 31470 | 23410 | 55052300701200 | 9 | Somerset | BEACHLY | PA 523 | LAUREL RUN | 55/201 - ADDISON | 39.7766 | -79.3107 | 20143571775 | Elect | Pennsylvania Electric Company | Joe Ritter, 814-269-6709, jritter@firstenergycorp.com, Dale Shaner, 814-768-4148, dshaner@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-05-23
348c | -- | 348 | 31470 | 23410 | 55052300701200 | 9 | Somerset | BEACHLY | PA 523 | LAUREL RUN | 55/201 - ADDISON | 39.7766 | -79.3107 | 20143571775 | Comm | Comcast Cable Communications, Inc. | Jeffrey (Jeff) Gilliland, 717-752-5036, Jeffrey_Gilliland@cable.comcast.com | OH |  |  | 2016-05-23
349a | -- | 349 | 31471 | 74446 | 55052300801065 | 9 | Somerset | DUMAS | PA 523 | TRIB TO WHITES CREEK | 55/201 - ADDISON | 39.7817 | -79.3174 | 20143580320 | Elect | Pennsylvania Electric Company | Joe Ritter, 814-269-6709, jritter@firstenergycorp.com | Both |  |  | 2016-05-16
349b | -- | 349 | 31471 | 74446 | 55052300801065 | 9 | Somerset | DUMAS | PA 523 | TRIB TO WHITES CREEK | 55/201 - ADDISON | 39.7817 | -79.3174 | 20143580320 | comm | Verizon North LLC | Eric Rodrigues, eric.rodrigues@verizon.com, 814-490-0176; Robert Preston (field engineer), robert.preston@cyient.com, 304-670-9999 | Both |  |  | 2016-05-16
349c | -- | 349 | 31471 | 74446 | 55052300801065 | 9 | Somerset | DUMAS | PA 523 | TRIB TO WHITES CREEK | 55/201 - ADDISON | 39.7817 | -79.3174 | 20143580320 | Comm | Comcast Cable Communications, Inc. | Jeffrey (Jeff) Gilliland, 717-752-5036, Jeffrey_Gilliland@cable.comcast.com | OH |  |  | 2016-05-16
350 | -- | 350 | 31521 | 23516 | 55100400101850 | 9 | Somerset | SHANKSVILLE BORO. | SR 1004 | RHOADS CREEK | 55/417 - SHANKSVILLE | 40.0153 | -78.9019 | 20150501450, 20150501451 |  | Shanksville Borough | Kimberly Belsterling (secy), 814-267-6421 | UG |  |  | 2017-05-22
351 | -- | 351 | 31528 | 23571 | 55100700300000 | 9 | Somerset | 0.99 MILE NORTH FROM PA 160 | SR 1007 | TRIB STONYCREEK RIVER | 55/223 - STONYCREEK | 39.97 | -78.9029 | 20150501474 | comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com |  |  |  | 2017-05-30
352 | -- | 352 | 31532 | 23588 | 55100701800000 | 9 | Somerset | LAMBERTSVILLE | SR 1007 | LAMBERT RUN | 55/223 - STONYCREEK | 40.0705 | -78.9142 | 20150501481 |  | all facilities responded clear per one call |  |  |  |  | 2017-06-05
353 | -- | 353 | 31588 | 74467 | 55200500300000 | 9 | Somerset | 1.95 MILE SO.FROM SR 2004 @ SUMMIT MILLS | SR 2005 | ELK LICK CREEK | 55/224 - SUMMIT | 39.8089 | -79.1065 | 20150501491, 20150501492 | Comm | Comcast Cable of Garrett County MD | 814-201-6274 |  |  |  | 2017-08-01
354a | -- | 354 | 31608 | 23428 | 55201301000000 | 9 | Somerset | 0.46 MILE SOUTH FROM SR 3002 | SR 2013 | POWDER RUN | 55/222 - SOUTHAMPTON | 39.7733 | -78.7894 | 20143580119 | gas | Columbia Gas of PA Design | Nicholas Seese (field engineer), 724-415-9210, nseese@nisource.com; Nelson White (Manager) nwhite@nisource.com | UG |  |  | 2016-04-14
354b | -- | 354 | 31608 | 23428 | 55201301000000 | 9 | Somerset | 0.46 MILE SOUTH FROM SR 3002 | SR 2013 | POWDER RUN | 55/222 - SOUTHAMPTON | 39.7733 | -78.7894 | 20143580119 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com; engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-04-14
354c | -- | 354 | 31608 | 23428 | 55201301000000 | 9 | Somerset | 0.46 MILE SOUTH FROM SR 3002 | SR 2013 | POWDER RUN | 55/222 - SOUTHAMPTON | 39.7733 | -78.7894 | 20143580119 | Comm | Verizon | Eric Rodrigues, eric.rodrigues@verizon.com, 814-490-0176; Robert Preston (field engineer), robert.preston@cyient.com, 304-670-9999 | OH |  |  | 2016-04-14
355a | -- | 355 | 31630 | 23549 | 55201800600000 | 9 | Somerset | BEECHDALE | SR 2018 | BUFFALO CREEK | 55/204 - BROTHERS VALLEY | 39.8996 | -79.0119 | 20143580311 |  | all facilities responded clear per one call |  |  |  |  | 2016-07-18
355b | -- | 355 | 31630 | 23549 | 55201800600000 | 9 | Somerset | BEECHDALE | SR 2018 | BUFFALO CREEK | 55/204 - BROTHERS VALLEY | 39.8996 | -79.0119 | 20143580311 | Elect | Pennsylvania Electric Company or Somerset County Rural Electric Coop - need to confirm | Joe Ritter, 814-269-6709, jritter@firstenergycorp.com, Dale Shaner, 814-768-4148, dshaner@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-07-18
356 | -- | 356 | 31651 | 23454 | 55202600300000 | 9 | Somerset | 2 MI.NE.OF MEYERSDALE | SR 2026 | BLUE LICK CREEK | 55/224 - SUMMIT | 39.8461 | -79.0011 | 20150501506 | Comm | Comcast Cable of Garrett County MD | 814-201-6274 |  |  |  | 2017-08-01
357a | -- | 357 | 31758 | 23601 | 55401900700000 | 9 | Somerset | OVER US 30 | SR 4019 | US 30 | 55/219 - QUEMAHONING | 40.1007 | -78.9565 | 20150501439 |  | Somerset TWP Municipal Auth | Carolyn Zambanini (secy) 814-445-5842 | UG |  |  | 2017-08-01
357b | -- | 357 | 31758 | 23601 | 55401900700000 | 9 | Somerset | OVER US 30 | SR 4019 | US 30 | 55/219 - QUEMAHONING | 40.1007 | -78.9565 | 20150501439 |  | Upper Stonycreek JT Muni Auth | John Toth, 814-893-5668 | UG |  |  | 2017-08-01
358a | -- | 358 | 2992 | 83197 | 3006600600000 | 10 | Armstrong | CARNAHAN RUN NO.1 | SR0066 | CARNAHAN RUN | 03/216 - PARKS | 40.6124 | -79.5838 | 20150330208 | wtr | Kiski Valley Water Pollution Control Auth | Gene Burns, eburns@kvwpca.com | UG |  |  | 2016-06-20
358b | -- | 358 | 2992 | 83197 | 3006600600000 | 10 | Armstrong | CARNAHAN RUN NO.1 | SR0066 | CARNAHAN RUN | 03/216 - PARKS | 40.6124 | -79.5838 | 20150330208 |  | Parks TWP | Mary Ralston (secy), 724-567-7764, parkstwp@comcast.net, 26 Jackson St North Vandergrift, PA 15690 | UG |  |  | 2016-06-20
358c | -- | 358 | 2992 | 83197 | 3006600600000 | 10 | Armstrong | CARNAHAN RUN NO.1 | SR0066 | CARNAHAN RUN | 03/216 - PARKS | 40.6124 | -79.5838 | 20150330208 |  | Parks Twp Municipal Auth | Peter Massetto, 724-567-7301 | UG |  |  | 2016-06-20
358d | -- | 358 | 2992 | 83197 | 3006600600000 | 10 | Armstrong | CARNAHAN RUN NO.1 | SR0066 | CARNAHAN RUN | 03/216 - PARKS | 40.6124 | -79.5838 | 20150330208 | Elect | West Penn Power | Lisa Marinelli, 724-830-5629, lmarine@firstenergycorp.com |  |  |  | 2016-06-20
359a | Y | 359 | 3097 | 24085 | 3083901001927 | 10 | Armstrong | SOUTH OF DAYTON NO. 2 | SR0839 | GLADE RUN | 03/206 - COWANSHANNOCK | 40.8639 | -79.2354 |  | Elect | WEST PENN POWER COMPANY | Kevin Baker, 724-548-3538, kbaker2@firstenergycorp.com | OH |  | RESTRICTIVE | 2015-07-16
359b | Y | 359 | 3097 | 24085 | 3083901001927 | 10 | Armstrong | SOUTH OF DAYTON NO. 2 | SR0839 | GLADE RUN | 03/206 - COWANSHANNOCK | 40.8639 | -79.2354 |  | TV | COMCAST CABLE CORPORATION | Mark Painter, 724-734-1977, mark_painter@cable.comcast.com | OH |  | RESTRICTIVE | 2015-07-16
359b | Y | 359 | 3097 | 24085 | 3083901001927 | 10 | Armstrong | SOUTH OF DAYTON NO. 2 | SR0839 | GLADE RUN | 03/206 - COWANSHANNOCK | 40.8639 | -79.2354 |  | TV | Salsgiver communications | Loren Salsgiver, 724-295-1970 x102, loren@salsgiver.com Construction Contact: Adam Nulph, 724-295-1970 x104, adamnulph@salsgiver.com | OH |  | RESTRICTIVE | 2015-07-16
359c | Y | 359 | 3097 | 24085 | 3083901001927 | 10 | Armstrong | SOUTH OF DAYTON NO. 2 | SR0839 | GLADE RUN | 03/206 - COWANSHANNOCK | 40.8639 | -79.2354 |  | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Tom Gerg, 814-849-3552, tom.gerg@windstream.com | OH |  | RESTRICTIVE | 2015-07-16
360a | Y | 360 | 3160 | 79606 | 3103900600000 | 10 | Armstrong | BRYAN | SR1039 | TRIB S FRK PINE CR | 03/206 - COWANSHANNOCK | 40.8317 | -79.2905 | 20130341535 | Elect | WEST PENN POWER COMPANY | Kevin Baker, 724-548-3538, kbaker2@firstenergycorp.com | OH |  | Coordinated | 2015-07-22
360b | Y | 360 | 3160 | 79606 | 3103900600000 | 10 | Armstrong | BRYAN | SR1039 | TRIB S FRK PINE CR | 03/206 - COWANSHANNOCK | 40.8317 | -79.2905 | 20130341535 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Kirk Myers, 724-543-7285, Kirk.Myers@windstream.com | OH |  | Coordinated | 2015-07-22
360c | Y | 360 | 3160 | 79606 | 3103900600000 | 10 | Armstrong | BRYAN | SR1039 | TRIB S FRK PINE CR | 03/206 - COWANSHANNOCK | 40.8317 | -79.2905 | 20130341535 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Kirk Myers, 724-543-7285, Kirk.Myers@windstream.com | OH |  | Coordinated | 2015-07-22
360d | Y | 360 | 3160 | 79606 | 3103900600000 | 10 | Armstrong | BRYAN | SR1039 | TRIB S FRK PINE CR | 03/206 - COWANSHANNOCK | 40.8317 | -79.2905 | 20130341535 | Gas | PEOPLES TWP, LLC | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  | Protect-In-Place | 2015-07-22
360e | Y | 360 | 3160 | 79606 | 3103900600000 | 10 | Armstrong | BRYAN | SR1039 | TRIB S FRK PINE CR | 03/206 - COWANSHANNOCK | 40.8317 | -79.2905 | 20130341535 | Gas | PEOPLES TWP, LLC | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  | Coordinated | 2015-07-22
361a | -- | 361 | 3169 | 24000 | 3200101402192 | 10 | Armstrong | RURAL VALLEY NO.3 | SR2001 | COWANSHANNOCK CREEK | 03/414 - RURAL VALLEY | 40.797 | -79.3157 | 20150410282 | Elect | Energy Corporation of America | Troy Medrich, 724-463-8400 |  |  |  | 2017-05-01
361b | -- | 361 | 3169 | 24000 | 3200101402192 | 10 | Armstrong | RURAL VALLEY NO.3 | SR2001 | COWANSHANNOCK CREEK | 03/414 - RURAL VALLEY | 40.797 | -79.3157 | 20150410282 | Gas | Peoples Gas Valley Division | Michelle Saxion, 412-208-7239 | UG |  |  | 2017-05-01
361c | -- | 361 | 3169 | 24000 | 3200101402192 | 10 | Armstrong | RURAL VALLEY NO.3 | SR2001 | COWANSHANNOCK CREEK | 03/414 - RURAL VALLEY | 40.797 | -79.3157 | 20150410282 | wtr | Rural Valley Borough Water Works | Vince Tonkin, foreman, vtonkin@eca.com | UG | 4" |  | 2017-05-01
361d | -- | 361 | 3169 | 24000 | 3200101402192 | 10 | Armstrong | RURAL VALLEY NO.3 | SR2001 | COWANSHANNOCK CREEK | 03/414 - RURAL VALLEY | 40.797 | -79.3157 | 20150410282 | sanitary | Shannock Valley General Services Auth | 724-783-2454 | UG |  |  | 2017-05-01
361e | -- | 361 | 3169 | 24000 | 3200101402192 | 10 | Armstrong | RURAL VALLEY NO.3 | SR2001 | COWANSHANNOCK CREEK | 03/414 - RURAL VALLEY | 40.797 | -79.3157 | 20150410282 |  | West Penn Power | Lisa Marinelli, 724-830-5629, lmarine@firstenergycorp.com |  |  |  | 2017-05-01
361f | -- | 361 | 3169 | 24000 | 3200101402192 | 10 | Armstrong | RURAL VALLEY NO.3 | SR2001 | COWANSHANNOCK CREEK | 03/414 - RURAL VALLEY | 40.797 | -79.3157 | 20150410282 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Chad Shepherd, 724-733-3295, chad.e.shepherd@windstream.com |  |  |  | 2017-05-01
362a | -- | 362 | 3176 | 83252 | 3200500500000 | 10 | Armstrong | BURRELL TWP-E OF BRICK CH | SR2005 | TRIB TO CHERRY RUN | 03/204 - BURRELL | 40.6885 | -79.4279 | 20150341109 | sanitary | Burrell TWP | David J. Semsick, 724-248-7272 | UG |  |  | 2017-02-24
362b | -- | 362 | 3176 | 83252 | 3200500500000 | 10 | Armstrong | BURRELL TWP-E OF BRICK CH | SR2005 | TRIB TO CHERRY RUN | 03/204 - BURRELL | 40.6885 | -79.4279 | 20150341109 | Gas | EQT Production (Carnegie Natural Gas Co) | George Pozzuto, 412-395-3127, gpozzuto@eqt.com | UG | 2" and 3" |  | 2017-02-24
362c | -- | 362 | 3176 | 83252 | 3200500500000 | 10 | Armstrong | BURRELL TWP-E OF BRICK CH | SR2005 | TRIB TO CHERRY RUN | 03/204 - BURRELL | 40.6885 | -79.4279 | 20150341109 | Elect | West Penn Power | Lisa Marinelli, 724-830-5629, lmarine@firstenergycorp.com |  |  |  | 2017-02-24
363a | -- | 363 | 3232 | 74202 | 3204701200000 | 10 | Armstrong | ROARING RUN | SR2047 | ROARING RUN | 03/210 - KISKIMINETAS | 40.5769 | -79.5012 | 20151412971 | Comm | Comcast Cable Communications, Inc. | Gary Barnett, gary_barnett@cable.comcast.com | UG |  |  | 2017-05-30
363b | -- | 363 | 3232 | 74202 | 3204701200000 | 10 | Armstrong | ROARING RUN | SR2047 | ROARING RUN | 03/210 - KISKIMINETAS | 40.5769 | -79.5012 | 20151412971 | Gas | KRIEBEL MINERALS INC | Barbara Flinspach, Bflinspach@kriebelgas.com, 814-226-4160 x130 | UG |  |  | 2017-05-30
363c | -- | 363 | 3232 | 74202 | 3204701200000 | 10 | Armstrong | ROARING RUN | SR2047 | ROARING RUN | 03/210 - KISKIMINETAS | 40.5769 | -79.5012 | 20151412971 | Gas | PEOPLES NATURAL GAS COMPANY LLC | Michelle Saxion, 412-208-7239 | UG |  |  | 2017-05-30
364a | -- | 364 | 3245 | 24023 | 3205700100245 | 10 | Armstrong | LAUREL POINT | SR2057 | CARNAHAN RUN | 03/216 - PARKS | 40.6367 | -79.5387 | 20143580317 | gas | Peoples Gas Company | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  |  | 2016-05-20
364b | -- | 364 | 3245 | 24023 | 3205700100245 | 10 | Armstrong | LAUREL POINT | SR2057 | CARNAHAN RUN | 03/216 - PARKS | 40.6367 | -79.5387 | 20143580317 | sanitary | Parks Twp Municipal Auth | Peter Massetto, 724-567-7301, ptma@verizon.net | UG |  |  | 2016-05-20
364c | -- | 364 | 3245 | 24023 | 3205700100245 | 10 | Armstrong | LAUREL POINT | SR2057 | CARNAHAN RUN | 03/216 - PARKS | 40.6367 | -79.5387 | 20143580317 | wtr | Parks Twp Municipal Auth | Peter Massetto, 724-567-7301, ptma@verizon.net | UG |  |  | 2016-05-20
364d | -- | 364 | 3245 | 24023 | 3205700100245 | 10 | Armstrong | LAUREL POINT | SR2057 | CARNAHAN RUN | 03/216 - PARKS | 40.6367 | -79.5387 | 20143580317 | Elect | West Penn Power Company | Zach Reedy, (724) 548-3578, zreedy@firstenergycorp.com | OH |  |  | 2016-05-20
364e | -- | 364 | 3245 | 24023 | 3205700100245 | 10 | Armstrong | LAUREL POINT | SR2057 | CARNAHAN RUN | 03/216 - PARKS | 40.6367 | -79.5387 | 20143580317 | Comm | Verizon North LLC | Barbara Witkowski, barb.witkowski@verizon.com | OH |  |  | 2016-05-20
364f | -- | 364 | 3245 | 24023 | 3205700100245 | 10 | Armstrong | LAUREL POINT | SR2057 | CARNAHAN RUN | 03/216 - PARKS | 40.6367 | -79.5387 | 20143580317 | Comm | Comcast | Rick Moslen, 412-999-0590, Richard_Moslen@cable.comcast.com | OH |  |  | 2016-05-20
365a | -- | 365 | 3278 | 24018 | 3300900800000 | 10 | Armstrong | CLAYPOOLE ROAD NO.3 | SR3009 | TRIB TO BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.833 | -79.6244 | 20143580322 | Comm | WINDSTREAM | Daniel Lingenfelter, (724)543-7286, Daniel.Lingenfelter@windstream.com | OH |  |  | 2016-05-31
365b | -- | 365 | 3278 | 24018 | 3300900800000 | 10 | Armstrong | CLAYPOOLE ROAD NO.3 | SR3009 | TRIB TO BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.833 | -79.6244 | 20143580322 | Comm | ARMSTRONG | Scott Bowser, 724-482-4885 ext. 224, Cell 724-321-5800, sbowser@agoc.com | OH |  |  | 2016-05-31
365c | -- | 365 | 3278 | 24018 | 3300900800000 | 10 | Armstrong | CLAYPOOLE ROAD NO.3 | SR3009 | TRIB TO BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.833 | -79.6244 | 20143580322 | Elect | West Penn Power Company | Troy Bruner, 724-548-3547, tbruner@firstenergycorp.com Zach Reedy, (724) 548-3578, zreedy@firstenergycorp.com | OH |  |  | 2016-05-31
365d | -- | 365 | 3278 | 24018 | 3300900800000 | 10 | Armstrong | CLAYPOOLE ROAD NO.3 | SR3009 | TRIB TO BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.833 | -79.6244 | 20143580322 | Gas | Peoples TWP LLC/TW Phillips | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  |  | 2016-05-31
365e | -- | 365 | 3278 | 24018 | 3300900800000 | 10 | Armstrong | CLAYPOOLE ROAD NO.3 | SR3009 | TRIB TO BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.833 | -79.6244 | 20143580322 | sanitary | West Franklin TWP | Mathew J. Hogg, wft@comcast.net | UG |  |  | 2016-05-31
365f | -- | 365 | 3278 | 24018 | 3300900800000 | 10 | Armstrong | CLAYPOOLE ROAD NO.3 | SR3009 | TRIB TO BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.833 | -79.6244 | 20143580322 | wtr | Worthington W Franklin JT Muni Auth | Dave Johns, 724-297-5630, westfranklin@aol.com | UG |  |  | 2016-05-31
366a | Y | 366 | 3282 | 24153 | 3301300602401 | 10 | Armstrong | NICHOLA NO.1 | SR3013 | BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.8627 | -79.676 | 20140221432 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  | NOT AFFECTED | 2015-07-20
366b | Y | 366 | 3282 | 24153 | 3301300602401 | 10 | Armstrong | NICHOLA NO.1 | SR3013 | BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.8627 | -79.676 | 20140221432 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  | NOT AFFECTED | 2015-07-20
366c | Y | 366 | 3282 | 24153 | 3301300602401 | 10 | Armstrong | NICHOLA NO.1 | SR3013 | BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.8627 | -79.676 | 20140221432 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  | CONDITIONAL RESTRICTION | 2015-07-20
366d | Y | 366 | 3282 | 24153 | 3301300602401 | 10 | Armstrong | NICHOLA NO.1 | SR3013 | BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.8627 | -79.676 | 20140221432 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  | NOT AFFECTED | 2015-07-20
366e | Y | 366 | 3282 | 24153 | 3301300602401 | 10 | Armstrong | NICHOLA NO.1 | SR3013 | BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.8627 | -79.676 | 20140221432 | Elect | CENTRAL ELECTRIC COOPERATIVE INC. | Chris Robinson, 1-800-521-0570 x 2181, crobinson@central.coop | OH |  | Coordinated | 2015-07-20
366f | Y | 366 | 3282 | 24153 | 3301300602401 | 10 | Armstrong | NICHOLA NO.1 | SR3013 | BUFFALO CREEK | 03/228 - WEST FRANKLIN | 40.8627 | -79.676 | 20140221432 | Elect | CENTRAL ELECTRIC COOPERATIVE INC. | Chris Robinson, 1-800-521-0570 x 2181, crobinson@central.coop | OH |  | Coordinated | 2015-07-20
367a | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | 20140221433 | Elect | WEST PENN POWER COMPANY | Kevin Baker, 724-548-3538, kbaker2@firstenergycorp.com | OH |  | Coordinated | 2015-07-16
367b | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | 20140221433 | Gas | PEOPLES NATURAL GAS COMPANY LLC | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  | RESTRICTIVE | 2015-07-16
367c | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | 20140221433 | Wtr | KITTANNING SUBURBAN JOINT WATER AUTHORITY | Michael Moore, 412-767-5100, mmoore@banksonengineers.com | UG |  | INCORPORATED | 2015-07-16
367d | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | 20140221433 | SS | WEST HILLS AREA WATER POLLUTION AUTH | Corey S. Heller, 724-545-9126 | UG |  | INCORPORATED | 2015-07-16
367e | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | 20140221433 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Kirk Myers, 724-543-7285, Kirk.Myers@windstream.com | OH |  | RESTRICTIVE | 2015-07-16
367f | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | 20140221433 | TV | COMCAST CABLE CORPORATION | Mark Painter, 724-734-1977, mark_painter@cable.comcast.com | OH |  | RESTRICTIVE | 2015-07-16
367g | Y | 367 | 3293 | 83284 | 3301702501033 | 10 | Armstrong | CENTER HILL NO. 6 | SR3017 | GLADE RUN | 03/215 - NORTH BUFFALO | 40.7994 | -79.5668 | 20140221433 | Comm | ZAYO | John Lynch, 724-850-6241, john.lynch@zayo.com | OH |  | RESTRICTIVE | 2015-07-16
368a | -- | 368 | 3294 | 98070 | 3301702801869 | 10 | Armstrong | BRIAR HILL | SR3017 | SR0422 EB/WB & RAMPS F&G | 03/207 - EAST FRANKLIN | 40.8086 | -79.5483 | 20150420541 | gas | Peoples Gas Valley Division | Michelle Saxion, 412-208-7239 | UG |  |  | 2017-03-01
368b | -- | 368 | 3294 | 98070 | 3301702801869 | 10 | Armstrong | BRIAR HILL | SR3017 | SR0422 EB/WB & RAMPS F&G | 03/207 - EAST FRANKLIN | 40.8086 | -79.5483 | 20150420541 |  | West Kittanning B/West Kittanning MA | 724-548-4740 | UG |  |  | 2017-03-01
368c | -- | 368 | 3294 | 98070 | 3301702801869 | 10 | Armstrong | BRIAR HILL | SR3017 | SR0422 EB/WB & RAMPS F&G | 03/207 - EAST FRANKLIN | 40.8086 | -79.5483 | 20150420541 | Elect | West Penn Power | Lisa Marinelli, 724-830-5629, lmarine@firstenergycorp.com |  |  |  | 2017-03-01
368d | -- | 368 | 3294 | 98070 | 3301702801869 | 10 | Armstrong | BRIAR HILL | SR3017 | SR0422 EB/WB & RAMPS F&G | 03/207 - EAST FRANKLIN | 40.8086 | -79.5483 | 20150420541 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Chad Shepherd, 724-733-3295, chad.e.shepherd@windstream.com | OH |  |  | 2017-03-01
369a | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | 20140510738 | SS | WESTERN BUTLER COUNTY AUTHORITY | Paul J. Kremer, 724 452-5501, wbca@zoominternet.net | UG | 12 | Not Affected | 2015-07-20
369b | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | 20140510738 | Gas | PEOPLES NATURAL GAS | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  | Not Affected | 2015-07-20
369c | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | 20140510738 | Wtr | ZELIENOPLE BOROUGH | Jill Ann Stedina, 724-452-6610 ext. 233 or Tom Thompson 724-662-2402 | UG | 8 | Prior | 2015-07-20
369d | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | 20140510738 | Elect | ARMSTRONG | Michael Cratty, 724-452-5695, mcratty@agoc.com | OH |  | RESTRICTIVE | 2015-07-20
369e | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | 20140510738 | Comm | VERIZON | Jim Garrett, 724-698-4202, james.garrett@rjetelecom.com | OH |  | RESTRICTIVE | 2015-07-20
369f | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | 20140510738 | Comm | VERIZON | Jim Garrett, 724-698-4202, james.garrett@rjetelecom.com | OH |  | RESTRICTIVE | 2015-07-20
369g | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | 20140510738 | Elect | ZELIENOPLE BOROUGH | Jill Ann Stedina, 724-452-6610 ext. 233 or Ed Sullivan, 412-781-1344, esullivan@quad3.com | OH |  | RESTRICTIVE | 2015-07-20
369h | Y | 369 | 7834 | 24806 | 10006800200616 | 10 | Butler | ZELIENOPLE BORO NO. 2 | LR78,SR0068 | GLADE RUN | 10/422 - ZELIENOPLE | 40.7866 | -80.145 | 20140510738 | Elect | ZELIENOPLE BOROUGH | Jill Ann Stedina, 724-452-6610 ext. 233 or Ed Sullivan, 412-781-1344, esullivan@quad3.com | OH |  | Coordinated | 2015-07-20
370 | -- | 370 | 7925 | 24757 | 10030800801195 | 10 | Butler | RIDER CHURCH | LR10056,SR0308 | TRIB TO STONY RUN | 10/205 - CENTER | 40.9514 | -79.9002 | 20151413015 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2017-05-30
371a | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | 20140510756 | Gas | PEOPLES TWP LLC | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG | 6 | RESTRICTIVE | 2015-08-03
371b | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | 20140510756 | Gas | PEOPLES TWP LLC | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG | 4 | RESTRICTIVE | 2015-08-03
371c | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | 20140510756 | Comm | CENTURY LINK TELEPHONE | Michael Montag, 724-284-7235, Michael.C.Montag@centurylink.com | OH |  | Coordinated | 2015-08-03
371d | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | 20140510756 | Comm | CENTURY LINK TELEPHONE | Michael Montag, 724-284-7235, Michael.C.Montag@centurylink.com | OH |  | Coordinated | 2015-08-03
371e | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | 20140510756 | Comm | CENTURY LINK TELEPHONE | Michael Montag, 724-284-7235, Michael.C.Montag@centurylink.com | OH |  | Coordinated | 2015-08-03
371f | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | 20140510756 | Elect | CENTRAL ELECTRIC COOPERATIVE INC. | Chris Robinson, 1-800-521-0570 x2181, crobinson@central.coop or Jeff Fleming, 800-521-0570 ext. 2196 | OH |  | Coordinated | 2015-08-03
371g | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | 20140510756 | Comm | DQE COMMUNICATIONS | Shawn Ross, 412-315-0929, Cell 724-600-4899, sross@dqe.com | OH |  | Coordinated | 2015-08-03
371h | Y | 371 | 7935 | 24667 | 10035603000333 | 10 | Butler | CALDWELL DRIVE | SR0356 | TRIB TO THORN CREEK | 10/218 - JEFFERSON | 40.8097 | -79.8375 | 20140510756 | Comm | ARMSTRONG | Scott Bowser, 724-482-4885 ext. 224, Cell 724-321-5800, sbowser@agoc.com | OH |  | Coordinated | 2015-08-03
372 | -- | 372 | 8016 | 24779 | 10102500100211 | 10 | Butler | RINGNECK | SR1025 | BONNIE BROOK | 10/228 - SUMMIT | 40.867 | -79.8292 | 20151422492 |  | all facilities responded clear per one call |  |  |  |  | 2017-06-01
373a | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | 20140371912 | Gas | PEOPLES NATURAL GAS | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  | Not Affected | 06-22-15 A
373b | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | 20140371912 | Gas | PEOPLES NATURAL GAS | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  | RESTRICTIVE | 06-22-15 A
373c | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | 20140371912 | Gas | PEOPLES NATURAL GAS | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  | RESTRICTIVE | 06-22-15 A
373d | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | 20140371912 | Gas | PEOPLES NATURAL GAS | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  | NOT AFFECTED | 06-22-15 A
373e | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | 20140371912 | Comm | CONSOLIDATED COMMUNICATIONS | Gabe White, 724-443-9832, gabe.white@consolidated.com or Jeff Hall, telephone 724-443-9639 | OH |  | Prior | 06-22-15 A
373f | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | 20140371912 | Comm | CONSOLIDATED COMMUNICATIONS | Gabe White, 724-443-9832, gabe.white@consolidated.com or Jeff Hall, telephone 724-443-9639 | OH |  | Prior | 06-22-15 A
373g | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | 20140371912 | TV | COMCAST CABLE CORPORATION | Kent Norton, 412-352-7045, Kent_Norton@cable.comcast.com | OH |  | Prior | 06-22-15 A
373h | Y | 373 | 8025 | 78002 | 10200700101196 | 10 | Butler | SAXONBURG BLVD NO.1 | SR2007 | BULL CREEK | 10/209 - CLINTON | 40.6743 | -79.8288 | 20140371912 | Elect | WEST PENN POWER COMPANY | Rick Hobbins, 724-334-5237, rhobbin@firstenergycorp.com | OH |  | RESTRICTIVE | 06-22-15 A
374 | -- | 374 | 8061 | 83332 | 10300400300433 | 10 | Butler | MCCALMONT NO.1 | SR3004 | CONNOQUENESSING CR | 10/101 - BUTLER | 40.8194 | -79.9457 | 20150300985 |  | all facilities responded clear per one call |  |  |  |  | 2016-08-05
375a | -- | 375 | 8071 | 24703 | 10301000600000 | 10 | Butler | BROWNSDALE ROAD | SR3010 | GLADE RUN | 10/215 - FORWARD | 40.7786 | -80.0096 | 20143571422 | gas | Peoples TWP LLC/TW Phillips | Mike Shearer, 724-287-2751, mike.shearer@peoplestwp.com | UG |  |  | 2016-07-08
375b | -- | 375 | 8071 | 24703 | 10301000600000 | 10 | Butler | BROWNSDALE ROAD | SR3010 | GLADE RUN | 10/215 - FORWARD | 40.7786 | -80.0096 | 20143571422 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com |  |  |  | 2016-07-08
376a | Y | 376 | 8073 | 83335 | 10301200500000 | 10 | Butler | CRUIKSHANK ROAD | LR10013,SR3012 | TRIB TO GLADE RUN | 10/222 - MIDDLESEX | 40.7394 | -79.9596 | 20140510700 | Elect | ARMSTRONG | Michael Cratty, 724-452-5695 | OH |  | Not Affected | 06-24-15 A
376b | Y | 376 | 8073 | 83335 | 10301200500000 | 10 | Butler | CRUIKSHANK ROAD | LR10013,SR3012 | TRIB TO GLADE RUN | 10/222 - MIDDLESEX | 40.7394 | -79.9596 | 20140510700 | Elect | WEST PENN POWER COMPANY | Rick Hobbins, 724-334-5237 | OH |  | Not Affected | 06-24-15 A
377a | -- | 377 | 8104 | 77989 | 10302700500194 | 10 | Butler | SENACA SCHOOL | SR3027 | LIT CONNOQUENESSING CR | 10/217 - JACKSON | 40.8102 | -80.1082 | 20151420256 | gas | PEOPLES NATURAL GAS COMPANY LLC | Christopher (Chris) Carlisle, christopher.carlisle@peoples-gas.com, 412-398-4543 | UG |  |  | 2017-03-06
377b | -- | 377 | 8104 | 77989 | 10302700500194 | 10 | Butler | SENACA SCHOOL | SR3027 | LIT CONNOQUENESSING CR | 10/217 - JACKSON | 40.8102 | -80.1082 | 20151420256 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | Both |  |  | 2017-03-06
378 | -- | 378 | 8113 | 89967 | 10400201302768 | 10 | Butler | SOUTH OF QUEEN JCT. | SR4002 | B & LE RR | 10/207 - CLAY | 40.9603 | -79.9313 | 20143580231 | comm | Centurylink formerly Embarq | Leo Hilbert, leo.c.hilbert@centurylink.com |  |  |  | 2016-05-19
379a | -- | 379 | 8334 | 24710 | 10800505000898 | 10 | Butler | ROCK LAKE SB RAMP NO.2 | SR8005 SB (RAMP F) | SR0019 NB | 10/217 - JACKSON | 40.7734 | -80.1304 | 20150341137 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com |  |  |  | 2017-04-11
379b | -- | 379 | 8334 | 24710 | 10800505000898 | 10 | Butler | ROCK LAKE SB RAMP NO.2 | SR8005 SB (RAMP F) | SR0019 NB | 10/217 - JACKSON | 40.7734 | -80.1304 | 20150341137 | sanitary | WESTERN BUTLER COUNTY AUTHORITY | Autumn Heckathorn, wbca@zoominternet.net | UG |  |  | 2017-04-11
379c | -- | 379 | 8334 | 24710 | 10800505000898 | 10 | Butler | ROCK LAKE SB RAMP NO.2 | SR8005 SB (RAMP F) | SR0019 NB | 10/217 - JACKSON | 40.7734 | -80.1304 | 20150341137 | gas | Peoples Gas (Equitable Gas) | Chris Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | UG |  |  | 2017-04-11
380a | -- | 380 | 10975 | 83229 | 16032201801102 | 10 | Clarion | SHIPPENVILLE STATION | SR0322 | DEER CREEK | 16/205 - ELK | 41.256 | -79.4723 | 20150330217 | gas | Gas City Oil and Gas Corp | John Exley, neigroup@aol.com |  |  |  | 2016-06-08
380b | -- | 380 | 10975 | 83229 | 16032201801102 | 10 | Clarion | SHIPPENVILLE STATION | SR0322 | DEER CREEK | 16/205 - ELK | 41.256 | -79.4723 | 20150330217 |  | Northeastern ITS | John Bruce at (877) 601-7662; William Hosack, william.hosack@spreadnetworks.com | UG |  |  | 2016-06-08
380c | -- | 380 | 10975 | 83229 | 16032201801102 | 10 | Clarion | SHIPPENVILLE STATION | SR0322 | DEER CREEK | 16/205 - ELK | 41.256 | -79.4723 | 20150330217 | Elect | Pennsylvania Electric Company | John Forbes, 814-868-8706, jforbes@firstenergy.com |  |  |  | 2016-06-08
380d | -- | 380 | 10975 | 83229 | 16032201801102 | 10 | Clarion | SHIPPENVILLE STATION | SR0322 | DEER CREEK | 16/205 - ELK | 41.256 | -79.4723 | 20150330217 | gas | Pine Roe Natural Gas Co | John Habjan, 814-227-2611 | UG |  |  | 2016-06-08
381a | -- | 381 | 10997 | 83232 | 16086100421587 | 10 | Clarion | WILDCAT NO.2 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0299 | -79.4817 | 20150330310 | Comm | Comcast Cable Communications, Inc. | Gary Barnett, gary_barnett@cable.comcast.com |  |  |  | 2016-06-16
381b | -- | 381 | 10997 | 83232 | 16086100421587 | 10 | Clarion | WILDCAT NO.2 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0299 | -79.4817 | 20150330310 |  | Madison TWP Clarion Co | Denny Montgomery, 814-473-6307 | UG |  |  | 2016-06-16
381c | -- | 381 | 10997 | 83232 | 16086100421587 | 10 | Clarion | WILDCAT NO.2 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0299 | -79.4817 | 20150330310 | gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2016-06-16
382a | -- | 382 | 10996 | 83234 | 16086100620656 | 10 | Clarion | DIAMOND NO.1 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0233 | -79.4814 | 20150330289 | Comm | Comcast Cable Communications, Inc. | Gary Barnett, gary_barnett@cable.comcast.com |  |  |  | 2016-06-17
382b | -- | 382 | 10996 | 83234 | 16086100620656 | 10 | Clarion | DIAMOND NO.1 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0233 | -79.4814 | 20150330289 |  | Madison TWP Clarion Co | Denny Montgomery, 814-473-6307 | UG |  |  | 2016-06-17
382c | -- | 382 | 10996 | 83234 | 16086100620656 | 10 | Clarion | DIAMOND NO.1 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0233 | -79.4814 | 20150330289 | Elect | West Penn Power | Lisa Marinelli, 724-830-5629, lmarine@firstenergycorp.com |  |  |  | 2016-06-17
382d | -- | 382 | 10996 | 83234 | 16086100620656 | 10 | Clarion | DIAMOND NO.1 | SR0861 | WILDCAT RUN | 16/211 - MADISON | 41.0233 | -79.4814 | 20150330289 | gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2016-06-17
383a | -- | 383 | 11042 | 25221 | 16200900100000 | 10 | Clarion | LAWSONHAM NO.1 | SR2009 | REDBANK CREEK | 16/211 - MADISON | 40.995 | -79.4857 | 20150341764, 20150341774 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2017-05-11
383b | -- | 383 | 11042 | 25221 | 16200900100000 | 10 | Clarion | LAWSONHAM NO.1 | SR2009 | REDBANK CREEK | 16/211 - MADISON | 40.995 | -79.4857 | 20150341764, 20150341774 | Comm | Comcast Cable Communications, Inc. | Gary Barnett, gary_barnett@cable.comcast.com |  |  |  | 2017-05-11
383c | -- | 383 | 11042 | 25221 | 16200900100000 | 10 | Clarion | LAWSONHAM NO.1 | SR2009 | REDBANK CREEK | 16/211 - MADISON | 40.995 | -79.4857 | 20150341764, 20150341774 | Elect | West Penn Power | Lisa Marinelli, 724-830-5629, lmarine@firstenergycorp.com |  |  |  | 2017-05-11
384a | -- | 384 | 11049 | 83241 | 16200902200128 | 10 | Clarion | ELDER ROAD | SR2009 | CHERRY RUN | 16/209 - LICKING | 41.1131 | -79.5653 | 20151461574 |  | Licking TWP | 814-358-2250, lickingtwp@windstream.net, 152 Canoe Ripple Road Sligo, PA 16255 |  |  |  | 2017-07-24
384b | -- | 384 | 11049 | 83241 | 16200902200128 | 10 | Clarion | ELDER ROAD | SR2009 | CHERRY RUN | 16/209 - LICKING | 41.1131 | -79.5653 | 20151461574 | Gas | UGI Central Penn Gas | Roy Carr (570) 829-8967 | UG |  |  | 2017-07-24
384c | -- | 384 | 11049 | 83241 | 16200902200128 | 10 | Clarion | ELDER ROAD | SR2009 | CHERRY RUN | 16/209 - LICKING | 41.1131 | -79.5653 | 20151461574 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com;Joseph (Joe) Green, Joseph.Green@windstream.com, 319-790-7510 | Both |  |  | 2017-07-24
385a | -- | 385 | 11088 | 83256 | 16401500301431 | 10 | Clarion | HUEFNER NO.3 | SR4015 | LICKING CREEK | 16/208 - KNOX | 41.3144 | -79.3887 | 20151413050 | Comm | ARMSTRONG | Scott Bowser, 724-482-4885 ext. 224, Cell 724-321-5800, sbowser@agoc.com |  |  |  | 2017-05-26
385b | -- | 385 | 11088 | 83256 | 16401500301431 | 10 | Clarion | HUEFNER NO.3 | SR4015 | LICKING CREEK | 16/208 - KNOX | 41.3144 | -79.3887 | 20151413050 |  | Knox TWP | 814-221-1234, jacquiblose@gmail.com, 27345 Route 66 Lucinda, PA 16235 |  |  |  | 2017-05-26
385c | -- | 385 | 11088 | 83256 | 16401500301431 | 10 | Clarion | HUEFNER NO.3 | SR4015 | LICKING CREEK | 16/208 - KNOX | 41.3144 | -79.3887 | 20151413050 | Gas | UGI Central Penn Gas | Roy Carr (570) 829-8967 | UG |  |  | 2017-05-26
385d | -- | 385 | 11088 | 83256 | 16401500301431 | 10 | Clarion | HUEFNER NO.3 | SR4015 | LICKING CREEK | 16/208 - KNOX | 41.3144 | -79.3887 | 20151413050 | Comm | Verizon | Cindy Oberholtzer, coberholtzer@usceng.com | UG |  |  | 2017-05-26
385e | -- | 385 | 11088 | 83256 | 16401500301431 | 10 | Clarion | HUEFNER NO.3 | SR4015 | LICKING CREEK | 16/208 - KNOX | 41.3144 | -79.3887 | 20151413050 | Gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2017-05-26
386a | -- | 386 | 19087 | 83293 | 32028601500520 | 10 | Indiana | CLARKSBURG NO.3 | SR0286 | BLACKLEGS CREEK | 32/224 - YOUNG | 40.5371 | -79.3754 | 20151421304 | wtr | Indiana County Municipal Services Authority | Dan Fmura, Gibson-Thomas Engineering Co, Inc, dan.fmura@gibson-thomas.com, 724-539-8562 | UG |  |  | 2017-05-22
386b | -- | 386 | 19087 | 83293 | 32028601500520 | 10 | Indiana | CLARKSBURG NO.3 | SR0286 | BLACKLEGS CREEK | 32/224 - YOUNG | 40.5371 | -79.3754 | 20151421304 |  | KASTLE RESOURCES ENTERPRISES INC | Jesse Welcheck, 814-602-6231, jwelcheck25@gmail.com |  |  |  | 2017-05-22
386c | -- | 386 | 19087 | 83293 | 32028601500520 | 10 | Indiana | CLARKSBURG NO.3 | SR0286 | BLACKLEGS CREEK | 32/224 - YOUNG | 40.5371 | -79.3754 | 20151421304 | Gas | Peoples Gas (Equitable Gas) | Michelle Saxion, 412-208-7239 | UG |  |  | 2017-05-22
387 | -- | 387 | 19183 | 95851 | 32055302000620 | 10 | Indiana | ALVERDA NO.2 | SR0553 | DUTCH RUN | 32/217 - PINE | 40.6265 | -78.8533 | 20150330361 |  | all facilities responded clear per one call |  |  |  |  | 2016-06-17
388a | -- | 388 | 19200 | 25780 | 32095403700000 | 10 | Indiana | WILLET | SR0954 | SOUTH BRANCH PLUM CREEK | 32/220 - WASHINGTON | 40.7287 | -79.2014 | 20143580238 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com. Email him first and he will verify if that is area or get you to the right person |  |  |  | 2016-05-26
388b | -- | 388 | 19200 | 25780 | 32095403700000 | 10 | Indiana | WILLET | SR0954 | SOUTH BRANCH PLUM CREEK | 32/220 - WASHINGTON | 40.7287 | -79.2014 | 20143580238 |  | XTO Energy Inc/Mountain Gathering LLC | Jerry Ondrizek, 412-585-2828, jerry_ondrizek@xtoenergy.com Derek Folmer, 724-772-9594, derek_folmer@xtoenergy.com |  |  |  | 2016-05-26
389a | -- | 389 | 19320 | 25584 | 32300701200000 | 10 | Indiana | MARSHALL RUN NO.2 | SR3007 | MARSHALL RUN | 32/210 - CONEMAUGH | 40.5283 | -79.3752 | 20151462676 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com. Email him first and he will verify if that is area or get you to the right person |  |  |  | 2017-07-24
389b | -- | 389 | 19320 | 25584 | 32300701200000 | 10 | Indiana | MARSHALL RUN NO.2 | SR3007 | MARSHALL RUN | 32/210 - CONEMAUGH | 40.5283 | -79.3752 | 20151462676 | gas | Peoples Gas (Equitable Gas) | Michelle Saxion, 412-208-7239 | UG |  |  | 2017-07-24
389c | -- | 389 | 19320 | 25584 | 32300701200000 | 10 | Indiana | MARSHALL RUN NO.2 | SR3007 | MARSHALL RUN | 32/210 - CONEMAUGH | 40.5283 | -79.3752 | 20151462676 | gas | XTO Energy | Jerry Onderizek, 412-585-2828 | UG |  |  | 2017-07-24
390a | -- | 390 | 19392 | 78120 | 32401000100530 | 10 | Indiana | KIMMEL RD NO.1 | SR4010 | CROOKED CREEK | 32/218 - RAYNE | 40.7137 | -79.1285 | 20150350459 | Elect | Pennsylvania Electric Company | Dale Shaner, 814-590-0256, dshaner@firstenergycorp.com. Email him first and he will verify if that is area or get you to the right person |  |  |  | 2017-05-11
390b | -- | 390 | 19392 | 78120 | 32401000100530 | 10 | Indiana | KIMMEL RD NO.1 | SR4010 | CROOKED CREEK | 32/218 - RAYNE | 40.7137 | -79.1285 | 20150350459 | gas | Peoples TWP LLC/TW Phillips | Mike Shearer, 724-287-2751, mike.shearer@peoplestwp.com | UG |  |  | 2017-05-11
391a | -- | 391 | 19550 | 83282 | 33003601701535 | 10 | Jefferson | CLOE NO.1 | SR0036 | CANOE CREEK | 33/203 - BELL | 40.9365 | -78.9339 | 20150170060 | Gas | KRIEBEL MINERALS INC | James Foley, 717-574-2045 (works for premier representing Kriebel) | UG |  |  | 2016-06-17
391b | -- | 391 | 19550 | 83282 | 33003601701535 | 10 | Jefferson | CLOE NO.1 | SR0036 | CANOE CREEK | 33/203 - BELL | 40.9365 | -78.9339 | 20150170060 | Wtr | Pennsylvania American Water CO | Bill Smith, 724-463-9830 | UG |  |  | 2016-06-17
391c | -- | 391 | 19550 | 83282 | 33003601701535 | 10 | Jefferson | CLOE NO.1 | SR0036 | CANOE CREEK | 33/203 - BELL | 40.9365 | -78.9339 | 20150170060 | gas | Peoples TWP LLC/TW Phillips | Jim Shaffer, 724-286-9010, John Carr, John.Carr@peoples-gas.com, 724-431-4985 | UG |  |  | 2016-06-17
392a | -- | 392 | 19699 | 83312 | 33200300700000 | 10 | Jefferson | FOXBURG | SR2003 | MAHONING CREEK | 33/401 - BIG RUN | 40.9642 | -78.8798 | 20151420341, 20151420342 | sanitary | Big Run Area Municipal Authority | 814-427-5091 | UG |  |  | 2017-05-30
392b | -- | 392 | 19699 | 83312 | 33200300700000 | 10 | Jefferson | FOXBURG | SR2003 | MAHONING CREEK | 33/401 - BIG RUN | 40.9642 | -78.8798 | 20151420341, 20151420342 | gas | Peoples TWP LLC/TW Phillips | Jim Shaffer, 724-286-9010, John Carr, John.Carr@peoples-gas.com, 724-431-4985 | UG |  |  | 2017-05-30
392c | -- | 392 | 19699 | 83312 | 33200300700000 | 10 | Jefferson | FOXBURG | SR2003 | MAHONING CREEK | 33/401 - BIG RUN | 40.9642 | -78.8798 | 20151420341, 20151420342 | Comm | Comcast Cable Communications, Inc. | David Bowen, 800-892-7300 |  |  |  | 2017-05-30
393 | -- | 393 | 19708 | 26151 | 33200802100200 | 10 | Jefferson | STUMP CREEK NO.2 | SR2008 | STUMP CREEK (CROSSING @ LOW) | 33/208 - HENDERSON | 41.0137 | -78.8303 | 20151462771 | gas | Peoples TWP LLC/TW Phillips | Jim Shaffer, 724-286-9010, John Carr, John.Carr@peoples-gas.com, 724-431-4985 | UG |  |  | 2017-07-24
394a | -- | 394 | 19737 | 26069 | 33300302500000 | 10 | Jefferson | NEAR OHL NO. 1 | SR3003 | BEAVER RUN | 33/202 - BEAVER | 41.0894 | -79.1532 | 20151420498 |  | Beaver TWP | 324 Tippecanoe Road Knox, PA 16232. 814-797-1408, beavertownship@windstream.net, hours M,TUE,F 9-3pm |  |  |  | 2017-05-26
394b | -- | 394 | 19737 | 26069 | 33300302500000 | 10 | Jefferson | NEAR OHL NO. 1 | SR3003 | BEAVER RUN | 33/202 - BEAVER | 41.0894 | -79.1532 | 20151420498 | GAS | National Fuel Supply/National Fuel Brook | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2017-05-26
394c | -- | 394 | 19737 | 26069 | 33300302500000 | 10 | Jefferson | NEAR OHL NO. 1 | SR3003 | BEAVER RUN | 33/202 - BEAVER | 41.0894 | -79.1532 | 20151420498 | gas | Peoples TWP LLC/TW Phillips | Jim Shaffer, 724-286-9010, John Carr, John.Carr@peoples-gas.com, 724-431-4985 | UG |  |  | 2017-05-26
395a | -- | 395 | 19807 | 83343 | 33400100700000 | 10 | Jefferson | NORTH OF ROSEVILLE | SR4001 | MILL CREEK | 33/219 - UNION | 41.2136 | -79.1473 | 20151420538, 20151420539 |  | Union TWP Jefferson Township | David Mathies (secy) 724-348-4250 |  |  |  | 2017-05-26
395b | -- | 395 | 19807 | 83343 | 33400100700000 | 10 | Jefferson | NORTH OF ROSEVILLE | SR4001 | MILL CREEK | 33/219 - UNION | 41.2136 | -79.1473 | 20151420538, 20151420539 |  | Eldred TWP Municipal Authority | 814-752-2881 |  |  |  | 2017-05-26
395c | -- | 395 | 19807 | 83343 | 33400100700000 | 10 | Jefferson | NORTH OF ROSEVILLE | SR4001 | MILL CREEK | 33/219 - UNION | 41.2136 | -79.1473 | 20151420538, 20151420539 | GAS | National Fuel Supply/National Fuel Brook | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2017-05-26
396a | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | 20150420290 | sanitary | Richland TWP | Jerry Reichart, 724-4443-5921, JREICHART@RICHLAND.PA.US | UG |  |  | 2016-07-11
396b | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | 20150420290 | GAS | Peoples Gas Design Gibsonia | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  |  | 2016-07-11
396c | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | 20150420290 | Comm | Consolidated Communications | Jeff Hall, 724-443-9639, Jeff.Hall@consolidated.com Gabe White, 724-443-9832, gabe.white@consolidated.com | OH |  |  | 2016-07-11
396d | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | 20150420290 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  |  | 2016-07-11
396e | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | 20150420290 | Comm | SUNESYS | Aaron Phillips, 412.779.5277 APhillips@sunesys.com | OH |  |  | 2016-07-11
396f | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | 20150420290 | Comm | ARMSTRONG | Michael Cratty, 724-452-5695, mcratty@agoc.com | OH |  |  | 2016-07-11
396g | -- | 396 | 505 | 62523 | 2000804101108 | 11 | Allegheny | @ INTERSECTION W/SR 0910 | WM.FLYNN HW | WEST BRANCH DEER CREEK | 02/217 - RICHLAND | 40.6347 | -79.9399 | 20150420290 | Comm | Verizon | Gary Redondo, 412-667-8618, gary.redondo@verizon.com | OH |  |  | 2016-07-11
397a | -- | 397 | 659 | 27272 | 2003001202263 | 11 | Allegheny | 400 FEET SE OF SR 3070 | LINCOLN HW | SOUTH FORK MONTOUR RUN | 02/214 - NORTH FAYETTE | 40.45 | -80.2504 | 20150161192 | gas | Peoples Gas of Hopewell Division | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-05-20
397b | -- | 397 | 659 | 27272 | 2003001202263 | 11 | Allegheny | 400 FEET SE OF SR 3070 | LINCOLN HW | SOUTH FORK MONTOUR RUN | 02/214 - NORTH FAYETTE | 40.45 | -80.2504 | 20150161192 | Elect | West Penn Power | Dan Henry, 724-838-6126, dhenry2@firstenergycorp.com |  |  |  | 2016-05-20
398a | -- | 398 | 664 | 28154 | 2003001901870 | 11 | Allegheny | @ INTER W/ BRADDOCK ROAD | ARDMORE BL | FALLS RUN | 02/431 - FOREST HILLS | 40.4243 | -79.8594 | 20150420382 | sanitary | Allegheny County Dept of Public Works | Michael Lichte, PE, 412-732-8004, michael.lichte@alcosan.org | UG |  |  | 2016-06-24
398b | -- | 398 | 664 | 28154 | 2003001901870 | 11 | Allegheny | @ INTER W/ BRADDOCK ROAD | ARDMORE BL | FALLS RUN | 02/431 - FOREST HILLS | 40.4243 | -79.8594 | 20150420382 |  | Forest Hills Borough | Steve Morus (manager/secy), 412-351-7330 | UG |  |  | 2016-06-24
398c | -- | 398 | 664 | 28154 | 2003001901870 | 11 | Allegheny | @ INTER W/ BRADDOCK ROAD | ARDMORE BL | FALLS RUN | 02/431 - FOREST HILLS | 40.4243 | -79.8594 | 20150420382 | Gas | Peoples Gas Pittsburgh Division | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-06-24
398d | -- | 398 | 664 | 28154 | 2003001901870 | 11 | Allegheny | @ INTER W/ BRADDOCK ROAD | ARDMORE BL | FALLS RUN | 02/431 - FOREST HILLS | 40.4243 | -79.8594 | 20150420382 | wtr | Wilkinsburg Penn Joint Water Auth | Bill Grassi, 412-728-6847, Gary Melvin, 412-243-6163 | UG | 6, 12, and 16" |  | 2016-06-24
399a | -- | 399 | 709 | 73522 | 2005100802710 | 11 | Allegheny | @ INTER.W/WEIGEL HILL RD. | SR 0051 | FALLEN TIMBER RUN | 02/105 - ELIZABETH | 40.2642 | -79.8786 | 20150420486, 20150420487 |  | Forward TWP | 724-258-7895 | UG |  |  | 2017-02-13
399b | -- | 399 | 709 | 73522 | 2005100802710 | 11 | Allegheny | @ INTER.W/WEIGEL HILL RD. | SR 0051 | FALLEN TIMBER RUN | 02/105 - ELIZABETH | 40.2642 | -79.8786 | 20150420486, 20150420487 | Gas | Peoples Gas Design Monongahela | Mary M. Vitalbo-Madden, 724-292-3415 | UG |  |  | 2017-02-13
399c | -- | 399 | 709 | 73522 | 2005100802710 | 11 | Allegheny | @ INTER.W/WEIGEL HILL RD. | SR 0051 | FALLEN TIMBER RUN | 02/105 - ELIZABETH | 40.2642 | -79.8786 | 20150420486, 20150420487 | Gas | Peoples Gas Monongahela Division | Mary M. Vitalbo-Madden, 724-292-3415 | UG |  |  | 2017-02-13
399d | -- | 399 | 709 | 73522 | 2005100802710 | 11 | Allegheny | @ INTER.W/WEIGEL HILL RD. | SR 0051 | FALLEN TIMBER RUN | 02/105 - ELIZABETH | 40.2642 | -79.8786 | 20150420486, 20150420487 | Elect | West Penn Power | Dave Lucas, 724-838-6126 |  |  |  | 2017-02-13
399e | -- | 399 | 709 | 73522 | 2005100802710 | 11 | Allegheny | @ INTER.W/WEIGEL HILL RD. | SR 0051 | FALLEN TIMBER RUN | 02/105 - ELIZABETH | 40.2642 | -79.8786 | 20150420486, 20150420487 | wtr | Municipal Auth of Westmoreland Cnty | April Tilson, 724-755-5955, atilson@mawc.org | UG | 8" |  | 2017-02-13
399f | -- | 399 | 709 | 73522 | 2005100802710 | 11 | Allegheny | @ INTER.W/WEIGEL HILL RD. | SR 0051 | FALLEN TIMBER RUN | 02/105 - ELIZABETH | 40.2642 | -79.8786 | 20150420486, 20150420487 |  | Elizabeth TWP AUTH | 412-751-2880 | UG |  |  | 2017-02-13
| R | 400 | 41065 | #REF! | 2013000420000 | 11 | Allegheny | 1 1/2 MILES E. OF PA 8 | #N/A | ABANDONED RR | 02/105 - ELIZABETH | 40.2642 | -79.8786 | [7 empty] | 2017-02-13
| R | 401 | 41066 | #REF! | 2013000420165 | 11 | Allegheny | 1 1/2 MILES E. OF PA 8 | #N/A | ABANDONED RR | 02/105 - ELIZABETH | 40.2642 | -79.8786 | [7 empty] | 2017-02-13
402a | -- | 402 | 954 | 37590 | 2013600500000 | 11 | Allegheny | 2 MI EAST OF MON CITY BR | MONONGAHELA RD | MON RIVER TRIBUTARY | 02/204 - FORWARD | 40.1978 | -79.8883 | 20143580439 | GAS | Peoples Gas (Equitable Gas) | Janis Saltzman, 412-395-3116, Janice.Kraus@Peoples-Gas.com Rocky Saporito, PE, 412-473-4163, rocky.saporito@peoples-gas.com | UG |  |  | 2016-06-17
402b | -- | 402 | 954 | 37590 | 2013600500000 | 11 | Allegheny | 2 MI EAST OF MON CITY BR | MONONGAHELA RD | MON RIVER TRIBUTARY | 02/204 - FORWARD | 40.1978 | -79.8883 | 20143580439 | Wtr | Municipal Auth of Westmoreland Cnty | Donald Guerra, PE, daguerra@mawc.org, Chris Kerr, 724-834-6500, John P. Shuey, 1-800-887-9190, M. Curtis Fontaine, PE, fontaine@mawc.org | UG | 8" |  | 2016-06-17
402c | -- | 402 | 954 | 37590 | 2013600500000 | 11 | Allegheny | 2 MI EAST OF MON CITY BR | MONONGAHELA RD | MON RIVER TRIBUTARY | 02/204 - FORWARD | 40.1978 | -79.8883 | 20143580439 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com | OH |  |  | 2016-06-17
403a | -- | 403 | 961 | 28597 | 2013601202172 | 11 | Allegheny | 100'W.OF INTER W/SR 2017 | WEST NEWTON RD | BRANCH OF GILLESPIE RUN | 02/105 - ELIZABETH | 40.2146 | -79.8275 | 20143580328 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | OH |  |  | 2016-05-19
403b | -- | 403 | 961 | 28597 | 2013601202172 | 11 | Allegheny | 100'W.OF INTER W/SR 2017 | WEST NEWTON RD | BRANCH OF GILLESPIE RUN | 02/105 - ELIZABETH | 40.2146 | -79.8275 | 20143580328 | Wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | UG |  |  | 2016-05-19
403b | -- | 403 | 961 | 28597 | 2013601202172 | 11 | Allegheny | 100'W.OF INTER W/SR 2017 | WEST NEWTON RD | BRANCH OF GILLESPIE RUN | 02/105 - ELIZABETH | 40.2146 | -79.8275 | 20143580328 | Comm | Verizon | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | OH |  |  | 2016-05-19
403b | -- | 403 | 961 | 28597 | 2013601202172 | 11 | Allegheny | 100'W.OF INTER W/SR 2017 | WEST NEWTON RD | BRANCH OF GILLESPIE RUN | 02/105 - ELIZABETH | 40.2146 | -79.8275 | 20143580328 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | OH |  |  | 2016-05-19
404a | -- | 404 | 1334 | 63321 | 2091002400485 | 11 | Allegheny | 1 MILE EAST OF RT 8 INT | GIBSONIA RD | WEST BRANCH OF DEER CREEK | 02/217 - RICHLAND | 40.625 | -79.9265 | 20150341089 | sanitary | Richland TWP | 724-443-5921 | UG |  |  | 2017-02-24
404b | -- | 404 | 1334 | 63321 | 2091002400485 | 11 | Allegheny | 1 MILE EAST OF RT 8 INT | GIBSONIA RD | WEST BRANCH OF DEER CREEK | 02/217 - RICHLAND | 40.625 | -79.9265 | 20150341089 | Gas | Peoples Gas (Equitable Gas) | Christopher (Chris) Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | UG |  |  | 2017-02-24
405a | Y | 405 | 1339 | 63324 | 2091003000000 | 11 | Allegheny | 250' SOUTH OF SR 1020 | GIBSONIA RD | DEER CREEK | 02/220 - WEST DEER | 40.6069 | -79.8913 | 20140162107 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | CONDITIONAL RESTRICTION | 2015-07-22
405b | Y | 405 | 1339 | 63324 | 2091003000000 | 11 | Allegheny | 250' SOUTH OF SR 1020 | GIBSONIA RD | DEER CREEK | 02/220 - WEST DEER | 40.6069 | -79.8913 | 20140162107 | Comm | CONSOLIDATED COMMUNICATIONS OF PA COMPANY, LLC | Harry R Brown, 724 443-9535 or Jeff Hall, 724-443-9639 | OH |  | Not Affected | 2015-07-22
405c | Y | 405 | 1339 | 63324 | 2091003000000 | 11 | Allegheny | 250' SOUTH OF SR 1020 | GIBSONIA RD | DEER CREEK | 02/220 - WEST DEER | 40.6069 | -79.8913 | 20140162107 | Comm | COMCAST CABLE CORPORATION | Rick Moslen, 412-999-0590 or Kent Norton, 724-594-0063 | OH |  | Not Affected | 2015-07-22
405d | Y | 405 | 1339 | 63324 | 2091003000000 | 11 | Allegheny | 250' SOUTH OF SR 1020 | GIBSONIA RD | DEER CREEK | 02/220 - WEST DEER | 40.6069 | -79.8913 | 20140162107 | Wtr | Oakmont Muni Auth | John Dunlap, 412-828-7220 or Jim McCaskey, 412-327-0096 | UG |  | Not Affected | 2015-07-22
405e | Y | 405 | 1339 | 63324 | 2091003000000 | 11 | Allegheny | 250' SOUTH OF SR 1020 | GIBSONIA RD | DEER CREEK | 02/220 - WEST DEER | 40.6069 | -79.8913 | 20140162107 | Wtr | SUNESYS, INC. | Dave Hayward, 267-927-2000 or Mike Coudriet, 412-462-4561X2353 | UG |  | Not Affected | 2015-07-22
405f | Y | 405 | 1339 | 63324 | 2091003000000 | 11 | Allegheny | 250' SOUTH OF SR 1020 | GIBSONIA RD | DEER CREEK | 02/220 - WEST DEER | 40.6069 | -79.8913 | 20140162107 | Unk | Deer Creek Drainage Basin | Enoch Jenkins, 724-265-5315 | UG |  | Not Affected | 2015-07-22
406a | -- | 406 | 1346 | 78185 | 2097800300000 | 11 | Allegheny | 2000'N. OF SR 3001 | MILLER'S RUN RD | FISHING RUN | 02/119 - SOUTH FAYETTE | 40.347 | -80.1695 | 20143580332 | Gas | Columbia Gas of PA Design | Dominic Tarella, dtarella@nisource.com, 724-462-3479 Stephanie Hardenstine Field Engineer Cell: 412-584-5015 Office: 412-220-1531 | UG |  |  | 2016-04-04
406b | -- | 406 | 1346 | 78185 | 2097800300000 | 11 | Allegheny | 2000'N. OF SR 3001 | MILLER'S RUN RD | FISHING RUN | 02/119 - SOUTH FAYETTE | 40.347 | -80.1695 | 20143580332 | SS | South Fayette TWP Municipal Auth | Jerry Brown, (412) 257-5100, jbrown@sftwp.com | UG |  |  | 2016-04-04
406c | -- | 406 | 1346 | 78185 | 2097800300000 | 11 | Allegheny | 2000'N. OF SR 3001 | MILLER'S RUN RD | FISHING RUN | 02/119 - SOUTH FAYETTE | 40.347 | -80.1695 | 20143580332 | Wtr | Pennsylvania American Water CO | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | UG |  |  | 2016-04-04
406d | -- | 406 | 1346 | 78185 | 2097800300000 | 11 | Allegheny | 2000'N. OF SR 3001 | MILLER'S RUN RD | FISHING RUN | 02/119 - SOUTH FAYETTE | 40.347 | -80.1695 | 20143580332 | Elect | West Penn Power | Scott Curcio, 724-796-1021 scurcio@firstenergycorp.com | OH |  |  | 2016-04-04
406e | -- | 406 | 1346 | 78185 | 2097800300000 | 11 | Allegheny | 2000'N. OF SR 3001 | MILLER'S RUN RD | FISHING RUN | 02/119 - SOUTH FAYETTE | 40.347 | -80.1695 | 20143580332 | Comm | Verizon | Daniel Barren, 412-633-4341, daniel.barren@1.verizon.com | OH |  |  | 2016-04-04
406f | -- | 406 | 1346 | 78185 | 2097800300000 | 11 | Allegheny | 2000'N. OF SR 3001 | MILLER'S RUN RD | FISHING RUN | 02/119 - SOUTH FAYETTE | 40.347 | -80.1695 | 20143580332 | Comm | Comcast Cable Communications, Inc. | Craig Tacy, 724-503-4362, Craig_Tacy@cable.comcast.com | OH |  |  | 2016-04-04
407a | -- | 407 | 1365 | 27185 | 2100102101194 | 11 | Allegheny | BARGE BASIN O/ABNDONED RR | FREEPORT RD | ABANDONED RR TRACK | 02/208 - HARMAR | 40.5314 | -79.8484 | 20143580503 | Comm | WINDSTREAM | Dustin Velcoff, 501-748-4434, dustin.velcoff@windstream.com |  |  |  | 2017-02-16
407b | -- | 407 | 1365 | 27185 | 2100102101194 | 11 | Allegheny | BARGE BASIN O/ABNDONED RR | FREEPORT RD | ABANDONED RR TRACK | 02/208 - HARMAR | 40.5314 | -79.8484 | 20143580503 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2017-02-16
407c | -- | 407 | 1365 | 27185 | 2100102101194 | 11 | Allegheny | BARGE BASIN O/ABNDONED RR | FREEPORT RD | ABANDONED RR TRACK | 02/208 - HARMAR | 40.5314 | -79.8484 | 20143580503 | Comm | AT&T Local Services | Nancy Spence, spence@ems.att.com |  |  |  | 2017-02-16
407d | -- | 407 | 1365 | 27185 | 2100102101194 | 11 | Allegheny | BARGE BASIN O/ABNDONED RR | FREEPORT RD | ABANDONED RR TRACK | 02/208 - HARMAR | 40.5314 | -79.8484 | 20143580503 | sanitary | TWP of Harmar | Mike Ziencik, harmar701@comcast.net | UG |  |  | 2017-02-16
407e | -- | 407 | 1365 | 27185 | 2100102101194 | 11 | Allegheny | BARGE BASIN O/ABNDONED RR | FREEPORT RD | ABANDONED RR TRACK | 02/208 - HARMAR | 40.5314 | -79.8484 | 20143580503 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2017-02-16
408a | -- | 408 | 1372 | 27188 | 2100103502537 | 11 | Allegheny | @ J.F.K.ELEM.SCHOOL | FREEPORT RD | CRAWFORD RUN | 02/104 - EAST DEER | 40.5816 | -79.7787 | 20150411801 | sanitary | Allegheny County Dept of Public Works | Michael Lichte, PE, 412-732-8004, michael.lichte@alcosan.org | UG |  |  | 2017-05-22
408b | -- | 408 | 1372 | 27188 | 2100103502537 | 11 | Allegheny | @ J.F.K.ELEM.SCHOOL | FREEPORT RD | CRAWFORD RUN | 02/104 - EAST DEER | 40.5816 | -79.7787 | 20150411801 |  | East Deer TWP | 724-224-3434 | UG |  |  | 2017-05-22
408c | -- | 408 | 1372 | 27188 | 2100103502537 | 11 | Allegheny | @ J.F.K.ELEM.SCHOOL | FREEPORT RD | CRAWFORD RUN | 02/104 - EAST DEER | 40.5816 | -79.7787 | 20150411801 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG | 20" |  | 2017-05-22
408d | -- | 408 | 1372 | 27188 | 2100103502537 | 11 | Allegheny | @ J.F.K.ELEM.SCHOOL | FREEPORT RD | CRAWFORD RUN | 02/104 - EAST DEER | 40.5816 | -79.7787 | 20150411801 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2017-05-22
408e | -- | 408 | 1372 | 27188 | 2100103502537 | 11 | Allegheny | @ J.F.K.ELEM.SCHOOL | FREEPORT RD | CRAWFORD RUN | 02/104 - EAST DEER | 40.5816 | -79.7787 | 20150411801 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Aldona (Ann) Pilarczyk 319-790-6779, Aldona.Pilarczyk@windstream.com |  |  |  | 2017-05-22
409a | -- | 409 | 1373 | 28128 | 2100103601567 | 11 | Allegheny | NEAR BAILEY RUN ROAD | FREEPORT RD | BAILEYS RUN | 02/104 - EAST DEER | 40.5864 | -79.7767 | 20150350272 | sanitary | Allegheny County Dept of Public Works | Michael Lichte, PE, 412-732-8004, michael.lichte@alcosan.org | UG |  |  | 2017-04-03
409b | -- | 409 | 1373 | 28128 | 2100103601567 | 11 | Allegheny | NEAR BAILEY RUN ROAD | FREEPORT RD | BAILEYS RUN | 02/104 - EAST DEER | 40.5864 | -79.7767 | 20150350272 |  | East Deer TWP | 724-224-3434 | UG |  |  | 2017-04-03
409c | -- | 409 | 1373 | 28128 | 2100103601567 | 11 | Allegheny | NEAR BAILEY RUN ROAD | FREEPORT RD | BAILEYS RUN | 02/104 - EAST DEER | 40.5864 | -79.7767 | 20150350272 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG | 12" |  | 2017-04-03
409d | -- | 409 | 1373 | 28128 | 2100103601567 | 11 | Allegheny | NEAR BAILEY RUN ROAD | FREEPORT RD | BAILEYS RUN | 02/104 - EAST DEER | 40.5864 | -79.7767 | 20150350272 | Gas | Peoples TWP LLC/TW Phillips | Larry Shane, 724-295-2600, Lawrence.R.Shane@peoples-gas.com | UG |  |  | 2017-04-03
409e | -- | 409 | 1373 | 28128 | 2100103601567 | 11 | Allegheny | NEAR BAILEY RUN ROAD | FREEPORT RD | BAILEYS RUN | 02/104 - EAST DEER | 40.5864 | -79.7767 | 20150350272 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2017-04-03
409f | -- | 409 | 1373 | 28128 | 2100103601567 | 11 | Allegheny | NEAR BAILEY RUN ROAD | FREEPORT RD | BAILEYS RUN | 02/104 - EAST DEER | 40.5864 | -79.7767 | 20150350272 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David (Dave) Ackerman, David.F.Ackerman@windstream.com, 319-790-1464 | UG |  |  | 2017-04-03
410a | -- | 410 | 1390 | 78220 | 2100600402405 | 11 | Allegheny | @ INTERSECT WITH SR 1013 | SAXONBURG BL | BR LITTLE PINE CREEK | 02/209 - INDIANA | 40.5495 | -79.9145 | 20150301463 | sanitary | DEER CREEK DRAINAGE BASIN AUTHORITY | Chuck Debaldo (412) 913-6684 - chuck@deercreekauthority .com | UG |  |  | 2016-07-07
410b | -- | 410 | 1390 | 78220 | 2100600402405 | 11 | Allegheny | @ INTERSECT WITH SR 1013 | SAXONBURG BL | BR LITTLE PINE CREEK | 02/209 - INDIANA | 40.5495 | -79.9145 | 20150301463 | wtr | HAMPTON SHALER WATER AUTHORITY | Sam Scarfone, 412-486-4867 | UG |  |  | 2016-07-07
411a | -- | 411 | 1397 | 89100 | 2101100101018 | 11 | Allegheny | 1028'N.OF FREEPORT RD. | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5355 | -79.8478 | 20150301475 | sanitary | TWP of Harmar | Mike Ziencik, harmar701@comcast.net | UG |  |  | 2016-07-11
411b | -- | 411 | 1397 | 89100 | 2101100101018 | 11 | Allegheny | 1028'N.OF FREEPORT RD. | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5355 | -79.8478 | 20150301475 | wtr | Municipal Auth of Harmar TWP | Andrew Kullen, 724-274-7383 | UG |  |  | 2016-07-11
411c | -- | 411 | 1397 | 89100 | 2101100101018 | 11 | Allegheny | 1028'N.OF FREEPORT RD. | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5355 | -79.8478 | 20150301475 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG | 8" |  | 2016-07-11
411d | -- | 411 | 1397 | 89100 | 2101100101018 | 11 | Allegheny | 1028'N.OF FREEPORT RD. | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5355 | -79.8478 | 20150301475 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2016-07-11
412a | Y | 412 | 1400 | 63342 | 2101100102295 | 11 | Allegheny | 1/2 MI.N.OF SR 0028 | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5377 | -79.851 | 20140162112 | SS | HARMAR TOWNSHIP | Annette Dietz, 724-274-4550 | UG |  | Incorporated | 2016-05-23
412b | Y | 412 | 1400 | 63342 | 2101100102295 | 11 | Allegheny | 1/2 MI.N.OF SR 0028 | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5377 | -79.851 | 20140162112 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 | UG | Unk | Coordinated | 2016-05-23
412c | Y | 412 | 1400 | 63342 | 2101100102295 | 11 | Allegheny | 1/2 MI.N.OF SR 0028 | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5377 | -79.851 | 20140162112 | Elect | West Penn Power | Nick Ensminger, 304-534-7437 | OH |  | Not Affected | 2016-05-23
412d | Y | 412 | 1400 | 63342 | 2101100102295 | 11 | Allegheny | 1/2 MI.N.OF SR 0028 | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5377 | -79.851 | 20140162112 | Tel | Verizon | Deborah D Delia, 412-633-3810 | OH |  | Not Affected | 2016-05-23
412e | Y | 412 | 1400 | 63342 | 2101100102295 | 11 | Allegheny | 1/2 MI.N.OF SR 0028 | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5377 | -79.851 | 20140162112 | Wtr | HARMAR TOWNSHIP MUNICIPAL WATER AUTHORITY | Joe McCullum, 724-274-7383 | UG |  | Incorporated | 2016-05-23
412f | Y | 412 | 1400 | 63342 | 2101100102295 | 11 | Allegheny | 1/2 MI.N.OF SR 0028 | GUYS RUN RD | GUYS RUN | 02/208 - HARMAR | 40.5377 | -79.851 | 20140162112 | TV | Comcast | Mike Gross, 412-875-1147 | OH |  | Not Affected | 2016-05-23
413 | -- | 413 | 1404 | 28603 | 2101200602013 | 11 | Allegheny | 70'E.INTER.W/TWP.RD.613 | CHURCH LN | SHAFERS RUN | 02/209 - INDIANA | 40.5812 | -79.9071 | 20150330137 | Gas | Peoples Gas Gibsonia | Christopher (Chris) Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | UG |  |  | 2016-09-02
414a | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | 20133610627 | Wtr | HAMPTON SHALER WATER AUTHORITY | Sam Scarfone, 412-486-4867 | UG | 6 | Prior | 2016-05-26
414b | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | 20133610627 | Wtr | HAMPTON SHALER WATER AUTHORITY | Sam Scarfone, 412-486-4867 | UG | 6 | RESTRICTIVE | 2016-05-26
414c | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | 20133610627 | Wtr | HAMPTON SHALER WATER AUTHORITY | Sam Scarfone, 412-486-4867 | UG | 6 | Incorporated | 2016-05-26
414d | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SR: 1013, Section A17 - SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | 20133610627 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 or Robert Layhew, 412-444-3231 | UG | 4 | Coordinated | 2016-05-26
414e | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | 20133610627 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | Not Affected | 2016-05-26
414f | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | 20133610627 | SS | SHALER TOWNSHIP | Timothy Rogers, 412-486-9700 | UG |  | Not Affected | 2016-05-26
414g | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | 20133610627 | Comm | COMCAST CABLE CORPORATION | Rick Moslen, 412-999-0590 or Kent Norton, 724-406-4133 | OH | TV | Not Affected | 2016-05-26
414h | Y | 414 | 1405 | 63343 | 2101300202226 | 11 | Allegheny | 4283' N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/118 - SHALER | 40.5206 | -79.9382 | 20133610627 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Ron Ranone, (412) 633-3779 | OH | Tele | Not Affected | 2016-05-26
415a | Y | 415 | 1406 | 63344 | 2101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/112 - OHARA | 40.523 | -79.936 | 20121380869 | Wtr | Hampton-Shaler | Sam Scarfone, 412-486-4867 | UG | 4 | Not Affected | 2015-07-16
415b | Y | 415 | 1406 | 63344 | 2101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/112 - OHARA | 40.523 | -79.936 | 20121380869 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 | UG | 8 | Coordinated | 2015-07-16
415c | Y | 415 | 1406 | 63344 | 2101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | SR: 1013, Section A14 - SAXONBURG BL | LITTLE PINE CREEK | 02/112 - OHARA | 40.523 | -79.936 | 20121380869 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 | UG | 8 | Coordinated | 2015-07-16
415d | Y | 415 | 1406 | 63344 | 2101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/112 - OHARA | 40.523 | -79.936 | 20121380869 | Elect | Duquesne | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | Not Affected | 2015-07-16
415e | Y | 415 | 1406 | 63344 | 2101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/112 - OHARA | 40.523 | -79.936 | 20121380869 | Comm | Verizon | Deborah D Delia, 412-633-3810 | OH | Tele | Not Affected | 2015-07-16
415f | Y | 415 | 1406 | 63344 | 2101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | SAXONBURG BL | LITTLE PINE CREEK | 02/112 - OHARA | 40.523 | -79.936 | 20121380869 | Comm | Comcast | Richard Maslen - (412) 999-0590 Kent Norton (412) 352-7045 | OH | TV | Not Affected | 2015-07-16
416a | Y | 416 | 42177 | 78223 | 2101300400000 | 11 | Allegheny | 2 MILES WEST OF SR 1006 | SAXONBURG BLVD. | BRANCH LITTLE PINE CREEK | 02/112 - OHARA | 40.5273 | -79.927 | 20140162094 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 Shane Moriarty (412) 473-3962 Bob Layhew (724) 444-3231 | UG | 8 | Coordinated | 2015-08-05
416b | Y | 416 | 42177 | 78223 | 2101300400000 | 11 | Allegheny | 2 MILES WEST OF SR 1006 | SAXONBURG BLVD. | BRANCH LITTLE PINE CREEK | 02/112 - OHARA | 40.5273 | -79.927 | 20140162094 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 | UG | 8 | Coordinated | 2015-08-05
416c | Y | 416 | 42177 | 78223 | 2101300400000 | 11 | Allegheny | 2 MILES WEST OF SR 1006 | SAXONBURG BLVD. | BRANCH LITTLE PINE CREEK | 02/112 - OHARA | 40.5273 | -79.927 | 20140162094 | Elect | Duquesne | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | Not Affected | 2015-08-05
416d | Y | 416 | 42177 | 78223 | 2101300400000 | 11 | Allegheny | 2 MILES WEST OF SR 1006 | SAXONBURG BLVD. | BRANCH LITTLE PINE CREEK | 02/112 - OHARA | 40.5273 | -79.927 | 20140162094 | Wtr | Hampton-Shaler | Sam Scarfone, 412-486-4867 | UG |  | Prior | 2015-08-05
416e | Y | 416 | 42177 | 78223 | 2101300400000 | 11 | Allegheny | 2 MILES WEST OF SR 1006 | SAXONBURG BLVD. | BRANCH LITTLE PINE CREEK | 02/112 - OHARA | 40.5273 | -79.927 | 20140162094 | Comm | Consolidated Communications | Gabe White, (412) 443-9832 | OH | tele | Not Affected | 2015-08-05
416f | Y | 416 | 42177 | 78223 | 2101300400000 | 11 | Allegheny | 2 MILES WEST OF SR 1006 | SAXONBURG BLVD. | BRANCH LITTLE PINE CREEK | 02/112 - OHARA | 40.5273 | -79.927 | 20140162094 | Comm | Comcast | Rick Moslen, 412-999-0590 | OH | TV | Not Affected | 2015-08-05
417a | -- | 417 | 1424 | 99687 | 2101500702617 | 11 | Allegheny | NORTH/RURAL RIDGE | LITTLE DEER CRE RD | BR.LITTLE DEER CREEK | 02/209 - INDIANA | 40.5917 | -79.8217 | 20150411810 | sanitary | Allegheny County Dept of Public Works | Michael Lichte, PE, 412-732-8004, michael.lichte@alcosan.org | UG |  |  | 2017-05-22
417b | -- | 417 | 1424 | 99687 | 2101500702617 | 11 | Allegheny | NORTH/RURAL RIDGE | LITTLE DEER CRE RD | BR.LITTLE DEER CREEK | 02/209 - INDIANA | 40.5917 | -79.8217 | 20150411810 | sanitary | DEER CREEK DRAINAGE BASIN AUTHORITY | Chuck Debaldo (412) 913-6684 - chuck@deercreekauthority .com | UG |  |  | 2017-05-22
417c | -- | 417 | 1424 | 99687 | 2101500702617 | 11 | Allegheny | NORTH/RURAL RIDGE | LITTLE DEER CRE RD | BR.LITTLE DEER CREEK | 02/209 - INDIANA | 40.5917 | -79.8217 | 20150411810 | wtr | Oakmont Borough Municipal Auth | 412-828-7220 | UG |  |  | 2017-05-22
417d | -- | 417 | 1424 | 99687 | 2101500702617 | 11 | Allegheny | NORTH/RURAL RIDGE | LITTLE DEER CRE RD | BR.LITTLE DEER CREEK | 02/209 - INDIANA | 40.5917 | -79.8217 | 20150411810 | Gas | Peoples TWP LLC/TW Phillips | Larry Shane, 724-295-2600, Lawrence.R.Shane@peoples-gas.com | UG |  |  | 2017-05-22
418a | Y | 418 | 1435 | 27287 | 2101600801980 | 11 | Allegheny | 70' WEST OF SR 1015 | LAFEVER HILL RD | LITTLE DEER CREEK | 02/209 - INDIANA | 40.5745 | -79.8227 | 20140162109 | SS | DEER CREEK DRAINAGE BASIN AUTHORITY | Chuck Debalno (412) 913-6684 - chuck@deercreekauthority .com | UG |  | Not Affected | 2016-04-04
418b | Y | 418 | 1435 | 27287 | 2101600801980 | 11 | Allegheny | 70' WEST OF SR 1015 | LAFEVER HILL RD | LITTLE DEER CREEK | 02/209 - INDIANA | 40.5745 | -79.8227 | 20140162109 | Gas | DOMINION TRANSMISSION | Bradley Buzzard (724) 331-3695 - Bradley.l.buzzard@dom .com or Jonathan Cherry (724) 468-7730 - jonathan.w.cherry@dom .com | UG |  | Not Affected | 2016-04-04
418c | Y | 418 | 1435 | 27287 | 2101600801980 | 11 | Allegheny | 70' WEST OF SR 1015 | LAFEVER HILL RD | LITTLE DEER CREEK | 02/209 - INDIANA | 40.5745 | -79.8227 | 20140162109 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | Prior | 2016-04-04
418d | Y | 418 | 1435 | 27287 | 2101600801980 | 11 | Allegheny | 70' WEST OF SR 1015 | LAFEVER HILL RD | LITTLE DEER CREEK | 02/209 - INDIANA | 40.5745 | -79.8227 | 20140162109 | Wtr | MUNICIPAL WATER AUTHORITY OF THE BOROUGH OF OAKMONT | Jim Mccaskey (412) 327-0096 - jfm@oakmontwater.com | UG |  | Prior | 2016-04-04
418e | Y | 418 | 1435 | 27287 | 2101600801980 | 11 | Allegheny | 70' WEST OF SR 1015 | LAFEVER HILL RD | LITTLE DEER CREEK | 02/209 - INDIANA | 40.5745 | -79.8227 | 20140162109 | Comm | Comcast | Rick Moslen, rickmoslen@cable.comcast.com 412-999-0590 or Kent Norton (412) 352-7045 - kentnorton@cable.comcast.com | OH | Tele | Coordinated | 2016-04-04
418f | Y | 418 | 1435 | 27287 | 2101600801980 | 11 | Allegheny | 70' WEST OF SR 1015 | LAFEVER HILL RD | LITTLE DEER CREEK | 02/209 - INDIANA | 40.5745 | -79.8227 | 20140162109 | Comm | Consolidated | Jeff Hall - (724) 443-9639 - jeff.hall@conso l idated .com | OH | TV | Coordinated | 2016-04-04
419a | Y | 419 | 1455 | 63356 | 2102801801751 | 11 | Allegheny | 200' WEST OF SR 1031 | BAKERSTOWN RD | LARDINTOWN RUN | 02/202 - FAWN | 40.652 | -79.7938 | 20140371911 | Unk | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 Bruce Burtner, (724) 287-2751 or James Barnett 412-290-2421 | UG |  | Not Affected | 2015-08-03
419b | Y | 419 | 1455 | 63356 | 2102801801751 | 11 | Allegheny | 200' WEST OF SR 1031 | BAKERSTOWN RD | LARDINTOWN RUN | 02/202 - FAWN | 40.652 | -79.7938 | 20140371911 | Elect | WEST PENN POWER COMPANY | Dan Henry 724-838-6126 or Richard Hobbins 724-334-5237 | OH |  | CONDITIONAL RESTRICTION | 2015-08-03
419c | Y | 419 | 1455 | 63356 | 2102801801751 | 11 | Allegheny | 200' WEST OF SR 1031 | BAKERSTOWN RD | LARDINTOWN RUN | 02/202 - FAWN | 40.652 | -79.7938 | 20140371911 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Gary Redondo, 412-237-2293 | OH | Tele | Not Affected | 2015-08-03
419d | Y | 419 | 1455 | 63356 | 2102801801751 | 11 | Allegheny | 200' WEST OF SR 1031 | BAKERSTOWN RD | LARDINTOWN RUN | 02/202 - FAWN | 40.652 | -79.7938 | 20140371911 | Comm | FAWN-FRAZIER JOINT WATER AUTHORITY | Nick Irvine, 724-884-6562 | OH | Tele | Not Affected | 2015-08-03
419e | Y | 419 | 1455 | 63356 | 2102801801751 | 11 | Allegheny | 200' WEST OF SR 1031 | BAKERSTOWN RD | LARDINTOWN RUN | 02/202 - FAWN | 40.652 | -79.7938 | 20140371911 | Comm | CONSOLIDATED COMMUNICATIONS OF PA COMPANY, LLC | Harry R Brown, 724 443-9535 or Jeff Hall, 724-443-9639 | OH | Tele | Not Affected | 2015-08-03
419f | Y | 419 | 1455 | 63356 | 2102801801751 | 11 | Allegheny | 200' WEST OF SR 1031 | BAKERSTOWN RD | LARDINTOWN RUN | 02/202 - FAWN | 40.652 | -79.7938 | 20140371911 | Comm | COMCAST CABLE CORPORATION | Rick Moslen, 412-999-0590 or John Radeshak, 724-212-7236 | OH | TV | Not Affected | 2015-08-03
420a | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | 20140410780, 20140371909 | Comm | COMCAST CABLE CORPORATION | Rick Moslen, 412-999-0590 or John Radeshak, 724-212-7236 | OH |  | Not Affected | 2015-08-06
420b | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | 20140410780, 20140371909 | Elect | WEST PENN POWER COMPANY | Dan Henry, 724-838-6126 or Richard Hobbins, 724-334-5237 | OH |  | Not Affected | 2015-08-06
420c | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | 20140410780, 20140371909 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Howard Jankey, 724-337-5673 | OH |  | Coordinated | 2015-08-06
420d | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | 20140410780, 20140371909 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Howard Jankey, 724-337-5673 | OH |  | Coordinated | 2015-08-06
420e | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | 20140410780, 20140371909 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Howard Jankey, 724-337-5673 | OH |  | Coordinated | 2015-08-06
420f | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | 20140410780, 20140371909 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Howard Jankey, 724-337-5673 | OH |  | Coordinated | 2015-08-06
420g | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | 20140410780, 20140371909 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Howard Jankey, 724-337-5673 | OH |  | Coordinated | 2015-08-06
420h | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | 20140410780, 20140371909 | wtr | Fawn-Frazier Joint Water Authority | Nick Irvine, 724-681-8208 | UG |  | Incorporated | 2015-08-06
420i | Y | 420 | 1471 | 63513 | 2103400501321 | 11 | Allegheny | 4200' S.E. OF SR 1033 | BULL CREEK RD | BULL CREEK | 02/202 - FAWN | 40.6322 | -79.7613 | 20140410780, 20140371909 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 Larry Shane, 412-473-3960 | UG |  | Coordinated | 2015-08-06
421a | -- | 421 | 1479 | 28607 | 2200100800335 | 11 | Allegheny | AT BAPTIST CHURCH | MONONGAHELA RD | TRIBUT. TO MONOGAHELA R. | 02/204 - FORWARD | 40.2381 | -79.9463 | 20143580442 | Gas | PEOPLES NATURAL GAS | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | UG |  |  | 2016-04-04
421b | -- | 421 | 1479 | 28607 | 2200100800335 | 11 | Allegheny | AT BAPTIST CHURCH | MONONGAHELA RD | TRIBUT. TO MONOGAHELA R. | 02/204 - FORWARD | 40.2381 | -79.9463 | 20143580442 | wtr | Municipal Auth of Westmoreland CO | M. Curtis Fontaine, 724-755-5950, fontaine@mawc.org | UG |  |  | 2016-04-04
421c | -- | 421 | 1479 | 28607 | 2200100800335 | 11 | Allegheny | AT BAPTIST CHURCH | MONONGAHELA RD | TRIBUT. TO MONOGAHELA R. | 02/204 - FORWARD | 40.2381 | -79.9463 | 20143580442 | Elect | West Penn Power Company | Christine Smith, 724-489-3237, smithc@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com |  |  |  | 2016-04-04
421d | -- | 421 | 1479 | 28607 | 2200100800335 | 11 | Allegheny | AT BAPTIST CHURCH | MONONGAHELA RD | TRIBUT. TO MONOGAHELA R. | 02/204 - FORWARD | 40.2381 | -79.9463 | 20143580442 | Comm | VERIZON PENNSYLVANIA LLC | Fred Fraer, 412-237-2292, f.g.fraer.jr@verizon.com, |  |  |  | 2016-04-04
421e | -- | 421 | 1479 | 28607 | 2200100800335 | 11 | Allegheny | AT BAPTIST CHURCH | MONONGAHELA RD | TRIBUT. TO MONOGAHELA R. | 02/204 - FORWARD | 40.2381 | -79.9463 | 20143580442 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com |  |  |  | 2016-04-04
422a | Y | 422 | 1481 | 62174 | 2200101300130 | 11 | Allegheny | AT PANGBURN RD | MONONGAHELA RD | PERRY MILL RUN (ADJACENT CSX) | 02/204 - FORWARD | 40.2516 | -79.9121 | 20133390194 | Elect | WEST PENN POWER COMPANY | Nick Ensminger, 304-534-7437 | OH |  | Coordinated | 2016-05-23
422b | Y | 422 | 1481 | 62174 | 2200101300130 | 11 | Allegheny | AT PANGBURN RD | MONONGAHELA RD | PERRY MILL RUN (ADJACENT CSX) | 02/204 - FORWARD | 40.2516 | -79.9121 | 20133390194 | Comm | Verizon | Deborah D Delia, 412-633-3810, Fred Fraer Jr, f.g.fraer.jr@verizon.com, 412-237-2292 work 412-216-9260 cell | OH |  | Coordinated | 2016-05-23
423a | -- | 423 | 1496 | 26417 | 2200800100053 | 11 | Allegheny | @ INTER. WITH SR 2010 | MILL HILL RD | WYLIE RUN | 02/105 - ELIZABETH | 40.2784 | -79.8559 | 20150161751, 20150161752 | Wtr | Pennsylvania American Water Company | Eric R. Beringer, eric.beringer@amwater.com 724-743-3108 | UG |  |  | 2016-06-17
423b | -- | 423 | 1496 | 26417 | 2200800100053 | 11 | Allegheny | @ INTER. WITH SR 2010 | MILL HILL RD | WYLIE RUN | 02/105 - ELIZABETH | 40.2784 | -79.8559 | 20150161751, 20150161752 | Elect | West Penn Power Company | Christine Smith, 724-489-3237, smithc@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | OH |  |  | 2016-06-17
423c | -- | 423 | 1496 | 26417 | 2200800100053 | 11 | Allegheny | @ INTER. WITH SR 2010 | MILL HILL RD | WYLIE RUN | 02/105 - ELIZABETH | 40.2784 | -79.8559 | 20150161751, 20150161752 | Comm | Verizon | Fred Fraer 412-237-2292 Fraer Jr, f.g.fraer.jr@verizon.com, | OH |  |  | 2016-06-17
423d | -- | 423 | 1496 | 26417 | 2200800100053 | 11 | Allegheny | @ INTER. WITH SR 2010 | MILL HILL RD | WYLIE RUN | 02/105 - ELIZABETH | 40.2784 | -79.8559 | 20150161751, 20150161752 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com | OH |  |  | 2016-06-17
424a | -- | 424 | 1498 | 73045 | 2201000102238 | 11 | Allegheny | 500'N.E.OF ROSS STREET | LOVEDALE ROAD | BRANCH OF WYLIE RUN | 02/105 - ELIZABETH | 40.277 | -79.869 | 20143580340 | Gas | Gas | Joseph (Joby) Lapkowicz jlapkowicz@nisource.com C: 724-415-9293 O: 724-425-2358 Dominic Tarella, 724-462-3479 dtarella@nisource.com | UG |  |  | 2016-04-22
424b | -- | 424 | 1498 | 73045 | 2201000102238 | 11 | Allegheny | 500'N.E.OF ROSS STREET | LOVEDALE ROAD | BRANCH OF WYLIE RUN | 02/105 - ELIZABETH | 40.277 | -79.869 | 20143580340 | sanitary | sanitary | Kurt Todd, 412-921-4030x184, ktodd@gatewayengineers.com Ruthann Omer, 421-921-4030, romer@gatewayengineers.com Gateway Engineers Ed Campbell, (412) 754-1643, Etsa1@comcast.net | UG |  |  | 2016-04-22
424c | -- | 424 | 1498 | 73045 | 2201000102238 | 11 | Allegheny | 500'N.E.OF ROSS STREET | LOVEDALE ROAD | BRANCH OF WYLIE RUN | 02/105 - ELIZABETH | 40.277 | -79.869 | 20143580340 | Elect | Elect | Christine Smith, 724-489-3237, smithc@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | OH |  |  | 2016-04-22
424d | -- | 424 | 1498 | 73045 | 2201000102238 | 11 | Allegheny | 500'N.E.OF ROSS STREET | LOVEDALE ROAD | BRANCH OF WYLIE RUN | 02/105 - ELIZABETH | 40.277 | -79.869 | 20143580340 | Wtr | Wtr | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | UG |  |  | 2016-04-22
424e | -- | 424 | 1498 | 73045 | 2201000102238 | 11 | Allegheny | 500'N.E.OF ROSS STREET | LOVEDALE ROAD | BRANCH OF WYLIE RUN | 02/105 - ELIZABETH | 40.277 | -79.869 | 20143580340 | Wtr | Comm | Fred Fraer, 412-237-2292, f.g.fraer.jr@verizon.com, | UG |  |  | 2016-04-22
424f | -- | 424 | 1498 | 73045 | 2201000102238 | 11 | Allegheny | 500'N.E.OF ROSS STREET | LOVEDALE ROAD | BRANCH OF WYLIE RUN | 02/105 - ELIZABETH | 40.277 | -79.869 | 20143580340 | Wtr | Comm | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | UG |  |  | 2016-04-22
425a | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | 20150170073 | sanitary | Elizabeth TWP AUTH | Kurt Todd, 412-921-4030x184, ktodd@gatewayengineers.com Ruthann Omer, 421-921-4030, romer@gatewayengineers.com Gateway Engineers Ed Campbell, (412) 754-1643, Etsa1@comcast.net | UG |  |  | 2016-04-20
425b | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | 20150170073 | Wtr | Pennsylvania American Water CO | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | UG |  |  | 2016-04-20
425c | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | 20150170073 | gas | Peoples Gas Design Monongahela | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | UG |  |  | 2016-04-20
425d | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | 20150170073 | gas | Peoples Gas Monongahela Division | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | UG |  |  | 2016-04-20
425e | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | 20150170073 | Elect | West Penn Power Company | Christine Smith, 724-489-3237, smithc@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | OH |  |  | 2016-04-20
425f | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | 20150170073 | Comm | Verizon | Fred Fraer, 412-237-2292, f.g.fraer.jr@verizon.com, | UG |  |  | 2016-04-20
425g | -- | 425 | 1519 | 27451 | 2201701301248 | 11 | Allegheny | @ SR 2014 | INDUSTRY RD | BOYDS HOLLOW RUN | 02/105 - ELIZABETH | 40.2726 | -79.7982 | 20150170073 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | OH |  |  | 2016-04-20
426a | -- | 426 | 1520 | 99665 | 2201701400112 | 11 | Allegheny | AT ROCK RUN RD | BUENA VISTA RD | WILDCAT RUN | 02/105 - ELIZABETH | 40.275 | -79.7993 | 20150161794 | sanitary | Allegheny County Dept of Public Works | Michael Lichte, PE, 412-732-8004, michael.lichte@alcosan.org | OH |  |  | 2016-06-17
426b | -- | 426 | 1520 | 99665 | 2201701400112 | 11 | Allegheny | AT ROCK RUN RD | BUENA VISTA RD | WILDCAT RUN | 02/105 - ELIZABETH | 40.275 | -79.7993 | 20150161794 | Wtr | Pennsylvania American Water CO | Jerry Hankey, 724-463-87069 or Matt Macek, 412-854-7603 | UG |  |  | 2016-06-17
426c | -- | 426 | 1520 | 99665 | 2201701400112 | 11 | Allegheny | AT ROCK RUN RD | BUENA VISTA RD | WILDCAT RUN | 02/105 - ELIZABETH | 40.275 | -79.7993 | 20150161794 | Gas | Peoples Gas Design Monongahela | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-06-17
427a | -- | 427 | 1523 | 78224 | 2201800400721 | 11 | Allegheny | 2082 FEET SW OF SR 48 | WEST SMITHFIELD RD | CREEK | 02/105 - ELIZABETH | 40.3083 | -79.8335 | 20150170076, 20150170077 | Wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | UG |  |  | 2016-04-20
427b | -- | 427 | 1523 | 78224 | 2201800400721 | 11 | Allegheny | 2082 FEET SW OF SR 48 | WEST SMITHFIELD RD | CREEK | 02/105 - ELIZABETH | 40.3083 | -79.8335 | 20150170076, 20150170077 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | OH |  |  | 2016-04-20
427c | -- | 427 | 1523 | 78224 | 2201800400721 | 11 | Allegheny | 2082 FEET SW OF SR 48 | WEST SMITHFIELD RD | CREEK | 02/105 - ELIZABETH | 40.3083 | -79.8335 | 20150170076, 20150170077 | sanitary | Elizabeth TWP AUTH | Kurt Todd, 412-921-4030x184, ktodd@gatewayengineers.com Ruthann Omer, 421-921-4030, romer@gatewayengineers.com Gateway Engineers Ed Campbell, (412) 754-1643, Etsa1@comcast.net | UG |  |  | 2016-04-20
427d | -- | 427 | 1523 | 78224 | 2201800400721 | 11 | Allegheny | 2082 FEET SW OF SR 48 | WEST SMITHFIELD RD | CREEK | 02/105 - ELIZABETH | 40.3083 | -79.8335 | 20150170076, 20150170077 | Gas | Peoples Gas Design Monongahela | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | UG |  |  | 2016-04-20
427e | -- | 427 | 1523 | 78224 | 2201800400721 | 11 | Allegheny | 2082 FEET SW OF SR 48 | WEST SMITHFIELD RD | CREEK | 02/105 - ELIZABETH | 40.3083 | -79.8335 | 20150170076, 20150170077 | Comm | Verizon | Fred Fraer, 412-237-2292, f.g.fraer.jr@verizon.com, | OH |  |  | 2016-04-20
427f | -- | 427 | 1523 | 78224 | 2201800400721 | 11 | Allegheny | 2082 FEET SW OF SR 48 | WEST SMITHFIELD RD | CREEK | 02/105 - ELIZABETH | 40.3083 | -79.8335 | 20150170076, 20150170077 | Comm | Comcast | Tim Gazda, 412-875-1388, Tim_Gazda@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | OH |  |  | 2016-04-20
428a | -- | 428 | 1527 | 99670 | 2202200102622 | 11 | Allegheny | 2644'N.E.OF LR02310 | STEWARTSVILLE H RD | BR. LONG RUN | 02/477 - WHITE OAK | 40.3309 | -79.7877 | 20150411843 | Gas | Peoples Gas Pittsburgh Division | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2017-05-22
428b | -- | 428 | 1527 | 99670 | 2202200102622 | 11 | Allegheny | 2644'N.E.OF LR02310 | STEWARTSVILLE H RD | BR. LONG RUN | 02/477 - WHITE OAK | 40.3309 | -79.7877 | 20150411843 | Wtr | Municipal Auth of Westmoreland Cnty | April Tilson, 724-755-5955, atilson@mawc.org | UG | 8" |  | 2017-05-22
429a | -- | 429 | 1559 | 63529 | 2204500300840 | 11 | Allegheny | DRAVOSBURG OVER UNION RR | MCKEESPORT BL | UNION RAILROAD | 02/423 - DRAVOSBURG | 40.351 | -79.8961 | 20143571433 | Comm | Verizon Pennsylvania LLC | Chuch Bartoles, 724-656-5206 | UG |  |  | 2017-02-16
429b | -- | 429 | 1559 | 63529 | 2204500300840 | 11 | Allegheny | DRAVOSBURG OVER UNION RR | MCKEESPORT BL | UNION RAILROAD | 02/423 - DRAVOSBURG | 40.351 | -79.8961 | 20143571433 |  | Borough of Dravosburg | George Cribbs, 412-401-0833 |  |  |  | 2017-02-16
429c | -- | 429 | 1559 | 63529 | 2204500300840 | 11 | Allegheny | DRAVOSBURG OVER UNION RR | MCKEESPORT BL | UNION RAILROAD | 02/423 - DRAVOSBURG | 40.351 | -79.8961 | 20143571433 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2017-02-16
429d | -- | 429 | 1559 | 63529 | 2204500300840 | 11 | Allegheny | DRAVOSBURG OVER UNION RR | MCKEESPORT BL | UNION RAILROAD | 02/423 - DRAVOSBURG | 40.351 | -79.8961 | 20143571433 |  | United States Steel Corp | Edward McKeever, 412-675-7459 |  |  |  | 2017-02-16
429e | -- | 429 | 1559 | 63529 | 2204500300840 | 11 | Allegheny | DRAVOSBURG OVER UNION RR | MCKEESPORT BL | UNION RAILROAD | 02/423 - DRAVOSBURG | 40.351 | -79.8961 | 20143571433 | wtr | Pennsylvania American Water CO | Gary Eiter, 412-854-7619, Gary.Eiter@amwater.com | UG |  |  | 2017-02-16
430a | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | 20150161783 | Gas | COLUMBIA GAS OF PA | Dominic Tarella, dtarella@nisource.com 724-462-3479 | UG |  |  | 2016-05-31
430b | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | 20150161783 | wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | UG |  |  | 2016-05-31
430c | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | 20150161783 | Gas | PEOPLES GAS COMPANY (EQUITABLE) | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  |  | 2016-05-31
430d | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | 20150161783 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  |  | 2016-05-31
430e | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | 20150161783 | Comm | SUNESYS | Aaron Phillips, 412.779.5277 APhillips@sunesys.com | OH |  |  | 2016-05-31
430f | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | 20150161783 | Comm | Verizon Pennsylvania LLC | Jon Gaunt, 412-237-2290, jon.c.gaunt@verizon.com | OH |  |  | 2016-05-31
430g | -- | 430 | 1562 | 78271 | 2204600401678 | 11 | Allegheny | AT INTER./ SR 3046 | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.352 | -79.9645 | 20150161783 | Comm | Comcast | Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | OH |  |  | 2016-05-31
431a | Y | 431 | 1567 | 63547 | 2204600800256 | 11 | Allegheny | 50'EAST/SCHUTE RD. | STREETS RUN RD | STREETS RUN (ADJACENT UNION) | 02/403 - BALDWIN | 40.3667 | -79.9493 |  | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 or Carl Taylor, 412-258-4616 | UG |  | Not Affected | 2015-09-01
431b | Y | 431 | 1567 | 63547 | 2204600800256 | 11 | Allegheny | 50'EAST/SCHUTE RD. | STREETS RUN RD | STREETS RUN (ADJACENT UNION) | 02/403 - BALDWIN | 40.3667 | -79.9493 |  | Wtr | Baldwin Borough | Ann Scott, Secy., telephone 412-882-9600X251 or John Barrett, 412-882-9600X251 | UG |  | Not Affected | 2015-09-01
431c | Y | 431 | 1567 | 63547 | 2204600800256 | 11 | Allegheny | 50'EAST/SCHUTE RD. | STREETS RUN RD | STREETS RUN (ADJACENT UNION) | 02/403 - BALDWIN | 40.3667 | -79.9493 |  | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Jon Gaunt, 412-237-2290 | OH |  | Not Affected | 2015-09-01
431d | Y | 431 | 1567 | 63547 | 2204600800256 | 11 | Allegheny | 50'EAST/SCHUTE RD. | STREETS RUN RD | STREETS RUN (ADJACENT UNION) | 02/403 - BALDWIN | 40.3667 | -79.9493 |  | Elect | Duquesne | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | Not Affected | 2015-09-01
431e | Y | 431 | 1567 | 63547 | 2204600800256 | 11 | Allegheny | 50'EAST/SCHUTE RD. | STREETS RUN RD | STREETS RUN (ADJACENT UNION) | 02/403 - BALDWIN | 40.3667 | -79.9493 |  | Wtr | PENNSYLVANIA AMERICAN WATER COMPANY | Jerry Hankey, 724-463-87069 or Matt Macek, 412-854-7603 | UG |  | Not Affected | 2015-09-01
431f | Y | 431 | 1567 | 63547 | 2204600800256 | 11 | Allegheny | 50'EAST/SCHUTE RD. | STREETS RUN RD | STREETS RUN (ADJACENT UNION) | 02/403 - BALDWIN | 40.3667 | -79.9493 |  | Comm | COMCAST CABLE COMMUNICATIONS, INC. | Rick Moslen, 412-999-0590 | OH |  | Not Affected | 2015-09-01
432a | -- | 432 | 1568 | 74324 | 2204600801088 | 11 | Allegheny | AT LUTZ HOLLOW ROAD | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.3682 | -79.9476 | 20150170081, 20150170082 | wtr | Pennsylvania American Water CO | Joe Tewell, joseph.tewell@amwater.com | UG |  |  | 2016-05-19
432b | -- | 432 | 1568 | 74324 | 2204600801088 | 11 | Allegheny | AT LUTZ HOLLOW ROAD | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.3682 | -79.9476 | 20150170081, 20150170082 | gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-05-19
432c | -- | 432 | 1568 | 74324 | 2204600801088 | 11 | Allegheny | AT LUTZ HOLLOW ROAD | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.3682 | -79.9476 | 20150170081, 20150170082 | gas | Sunoco Pipeline LP | sxldesignreviews@sunocologistics.com; Tracy Hoffman, 610-670-3256, tlhoffman@sunocologistics.com | UG |  |  | 2016-05-19
432d | -- | 432 | 1568 | 74324 | 2204600801088 | 11 | Allegheny | AT LUTZ HOLLOW ROAD | STREETS RUN RD | STREETS RUN | 02/403 - BALDWIN | 40.3682 | -79.9476 | 20150170081, 20150170082 |  | West Mifflin Borough | Howard Bednar, 412-466-8170 | UG |  |  | 2016-05-19
433a | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | SS | Penn Hills Municipality | Tom O’Grady, 412-798-2171 | UG |  | CONDITIONAL RESTRICTION | 2016-02-17
433b | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | SS | ALLEGHENY COUNTY SANITARY AUTHORITY (ALCOSAN) | Mr. Dave Boreman, 412-766-4810 | UG |  | CONDITIONAL RESTRICTION | 2016-02-17
433c | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 or Carl Taylor, (412) 258-4616 | UG |  | CONDITIONAL RESTRICTION | 2016-02-17
433d | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | Comm | Comcast | Rick Moslen, 412-999-0590 | OH |  | Not Affected | 2016-02-17
433e | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Peter Zlkoas, (412) 824-0760 | OH |  | Coordinated | 2016-02-17
433f | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 or Peter Zlkoas, (412) 824-0760 | OH |  | Coordinated | 2016-02-17
433g | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | SS | Wilkins Township | Paul Vargo, 412-824-6650 | UG |  | Protect-In-Place | 2016-02-17
433h | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | Not Affected | 2016-02-17
433i | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | Coordinated | 2016-02-17
433j | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | Coordinated | 2016-02-17
433k | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | SS | Churchill Borough | Craig Robinson, 412-241-7113 | UG |  | CONDITIONAL RESTRICTION | 2016-02-17
433l | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | SS | Monroeville Municipal Authority | Timothy Little, (412) 856-3304 or Joe Storey, (412) 287-6015 | UG |  | CONDITIONAL RESTRICTION | 2016-02-17
433m | Y | 433 | 1600 | 27419 | 2206500402452 | 11 | Allegheny | 2656' N.E. OF SR 2053 | THOMPSON RUN RD | THOMPSON RUN | 02/124 - WILKINS | 40.4258 | -79.808 | 20140162146 | SS | Turtle Creek Borough | Julie Pantalone, 412 824-2500 | UG |  | CONDITIONAL RESTRICTION | 2016-02-17
434a | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | 20150170083 | gas | Peoples Gas Pittsburgh Division | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-06-17
434b | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | 20150170083 | gas | Peoples TWP LLC/TW Phillips | michael.denny@peoplestwp.com | UG | 4" |  | 2016-06-17
434c | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | 20150170083 |  | Plum Borough Municipal Auth | Howard Theis, htheis@plumboroughhma.com | UG |  |  | 2016-06-17
434d | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | 20150170083 | sanitary | Allegheny County Dept of Public Works | Michael Lichte, PE, 412-732-8004, michael.lichte@alcosan.org | UG |  |  | 2016-06-17
434e | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | 20150170083 |  | Plum Borough | Bill Binnie, 412-795-6800 x4601 | UG |  |  | 2016-06-17
434f | -- | 434 | 1620 | 89124 | 2207500900000 | 11 | Allegheny | OVER BR. LITTLE PLUM CR. | NEW TEXAS RD | BR. LITTLE PLUM CREEK | 02/466 - PLUM | 40.4922 | -79.7436 | 20150170083 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Dennis Rachocki, 814-333-0288, dennis.rachocki@windstream.com |  |  |  | 2016-06-17
435a | -- | 435 | 1626 | 27275 | 2207501900000 | 11 | Allegheny | 200'N.OF ENTRANCE DRIVE | LOGAN FERRY RD | AVR RAILROAD | 02/466 - PLUM | 40.5441 | -79.7605 | 20151471652 | gas | Peoples Gas (Equitable Gas) | Christopher (Chris) Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | UG | 12 & 6" |  | 2017-07-28
435b | -- | 435 | 1626 | 27275 | 2207501900000 | 11 | Allegheny | 200'N.OF ENTRANCE DRIVE | LOGAN FERRY RD | AVR RAILROAD | 02/466 - PLUM | 40.5441 | -79.7605 | 20151471652 |  | Plum Borough | Bill Binnie, 412-795-6800 x4601 |  |  |  | 2017-07-28
435c | -- | 435 | 1626 | 27275 | 2207501900000 | 11 | Allegheny | 200'N.OF ENTRANCE DRIVE | LOGAN FERRY RD | AVR RAILROAD | 02/466 - PLUM | 40.5441 | -79.7605 | 20151471652 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; David (Dave) Ackerman, David.F.Ackerman@windstream.com, 319-790-1464 |  |  |  | 2017-07-28
435d | -- | 435 | 1626 | 27275 | 2207501900000 | 11 | Allegheny | 200'N.OF ENTRANCE DRIVE | LOGAN FERRY RD | AVR RAILROAD | 02/466 - PLUM | 40.5441 | -79.7605 | 20151471652 | gas | PEOPLES NATURAL GAS COMPANY LLC | Michelle Saxion, 412-208-7239 | UG |  |  | 2017-07-28
436a | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 |  | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | Coordinated | 2015-08-07
436b | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 |  | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | Coordinated | 2015-08-07
436c | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 |  | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | Coordinated | 2015-08-07
436d | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 |  | Comm | Comcast | Tim Gazda, Tim_Gazda@cable.comcast.com, 412-875-1388 Rick Moslen, 412-999-0590 | OH |  | Coordinated | 2015-08-07
436e | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 |  | Gas | Equitrans LP | Chris Baacke 412-395-2685, cbaacke@eqt.com Robert Crites, 724-852-7348 | UG |  | Not Affected | 2015-08-07
436f | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 |  | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 Bart Ryan, telephone: 412-244-2210 | UG |  | Coordinated | 2015-08-07
436g | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 |  | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127 Bart Ryan, telephone: 412-244-2210 | UG |  | Coordinated | 2015-08-07
436h | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 |  | Comm | Verizon | Deborah D Delia, 412-633-3810 Fred Fraer, telephone: 412-237-2292 | OH |  | Coordinated | 2015-08-07
436i | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 |  | Unk | Municipal Authority of Westmoreland County | M. Curtis Fontaine, 724-755-5950 | UG |  | Not Affected | 2015-08-07
436j | Y | 436 | 1671 | 63557 | 2211800203544 | 11 | Allegheny | 500' SOUTHEAST OF SR 0048 | CENTER ST | LONG RUN | 02/477 - WHITE OAK | 40.3278 | -79.8165 |  | Unk | Municipal Authority of the City of McKeesport | Michael Majzer, 412-673-8276 | UG |  | Not Affected | 2015-08-07
437a | -- | 437 | 1704 | 27436 | 2300800420000 | 11 | Allegheny | 200'W.OF INTER.W/SR 3004 | MORROW RD | MCLAUGHLIN RUN | 02/123 - UPPER ST CLAIR | 40.3402 | -80.0791 | 20150161202 | wtr | Pennsylvania American Water CO | Joe Tewell, joseph.tewell@amwater.com | UG |  |  | 2016-06-16
437b | -- | 437 | 1704 | 27436 | 2300800420000 | 11 | Allegheny | 200'W.OF INTER.W/SR 3004 | MORROW RD | MCLAUGHLIN RUN | 02/123 - UPPER ST CLAIR | 40.3402 | -80.0791 | 20150161202 | Gas | Peoples Gas Design Monongahela | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-06-16
437c | -- | 437 | 1704 | 27436 | 2300800420000 | 11 | Allegheny | 200'W.OF INTER.W/SR 3004 | MORROW RD | MCLAUGHLIN RUN | 02/123 - UPPER ST CLAIR | 40.3402 | -80.0791 | 20150161202 | sanitary | Upper St. Clair TWP | 421-831-9000, yelich@twpusc.com | UG |  |  | 2016-06-16
438a | Y | 438 | 1715 | 28446 | 2301400302259 | 11 | Allegheny | 3/4 MI.N.W.OF SR 3015 | PINEY FORK RD | PINEY FORK CREEK | 02/219 - SOUTH PARK | 40.2783 | -79.9773 | 20133390204 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127, 412-473-3960 | UG |  | Not Affected | 2015-09-21
438b | Y | 438 | 1715 | 28446 | 2301400302259 | 11 | Allegheny | 3/4 MI.N.W.OF SR 3015 | PINEY FORK RD | PINEY FORK CREEK | 02/219 - SOUTH PARK | 40.2783 | -79.9773 | 20133390204 | Comm | VERIZON PENNSYLVANIA LLC | Deborah D Delia, 412-633-3810 | OH |  | Coordinated | 2015-09-21
438c | Y | 438 | 1715 | 28446 | 2301400302259 | 11 | Allegheny | 3/4 MI.N.W.OF SR 3015 | PINEY FORK RD | PINEY FORK CREEK | 02/219 - SOUTH PARK | 40.2783 | -79.9773 | 20133390204 | wtr | SOUTH PARK TOWNSHIP | Bruce Beaver, 412-831-7000 | UG |  | Not Affected | 2015-09-21
438d | Y | 438 | 1715 | 28446 | 2301400302259 | 11 | Allegheny | 3/4 MI.N.W.OF SR 3015 | PINEY FORK RD | PINEY FORK CREEK | 02/219 - SOUTH PARK | 40.2783 | -79.9773 | 20133390204 | Elect | First Energy Corporation (West Penn Power) | Dan Henry, 724-838-6126 | OH |  | Coordinated | 2015-09-21
438e | Y | 438 | 1715 | 28446 | 2301400302259 | 11 | Allegheny | 3/4 MI.N.W.OF SR 3015 | PINEY FORK RD | PINEY FORK CREEK | 02/219 - SOUTH PARK | 40.2783 | -79.9773 | 20133390204 | Comm | COMCAST CABLE COMMUNICATIONS, INC. | Rick Moslen, 412-999-0590 | OH |  | Coordinated | 2015-09-21
438f | Y | 438 | 1715 | 28446 | 2301400302259 | 11 | Allegheny | 3/4 MI.N.W.OF SR 3015 | PINEY FORK RD | PINEY FORK CREEK | 02/219 - SOUTH PARK | 40.2783 | -79.9773 | 20133390204 | wtr | PENNSYLVANIA AMERICAN WATER COMPANY | Jay Lucas, 724-873-3653 | UG |  | Incorporated | 2015-09-21
439a | -- | 439 | 1727 | 27386 | 2301800260000 | 11 | Allegheny | 820' S.W. OF SR 3021 | SCHEINBACH RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2661 | -79.9305 | 20150170090 | Gas | GUARDIAN INDUSTRIES CORPORATION | Tim Zeuger (Roach and Assoc), twzeuger@roachassoc.com, 412-706-2581 | UG |  |  | 2016-06-17
439b | -- | 439 | 1727 | 27386 | 2301800260000 | 11 | Allegheny | 820' S.W. OF SR 3021 | SCHEINBACH RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2661 | -79.9305 | 20150170090 | Wtr | Pennsylvania American Water CO | Joe Tewell, joseph.tewell@amwater.com | UG |  |  | 2016-06-17
439c | -- | 439 | 1727 | 27386 | 2301800260000 | 11 | Allegheny | 820' S.W. OF SR 3021 | SCHEINBACH RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2661 | -79.9305 | 20150170090 | Elect | West Penn Power | William (Brad) McCleary, 717-765-2238, wmcclea@firstenergycorp.com Dan Henry, DHENRY2@firstenergycorp.com, engineering supervisor - Don Morchesky, dmorche@firstenergycorp.com |  |  |  | 2016-06-17
440a | -- | 440 | 1733 | 28136 | 2302100300941 | 11 | Allegheny | 100' SOUTHEAST OF SR 3018 | WALTON RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2685 | -79.9259 | 20150341098 | Gas | GUARDIAN INDUSTRIES CORPORATION | Tim Zeuger (Roach and Assoc), twzeuger@roachassoc.com, 412-706-2581 | UG | 4" |  | 2016-07-11
440b | -- | 440 | 1733 | 28136 | 2302100300941 | 11 | Allegheny | 100' SOUTHEAST OF SR 3018 | WALTON RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2685 | -79.9259 | 20150341098 |  | Borough of Jefferson Hills | 412-828-0101 |  |  |  | 2016-07-11
440c | -- | 440 | 1733 | 28136 | 2302100300941 | 11 | Allegheny | 100' SOUTHEAST OF SR 3018 | WALTON RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2685 | -79.9259 | 20150341098 | Wtr | Pennsylvania American Water CO | Joe Tewell, joseph.tewell@amwater.com | UG |  |  | 2016-07-11
440d | -- | 440 | 1733 | 28136 | 2302100300941 | 11 | Allegheny | 100' SOUTHEAST OF SR 3018 | WALTON RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2685 | -79.9259 | 20150341098 | Elect | West Penn Power | Heather Buknic, 724-942-5295, Dan Henry, DHENRY2@firstenergycorp.com |  |  |  | 2016-07-11
440e | -- | 440 | 1733 | 28136 | 2302100300941 | 11 | Allegheny | 100' SOUTHEAST OF SR 3018 | WALTON RD | LOBBS RUN | 02/440 - JEFFERSON HILLS | 40.2685 | -79.9259 | 20150341098 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-07-11
441a | -- | 441 | 1776 | 27454 | 2304801200000 | 11 | Allegheny | 1 MI. W. OF SR3041 | NOBLESTOWN RD | BR. ROBINSON RUN | 02/102 - COLLIER | 40.4113 | -80.1556 | 20150301240 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2016-06-22
441b | -- | 441 | 1776 | 27454 | 2304801200000 | 11 | Allegheny | 1 MI. W. OF SR3041 | NOBLESTOWN RD | BR. ROBINSON RUN | 02/102 - COLLIER | 40.4113 | -80.1556 | 20150301240 | wtr | Pennsylvania American Water CO | Gary Eiter, 412-854-7619, Gary.Eiter@amwater.com | UG |  |  | 2016-06-22
442a | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | 20150170118, 20150170119 | gas | COLUMBIA GAS OF PA | Dominic Tarella, dtarella@nisource.com 724-462-3479 | UG |  |  | 2016-04-06
442b | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | 20150170118, 20150170119 | Wtr | Pennsylvania American Water Company | Eric Beringer, 724-743-3108, eric.beringer@amwater.com | UG |  |  | 2016-04-06
442c | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | 20150170118, 20150170119 | Gas | Peoples Gas Company | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  |  | 2016-04-06
442d | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | 20150170118, 20150170119 | sanitary | Pittsburgh Water and Sewer Authority | Robert Christian, (412) 255-2579, rchristian@pgh2o.com | UG |  |  | 2016-04-06
442e | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | 20150170118, 20150170119 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  |  | 2016-04-06
442f | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | 20150170118, 20150170119 | Comm | Verizon Pennsylvania LLC | Jon Gaunt, 412-237-2290, jon.c.gaunt@verizon.com | OH |  |  | 2016-04-06
442g | -- | 442 | 1859 | 27430 | 2309800500762 | 11 | Allegheny | 1 1/2 MI FROM GLNWOOD INT | GLASS RUN RD | GLASS RUN | 02/301 - PITTSBURGH | 40.3896 | -79.9556 | 20150170118, 20150170119 | Comm | Comcast | Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | OH |  |  | 2016-04-06
443a | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | 20150161724 | Wtr | Pennsylvania American Water CO | Ed Benson, 724-981-1200 | UG |  |  | 2016-06-17
443b | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | 20150161724 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-06-17
443c | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | 20150161724 |  | Pittsburgh City Dept of Public Works | 412-255-8850 |  |  |  | 2016-06-17
443d | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | 20150161724 | sanitary | Pittsburgh Water and Sewer Authority | Rich Barr, 412-255-8800 x8030, Don Waldorf, dwaldorf@pgh20.com | UG |  |  | 2016-06-17
443e | -- | 443 | 1860 | 27429 | 2309800601125 | 11 | Allegheny | NEAR SR 3100 | GLASS RUN RD | GLASS RUN CREEK | 02/301 - PITTSBURGH | 40.3895 | -79.941 | 20150161724 | gas | Sunoco Pipeline LP | sxldesignreviews@sunocologistics.com; Tracy Hoffman, 610-670-3256, tlhoffman@sunocologistics.com | UG |  |  | 2016-06-17
444a | -- | 444 | 1881 | 89079 | 2310800100174 | 11 | Allegheny | 200' S.W. OF SR 3049 | NORTH BRANCH RD | NORTH BRANCH ROBINSON RN | 02/214 - NORTH FAYETTE | 40.3953 | -80.2586 | 20150170120, 20150170121 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com |  |  |  | 2016-05-23
444b | -- | 444 | 1881 | 89079 | 2310800100174 | 11 | Allegheny | 200' S.W. OF SR 3049 | NORTH BRANCH RD | NORTH BRANCH ROBINSON RN | 02/214 - NORTH FAYETTE | 40.3953 | -80.2586 | 20150170120, 20150170121 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Dennis Rachocki, 814-333-0288, dennis.rachocki@windstream.com |  |  |  | 2016-05-23
444c | -- | 444 | 1881 | 89079 | 2310800100174 | 11 | Allegheny | 200' S.W. OF SR 3049 | NORTH BRANCH RD | NORTH BRANCH ROBINSON RN | 02/214 - NORTH FAYETTE | 40.3953 | -80.2586 | 20150170120, 20150170121 |  | Robinson TWP | Anthony Lenze, 412-923-2411 | UG |  |  | 2016-05-23
444d | -- | 444 | 1881 | 89079 | 2310800100174 | 11 | Allegheny | 200' S.W. OF SR 3049 | NORTH BRANCH RD | NORTH BRANCH ROBINSON RN | 02/214 - NORTH FAYETTE | 40.3953 | -80.2586 | 20150170120, 20150170121 |  | Municipal Auth of Western Allegheny Cnty | Ron Usenic, 412-788-4337 | UG |  |  | 2016-05-23
445a | -- | 445 | 1882 | 78407 | 2310800301395 | 11 | Allegheny | 100' N.E. OF SR 3053 | NORTH BRANCH RD | BR. NORTH BR.ROBINSON RN | 02/214 - NORTH FAYETTE | 40.4014 | -80.2449 | 20150420669 |  | North Fayette TWP | Robert Grimm, 412-788-4888 | UG |  |  | 2017-05-22
445b | -- | 445 | 1882 | 78407 | 2310800301395 | 11 | Allegheny | 100' N.E. OF SR 3053 | NORTH BRANCH RD | BR. NORTH BR.ROBINSON RN | 02/214 - NORTH FAYETTE | 40.4014 | -80.2449 | 20150420669 | Gas | Peoples Gas Hopewell Division | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2017-05-22
445c | -- | 445 | 1882 | 78407 | 2310800301395 | 11 | Allegheny | 100' N.E. OF SR 3053 | NORTH BRANCH RD | BR. NORTH BR.ROBINSON RN | 02/214 - NORTH FAYETTE | 40.4014 | -80.2449 | 20150420669 | Elect | West Penn Power | Heather Buknic, 724-942-5295, Dan Henry, DHENRY2@firstenergycorp.com |  |  |  | 2017-05-22
445d | -- | 445 | 1882 | 78407 | 2310800301395 | 11 | Allegheny | 100' N.E. OF SR 3053 | NORTH BRANCH RD | BR. NORTH BR.ROBINSON RN | 02/214 - NORTH FAYETTE | 40.4014 | -80.2449 | 20150420669 |  | Municipal Auth of Western Allegheny Cnty | Ron Usenic, 412-788-4337 | UG |  |  | 2017-05-22
446a | Y | 446 | 1950 | 74338 | 2401700500880 | 11 | Allegheny | NEAR TWP GARAGE | PINE CREEK RD | LITTLE PINE CREEK | 02/118 - SHALER | 40.5209 | -79.9658 | 20140162092 | Comm | SUNESYS | Mike Coudriet, (412) 462-4561 X 2353 | OH |  | Coordinated | 2015-08-07
446b | Y | 446 | 1950 | 74338 | 2401700500880 | 11 | Allegheny | NEAR TWP GARAGE | PINE CREEK RD | LITTLE PINE CREEK | 02/118 - SHALER | 40.5209 | -79.9658 | 20140162092 | Comm | Verizon | Deborah D Delia, 412-633-3810 | OH |  | Coordinated | 2015-08-07
446c | Y | 446 | 1950 | 74338 | 2401700500880 | 11 | Allegheny | NEAR TWP GARAGE | PINE CREEK RD | LITTLE PINE CREEK | 02/118 - SHALER | 40.5209 | -79.9658 | 20140162092 | Wtr | Hampton-Shaler | Sam Scarfone, 412-486-4867 | UG |  | Prior | 2015-08-07
446d | Y | 446 | 1950 | 74338 | 2401700500880 | 11 | Allegheny | NEAR TWP GARAGE | PINE CREEK RD | LITTLE PINE CREEK | 02/118 - SHALER | 40.5209 | -79.9658 | 20140162092 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127, 412-473-3960 | UG |  | Prior | 2015-08-07
446e | Y | 446 | 1950 | 74338 | 2401700500880 | 11 | Allegheny | NEAR TWP GARAGE | PINE CREEK RD | LITTLE PINE CREEK | 02/118 - SHALER | 40.5209 | -79.9658 | 20140162092 | Gas | PEOPLES NATURAL GAS | Jerome Vergenes, JEROME.P.VERGENES@peoples-gas.com, 1-724-857-2127, 412-473-3960 | UG |  | Coordinated | 2015-08-07
446f | Y | 446 | 1950 | 74338 | 2401700500880 | 11 | Allegheny | NEAR TWP GARAGE | PINE CREEK RD | LITTLE PINE CREEK | 02/118 - SHALER | 40.5209 | -79.9658 | 20140162092 | Elect | DUQUESNE LIGHT COMPANY | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  | Prior | 2015-08-07
447 | -- | 447 | 1974 | 78413 | 2403200902202 | 11 | Allegheny | 419' W OF LR 02090 | FERN HOLLOW RD | BR LITTLE SEWICKLEY CRK | 02/459 - SEWICKLEY HEIGH | 40.5816 | -80.1483 | 20150340804 |  | all facilities responded clear per one call |  |  |  |  | 2016-07-14
448 | -- | 448 | 1976 | 78414 | 2403600701676 | 11 | Allegheny | @ INTER.TURKEY FOOT ROAD | BIG SEWICKLEY C RD | BR.BIG SEWICKLEY CREEK | 02/480 - BELL ACRES | 40.5953 | -80.1949 | 20150340889 | wtr | Ambridge Water Authority | Bill Bebout, 724-266-7810, Jeff Allen, jallen@ambwater.org | UG |  |  | 2017-02-21
449a | -- | 449 | 1980 | 78416 | 2403601303135 | 11 | Allegheny | @ CAMP MEETING RD. EXT. | BIG SEWICKLEY CK R | BR.BIG SEWICKLEY CREEK | 02/480 - BELL ACRES | 40.6087 | -80.1593 | 20150301286 |  | Municipal Auth of Western Allegheny Cnty | Ron Usenic, 412-788-4337 | UG |  |  | 2016-07-08
449b | -- | 449 | 1980 | 78416 | 2403601303135 | 11 | Allegheny | @ CAMP MEETING RD. EXT. | BIG SEWICKLEY CK R | BR.BIG SEWICKLEY CREEK | 02/480 - BELL ACRES | 40.6087 | -80.1593 | 20150301286 | wtr | Ambridge Water Authority | Bill Bebout, 724-266-7810, Jeff Allen, jallen@ambwater.org | UG |  |  | 2016-07-08
449c | -- | 449 | 1980 | 78416 | 2403601303135 | 11 | Allegheny | @ CAMP MEETING RD. EXT. | BIG SEWICKLEY CK R | BR.BIG SEWICKLEY CREEK | 02/480 - BELL ACRES | 40.6087 | -80.1593 | 20150301286 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2016-07-08
449d | -- | 449 | 1980 | 78416 | 2403601303135 | 11 | Allegheny | @ CAMP MEETING RD. EXT. | BIG SEWICKLEY CK R | BR.BIG SEWICKLEY CREEK | 02/480 - BELL ACRES | 40.6087 | -80.1593 | 20150301286 | Comm | COMCAST CABLE COMMUNICATIONS, INC. | Raymond Jones, raymond_jones@cable.comcast.com |  |  |  | 2016-07-08
450a | -- | 450 | 1982 | 78417 | 2403601400961 | 11 | Allegheny | @ INTER.WITH APPL.4846 | BIG SEWICKLEY CR | BR.BIG SEWICKLEY CREEK | 02/411 - BRADDOCK HILLS | 40.6105 | -80.1539 | 20150170123 | wtr | Ambridge Water Authority | Bill Bebout, 724-266-7810, Jeff Allen, jallen@ambwater.org | UG |  |  | 2016-05-19
450b | -- | 450 | 1982 | 78417 | 2403601400961 | 11 | Allegheny | @ INTER.WITH APPL.4846 | BIG SEWICKLEY CR | BR.BIG SEWICKLEY CREEK | 02/411 - BRADDOCK HILLS | 40.6105 | -80.1539 | 20150170123 | sanitary | Economy Borough Municipal Auth | Jim Skonieczny, gymsko10@gmail.com | UG |  |  | 2016-05-19
450c | -- | 450 | 1982 | 78417 | 2403601400961 | 11 | Allegheny | @ INTER.WITH APPL.4846 | BIG SEWICKLEY CR | BR.BIG SEWICKLEY CREEK | 02/411 - BRADDOCK HILLS | 40.6105 | -80.1539 | 20150170123 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2016-05-19
451a | -- | 451 | 3599 | 70804 | 4016803300983 | 11 | Beaver | 100'N.OF SR 4034 | FAIRVIEW RD | UPPER DRY RUN | 04/430 - OHIOVILLE | 40.6602 | -80.4773 | 20151472773 |  | Ohioville Borough Municipal Authority | 724-643-6712, 146 Fairlane Dr Industry PA 15052 | UG |  |  | 2017-06-06
451b | -- | 451 | 3599 | 70804 | 4016803300983 | 11 | Beaver | 100'N.OF SR 4034 | FAIRVIEW RD | UPPER DRY RUN | 04/430 - OHIOVILLE | 40.6602 | -80.4773 | 20151472773 | Gas | PEOPLES NATURAL GAS COMPANY LLC | Michael Fontana, 724-857-2176 | UG |  |  | 2017-06-06
452 | -- | 452 | 3602 | 28944 | 4016805001748 | 11 | Beaver | .4 MI.SW OF TWP.RD.603 | Tuscarawas Road | PAINTERS RUN | 04/217 - SOUTH BEAVER | 40.784 | -80.4542 | 20151470662 |  | all facilities responded clear per one call |  |  |  |  | 2017-05-22
453a | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | 20150170125 | gas | NATIONAL FUEL GAS DISTRIBUTION CORPORATION | James Kennedy, kennedyj@natfuel.com. 716-857-7368 | UG |  |  | 2016-05-25
453b | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | 20150170125 | Comm | ARMSTRONG | William Norris, 724-452-5213 |  |  |  | 2016-05-25
453c | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | 20150170125 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2016-05-25
453d | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | 20150170125 | gas | Columbia Gas Transmission Ellwood | Ken Houston, 724-858-7676, kphouston@nisource.com | UG |  |  | 2016-05-25
453e | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | 20150170125 | wtr | North Sewickley TWP Water Auth | Ken Douglass, 724-846-7480 | UG |  |  | 2016-05-25
453f | -- | 453 | 3647 | 93613 | 4100500202450 | 11 | Beaver | 1/4 MI. NORTH OF SR 1012 | CHAPEL DR | BR. CONNOQUENESSING CR. | 04/212 - NORTH SEWICKLEY | 40.8218 | -80.254 | 20150170125 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG |  |  | 2016-05-25
454a | -- | 454 | 3654 | 80062 | 4101400700193 | 11 | Beaver | 100'NORTHEAST OF PIKE | WISE'S GROVE RD | BRUSH CREEK | 04/210 - MARION | 40.7723 | -80.2369 | 20150350331 | Comm | ARMSTRONG | William Norris, 724-452-5213 |  |  |  | 2017-05-11
454b | -- | 454 | 3654 | 80062 | 4101400700193 | 11 | Beaver | 100'NORTHEAST OF PIKE | WISE'S GROVE RD | BRUSH CREEK | 04/210 - MARION | 40.7723 | -80.2369 | 20150350331 | Wtr | North Sewickley TWP Water Auth | Ken Douglass, 724-846-7480 | UG |  |  | 2017-05-11
454c | -- | 454 | 3654 | 80062 | 4101400700193 | 11 | Beaver | 100'NORTHEAST OF PIKE | WISE'S GROVE RD | BRUSH CREEK | 04/210 - MARION | 40.7723 | -80.2369 | 20150350331 | Elect | PENNSYLVANIA POWER CO | Dave Nickel, 724-962-1083, nickeld@firstenergycorp.com | OH |  |  | 2017-05-11
455a | -- | 455 | 3693 | 69069 | 4300500800933 | 11 | Beaver | @ INTER.W/TWP.RD.491 | CHAPEL RD | MOON RUN | 04/202 - CENTER | 40.6718 | -80.294 | 20150341801 | sanitary | Center TWP Sanitary Auth | Bob Zupsic, 724-774-0326 | UG |  |  | 2017-04-24
455b | -- | 455 | 3693 | 69069 | 4300500800933 | 11 | Beaver | @ INTER.W/TWP.RD.491 | CHAPEL RD | MOON RUN | 04/202 - CENTER | 40.6718 | -80.294 | 20150341801 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2017-04-24
456a | -- | 456 | 3695 | 67378 | 4300900600000 | 11 | Beaver | 0.5 MI.SOUTH OF SR 3007 | KANE RD | TRAMP MILL RUN | 04/103 - HOPEWELL | 40.5944 | -80.28 | 20150341820 | Wtr | Creswell Heights Joint Auth | George McElhaney, 724-375-6155 | UG |  |  | 2017-04-24
456b | -- | 456 | 3695 | 67378 | 4300900600000 | 11 | Beaver | 0.5 MI.SOUTH OF SR 3007 | KANE RD | TRAMP MILL RUN | 04/103 - HOPEWELL | 40.5944 | -80.28 | 20150341820 | Wtr | Hopewell TWP | Jim Somerville, 724-378-1460 | UG |  |  | 2017-04-24
457 | -- | 457 | 3717 | 70805 | 4302500701409 | 11 | Beaver | @ INTER. WITH TWP.RD.544 | BOCKTOWN CORK RD | RAREDON RUN | 04/209 - INDEPENDENCE | 40.5417 | -80.3008 | 20143580299 |  | all facilities responded clear per one call |  |  |  |  | 2016-05-20
458a | -- | 458 | 3722 | 70807 | 4302700400000 | 11 | Beaver | .5 MILE NORTH OF SR 168 | GEORGETOWN RD | MILL CREEK | 04/207 - GREENE | 40.6116 | -80.4874 | 20143570586 | Elect | DUQUESNE LIGHT | Jim Runatz, 412-779-1800 jrunatz@duqlight.com | OH |  |  | 2016-05-19
458b | -- | 458 | 3722 | 70807 | 4302700400000 | 11 | Beaver | .5 MILE NORTH OF SR 168 | GEORGETOWN RD | MILL CREEK | 04/207 - GREENE | 40.6116 | -80.4874 | 20143570586 | Comm | Verizon | Karen McBeth, karen.s.mcbeth@verizon.com | OH |  |  | 2016-05-19
458c | -- | 458 | 3722 | 70807 | 4302700400000 | 11 | Beaver | .5 MILE NORTH OF SR 168 | GEORGETOWN RD | MILL CREEK | 04/207 - GREENE | 40.6116 | -80.4874 | 20143570586 | Comm | Comcast | Craig Tacy, 724-503-4362, Craig_Tacy@cable.comcast.com | OH |  |  | 2016-05-19
459 | -- | 459 | 3723 | 89058 | 4302700460000 | 11 | Beaver | GREENE TWP.-MILL CREEK | GEORGETOWN RD | MILL CREEK | 04/207 - GREENE | 40.6224 | -80.4971 | 20150161766 |  | all facilities responded clear per one call |  |  |  |  | 2016-06-08
460 | -- | 460 | 3747 | 99793 | 4401201000519 | 11 | Beaver | 200'EAST&UNDER SR 0060 | BRADY RUN RD | SOUTH BRANCH BRADY RUN | 04/201 - BRIGHTON | 40.7235 | -80.367 | 20150161774 |  | all facilities responded clear per one call |  |  |  |  | 2016-05-31
461 | -- | 461 | 3749 | 29062 | 4401201100256 | 11 | Beaver | .2 MI. N.E. OF SR 4018 | BRADYS RUN RD | SOUTH BRANCH BRADY'S RUN | 04/201 - BRIGHTON | 40.7245 | -80.3626 | 20151471730 |  | all facilities responded clear per one call |  |  |  |  | 2017-05-30
462 | -- | 462 | 3750 | 78310 | 4401201500926 | 11 | Beaver | 100 FT WEST OF SR 0051 | BRADYS RUN RD | BRADYS RUN | 04/201 - BRIGHTON | 40.7325 | -80.3365 | 20151472898, 20151472899 |  | all facilities responded clear per one call |  |  |  |  | 2017-03-06
463a | -- | 463 | 3755 | 99794 | 4401900500000 | 11 | Beaver | 1/2 MI. WEST OF SR 4021 | PARK RD | N.BR.BRADYS RUN | 04/203 - CHIPPEWA | 40.7468 | -80.3856 | 20150330155 |  | Beaver Falls Municipal Auth | Sam Aloi, aloi@bfwater.net | UG |  |  | 2016-08-15
463b | -- | 463 | 3755 | 99794 | 4401900500000 | 11 | Beaver | 1/2 MI. WEST OF SR 4021 | PARK RD | N.BR.BRADYS RUN | 04/203 - CHIPPEWA | 40.7468 | -80.3856 | 20150330155 | sanitary | Bradys Run Sanitary Auth | Ron Newhouse, wwtp@chippewa-sewer.org | UG |  |  | 2016-08-15
463c | -- | 463 | 3755 | 99794 | 4401900500000 | 11 | Beaver | 1/2 MI. WEST OF SR 4021 | PARK RD | N.BR.BRADYS RUN | 04/203 - CHIPPEWA | 40.7468 | -80.3856 | 20150330155 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com |  |  |  | 2016-08-15
464 | -- | 464 | 3769 | 78313 | 4403400200000 | 11 | Beaver | 500' WEST OF SR 0068 | WESTWOOD RD | UPPER DRY RUN | 04/430 - OHIOVILLE | 40.6606 | -80.4837 | 20150620724 | Gas | Access Midstream | 607-739-3616 | UG |  |  | 2017-04-24
465a | -- | 465 | 22262 | 29374 | 37020800700000 | 11 | Lawrence | 1.5 MI. FROM ST.LINE | PULASKI RD | OVER DEER CREEK | 37/209 - PULASKI | 41.1081 | -80.4759 | 20151470992 |  | Pulaski TWP | Frank Taylor, 724-654-6141 |  |  |  | 2017-05-26
465b | -- | 465 | 22262 | 29374 | 37020800700000 | 11 | Lawrence | 1.5 MI. FROM ST.LINE | PULASKI RD | OVER DEER CREEK | 37/209 - PULASKI | 41.1081 | -80.4759 | 20151470992 |  | Pulaski TWP Municipal Authority | 724-964-8891 x103 | UG |  |  | 2017-05-26
465c | -- | 465 | 22262 | 29374 | 37020800700000 | 11 | Lawrence | 1.5 MI. FROM ST.LINE | PULASKI RD | OVER DEER CREEK | 37/209 - PULASKI | 41.1081 | -80.4759 | 20151470992 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG |  |  | 2017-05-26
466 | -- | 466 | 22265 | 78362 | 37020801000000 | 11 | Lawrence | 3000' WEST OF SR 0551 | PULASKI RD | BRANCH DEER CREEK | 37/209 - PULASKI | 41.1062 | -80.4504 | 20151411253 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG |  |  | 2016-07-05
467a | -- | 467 | 22269 | 29534 | 37020802201379 | 11 | Lawrence | 1/2 MI.WEST / SR0158 | PULASKI RD | MCCLURES RUN | 37/217 - WILMINGTON | 41.1211 | -80.342 | 20150351122 | Gas | Peoples Gas Grove City Division | Christopher (Chris) Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | UG |  |  | 2017-04-24
467b | -- | 467 | 22269 | 29534 | 37020802201379 | 11 | Lawrence | 1/2 MI.WEST / SR0158 | PULASKI RD | MCCLURES RUN | 37/217 - WILMINGTON | 41.1211 | -80.342 | 20150351122 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG |  |  | 2017-04-24
468 | -- | 468 | 22277 | 78318 | 37022400601429 | 11 | Lawrence | NEAR SR 3016 | YOUNGSTOWN POLA RD | SWAMP | 37/204 - MAHONING | 41.0081 | -80.4686 | 20150411766 | Wtr | Aqua Pennsylvania | Dan Conley, 724-981-1200 x50715, DJConley@aquaamerica.com | UG |  |  | 2017-04-03
469a | -- | 469 | 22281 | 89094 | 37022401100412 | 11 | Lawrence | @ INTER. WITH SR 4006 | YOUNGSTOWN POLA RD | BRANCH OF MAHONING RIVER | 37/204 - MAHONING | 41.0251 | -80.4328 | 20150420614 | Wtr | Aqua Pennsylvania | Dan Conley, 724-981-1200 x50715, DJConley@aquaamerica.com | UG |  |  | 2017-04-24
469b | -- | 469 | 22281 | 89094 | 37022401100412 | 11 | Lawrence | @ INTER. WITH SR 4006 | YOUNGSTOWN POLA RD | BRANCH OF MAHONING RIVER | 37/204 - MAHONING | 41.0251 | -80.4328 | 20150420614 | Wtr | Pennsylvania American Water CO | Jack Cypher, 412-384-4190 x14 | UG |  |  | 2017-04-24
469c | -- | 469 | 22281 | 89094 | 37022401100412 | 11 | Lawrence | @ INTER. WITH SR 4006 | YOUNGSTOWN POLA RD | BRANCH OF MAHONING RIVER | 37/204 - MAHONING | 41.0251 | -80.4328 | 20150420614 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG & OH |  |  | 2017-04-24
470a | -- | 470 | 22358 | 78370 | 37095601200542 | 11 | Lawrence | 2 MI.EAST OF SR 0018 | NESHANN0CK FALLS R | NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0894 | -80.289 | 20151471060 | Comm | Centurylink formerly Embarq | Leo Hilbert, leo.c.hilbert@centurylink.com | UG |  |  | 2017-05-22
470b | -- | 470 | 22358 | 78370 | 37095601200542 | 11 | Lawrence | 2 MI.EAST OF SR 0018 | NESHANN0CK FALLS R | NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0894 | -80.289 | 20151471060 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG |  |  | 2017-05-22
471a | -- | 471 | 22359 | 69103 | 37095601501187 | 11 | Lawrence | 1/2 MI. S.E. OF SR 1005 | NESHANNOCK FALLS R | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0895 | -80.3154 | 20150161711 | Elect | PENNSYLVANIA POWER CO | Ted Wyvratt, 724-453-3403, twyvratt@firstenergycorp.com | UG & OH |  |  | 2016-06-08
471b | -- | 471 | 22359 | 69103 | 37095601501187 | 11 | Lawrence | 1/2 MI. S.E. OF SR 1005 | NESHANNOCK FALLS R | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0895 | -80.3154 | 20150161711 | Comm | Verizon North LLC | Robert Preston, (304) 670-9999, robert.preston@cyient.com Eric Rodrigues, 814 871-2317, eric.rodrigues@verizon.com | UG & OH |  |  | 2016-06-08
471c | -- | 471 | 22359 | 69103 | 37095601501187 | 11 | Lawrence | 1/2 MI. S.E. OF SR 1005 | NESHANNOCK FALLS R | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0895 | -80.3154 | 20150161711 | Comm | Comcast | Mark Painter, 724-734-1977, mark_painter@cable.comcast.com Rick Moslen, 412-999-0590 Richard_Moslen@cable.comcast.com | OH |  |  | 2016-06-08
472 | -- | 472 | 22362 | 78374 | 37095601900000 | 11 | Lawrence | 1 MI.NORTH TWP.RD.601 | NESHANNOCK FALL RD | BR.LITTLE NESHANNOCK CR. | 37/217 - WILMINGTON | 41.1063 | -80.3292 | 20150411781 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com |  |  |  | 2017-03-01
473a | -- | 473 | 22369 | 69231 | 37100501501309 | 11 | Lawrence | 1/4 MI. N.E. OF SR 0956 | HIGHLAND AV. | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0944 | -80.3191 | 20150351122, 20151471110 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG |  |  | 2017-07-24
473b | -- | 473 | 22369 | 69231 | 37100501501309 | 11 | Lawrence | 1/4 MI. N.E. OF SR 0956 | HIGHLAND AV. | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0944 | -80.3191 | 20150351122, 20151471110 | Gas | Peoples Gas Design Grove City | Christopher (Chris) Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | UG |  |  | 2017-07-24
473c | -- | 473 | 22369 | 69231 | 37100501501309 | 11 | Lawrence | 1/4 MI. N.E. OF SR 0956 | HIGHLAND AV. | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0944 | -80.3191 | 20150351122, 20151471110 | Gas | Peoples Gas Grove City Division | Christopher (Chris) Carlisle, 412-398-4543, Chris.A.Carlisle@peoples-gas.com | UG | 4" |  | 2017-07-24
473d | -- | 473 | 22369 | 69231 | 37100501501309 | 11 | Lawrence | 1/4 MI. N.E. OF SR 0956 | HIGHLAND AV. | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0944 | -80.3191 | 20150351122, 20151471110 | Gas | Laurel Mountain Midstream LLC | Delbert Woloski, delbert.woloski@williams.com | UG |  |  | 2017-07-24
473e | -- | 473 | 22369 | 69231 | 37100501501309 | 11 | Lawrence | 1/4 MI. N.E. OF SR 0956 | HIGHLAND AV. | LITTLE NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0944 | -80.3191 | 20150351122, 20151471110 | Comm | Verizon North LLC | Michael Geary, michael.geary@verizon.net |  |  |  | 2017-07-24
474 | -- | 474 | 22374 | 78378 | 37100900603315 | 11 | Lawrence | 100' SOUTH OF SR 0956 | NESHANNOCK FALL RD | BRANCH NESHANNOCK CREEK | 37/217 - WILMINGTON | 41.0892 | -80.2875 | 20150341698 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com |  |  |  | 2016-07-08
475a | -- | 475 | 22378 | 99796 | 37101200700000 | 11 | Lawrence | 300'WEST OF TWP.RD.478 | FREW MILL RD. | BIG RUN | 37/212 - SLIPPERY ROCK | 40.9918 | -80.2619 | 20150350479 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com |  |  |  | 2017-05-11
475b | -- | 475 | 22378 | 99796 | 37101200700000 | 11 | Lawrence | 300'WEST OF TWP.RD.478 | FREW MILL RD. | BIG RUN | 37/212 - SLIPPERY ROCK | 40.9918 | -80.2619 | 20150350479 |  | Slippery Rock TWP | Jack Armagost, 724-924-2482, srtwp@zoominternt.net | UG |  |  | 2017-05-11
476a | -- | 476 | 22379 | 29321 | 37101200900000 | 11 | Lawrence | .5 MI.W.TWP.RD.488 | FREW MILL RD | BIG RUN | 37/212 - SLIPPERY ROCK | 40.9941 | -80.2446 | 20150291606 | Comm | ARMSTRONG | William Norris, 724-452-5213 |  |  |  | 2016-08-03
476b | -- | 476 | 22379 | 29321 | 37101200900000 | 11 | Lawrence | .5 MI.W.TWP.RD.488 | FREW MILL RD | BIG RUN | 37/212 - SLIPPERY ROCK | 40.9941 | -80.2446 | 20150291606 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG & OH |  |  | 2016-08-03
476c | -- | 476 | 22379 | 29321 | 37101200900000 | 11 | Lawrence | .5 MI.W.TWP.RD.488 | FREW MILL RD | BIG RUN | 37/212 - SLIPPERY ROCK | 40.9941 | -80.2446 | 20150291606 |  | Slippery Rock TWP | Jack Armagost, 724-924-2482, srtwp@zoominternt.net | UG |  |  | 2016-08-03
476d | -- | 476 | 22379 | 29321 | 37101200900000 | 11 | Lawrence | .5 MI.W.TWP.RD.488 | FREW MILL RD | BIG RUN | 37/212 - SLIPPERY ROCK | 40.9941 | -80.2446 | 20150291606 | Comm | Verizon North LLC | Michael Geary, michael.geary@verizon.net |  |  |  | 2016-08-03
477 | -- | 477 | 22396 | 29387 | 37200100802619 | 11 | Lawrence | 100' SOUTH OF SR 2012 | SAVANNAH RD | MCKEE RUN | 37/211 - SHENANGO | 40.9363 | -80.3418 | 20150330166 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG & OH |  |  | 2016-08-15
478a | -- | 478 | 22416 | 99798 | 37201200103494 | 11 | Lawrence | 100' WEST OF TWP.RD.434 | UNION VALLEY RD | BRANCH OF MCKEE RUN | 37/211 - SHENANGO | 40.9379 | -80.3513 | 20150351748 20150351749 | Wtr | Pennsylvania American Water CO | Jack Cypher, 412-384-4190 x14 | UG |  |  | 2017-04-24
478b | -- | 478 | 22416 | 99798 | 37201200103494 | 11 | Lawrence | 100' WEST OF TWP.RD.434 | UNION VALLEY RD | BRANCH OF MCKEE RUN | 37/211 - SHENANGO | 40.9379 | -80.3513 | 20150351748 20150351749 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com |  |  |  | 2017-04-24
479a | -- | 479 | 22433 | 29525 | 37300100300259 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | SOUTH MAIN ST | BESSEMER HAUL ROAD | 37/401 - BESSEMER | 40.9714 | -80.4936 | 20150341785 |  | Borough of Bessemer | Mary Ann Cardella (secy), 412-667-7061 | UG |  |  | 2017-05-11
479b | -- | 479 | 22433 | 29525 | 37300100300259 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | SOUTH MAIN ST | BESSEMER HAUL ROAD | 37/401 - BESSEMER | 40.9714 | -80.4936 | 20150341785 |  | Bessemer Municipal Auth | Mary Ann Cardella (secy), 412-667-7061 | UG |  |  | 2017-05-11
479c | -- | 479 | 22433 | 29525 | 37300100300259 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | SOUTH MAIN ST | BESSEMER HAUL ROAD | 37/401 - BESSEMER | 40.9714 | -80.4936 | 20150341785 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG | 4" |  | 2017-05-11
479d | -- | 479 | 22433 | 29525 | 37300100300259 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | SOUTH MAIN ST | BESSEMER HAUL ROAD | 37/401 - BESSEMER | 40.9714 | -80.4936 | 20150341785 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG & OH |  |  | 2017-05-11
480a | -- | 480 | 22439 | 99797 | 37300300800000 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | STATE LINE RD. | HICKORY CREEK | 37/206 - NORTH BEAVER | 40.9684 | -80.5192 | 20150420644 |  | North Beaver TWP | Margaret J. Seltzer (secy), 412-667-7956 | UG |  |  | 2017-03-20
480b | -- | 480 | 22439 | 99797 | 37300300800000 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | STATE LINE RD. | HICKORY CREEK | 37/206 - NORTH BEAVER | 40.9684 | -80.5192 | 20150420644 |  | North Beaver TWP Muncipal Auth | Margaret J. Seltzer (secy), 412-667-7956 | UG |  |  | 2017-03-20
480c | -- | 480 | 22439 | 99797 | 37300300800000 | 11 | Lawrence | 1/4 MI. SOUTH OF SR 0317 | STATE LINE RD. | HICKORY CREEK | 37/206 - NORTH BEAVER | 40.9684 | -80.5192 | 20150420644 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com | UG & OH |  |  | 2017-03-20
481a | -- | 481 | 22441 | 29549 | 37300400600000 | 11 | Lawrence | 3/4 MILE W OF TR 551 | PETERSBURG RD | OVER BR OF HONEY CREEK | 37/206 - NORTH BEAVER | 40.9214 | -80.4775 | 20150361529 |  | North Beaver TWP | Margaret J. Seltzer (secy), 412-667-7956 | UG |  |  | 2017-04-24
481b | -- | 481 | 22441 | 29549 | 37300400600000 | 11 | Lawrence | 3/4 MILE W OF TR 551 | PETERSBURG RD | OVER BR OF HONEY CREEK | 37/206 - NORTH BEAVER | 40.9214 | -80.4775 | 20150361529 |  | North Beaver TWP Muncipal Auth | Margaret J. Seltzer (secy), 412-667-7956 | UG |  |  | 2017-04-24
481c | -- | 481 | 22441 | 29549 | 37300400600000 | 11 | Lawrence | 3/4 MILE W OF TR 551 | PETERSBURG RD | OVER BR OF HONEY CREEK | 37/206 - NORTH BEAVER | 40.9214 | -80.4775 | 20150361529 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com |  |  |  | 2017-04-24
481d | -- | 481 | 22441 | 29549 | 37300400600000 | 11 | Lawrence | 3/4 MILE W OF TR 551 | PETERSBURG RD | OVER BR OF HONEY CREEK | 37/206 - NORTH BEAVER | 40.9214 | -80.4775 | 20150361529 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Gail Schmitz, Gail.Schmitz@windstream.com | UG |  |  | 2017-04-24
482 | -- | 482 | 22455 | 80677 | 37301500201288 | 11 | Lawrence | 1/4 MI W OF SR 2012 | MORAVIA ST | MCKEE RUN | 37/213 - TAYLOR | 40.9376 | -80.3662 | 20143571138 | Elect | PENNSYLVANIA POWER CO | Eric Powell, Ohio Edison Engineering, 330-740-7617, epowell@firstenergycorp.com |  |  |  | 2016-05-20
483a | -- | 483 | 16651 | 51503 | 26016603900000 | 12 | Fayette | REDSTONE & LUZERNE TWPS. | SR 0166 | DUNLAP CREEK | 26/216 - REDSTONE | 39.9603 | -79.8778 | 20143571450, 20143571452 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2016-05-19
483b | -- | 483 | 16651 | 51503 | 26016603900000 | 12 | Fayette | REDSTONE & LUZERNE TWPS. | SR 0166 | DUNLAP CREEK | 26/216 - REDSTONE | 39.9603 | -79.8778 | 20143571450, 20143571452 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | UG |  |  | 2016-05-19
483c | -- | 483 | 16651 | 51503 | 26016603900000 | 12 | Fayette | REDSTONE & LUZERNE TWPS. | SR 0166 | DUNLAP CREEK | 26/216 - REDSTONE | 39.9603 | -79.8778 | 20143571450, 20143571452 | Wtr | Southwestern PA Water Authority | Edward J. Mihalsky, repshop@verizon.net | UG |  |  | 2016-05-19
484a | -- | 484 | 16673 | 51484 | 26038100801000 | 12 | Fayette | WHARTON TOWNSHIP | SR 0381 | STONY RUN | 26/224 - WHARTON | 39.7661 | -79.6245 | 20143580452 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2017-05-23
484b | -- | 484 | 16673 | 51484 | 26038100801000 | 12 | Fayette | WHARTON TOWNSHIP | SR 0381 | STONY RUN | 26/224 - WHARTON | 39.7661 | -79.6245 | 20143580452 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | UG |  |  | 2017-05-23
484c | -- | 484 | 16673 | 51484 | 26038100801000 | 12 | Fayette | WHARTON TOWNSHIP | SR 0381 | STONY RUN | 26/224 - WHARTON | 39.7661 | -79.6245 | 20143580452 | Comm | Comcast Cable of Garrett County MD | Randy Heel, randy_reel@cable.comcast.com |  |  |  | 2017-05-23
484d | -- | 484 | 16673 | 51484 | 26038100801000 | 12 | Fayette | WHARTON TOWNSHIP | SR 0381 | STONY RUN | 26/224 - WHARTON | 39.7661 | -79.6245 | 20143580452 |  | Wharton TWP | Laura Savage (secy), 724-329-8503 | UG |  |  | 2017-05-23
485a | -- | 485 | 16713 | 74174 | 26100100200639 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1001 | MILL RUN | 26/219 - SPRINGFIELD | 39.9514 | -79.4421 | 20151461291 | wtr | INDIAN CREEK VALLEY WATER AUTHORITY | M. Colburn or R. Kerry Witt, 724-455-2905 | UG |  |  | 2017-06-05
485b | -- | 485 | 16713 | 74174 | 26100100200639 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1001 | MILL RUN | 26/219 - SPRINGFIELD | 39.9514 | -79.4421 | 20151461291 |  | Springfield TWP | Donna J. Kooser (secy), 724-455-3015 |  |  |  | 2017-06-05
485c | -- | 485 | 16713 | 74174 | 26100100200639 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1001 | MILL RUN | 26/219 - SPRINGFIELD | 39.9514 | -79.4421 | 20151461291 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com |  |  |  | 2017-06-05
485d | -- | 485 | 16713 | 74174 | 26100100200639 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1001 | MILL RUN | 26/219 - SPRINGFIELD | 39.9514 | -79.4421 | 20151461291 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-06-05
486a | -- | 486 | 16720 | 74176 | 26100300320000 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1003 | LAUREL RUN | 26/219 - SPRINGFIELD | 39.9931 | -79.4141 | 20150350447 | Wtr | INDIAN CREEK VALLEY WATER AUTHORITY | M. Colburn or R. Kerry Witt, 724-455-2905 | UG |  |  | 2017-04-10
486b | -- | 486 | 16720 | 74176 | 26100300320000 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1003 | LAUREL RUN | 26/219 - SPRINGFIELD | 39.9931 | -79.4141 | 20150350447 |  | Springfield TWP | Donna J. Kooser (secy), 724-455-3015 | UG |  |  | 2017-04-10
486c | -- | 486 | 16720 | 74176 | 26100300320000 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1003 | LAUREL RUN | 26/219 - SPRINGFIELD | 39.9931 | -79.4141 | 20150350447 | Comm | Verizon North LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com |  |  |  | 2017-04-10
486d | -- | 486 | 16720 | 74176 | 26100300320000 | 12 | Fayette | SPRINGFIELD TOWNSHIP | SR 1003 | LAUREL RUN | 26/219 - SPRINGFIELD | 39.9931 | -79.4141 | 20150350447 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | UG |  |  | 2017-04-10
487 | -- | 487 | 16725 | 81961 | 26100700300000 | 12 | Fayette | SALTLICK TOWNSHIP | SR 1007 | CHAMPION CREEK | 26/217 - SALTLICK | 40.0681 | -79.3992 | 20151422555 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-06-09
488 | -- | 488 | 16736 | 29781 | 26101800100206 | 12 | Fayette | N. UNION & FRANKLIN TWPS. | SR 1018 | BUTE RUN | 26/214 - NORTH UNION | 39.9522 | -79.73 | 20150281894 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | UG |  |  | 2016-08-05
489a | -- | 489 | 16752 | 69229 | 26103100100053 | 12 | Fayette | CONNELLSVILLE CITY & TWP. | SR 1031 | MOUNTS CREEK | 26/301 - CONNELLSVILLE | 40.0264 | -79.5896 | 20150291510 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2016-07-08
489b | -- | 489 | 16752 | 69229 | 26103100100053 | 12 | Fayette | CONNELLSVILLE CITY & TWP. | SR 1031 | MOUNTS CREEK | 26/301 - CONNELLSVILLE | 40.0264 | -79.5896 | 20150291510 |  | City of Connellsville | Antoinette Tesauro, cvstreet@zoominternet.net |  |  |  | 2016-07-08
489c | -- | 489 | 16752 | 69229 | 26103100100053 | 12 | Fayette | CONNELLSVILLE CITY & TWP. | SR 1031 | MOUNTS CREEK | 26/301 - CONNELLSVILLE | 40.0264 | -79.5896 | 20150291510 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-07-08
489d | -- | 489 | 16752 | 69229 | 26103100100053 | 12 | Fayette | CONNELLSVILLE CITY & TWP. | SR 1031 | MOUNTS CREEK | 26/301 - CONNELLSVILLE | 40.0264 | -79.5896 | 20150291510 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 |  |  |  | 2016-07-08
489e | -- | 489 | 16752 | 69229 | 26103100100053 | 12 | Fayette | CONNELLSVILLE CITY & TWP. | SR 1031 | MOUNTS CREEK | 26/301 - CONNELLSVILLE | 40.0264 | -79.5896 | 20150291510 | Wtr | Pennsylvania American Water CO | Clayton Wene, clayton.wene@amwater.com | UG |  |  | 2016-07-08
490a | -- | 490 | 16757 | 74345 | 26103100601336 | 12 | Fayette | UPPER TYRONE TOWNSHIP | SR 1031 | GALLEY RUN | 26/222 - UPPER TYRONE | 40.0518 | -79.6059 | 20151461419, 20151461420 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 |  |  |  | 2017-06-12
490b | -- | 490 | 16757 | 74345 | 26103100601336 | 12 | Fayette | UPPER TYRONE TOWNSHIP | SR 1031 | GALLEY RUN | 26/222 - UPPER TYRONE | 40.0518 | -79.6059 | 20151461419, 20151461420 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-06-12
491a | -- | 491 | 16758 | 76009 | 26103100700299 | 12 | Fayette | CONNELLSVILLE & U. TYRONE | SR 1031 | BRANCH OF GALLEY RUN | 26/203 - CONNELLSVILLE | 40.0531 | -79.6047 | 20150341153 20150341154 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 |  |  |  | 2017-02-27
491b | -- | 491 | 16758 | 76009 | 26103100700299 | 12 | Fayette | CONNELLSVILLE & U. TYRONE | SR 1031 | BRANCH OF GALLEY RUN | 26/203 - CONNELLSVILLE | 40.0531 | -79.6047 | 20150341153 20150341154 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-02-27
492a | -- | 492 | 16782 | 76012 | 26104300200093 | 12 | Fayette | N. UNION & FRANKLIN TWPS. | SR 1043 | REDSTONE CREEK | 26/214 - NORTH UNION | 39.9512 | -79.7354 | 20143580347, 20143580348 | Wtr | North Fayette Cnty Municipal Auth | Bob Softcheck, nfcmabs@zoominternet.net | UG |  |  | 2016-07-08
492b | -- | 492 | 16782 | 76012 | 26104300200093 | 12 | Fayette | N. UNION & FRANKLIN TWPS. | SR 1043 | REDSTONE CREEK | 26/214 - NORTH UNION | 39.9512 | -79.7354 | 20143580347, 20143580348 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-07-08
492c | -- | 492 | 16782 | 76012 | 26104300200093 | 12 | Fayette | N. UNION & FRANKLIN TWPS. | SR 1043 | REDSTONE CREEK | 26/214 - NORTH UNION | 39.9512 | -79.7354 | 20143580347, 20143580348 |  | North Union TWP Municipal Services Auth | Kathy Gilbert, nutmsa@atlanticbb.net | UG |  |  | 2016-07-08
493a | -- | 493 | 16789 | 29820 | 26105000101121 | 12 | Fayette | BULLSKIN TOWNSHIP | SR 1050 | MOUNTS CREEK | 26/202 - BULLSKIN | 40.0549 | -79.555 | 20143571183 | Wtr | PLEASANT VALLEY WATER AUTHORITY | Mark Bageant, 412-628-2930, pvwamark@zoominternet.net | UG |  |  | 2016-03-14
493b | -- | 493 | 16789 | 29820 | 26105000101121 | 12 | Fayette | BULLSKIN TOWNSHIP | SR 1050 | MOUNTS CREEK | 26/202 - BULLSKIN | 40.0549 | -79.555 | 20143571183 | Elect | WEST PENN POWER | Frank McLaughlin, 724-626-6239, fmclaug@firstenergycorp.com Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-03-14
493c | -- | 493 | 16789 | 29820 | 26105000101121 | 12 | Fayette | BULLSKIN TOWNSHIP | SR 1050 | MOUNTS CREEK | 26/202 - BULLSKIN | 40.0549 | -79.555 | 20143571183 | Comm | ARMSTRONG | Tony Kowalewski, tkowalewski@agoc.com, 724-628-6600 |  |  |  | 2016-03-14
493d | -- | 493 | 16789 | 29820 | 26105000101121 | 12 | Fayette | BULLSKIN TOWNSHIP | SR 1050 | MOUNTS CREEK | 26/202 - BULLSKIN | 40.0549 | -79.555 | 20143571183 | Comm | Verizon | Deborah Delia, (412) 237-2285 deborah.d.delia@verizon.com |  |  |  | 2016-03-14
494 | -- | 494 | 16794 | 90965 | 26105002101302 | 12 | Fayette | SALTLICK TOWNSHIP | SR 1050 | CHAMPION CREEK | 26/217 - SALTLICK | 40.0871 | -79.393 | 20151463422 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-09-05
495a | -- | 495 | 16806 | 89075 | 26105103000845 | 12 | Fayette | BULLSKIN TOWNSHIP | SR 1051 | BRANCH OF BREAKNECK RUN | 26/202 - BULLSKIN | 40.0434 | -79.5299 | 20151412100 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 |  |  |  | 2017-05-15
495b | -- | 495 | 16806 | 89075 | 26105103000845 | 12 | Fayette | BULLSKIN TOWNSHIP | SR 1051 | BRANCH OF BREAKNECK RUN | 26/202 - BULLSKIN | 40.0434 | -79.5299 | 20151412100 | wtr | PLEASANT VALLEY WATER AUTHORITY | Mark Bageant, 412-628-2930, pvwamark@zoominternet.net | UG |  |  | 2017-05-15
496 | -- | 496 | 16827 | 29823 | 26105501401377 | 12 | Fayette | DUNBAR TOWNSHIP | SR 1055 | TUCKER RUN | 26/404 - DUNBAR | 39.9448 | -79.5793 | 20151461674 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 |  |  |  | 2017-05-30
497a | -- | 497 | 16840 | 29926 | 26105801300142 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/205 - FRANKLIN | 40.0751 | -79.358 | 20143580467, 20143580470 | Elect | West Penn Power Company | Scott Clausner, 724-626-6238, sclausn@firstenergycorp.com Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-07-01
497b | -- | 497 | 16840 | 29926 | 26105801300142 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/205 - FRANKLIN | 40.0751 | -79.358 | 20143580467, 20143580470 | Wtr | INDIAN CREEK VALLEY WATER AUTHORITY | R. Kerry Witt, 724-455-2905, rkwitt@icvwater.org | UG |  |  | 2016-07-01
497c | -- | 497 | 16840 | 29926 | 26105801300142 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/205 - FRANKLIN | 40.0751 | -79.358 | 20143580467, 20143580470 | Comm | Verizon Pennsylvania LLC | Jeff Guido, 412-793-7501, jeffrey.d.guido@verizon.com | OH |  |  | 2016-07-01
497d | -- | 497 | 16840 | 29926 | 26105801300142 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/205 - FRANKLIN | 40.0751 | -79.358 | 20143580467, 20143580470 | Comm | LAUREL HIGHLAND TOTAL COMMUNICATION | Jeff Stough, 724-455-2411, jstough@lhtot.com | OH |  |  | 2016-07-01
498a | -- | 498 | 16841 | 29893 | 26105801300864 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/217 - SALTLICK | 40.0744 | -79.3556 | 20143571250 | Wtr | INDIAN CREEK VALLEY WATER AUTHORITY | M. Colburn or R. Kerry Witt, 724-455-2905 | UG |  |  | 2016-05-09
498b | -- | 498 | 16841 | 29893 | 26105801300864 | 12 | Fayette | SALTLICK & DONEGAL TWPS. | SR 1058 | INDIAN CREEK | 26/217 - SALTLICK | 40.0744 | -79.3556 | 20143571250 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-05-09
499a | -- | 499 | 16868 | 74184 | 26201500300000 | 12 | Fayette | WHARTON TOWNSHIP | SR 2015 | MEADOW RUN | 26/224 - WHARTON | 39.8234 | -79.5687 | 20150291578 | Comm | Comcast Cable of Garrett County MD | Randy Heel, randy_reel@cable.comcast.com |  |  |  | 2016-08-05
499b | -- | 499 | 16868 | 74184 | 26201500300000 | 12 | Fayette | WHARTON TOWNSHIP | SR 2015 | MEADOW RUN | 26/224 - WHARTON | 39.8234 | -79.5687 | 20150291578 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-08-05
499c | -- | 499 | 16868 | 74184 | 26201500300000 | 12 | Fayette | WHARTON TOWNSHIP | SR 2015 | MEADOW RUN | 26/224 - WHARTON | 39.8234 | -79.5687 | 20150291578 | Comm | Qcol Inc | Brian Frazee, bfrazee@qcol.net |  |  |  | 2016-08-05
499d | -- | 499 | 16868 | 74184 | 26201500300000 | 12 | Fayette | WHARTON TOWNSHIP | SR 2015 | MEADOW RUN | 26/224 - WHARTON | 39.8234 | -79.5687 | 20150291578 |  | Wharton TWP | Laura Savage (secy), 724-329-8503 | UG |  |  | 2016-08-05
500 | -- | 500 | 16910 | 74189 | 26301100900000 | 12 | Fayette | NICHOLSON & GERMAN TWPS. | SR 3011 | CATS CREEK | 26/213 - NICHOLSON | 39.8401 | -79.8968 | 20150301307 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-08-22
501a | -- | 501 | 16922 | 79325 | 26301301700955 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8992 | -79.898 | 20150411739 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2017-05-16
501b | -- | 501 | 16922 | 79325 | 26301301700955 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8992 | -79.898 | 20150411739 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-05-16
502 | -- | 502 | 16928 | 79328 | 26301301900753 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8926 | -79.914 | 20151462809 | Gas | Peoples Gas (Equitable Gas) | Daniel Andree, 724-832-2859, daniel.andree@peoples-gas.com | UG |  |  | 2017-07-26
503a | -- | 503 | 17052 | 79337 | 26404400201593 | 12 | Fayette | WASHINGTON TOWNSHIP | SR 4044 | DOWNERS RUN | 26/223 - WASHINGTON | 40.1092 | -79.8319 | 20150301378 |  | Washington TWP Fayette Cnty | Amy Naulty, 412-223-4200 | UG |  |  | 2016-09-06
503b | -- | 503 | 17052 | 79337 | 26404400201593 | 12 | Fayette | WASHINGTON TOWNSHIP | SR 4044 | DOWNERS RUN | 26/223 - WASHINGTON | 40.1092 | -79.8319 | 20150301378 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-09-06
504a | -- | 504 | 18013 | 79340 | 30001802400670 | 12 | Greene | CENTER TOWNSHIP | SR 0018 | HOUSE RUN | 30/202 - CENTER | 39.8548 | -80.3139 | 20143571263 | Comm | Windstream | Bob Dern, 724-852-8227, Robert.Dern@windstream.com | UG |  |  | 2016-04-04
504b | -- | 504 | 18013 | 79340 | 30001802400670 | 12 | Greene | CENTER TOWNSHIP | SR 0018 | HOUSE RUN | 30/202 - CENTER | 39.8548 | -80.3139 | 20143571263 | gas | Columbia Gas of PA Design | Stephanie Hardenstine Cell: 412-584-5015 Office: 412-220-1531 shardenstine@nisource.com | UG |  |  | 2016-04-04
504c | -- | 504 | 18013 | 79340 | 30001802400670 | 12 | Greene | CENTER TOWNSHIP | SR 0018 | HOUSE RUN | 30/202 - CENTER | 39.8548 | -80.3139 | 20143571263 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | OH |  |  | 2016-04-04
505a | -- | 505 | 18044 | 79342 | 30001805800146 | 12 | Greene | MORRIS TOWNSHIP | SR 0018 | BROWNS CREEK | 30/214 - MORRIS | 39.9689 | -80.317 | 20150411755 | Elect | WEST PENN POWER | Timothy Blasinsky, tblasin@firstenergycorp.com Dan Oswald, 724-942-5239, doswald@firstenergycorp.com | OH |  |  | 2017-02-06
505b | -- | 505 | 18044 | 79342 | 30001805800146 | 12 | Greene | MORRIS TOWNSHIP | SR 0018 | BROWNS CREEK | 30/214 - MORRIS | 39.9689 | -80.317 | 20150411755 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Aldona Pilarczyk, Aldona.Pilarczyk@windstream.com, 319-790-6779 | UG & OH |  |  | 2017-02-06
506a | -- | 506 | 18154 | 30291 | 30018800300000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 0188 | GRIMES RUN | 30/205 - FRANKLIN | 39.9048 | -80.1507 | 20143571273 | Gas | EQUITRANS LP | Dave Spencer, 724-852-7330, dspencer@eqt.com | UG |  |  | 2016-05-20
506b | -- | 506 | 18154 | 30291 | 30018800300000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 0188 | GRIMES RUN | 30/205 - FRANKLIN | 39.9048 | -80.1507 | 20143571273 | SS | FRANKLIN TOWNSHIP SEWER AUTHORITY | George Scott, 724-998-6939, 724-627-9728 joyce@ftsasewer.com | UG |  |  | 2016-05-20
506c | -- | 506 | 18154 | 30291 | 30018800300000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 0188 | GRIMES RUN | 30/205 - FRANKLIN | 39.9048 | -80.1507 | 20143571273 | Gas | Peoples Gas | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | UG |  |  | 2016-05-20
506d | -- | 506 | 18154 | 30291 | 30018800300000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 0188 | GRIMES RUN | 30/205 - FRANKLIN | 39.9048 | -80.1507 | 20143571273 | Elect | West Penn Power Company | Tim Blasinsky, 724-942-5239, tblasin@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | OH |  |  | 2016-05-20
506e | -- | 506 | 18154 | 30291 | 30018800300000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 0188 | GRIMES RUN | 30/205 - FRANKLIN | 39.9048 | -80.1507 | 20143571273 | Wtr | SOUTHWESTERN PA WATER AUTH | Tim Faddis, 412-260-8294, faddistim@windstream.net | UG |  |  | 2016-05-20
506f | -- | 506 | 18154 | 30291 | 30018800300000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 0188 | GRIMES RUN | 30/205 - FRANKLIN | 39.9048 | -80.1507 | 20143571273 | Comm | WINDSTREAM | Bob Dern, 724-852-8227, Robert.Dern@windstream.com | OH |  |  | 2016-05-20
507a | -- | 507 | 18164 | 76037 | 30018801800000 | 12 | Greene | JEFFERSON TOWNSHIP | SR 0188 | BR SOUTH FORK TENMILE CK | 30/211 - JEFFERSON | 39.9381 | -80.0456 | 20143571371 | Comm | WINDSTREAM | Bob Dern, 724-852-8227, Robert.Dern@windstream.com | OH |  |  | 2016-05-17
507b | -- | 507 | 18164 | 76037 | 30018801800000 | 12 | Greene | JEFFERSON TOWNSHIP | SR 0188 | BR SOUTH FORK TENMILE CK | 30/211 - JEFFERSON | 39.9381 | -80.0456 | 20143571371 | Comm | Verizon | Deborah Delia, (412) 237-2285, deborah.d.delia@verizon.com | UG |  |  | 2016-05-17
507c | -- | 507 | 18164 | 76037 | 30018801800000 | 12 | Greene | JEFFERSON TOWNSHIP | SR 0188 | BR SOUTH FORK TENMILE CK | 30/211 - JEFFERSON | 39.9381 | -80.0456 | 20143571371 | SS | DRY TAVERN SEWER AUTHORITY | Eric Harris or Timothy Neil, 724-966-9295, hnhwc@windstream.com | UG |  |  | 2016-05-17
507d | -- | 507 | 18164 | 76037 | 30018801800000 | 12 | Greene | JEFFERSON TOWNSHIP | SR 0188 | BR SOUTH FORK TENMILE CK | 30/211 - JEFFERSON | 39.9381 | -80.0456 | 20143571371 | Gas | Peoples Gas Design Monongahela | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | UG |  |  | 2016-05-17
507e | -- | 507 | 18164 | 76037 | 30018801800000 | 12 | Greene | JEFFERSON TOWNSHIP | SR 0188 | BR SOUTH FORK TENMILE CK | 30/211 - JEFFERSON | 39.9381 | -80.0456 | 20143571371 | Elect | West Penn Power Company | Cody Andrews, 724-883-5258, candrews@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com |  |  |  | 2016-05-17
507f | -- | 507 | 18164 | 76037 | 30018801800000 | 12 | Greene | JEFFERSON TOWNSHIP | SR 0188 | BR SOUTH FORK TENMILE CK | 30/211 - JEFFERSON | 39.9381 | -80.0456 | 20143571371 | Wtr | SOUTHWESTERN PA WATER AUTH | Tim Faddis, 412-260-8294, faddistim@windstream.net Edward J. Mihalsky, 412-260-8945 repshop@verizon.net | UG |  |  | 2016-05-17
508a | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 | 20143580303, 20143580304 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-05-19
508b | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 | 20143580303, 20143580304 |  | Clarksville Borough | Sam Benyi, clarksvilleboro@windstream.net |  |  |  | 2016-05-19
508c | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 | 20143580303, 20143580304 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-05-19
508d | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 | 20143580303, 20143580304 | Wtr | Southwestern PA Water Authority | Edward J. Mihalsky, repshop@verizon.net | UG |  |  | 2016-05-19
508e | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 | 20143580303, 20143580304 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2016-05-19
508f | -- | 508 | 18214 | 89031 | 30101101500501 | 12 | Greene | JEFFERSON T & CLARKSVILLE | SR 1011 | SOUTH FORK TENMILE CREEK | 30/402 - CLARKSVILLE | 39.9728 | -80.0461 | 20143580303, 20143580304 | sanitary | DRY TAVERN SEWER AUTHORITY | Edgar Harris, Jr., 724-966-2278 | UG |  |  | 2016-05-19
509 | -- | 509 | 18222 | 74203 | 30101400803315 | 12 | Greene | MORGAN TOWNSHIP | SR 1014 | CASTILE RUN | 30/213 - MORGAN | 39.9619 | -80.0536 | 20150420316 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | OH |  |  | 2016-07-25
510a | -- | 510 | 18261 | 30335 | 30200303301330 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2003 | TENMILE CREEK (CROSSING @ LOW) | 30/205 - FRANKLIN | 39.8937 | -80.1789 | 20150291598, 20150291599 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Leigh Anderson, Leigh.Anderson@windstream.com, 501-748-5524 | OH |  |  | 2016-07-18
510b | -- | 510 | 18261 | 30335 | 30200303301330 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2003 | TENMILE CREEK (CROSSING @ LOW) | 30/205 - FRANKLIN | 39.8937 | -80.1789 | 20150291598, 20150291599 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-07-18
510c | -- | 510 | 18261 | 30335 | 30200303301330 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2003 | TENMILE CREEK (CROSSING @ LOW) | 30/205 - FRANKLIN | 39.8937 | -80.1789 | 20150291598, 20150291599 | sanitary | Franklin TWP Sewer Auth | Chad Coss, sbc1@windstream.net | UG |  |  | 2016-07-18
510d | -- | 510 | 18261 | 30335 | 30200303301330 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2003 | TENMILE CREEK (CROSSING @ LOW) | 30/205 - FRANKLIN | 39.8937 | -80.1789 | 20150291598, 20150291599 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-07-18
510e | -- | 510 | 18261 | 30335 | 30200303301330 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2003 | TENMILE CREEK (CROSSING @ LOW) | 30/205 - FRANKLIN | 39.8937 | -80.1789 | 20150291598, 20150291599 | Wtr | Southwestern PA Water Authority | Edward J. Mihalsky, repshop@verizon.net | UG |  |  | 2016-07-18
510f | -- | 510 | 18261 | 30335 | 30200303301330 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2003 | TENMILE CREEK (CROSSING @ LOW) | 30/205 - FRANKLIN | 39.8937 | -80.1789 | 20150291598, 20150291599 |  | Waynesburg Borough | Bonnie Baily (secy), 724-627-8111, wbgboro@alltel.net | uG |  |  | 2016-07-18
511a | -- | 511 | 18279 | 79353 | 30201103700000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2011 | COAL LICK RUN | 30/205 - FRANKLIN | 39.8727 | -80.1211 | 20150330424 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG | 14" |  | 2016-07-18
511b | -- | 511 | 18279 | 79353 | 30201103700000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2011 | COAL LICK RUN | 30/205 - FRANKLIN | 39.8727 | -80.1211 | 20150330424 | Wtr | Southwestern PA Water Authority | Edward J. Mihalsky, repshop@verizon.net | UG |  |  | 2016-07-18
511c | -- | 511 | 18279 | 79353 | 30201103700000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2011 | COAL LICK RUN | 30/205 - FRANKLIN | 39.8727 | -80.1211 | 20150330424 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-07-18
511d | -- | 511 | 18279 | 79353 | 30201103700000 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2011 | COAL LICK RUN | 30/205 - FRANKLIN | 39.8727 | -80.1211 | 20150330424 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; LaKisha Johnson, Lakisha.Jackson@windstream.com, 501-748-4433 | UG & OH |  |  | 2016-07-18
512a | -- | 512 | 18287 | 30289 | 30201600701702 | 12 | Greene | MONOGAHELA TOWNSHIP | SR 2016 | WHITELEY CREEK | 30/212 - MONONGAHELA | 39.8048 | -79.9493 | 20143580312 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-03-16
512b | -- | 512 | 18287 | 30289 | 30201600701702 | 12 | Greene | MONOGAHELA TOWNSHIP | SR 2016 | WHITELEY CREEK | 30/212 - MONONGAHELA | 39.8048 | -79.9493 | 20143580312 |  | Monongahela TWP | Louis Kovach, 724-943-3034 | UG |  |  | 2017-03-16
512c | -- | 512 | 18287 | 30289 | 30201600701702 | 12 | Greene | MONOGAHELA TOWNSHIP | SR 2016 | WHITELEY CREEK | 30/212 - MONONGAHELA | 39.8048 | -79.9493 | 20143580312 | Gas | Peoples Gas Monongahela Division | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2017-03-16
513a | -- | 513 | 18315 | 79356 | 30202600100590 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | LAUREL RUN | 30/205 - FRANKLIN | 39.8939 | -80.1591 | 20150341683 | Gas | Equitrans LP | Dave Spencer, 724-852-7330, dspencer@eqt.com | UG |  |  | 2017-04-03
513b | -- | 513 | 18315 | 79356 | 30202600100590 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | LAUREL RUN | 30/205 - FRANKLIN | 39.8939 | -80.1591 | 20150341683 | sanitary | Franklin TWP Sewer Auth | Carol T. Moore (Secy), 724-627-5473 | UG |  |  | 2017-04-03
513c | -- | 513 | 18315 | 79356 | 30202600100590 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | LAUREL RUN | 30/205 - FRANKLIN | 39.8939 | -80.1591 | 20150341683 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2017-04-03
513d | -- | 513 | 18315 | 79356 | 30202600100590 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | LAUREL RUN | 30/205 - FRANKLIN | 39.8939 | -80.1591 | 20150341683 | Wtr | Southwestern PA Water Authority | Edward J. Mihalsky, repshop@verizon.net | UG |  |  | 2017-04-03
513e | -- | 513 | 18315 | 79356 | 30202600100590 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | LAUREL RUN | 30/205 - FRANKLIN | 39.8939 | -80.1591 | 20150341683 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-04-03
514a | -- | 514 | 18317 | 79357 | 30202600501285 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | BRADENS RUN | 30/205 - FRANKLIN | 39.8905 | -80.1222 | 20150161837 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Daniel Piser, 724-852-8301 |  |  |  | 2016-06-17
514b | -- | 514 | 18317 | 79357 | 30202600501285 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | BRADENS RUN | 30/205 - FRANKLIN | 39.8905 | -80.1222 | 20150161837 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-06-17
514c | -- | 514 | 18317 | 79357 | 30202600501285 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | BRADENS RUN | 30/205 - FRANKLIN | 39.8905 | -80.1222 | 20150161837 | Wtr | Southwestern PA Water Authority | Edward J. Mihalsky, repshop@verizon.net | UG |  |  | 2016-06-17
514d | -- | 514 | 18317 | 79357 | 30202600501285 | 12 | Greene | FRANKLIN TOWNSHIP | SR 2026 | BRADENS RUN | 30/205 - FRANKLIN | 39.8905 | -80.1222 | 20150161837 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG | 3 & 4" |  | 2016-06-17
515a | -- | 515 | 18351 | 88079 | 30300600100674 | 12 | Greene | GILMORE TOWNSHIP | SR 3006 | PA. FORK DUNKARD CREEK | 30/207 - GILMORE | 39.723 | -80.3497 | 20143571385 | GAS | Columbia Gas Transmission | Ron Johns, rjohns@nisource.com | UG |  |  | 2016-05-19
515b | -- | 515 | 18351 | 88079 | 30300600100674 | 12 | Greene | GILMORE TOWNSHIP | SR 3006 | PA. FORK DUNKARD CREEK | 30/207 - GILMORE | 39.723 | -80.3497 | 20143571385 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-05-19
515c | -- | 515 | 18351 | 88079 | 30300600100674 | 12 | Greene | GILMORE TOWNSHIP | SR 3006 | PA. FORK DUNKARD CREEK | 30/207 - GILMORE | 39.723 | -80.3497 | 20143571385 | sanitary | Gilmore TWP | Lisa Gatrell, 724-451-8390 | UG |  |  | 2016-05-19
515d | -- | 515 | 18351 | 88079 | 30300600100674 | 12 | Greene | GILMORE TOWNSHIP | SR 3006 | PA. FORK DUNKARD CREEK | 30/207 - GILMORE | 39.723 | -80.3497 | 20143571385 | Comm | WINDSTREAM | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Daniel Piser, 724-852-8301 | OH |  |  | 2016-05-19
516a | -- | 516 | 18403 | 30231 | 30301300900000 | 12 | Greene | WAYNE TOWNSHIP | SR 3013 | BELLS RUN | 30/219 - WAYNE | 39.7715 | -80.2717 | 20143571401 | Elect | West Penn Power Company | Cody Andrews, 724-883-5258, candrews@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | OH |  |  | 2016-05-16
516b | -- | 516 | 18403 | 30231 | 30301300900000 | 12 | Greene | WAYNE TOWNSHIP | SR 3013 | BELLS RUN | 30/219 - WAYNE | 39.7715 | -80.2717 | 20143571401 | Gas | Peoples Gas Design Monongahela | Joe Zaradzki, 724-640-0183, JOSEPH.M.ZARADZKI@peoples-gas.com | UG |  |  | 2016-05-16
516c | -- | 516 | 18403 | 30231 | 30301300900000 | 12 | Greene | WAYNE TOWNSHIP | SR 3013 | BELLS RUN | 30/219 - WAYNE | 39.7715 | -80.2717 | 20143571401 | Gas | CNX Gas Corp | JEFF MALCOLM BLUE MOUNTAIN INC J.Malcolm@bluemtninc.com | UG |  |  | 2016-05-16
517a | -- | 517 | 34335 | 30975 | 62001900400000 | 12 | Washington | AMWELL TOWNSHIP | SR 0019 | BANE CREEK | 62/201 - AMWELL | 40.024 | -80.2053 | 20150350499 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-07-05
517b | -- | 517 | 34335 | 30975 | 62001900400000 | 12 | Washington | AMWELL TOWNSHIP | SR 0019 | BANE CREEK | 62/201 - AMWELL | 40.024 | -80.2053 | 20150350499 | Gas | Peoples Gas Monongahela Division | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-07-05
518a | -- | 518 | 34417 | 30639 | 62005003300000 | 12 | Washington | CECIL TOWNSHIP | SR 0050 | MILLER RUN | 62/206 - CECIL | 40.321 | -80.2307 | 20150161840 |  | Cecil TWP | Donald A. Gennuso, manager@ceciltownship.com | UG |  |  | 2016-05-23
518b | -- | 518 | 34417 | 30639 | 62005003300000 | 12 | Washington | CECIL TOWNSHIP | SR 0050 | MILLER RUN | 62/206 - CECIL | 40.321 | -80.2307 | 20150161840 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2016-05-23
518c | -- | 518 | 34417 | 30639 | 62005003300000 | 12 | Washington | CECIL TOWNSHIP | SR 0050 | MILLER RUN | 62/206 - CECIL | 40.321 | -80.2307 | 20150161840 | Wtr | Pennsylvania American Water CO | Clayton Wene, clayton.wene@amwater.com | UG |  |  | 2016-05-23
518d | -- | 518 | 34417 | 30639 | 62005003300000 | 12 | Washington | CECIL TOWNSHIP | SR 0050 | MILLER RUN | 62/206 - CECIL | 40.321 | -80.2307 | 20150161840 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-05-23
519a | -- | 519 | 34609 | 30997 | 62008804902545 | 12 | Washington | SPEERS & CHARLEROI BORO. | SR 0088 | MAPLE CREEK | 62/408 - CHARLEROI | 40.1324 | -79.8909 | 20150341717 20150341718 | Wtr | Authority of the Borough of Charleroi | Michael Kalamaras, MichaelKalamaras@abcwater.org | UG |  |  | 2017-02-21
519b | -- | 519 | 34609 | 30997 | 62008804902545 | 12 | Washington | SPEERS & CHARLEROI BORO. | SR 0088 | MAPLE CREEK | 62/408 - CHARLEROI | 40.1324 | -79.8909 | 20150341717 20150341718 |  | Borough of Charleroi | Elaine T. Martinko (secy), 724-483-6011, bcso@charleroiboro.org | UG |  |  | 2017-02-21
519c | -- | 519 | 34609 | 30997 | 62008804902545 | 12 | Washington | SPEERS & CHARLEROI BORO. | SR 0088 | MAPLE CREEK | 62/408 - CHARLEROI | 40.1324 | -79.8909 | 20150341717 20150341718 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2017-02-21
519d | -- | 519 | 34609 | 30997 | 62008804902545 | 12 | Washington | SPEERS & CHARLEROI BORO. | SR 0088 | MAPLE CREEK | 62/408 - CHARLEROI | 40.1324 | -79.8909 | 20150341717 20150341718 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-02-21
520a | -- | 520 | 34623 | 73058 | 62008807600000 | 12 | Washington | FINLEYVILLE BOROUGH | SR 0088 | PETERS CREEK | 62/418 - FINLEYVILLE | 40.2504 | -80.0035 | 20150291622 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-06-23
520b | -- | 520 | 34623 | 73058 | 62008807600000 | 12 | Washington | FINLEYVILLE BOROUGH | SR 0088 | PETERS CREEK | 62/418 - FINLEYVILLE | 40.2504 | -80.0035 | 20150291622 |  | Finleyville Borough | Sandra Mayak, 724-348-5100 | UG |  |  | 2016-06-23
520c | -- | 520 | 34623 | 73058 | 62008807600000 | 12 | Washington | FINLEYVILLE BOROUGH | SR 0088 | PETERS CREEK | 62/418 - FINLEYVILLE | 40.2504 | -80.0035 | 20150291622 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-06-23
520d | -- | 520 | 34623 | 73058 | 62008807600000 | 12 | Washington | FINLEYVILLE BOROUGH | SR 0088 | PETERS CREEK | 62/418 - FINLEYVILLE | 40.2504 | -80.0035 | 20150291622 | Wtr | Pennsylvania American Water Co | Gary Eiter, 412-854-7619, Gary.Eiter@amwater.com | UG |  |  | 2016-06-23
520e | -- | 520 | 34623 | 73058 | 62008807600000 | 12 | Washington | FINLEYVILLE BOROUGH | SR 0088 | PETERS CREEK | 62/418 - FINLEYVILLE | 40.2504 | -80.0035 | 20150291622 | sanitary | Peters Creek Sanitary Auth | Rick Kovack, rickkovach@verizon.net, 724-348-6860 | UG |  |  | 2016-06-23
521a | -- | 521 | 34650 | 89048 | 62022100802172 | 12 | Washington | MORRIS TOWNSHIP | SR 0221 | TENMILE CREEK | 62/216 - MORRIS | 40.0344 | -80.2664 | 20150330537 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-06-27
521b | -- | 521 | 34650 | 89048 | 62022100802172 | 12 | Washington | MORRIS TOWNSHIP | SR 0221 | TENMILE CREEK | 62/216 - MORRIS | 40.0344 | -80.2664 | 20150330537 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-06-27
522a | -- | 522 | 34673 | 88078 | 62023104300092 | 12 | Washington | BLAINE & INDEPENDENCE TWP | SR 0231 | BRUSH RUN | 62/214 - INDEPENDENCE | 40.1954 | -80.4481 | 20143580124, 20143580125 | Gas | Markwest Liberty Midstream and Resources | David Allum 724-579-0440 David.Allum@markwest.com | UG |  |  | 2016-05-19
522b | -- | 522 | 34673 | 88078 | 62023104300092 | 12 | Washington | BLAINE & INDEPENDENCE TWP | SR 0231 | BRUSH RUN | 62/214 - INDEPENDENCE | 40.1954 | -80.4481 | 20143580124, 20143580125 | Elect | West Penn Power Company | Dave Lucas, 724-942-5239, doswald@firstenergycorp.com Dan Oswald, (724) 942-5239, doswald@firstenergycorp.com | OH |  |  | 2016-05-19
523a | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | 20150161845 | gas | CNX Gas Corp | JEFF MALCOLM BLUE MOUNTAIN INC J.Malcolm@bluemtninc.com | UG |  |  | 2016-05-23
523b | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | 20150161845 | gas | EQUITRANS LP | Robert Crites, 724- 627-5176, rcrites@eqt.com | UG |  |  | 2016-05-23
523c | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | 20150161845 | gas | PEOPLES GAS COMPANY (EQUITABLE) | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  |  | 2016-05-23
523d | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | 20150161845 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | OH |  |  | 2016-05-23
523e | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | 20150161845 | Wtr | West Pike Run TWP | Kerry Krider, 724.916.0061, 724-916-2245, kk@hmtandassociates.com Ruth Dodds, township238@gmail.com, 724-938-9194 | UG |  |  | 2016-05-23
523f | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | 20150161845 | sanitary | West Pike Run TWP Municipal Auth | Kerry Krider, 724.916.0061, 724-916-2245, kk@hmtandassociates.com Ruth Dodds, township238@gmail.com, 724-938-9194 | UG |  |  | 2016-05-23
523g | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | 20150161845 | Comm | ARMSTRONG | Tony Kowalewski tkowalewski@agoc.com, 724-628-6600 | OH |  |  | 2016-05-23
523h | -- | 523 | 34692 | 76062 | 62048100500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 0481 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0596 | -79.9682 | 20150161845 | Comm | VERIZON PENNSYLVANIA LLC | Barb Witkowski, 814-871-2275, barb.witkowski@verizon.com | OH |  |  | 2016-05-23
524a | -- | 524 | 34702 | 30813 | 62048102400990 | 12 | Washington | CARROLL TOWNSHIP | SR 0481 | TAYLOR RUN | 62/205 - CARROLL | 40.1804 | -79.9387 | 20151461752 | GAS | M3 Appalachia Gathering LLC | Stephen Montgomery, s.montgomery@m3midstream.com | UG |  |  | 2017-07-28
524b | -- | 524 | 34702 | 30813 | 62048102400990 | 12 | Washington | CARROLL TOWNSHIP | SR 0481 | TAYLOR RUN | 62/205 - CARROLL | 40.1804 | -79.9387 | 20151461752 | gas | Peoples Gas (Equitable Gas) | Daniel Andree, 724-832-2859, daniel.andree@peoples-gas.com | UG |  |  | 2017-07-28
525a | -- | 525 | 34847 | 31155 | 62104900520000 | 12 | Washington | SOUTH STRABANE TOWNSHIP | SR 1049 | BR. LITTLE CHARTIERS CK. | 62/227 - SOUTH STRABANE | 40.1717 | -80.1749 | 20150301020 | Wtr | Pennsylvania American Water Co | Greg Hlasnick, greg.hlasnick@amwater.com | UG |  |  | 2016-08-05
525b | -- | 525 | 34847 | 31155 | 62104900520000 | 12 | Washington | SOUTH STRABANE TOWNSHIP | SR 1049 | BR. LITTLE CHARTIERS CK. | 62/227 - SOUTH STRABANE | 40.1717 | -80.1749 | 20150301020 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-08-05
526a | -- | 526 | 34879 | 98374 | 62200700200048 | 12 | Washington | AMWELL TOWNSHIP | SR 2007 | HORNE RUN | 62/201 - AMWELL | 40.0394 | -80.2224 | 20150330178 |  | Amwell TWP | Kathleen Wall, amwelltownship@comcast.net | UG |  |  | 2016-08-15
526b | -- | 526 | 34879 | 98374 | 62200700200048 | 12 | Washington | AMWELL TOWNSHIP | SR 2007 | HORNE RUN | 62/201 - AMWELL | 40.0394 | -80.2224 | 20150330178 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-08-15
527a | -- | 527 | 34901 | 76072 | 62201102800165 | 12 | Washington | AMWELL TOWNSHIP | SR 2011 | LITTLE TENMILE CREEK | 62/201 - AMWELL | 40.0808 | -80.1777 | 20151461810 |  | Amwell TWP | Kathleen Wall, amwelltownship@comcast.net |  |  |  | 2017-07-28
527b | -- | 527 | 34901 | 76072 | 62201102800165 | 12 | Washington | AMWELL TOWNSHIP | SR 2011 | LITTLE TENMILE CREEK | 62/201 - AMWELL | 40.0808 | -80.1777 | 20151461810 | gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2017-07-28
527c | -- | 527 | 34901 | 76072 | 62201102800165 | 12 | Washington | AMWELL TOWNSHIP | SR 2011 | LITTLE TENMILE CREEK | 62/201 - AMWELL | 40.0808 | -80.1777 | 20151461810 | gas | Peoples Gas (Equitable Gas) | Daniel Andree, 724-832-2859, daniel.andree@peoples-gas.com | UG | 8" |  | 2017-07-28
528a | -- | 528 | 34907 | 98377 | 62201500200805 | 12 | Washington | WEST BETHLEHEM TOWNSHIP | SR 2015 | DANIELS RUN | 62/229 - WEST BETHLEHEM | 40.0429 | -80.0907 | 20150301451 | sanitary | Marianna West Beth Joint Sewage Auth | Betty Girdish, 724-267-4449 | UG |  |  | 2016-07-25
528b | -- | 528 | 34907 | 98377 | 62201500200805 | 12 | Washington | WEST BETHLEHEM TOWNSHIP | SR 2015 | DANIELS RUN | 62/229 - WEST BETHLEHEM | 40.0429 | -80.0907 | 20150301451 |  | West Bethlehem TWP | Robert Mercante, 412-267-4665 |  |  |  | 2016-07-25
528c | -- | 528 | 34907 | 98377 | 62201500200805 | 12 | Washington | WEST BETHLEHEM TOWNSHIP | SR 2015 | DANIELS RUN | 62/229 - WEST BETHLEHEM | 40.0429 | -80.0907 | 20150301451 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-07-25
528d | -- | 528 | 34907 | 98377 | 62201500200805 | 12 | Washington | WEST BETHLEHEM TOWNSHIP | SR 2015 | DANIELS RUN | 62/229 - WEST BETHLEHEM | 40.0429 | -80.0907 | 20150301451 | Comm | Windstream | Glen Esenwein, 610-404-6239, gesenwein@decommunications.com; Anthony Seekins, Anthony.Seekins@windstream.com, 501-748-4447 |  |  |  | 2016-07-25
| -- | 529 | 34946 | 89142 | 62202300800032 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2023 | BRANCH OF PIGEON CREEK | 62/211 - FALLOWFIELD | 40.1273 | -79.9895 | 20143580131 | [6 empty] | 2017-02-08
530a | -- | 530 | 34949 | 98864 | 62202301100756 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2023 | PIGEON CREEK | 62/211 - FALLOWFIELD | 40.1481 | -79.9792 | 20150330391 | Wtr | Authority of the Borough of Charleroi | Michael Kalamaras, MichaelKalamaras@abcwater.org | UG |  |  | 2017-02-13
530b | -- | 530 | 34949 | 98864 | 62202301100756 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2023 | PIGEON CREEK | 62/211 - FALLOWFIELD | 40.1481 | -79.9792 | 20150330391 | Gas | M3 Appalachia Gathering LLC | Stephen Montgomery, s.montgomery@m3midstream.com | UG |  |  | 2017-02-13
530c | -- | 530 | 34949 | 98864 | 62202301100756 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2023 | PIGEON CREEK | 62/211 - FALLOWFIELD | 40.1481 | -79.9792 | 20150330391 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-02-13
531a | -- | 531 | 34977 | 51507 | 62203400500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2034 | BRANCH OF PIKE RUN | 62/231 - WEST PIKE RUN | 40.0634 | -79.982 | 20150161815 | gas | CNX Gas Corp | JEFF MALCOLM BLUE MOUNTAIN INC J.Malcolm@bluemtninc.com | UG |  |  | 2016-05-17
531b | -- | 531 | 34977 | 51507 | 62203400500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2034 | BRANCH OF PIKE RUN | 62/231 - WEST PIKE RUN | 40.0634 | -79.982 | 20150161815 | Elect | West Penn Power Company | Dan Oswald (724) 942-5239 doswald@firstenergycorp.com | OH |  |  | 2016-05-17
531c | -- | 531 | 34977 | 51507 | 62203400500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2034 | BRANCH OF PIKE RUN | 62/231 - WEST PIKE RUN | 40.0634 | -79.982 | 20150161815 | Wtr | West Pike Run TWP | Kerry Krider, 724.916.0061, 724-916-2245, kk@hmtandassociates.com Ruth Dodds, township238@gmail.com, 724-938-9194 | UG |  |  | 2016-05-17
531d | -- | 531 | 34977 | 51507 | 62203400500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2034 | BRANCH OF PIKE RUN | 62/231 - WEST PIKE RUN | 40.0634 | -79.982 | 20150161815 | sanitary | West Pike Run TWP Municipal Auth | Kerry Krider, 724.916.0061, 724-916-2245, kk@hmtandassociates.com Ruth Dodds, township238@gmail.com, 724-938-9194 | UG |  |  | 2016-05-17
532a | -- | 532 | 34980 | 31157 | 62203600101601 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0563 | -79.9628 | 20150301127 | GAS | CNX Gas Corp | Jeff Malcolm, bluemountain5876@gmail.com; Shane Lamkie, 724-954-9067, shane@paproduction.com | UG |  |  | 2016-07-11
532b | -- | 532 | 34980 | 31157 | 62203600101601 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0563 | -79.9628 | 20150301127 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-07-11
532c | -- | 532 | 34980 | 31157 | 62203600101601 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0563 | -79.9628 | 20150301127 |  | West Pike Run TWP | Ruth Dodds, township238@gmail.com | UG |  |  | 2016-07-11
532d | -- | 532 | 34980 | 31157 | 62203600101601 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0563 | -79.9628 | 20150301127 |  | West Pike Run TWP Municipal Auth | Ruth Dodds, township238@gmail.com | UG |  |  | 2016-07-11
532e | -- | 532 | 34980 | 31157 | 62203600101601 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0563 | -79.9628 | 20150301127 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-07-11
533a | -- | 533 | 34985 | 81841 | 62203600500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0523 | -79.9361 | 20151420569 | wtr | Pennsylvania American Water CO Brownsville | Greg Hlasnick, greg.hlasnick@amwater.com | UG |  |  | 2017-05-25
533b | -- | 533 | 34985 | 81841 | 62203600500000 | 12 | Washington | WEST PIKE RUN TOWNSHIP | SR 2036 | PIKE RUN | 62/231 - WEST PIKE RUN | 40.0523 | -79.9361 | 20151420569 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-05-25
534a | -- | 534 | 34996 | 30715 | 62203700403160 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2037 | MAPLE CREEK | 62/211 - FALLOWFIELD | 40.1311 | -79.9255 | 20151412755 |  | Authority of the Borough of Charleroi | Michael Kalamaras, MichaelKalamaras@abcwater.org | UG |  |  | 2017-05-04
534b | -- | 534 | 34996 | 30715 | 62203700403160 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2037 | MAPLE CREEK | 62/211 - FALLOWFIELD | 40.1311 | -79.9255 | 20151412755 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2017-05-04
534c | -- | 534 | 34996 | 30715 | 62203700403160 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2037 | MAPLE CREEK | 62/211 - FALLOWFIELD | 40.1311 | -79.9255 | 20151412755 | Gas | Equitrans LP | Dave Spencer, 724-852-7330, dspencer@eqt.com | UG |  |  | 2017-05-04
534d | -- | 534 | 34996 | 30715 | 62203700403160 | 12 | Washington | FALLOWFIELD TOWNSHIP | SR 2037 | MAPLE CREEK | 62/211 - FALLOWFIELD | 40.1311 | -79.9255 | 20151412755 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2017-05-04
535 | -- | 535 | 35090 | 30881 | 62303700801515 | 12 | Washington | WEST FINLEY TOWNSHIP | SR 3037 | ROBINSON RUN | 62/230 - WEST FINLEY | 40.0024 | -80.4726 | 20150330097 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-08-05
536 | -- | 536 | 35103 | 31146 | 62400300701841 | 12 | Washington | HANOVER TOWNSHIP | SR 4003 | KINGS CREEK | 62/212 - HANOVER | 40.4654 | -80.4784 | 20150161847 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-06-17
537 | -- | 537 | 35171 | 30552 | 62402300200000 | 12 | Washington | CROSS CREEK TOWNSHIP | SR 4023 | NORTH FORK CROSS CREEK | 62/208 - CROSS CREEK | 40.321 | -80.4418 | 20151462383 | sanitary | Independence Cross Creek JT SWR Auth | 724-507-6464 | UG |  |  | 2017-07-28
538a | -- | 538 | 35178 | 30702 | 62402700100687 | 12 | Washington | CROSS CREEK TOWNSHIP | SR 4027 | NORTH FORK CROSS CREEK | 62/208 - CROSS CREEK | 40.3099 | -80.4451 | 20150330108 | Comm | HTC Communications | David Kriebel, htcdig@hky.com |  |  |  | 2016-08-05
538b | -- | 538 | 35178 | 30702 | 62402700100687 | 12 | Washington | CROSS CREEK TOWNSHIP | SR 4027 | NORTH FORK CROSS CREEK | 62/208 - CROSS CREEK | 40.3099 | -80.4451 | 20150330108 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-08-05
539 | -- | 539 | 35201 | 81846 | 62403900701840 | 12 | Washington | MOUNT PLEASANT TOWNSHIP | SR 4039 | MILLERS RUN | 62/217 - MOUNT PLEASANT | 40.3266 | -80.2548 | 20151463040 |  | all facilities responded clear per one call |  |  |  |  | 2017-07-24
540 | -- | 540 | 35227 | 30635 | 62406100401960 | 12 | Washington | HOPEWELL AND BLAINE TWP. | SR 4061 | BRUSH RUN | 62/213 - HOPEWELL | 40.1984 | -80.4077 | 20150351050 20150351051 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-03-03
541a | -- | 541 | 35982 | 32045 | 64003103302148 | 12 | Westmoreland | MT. PLEASANT & BULLSKIN T | SR 0031 | JACOBS CREEK | 64/212 - MOUNT PLEASANT | 40.143 | -79.4865 | 20150161856, 20150161857 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 |  |  |  | 2016-05-23
541b | -- | 541 | 35982 | 32045 | 64003103302148 | 12 | Westmoreland | MT. PLEASANT & BULLSKIN T | SR 0031 | JACOBS CREEK | 64/212 - MOUNT PLEASANT | 40.143 | -79.4865 | 20150161856, 20150161857 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-05-23
542a | Y | 542 | 36002 | 76089 | 64005600501506 | 12 | Westmoreland | CITY OF NEW KENSINGTON | SR 0056 | LITTLE PUCKETA CREEK | 64/305 - NEW KENSINGTON | 40.5714 | -79.7495 | 20140660772 | Elect | WEST PENN POWER | Brian Hixenbaugh, 724-334-5236 | OH |  | Coordinated | 2015-07-24
543a | -- | 543 | 36130 | 79402 | 64013602502924 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 0136 | BR. LITTLE SEWICKLEY CK. | 64/209 - HEMPFIELD | 40.2804 | -79.6488 | 20150341825 | Gas | CNX Gas Corp | Jeff Malcolm, bluemountain5876@gmail.com; Shane Lamkie, 724-954-9067, shane@paproduction.com | UG |  |  | 2017-03-22
543b | -- | 543 | 36130 | 79402 | 64013602502924 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 0136 | BR. LITTLE SEWICKLEY CK. | 64/209 - HEMPFIELD | 40.2804 | -79.6488 | 20150341825 | gas | DOMINION TRANSMISSION | Bradley Buzzard (724) 331-3695 - Bradley.l.buzzard@dom .com or Jonathan Cherry (724) 468-7730 - jonathan.w.cherry@dom .com | UG |  |  | 2017-03-22
543c | -- | 543 | 36130 | 79402 | 64013602502924 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 0136 | BR. LITTLE SEWICKLEY CK. | 64/209 - HEMPFIELD | 40.2804 | -79.6488 | 20150341825 |  | HEMPFIELD TWP MUNICIPAL AUTHORITY | Donald C. Denezza (secy), 724-834-7232 | UG |  |  | 2017-03-22
543d | -- | 543 | 36130 | 79402 | 64013602502924 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 0136 | BR. LITTLE SEWICKLEY CK. | 64/209 - HEMPFIELD | 40.2804 | -79.6488 | 20150341825 | gas | Peoples Gas (Equitable Gas) | Colleen Corona, Rocky Saporito; PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG | 4" |  | 2017-03-22
543e | -- | 543 | 36130 | 79402 | 64013602502924 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 0136 | BR. LITTLE SEWICKLEY CK. | 64/209 - HEMPFIELD | 40.2804 | -79.6488 | 20150341825 | Wtr | Municipal Auth of Westmoreland Cnty | Donald Guerra, PE, daguerra@mawc.org, 724-755-5800 | UG | 8 & 20" |  | 2017-03-22
544a | Y | 544 | 36168 | 31601 | 64025900700000 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0259 | COALPIT RUN | 64/210 - LIGONIER | 40.2855 | -79.2348 | 20140660772 | NA | NA | NA |  |  | Not Affected | 2015-08-05
545a | Y | 545 | 36207 | 74418 | 64036601720000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 0366 | PUCKETA CREEK | 64/437 - MURRYSVILLE | 40.5188 | -79.6934 |  | Comm | VERIZON PENNSYLVANIA | Gary Redondo, 412-667-8618 | OH |  | Coordinated | 2015-07-16
545b | Y | 545 | 36207 | 74418 | 64036601720000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 0366 | PUCKETA CREEK | 64/437 - MURRYSVILLE | 40.5188 | -79.6934 |  | Comm | COMCAST | David Schade, 724-388-1652 | OH |  | Coordinated | 2015-07-16
546a | Y | 546 | 36228 | 31826 | 64038102400504 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LINN RUN | 64/210 - LIGONIER | 40.1957 | -79.2407 | 20140570767 | Elect | WEST PENN POWER | Brad Herrington, 724-830-2966 | OH |  | Prior | 2016-04-18
546b | Y | 546 | 36228 | 31826 | 64038102400504 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LINN RUN | 64/210 - LIGONIER | 40.1957 | -79.2407 | 20140570767 | Comm | COMCAST | Doug Olszewski, 724-459-9042 | OH |  | Prior | 2016-04-18
546c | Y | 546 | 36228 | 31826 | 64038102400504 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LINN RUN | 64/210 - LIGONIER | 40.1957 | -79.2407 | 20140570767 | Comm | VERIZON PENNSYLVANIA | Mike Fowkes, 412-558-5601 | OH |  | Prior | 2016-04-18
547a | Y | 547 | 36230 | 31614 | 64038103000000 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LAUGHLINTOWN RUN | 64/210 - LIGONIER | 40.2189 | -79.2191 | 20140570765 | Gas | PEOPLES NATURAL GAS | Daniel Andree, 724-832-2859; Melinda Zhukas | UG | 6 | Prior | 06-22-15 A
547b | Y | 547 | 36230 | 31614 | 64038103000000 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LAUGHLINTOWN RUN | 64/210 - LIGONIER | 40.2189 | -79.2191 | 20140570765 | Comm | VERIZON PENNSYLVANIA | Mike Fowkes, 412-558-5601 | OH |  | Not Affected | 06-22-15 A
547c | Y | 547 | 36230 | 31614 | 64038103000000 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LAUGHLINTOWN RUN | 64/210 - LIGONIER | 40.2189 | -79.2191 | 20140570765 | Comm | COMCAST | Doug Olszewski, 724-459-9042 | OH |  | Not Affected | 06-22-15 A
547d | Y | 547 | 36230 | 31614 | 64038103000000 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0381 | LAUGHLINTOWN RUN | 64/210 - LIGONIER | 40.2189 | -79.2191 | 20140570765 | Elect | WEST PENN POWER | Brad Herrington, 724-830-2966 | OH |  | Not Affected | 06-22-15 A
548a | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | 20150161833 | Wtr | LIGONIER TOWNSHIP MUNICIPAL AUTHORITY | Paul Knupp, 724-238-7464, ligtwpmunauth@hotmail.com | UG |  |  | 2016-05-23
548b | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | 20150161833 | gas | Peoples Gas Greensburg Division | Jim Barnett, 412-290-2421, james.l.barnett@peoples-gas.com | UG |  |  | 2016-05-23
548c | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | 20150161833 | Wtr | Municipal Auth of Westmoreland CO | M. Curtis Fontaine, 724-755-5950, fontaine@mawc.org | UG | 16" |  | 2016-05-23
548d | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | 20150161833 | Elect | West Penn Power Company | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com | OH | 16" |  | 2016-05-23
548e | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | 20150161833 | Comm | SUNESYS | Aaron Phillips, 412.779.5277 APhillips@sunesys.com | OH | 16" |  | 2016-05-23
548f | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | 20150161833 | Comm | ZAYO | John Lynch, 724-850-6241, 724-972-5667 john.lynch@zayo.com | OH | 16" |  | 2016-05-23
548g | -- | 548 | 36248 | 76121 | 64071102601107 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.2513 | -79.2218 | 20150161833 | Comm | VERIZON PENNSYLVANIA | Mike Fowkes, 412-558-5601, michael.g.fowkes@verizon.com | OH | 16" |  | 2016-05-23
549a | Y | 549 | 36251 | 76122 | 64071103000565 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.262 | -79.1966 | 20140570776 | Elect | WEST PENN POWER | James Piper, 724-830-2937 | OH |  | Coordinated | 2015-07-16
549b | Y | 549 | 36251 | 76122 | 64071103000565 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.262 | -79.1966 | 20140570776 | Comm | COMCAST | Doug Olszewski, 724-459-9042 | OH |  | Coordinated | 2015-07-16
549c | Y | 549 | 36251 | 76122 | 64071103000565 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.262 | -79.1966 | 20140570776 | Comm | COMCAST | Doug Olszewski, 724-459-9042 | OH |  | Prior | 2015-07-16
549d | Y | 549 | 36251 | 76122 | 64071103000565 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 0711 | MILL CREEK | 64/210 - LIGONIER | 40.262 | -79.1966 | 20140570776 | Comm | VERIZON PENNSYLVANIA | Mike Fowkes, 412-558-5601 | OH |  | Prior | 2015-07-16
550a | -- | 550 | 36331 | 98633 | 64098201701219 | 12 | Westmoreland | UNITY TOWNSHIP | SR 0982 | NINEMILE RUN | 64/217 - UNITY | 40.2522 | -79.3904 | 20143571496 | Wtr | Municipal Auth of Westmoreland Cnty | Donald Guerra, PE, daguerra@mawc.org, 724-755-5800 | UG |  |  | 2016-05-16
550b | -- | 550 | 36331 | 98633 | 64098201701219 | 12 | Westmoreland | UNITY TOWNSHIP | SR 0982 | NINEMILE RUN | 64/217 - UNITY | 40.2522 | -79.3904 | 20143571496 |  | Unity Township Municipal Auth | Douglas A. Pike, dougp@utmapa.org | UG |  |  | 2016-05-16
551 | -- | 551 | 36365 | 31972 | 64100400200165 | 12 | Westmoreland | FAIRFIELD TOWNSHIP | SR 1004 | HENDRICKS CREEK | 64/207 - FAIRFIELD | 40.3219 | -79.1307 | 20150301149 |  | all facilities responded clear per one call |  |  |  |  | 2016-08-04
552a | Y | 552 | 36387 | 31611 | 64101700400238 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 1017 | MILL CREEK | 64/210 - LIGONIER | 40.2604 | -79.2015 | 20140570776 | Elect | WEST PENN POWER | James Piper, 724-830-2937 | OH |  | Coordinated | 2016-06-27
552b | Y | 552 | 36387 | 31611 | 64101700400238 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 1017 | MILL CREEK | 64/210 - LIGONIER | 40.2604 | -79.2015 | 20140570776 | Comm | COMCAST | Doug Olszewski, 724-459-9042 | OH |  | Prior | 2016-06-27
552c | Y | 552 | 36387 | 31611 | 64101700400238 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 1017 | MILL CREEK | 64/210 - LIGONIER | 40.2604 | -79.2015 | 20140570776 | Comm | VERIZON PENNSYLVANIA | Mike Fowkes, 412-558-5601 | OH |  | Prior | 2016-06-27
552d | Y | 552 | 36387 | 31611 | 64101700400238 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 1017 | MILL CREEK | 64/210 - LIGONIER | 40.2604 | -79.2015 | 20140570776 | Wtr | LIGONIER TOWNSHIP MUNICIPAL AUTHORITY | Paul Knupp, 724-238-7464 | UG |  | Protect-In-Place | 2016-06-27
553a | -- | 553 | 36389 | 89037 | 64101700600042 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 1017 | BRANCH OF HANNAS RUN | 64/210 - LIGONIER | 40.2753 | -79.2044 | 20151412821 |  | LIGONIER TOWNSHIP MUNICIPAL AUTHORITY | Mary Lou Johnston, 412 238-9852 | UG |  |  | 2017-05-04
553b | -- | 553 | 36389 | 89037 | 64101700600042 | 12 | Westmoreland | LIGONIER TOWNSHIP | SR 1017 | BRANCH OF HANNAS RUN | 64/210 - LIGONIER | 40.2753 | -79.2044 | 20151412821 | Wtr | Municipal Auth of Westmoreland Cnty | M. Curtis Fontaine, 724-755-5950 | UG | 16" |  | 2017-05-04
554a | Y | 554 | 36431 | 31304 | 64103400500000 | 12 | Westmoreland | SALEM TOWNSHIP | SR 1034 | BEAVER RUN | 64/214 - SALEM | 40.4404 | -79.5439 | 20140661426 | NA | NA | NA |  |  | Not Affected | 2015-07-30
555a | -- | 555 | 36481 | 79404 | 64201201301481 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2012 | BRINKER RUN | 64/212 - MOUNT PLEASANT | 40.2197 | -79.5095 | 20150361577 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 |  |  |  | 2017-04-13
555b | -- | 555 | 36481 | 79404 | 64201201301481 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2012 | BRINKER RUN | 64/212 - MOUNT PLEASANT | 40.2197 | -79.5095 | 20150361577 |  | Mount Pleasant TWP Municipal Auth | Jaynette Brown (secy), 724-547-6745 | UG |  |  | 2017-04-13
555c | -- | 555 | 36481 | 79404 | 64201201301481 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2012 | BRINKER RUN | 64/212 - MOUNT PLEASANT | 40.2197 | -79.5095 | 20150361577 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-04-13
555d | -- | 555 | 36481 | 79404 | 64201201301481 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2012 | BRINKER RUN | 64/212 - MOUNT PLEASANT | 40.2197 | -79.5095 | 20150361577 | Wtr | Municipal Auth of Westmoreland Cnty | Engineering Clerk, 724-755-5955 | UG | 12" |  | 2017-04-13
556a | Y | 556 | 36482 | 79418 | 64201300201727 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 2013 | SLATE CREEK | 64/209 - HEMPFIELD | 40.2869 | -79.5109 | 20140631600 | Gas | KRIEBEL MINERALS INC | Michele A. Wice 814.226.4160 x 112 MWice@kriebelgas.com or Ron Seich, 814-221-8626 | UG |  | Prior | 2015-08-17
556b | Y | 556 | 36482 | 79418 | 64201300201727 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 2013 | SLATE CREEK | 64/209 - HEMPFIELD | 40.2869 | -79.5109 | 20140631600 | Comm | VERIZON PENNSYLVANIA | Jeff Guido, 412-793-7501 | OH |  | Coordinated | 2015-08-17
556c | Y | 556 | 36482 | 79418 | 64201300201727 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 2013 | SLATE CREEK | 64/209 - HEMPFIELD | 40.2869 | -79.5109 | 20140631600 | Elect | WEST PENN POWER | Grady Bryant, 724-523-7238 | OH |  | Coordinated | 2015-08-17
556d | Y | 556 | 36482 | 79418 | 64201300201727 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 2013 | SLATE CREEK | 64/209 - HEMPFIELD | 40.2869 | -79.5109 | 20140631600 | Comm | COMCAST | Brian Woller, 724-219-2571 | OH |  | Coordinated | 2015-08-17
556e | Y | 556 | 36482 | 79418 | 64201300201727 | 12 | Westmoreland | HEMPFIELD TOWNSHIP | SR 2013 | SLATE CREEK | 64/209 - HEMPFIELD | 40.2869 | -79.5109 | 20140631600 | SS | HEMPFIELD TOWNSHIP MUNICIPAL AUTHORITY | Brandon Hassinger, 724-832-0911 | UG |  | Not Affected | 2015-08-17
557a | -- | 557 | 36493 | 79419 | 64202100601976 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2021 | SEWICKLEY CREEK | 64/212 - MOUNT PLEASANT | 40.2137 | -79.4974 | 20150161835 | Comm | ARMSTRONG | Carl Rose, 724-628-6600 |  |  |  | 2016-06-10
557b | -- | 557 | 36493 | 79419 | 64202100601976 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2021 | SEWICKLEY CREEK | 64/212 - MOUNT PLEASANT | 40.2137 | -79.4974 | 20150161835 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-06-10
557c | -- | 557 | 36493 | 79419 | 64202100601976 | 12 | Westmoreland | MOUNT PLEASANT TOWNSHIP | SR 2021 | SEWICKLEY CREEK | 64/212 - MOUNT PLEASANT | 40.2137 | -79.4974 | 20150161835 | Wtr | Municipal Auth of Westmoreland Cnty | Donald Guerra, PE, daguerra@mawc.org | UG | 4" |  | 2016-06-10
558a | -- | 558 | 36684 | 31699 | 64400700200691 | 12 | Westmoreland | CITY OF JEANNETTE | SR 4007 | BULL RUN | 64/303 - JEANNETTE | 40.3302 | -79.6148 | 20151461534 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2017-03-06
558b | -- | 558 | 36684 | 31699 | 64400700200691 | 12 | Westmoreland | CITY OF JEANNETTE | SR 4007 | BULL RUN | 64/303 - JEANNETTE | 40.3302 | -79.6148 | 20151461534 | wtr | City of Jeannette | Edward Antonacci, City Engineer, 724-527-7771, edward.antonacci@verizon.net | UG |  |  | 2017-03-06
558c | -- | 558 | 36684 | 31699 | 64400700200691 | 12 | Westmoreland | CITY OF JEANNETTE | SR 4007 | BULL RUN | 64/303 - JEANNETTE | 40.3302 | -79.6148 | 20151461534 | sanitary | City of Jeannette Municipal Auth | Robert Bible, Gannett Fleming, Authority Engineer, 724-527-4022 | UG |  |  | 2017-03-06
558d | -- | 558 | 36684 | 31699 | 64400700200691 | 12 | Westmoreland | CITY OF JEANNETTE | SR 4007 | BULL RUN | 64/303 - JEANNETTE | 40.3302 | -79.6148 | 20151461534 | Gas | Peoples Gas (Equitable Gas) | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2017-03-06
558e | -- | 558 | 36684 | 31699 | 64400700200691 | 12 | Westmoreland | CITY OF JEANNETTE | SR 4007 | BULL RUN | 64/303 - JEANNETTE | 40.3302 | -79.6148 | 20151461534 | Wtr | Municipal Auth of Westmoreland Cnty | M. Curtis Fontaine, 724-755-5950 | UG |  |  | 2017-03-06
559a | Y | 559 | 36750 | 91189 | 64405300120000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 4053 | TURTLE CREEK | 64/437 - MURRYSVILLE | 40.4233 | -79.6367 |  | Elect | WEST PENN POWER | Robert Holman, 724-523-7238 | OH |  | Prior | 2015-08-11
559b | Y | 559 | 36750 | 91189 | 64405300120000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 4053 | TURTLE CREEK | 64/437 - MURRYSVILLE | 40.4233 | -79.6367 |  | Elect | WEST PENN POWER | Robert Holman, 724-523-7238 | OH |  | Coordinated | 2015-08-11
559c | Y | 559 | 36750 | 91189 | 64405300120000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 4053 | TURTLE CREEK | 64/437 - MURRYSVILLE | 40.4233 | -79.6367 |  | Comm | Windstream | Jerry Starenchak, 724-733-3333 | OH |  | Prior | 2015-08-11
559d | Y | 559 | 36750 | 91189 | 64405300120000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 4053 | TURTLE CREEK | 64/437 - MURRYSVILLE | 40.4233 | -79.6367 |  | Gas | PEOPLES NATURAL GAS | Daniel Andree, 724-832-2859 | UG |  | Prior | 2015-08-11
559e | Y | 559 | 36750 | 91189 | 64405300120000 | 12 | Westmoreland | MUNICIPAL. OF MURRYSVILLE | SR 4053 | TURTLE CREEK | 64/437 - MURRYSVILLE | 40.4233 | -79.6367 |  | SS | FRANKLIN TOWNSHIP SANITARY AUTHORITY | Kevin Kaplan, 724-327-1950 | UG |  | Protect-In-Place | 2015-08-11
560a | -- | 560 | 37037 | 89049 | 64801105100448 | 12 | Westmoreland | ROSTRAVER TOWNSHIP | SR 8011 RAMP A | POLLOCK RUN | 64/103 - ROSTRAVER | 40.1812 | -79.8058 | 20150410236 | Gas | Peoples Gas Design Monongahela | Mary M. Vitalbo-Madden, 724-292-3415 | UG |  |  | 2017-04-24
560b | -- | 560 | 37037 | 89049 | 64801105100448 | 12 | Westmoreland | ROSTRAVER TOWNSHIP | SR 8011 RAMP A | POLLOCK RUN | 64/103 - ROSTRAVER | 40.1812 | -79.8058 | 20150410236 | gas | Peoples Gas Monongahela Division | Mary M. Vitalbo-Madden, 724-292-3415 | UG |  |  | 2017-04-24
560c | -- | 560 | 37037 | 89049 | 64801105100448 | 12 | Westmoreland | ROSTRAVER TOWNSHIP | SR 8011 RAMP A | POLLOCK RUN | 64/103 - ROSTRAVER | 40.1812 | -79.8058 | 20150410236 | sanitary | Rostraver TWP Sewage Authority | 724-930-7667 | UG |  |  | 2017-04-24
560d | -- | 560 | 37037 | 89049 | 64801105100448 | 12 | Westmoreland | ROSTRAVER TOWNSHIP | SR 8011 RAMP A | POLLOCK RUN | 64/103 - ROSTRAVER | 40.1812 | -79.8058 | 20150410236 | Elect | West Penn Power | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-04-24
560e | -- | 560 | 37037 | 89049 | 64801105100448 | 12 | Westmoreland | ROSTRAVER TOWNSHIP | SR 8011 RAMP A | POLLOCK RUN | 64/103 - ROSTRAVER | 40.1812 | -79.8058 | 20150410236 | Wtr | Municipal Auth of Westmoreland Cnty | M. Curtis Fontaine, 724-755-5950 | UG |  |  | 2017-04-24
561a | -- | 561 | 16920 | 81636 | 26301301601348 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.9017 | -79.8937 | 20151462477 | wtr | Southwestern PA Water Authority | Kenneth Frameli, 724-883-2301 | UG |  |  | 2017-07-24
561b | -- | 561 | 16920 | 81636 | 26301301601348 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.9017 | -79.8937 | 20151462477 | Gas | Peoples Gas (Equitable Gas) | Daniel Andree, 724-832-2859, daniel.andree@peoples-gas.com | UG |  |  | 2017-07-24
562a | -- | 562 | 16923 | 79326 | 26301301701416 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8982 | -79.8993 | 20150341666 | Gas | Columbia Gas of PA Design | SHANNON GRIEST, sgriest@nisource.com | UG |  |  | 2017-02-24
562b | -- | 562 | 16923 | 79326 | 26301301701416 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8982 | -79.8993 | 20150341666 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2017-02-24
563a | -- | 563 | 16930 | 74190 | 26301301901171 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8931 | -79.9153 | 20150301334 | gas | Peoples Gas Design Monongahela | Rocky Saporito, PE, 412-473-3960, rocky.saporito@peoples-gas.com | UG |  |  | 2016-08-05
563b | -- | 563 | 16930 | 74190 | 26301301901171 | 12 | Fayette | GERMAN TOWNSHIP | SR 3013 | MIDDLE RUN | 26/207 - GERMAN | 39.8931 | -79.9153 | 20150301334 | Elect | WEST PENN POWER | Don Morchesky, 412-554-5886, dmorche@firstenergycorp.com |  |  |  | 2016-08-05
564 | -- | 564 | 13897 | 102789 | 21203100100187 | 8 | Cumberland | S. of Lisburn on Spangler Mill, mill race (Y.B.) | SR 2031 | MILL RACE | 21/102 - LOWER ALLEN | 40.212 | -76.9072 | 20151410994 |  | all facilities responded clear per one call |  |  |  |  | 2017-04-17
#N/A
1843 |  | 1850 | #DIV/0!
Formulas:
Anticipated Construction Start Date = LOOKUP(Table1[[#This Row],[JV '#]],Table4[JV '#],Table4[Construction Start Dates])

## Utility Relocation Work Summary
***PLEASE NOTE THESE ARE ALL CALCULATED COLUMNS. DO NOT ENTER DATA HERE. ENTER DATA IN "UTILITY TRACKING LOG".
[5 empty] | Bridge Data |  |  |  | Schedule | [5 empty] | Utility Relocation Description |  |  | Facility Location |  |  | Participation Description
| JV Number | MPMS Number | Early Completion Bridge | Region | District | County | Facility Quantity | Construction Start | Coordinated Participation Start | Utility Relocation Duration | Prior | Restrictive | Concurrent | Coordinated | Not Affected | Incorporated | Overhead | Underground | Requires Clear/Grub | Requires Stakeout | Requires Earthwork | Requires Guardrail Adjustment | Requires Other Action
1 | 1 | 97120 | -- | #REF! | 1 | Crawford | 2 | 2017-05-11 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
2 | 2 | 90155 | -- | #REF! | 1 | Crawford | 3 | 2016-08-08 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
3 | 3 | 97121 | -- | #REF! | 1 | Crawford | 1 | 2017-07-10 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
4 | 4 | 97117 | -- | #REF! | 1 | Crawford | 4 | 2016-05-13 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
5 | 5 | 97118 | -- | #REF! | 1 | Crawford | 4 | 2016-05-23 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
6 | 6 | 89176 | -- | #REF! | 1 | Crawford | 3 | 2017-03-27 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
7 | 7 | 97124 | -- | #REF! | 1 | Crawford | 3 | 2016-08-18 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
8 | 8 | 1140 | -- | #REF! | 1 | Erie | 1 | 2017-09-08 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
9 | 9 | 74663 | -- | #REF! | 1 | Forest | 1 | 2017-03-27 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
10 | 10 | 1370 | -- | #REF! | 1 | Forest | 5 | 2016-06-17 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
11 | 11 | 93595 | -- | #REF! | 1 | Forest | 3 | 2017-06-05 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
12 | 12 | 1398 | -- | #REF! | 1 | Forest | 4 | 2016-05-23 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
13 | 13 | 97328 | -- | #REF! | 1 | Mercer | 4 | 2017-08-21 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
14 | 14 | 1686 | -- | #REF! | 1 | Mercer | 2 | 2017-02-24 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
15 | 15 | 58092 | -- | #REF! | 1 | Mercer | 1 | 2017-05-30 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
16 | 16 | 93160 | -- | #REF! | 1 | Venango | 3 | 2017-02-24 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
17 | 17 | 2251 | -- | #REF! | 1 | Venango | 5 | 2017-06-01 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
18 | 18 | 97457 | -- | #REF! | 1 | Warren | 2 | 2017-02-21 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
19 | 19 | 2438 | -- | #REF! | 1 | Warren | 3 | 2017-03-08 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
20 | 20 | 2546 | -- | #REF! | 1 | Warren | 3 | 2017-06-02 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
21 | 21 | 2580 | -- | #REF! | 1 | Warren | 3 | 2016-08-18 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
22 | 22 | 2548 | -- | #REF! | 1 | Warren | 3 | 2017-08-21 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
23 | 23 | 84954 | -- | #REF! | 1 | Warren | 2 | 2017-05-18 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
24 | 24 | 97452 | -- | #REF! | 1 | Warren | 2 | 2016-05-12 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
25 | 25 | 85095 | -- | #REF! | 2 | Cameron | 2 | 2017-05-12 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
26 | 26 | 88201 | -- | #REF! | 2 | Centre | 4 | 2017-06-13 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
27 | 27 | 88155 | -- | #REF! | 2 | Centre | 4 | 2017-02-13 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
28 | 28 | 85135 | -- | #REF! | 2 | Centre | 1 | 2017-05-11 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
29 | 29 | 81359 | -- | #REF! | 2 | Centre | 2 | 2017-08-01 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
30 | 30 | 2893 | -- | #REF! | 2 | Centre | 1 | 2017-08-03 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
31 | 31 | 85125 | -- | #REF! | 2 | Centre | 4 | 2017-02-13 | #REF! | #REF! | [6 empty] | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
32 | 32 | 85128 | -- | #REF! | 2 | Centre | 6 | 2016-04-07 | #REF! | #REF! | [6 empty] | 2 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
33 | 33 | 88199 | -- | #REF! | 2 | Centre | 3 | 2017-02-13 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
34 | 34 | 91413 | -- | #REF! | 2 | Centre | 4 | 2017-05-11 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
35 | 35 | 3195 | -- | #REF! | 2 | Centre | 4 | 2016-06-08 | #REF! | #REF! | [6 empty] | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
36 | 36 | 69443 | -- | #REF! | 2 | Clearfield | 2 | 2016-04-14 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
37 | 37 | 91508 | -- | #REF! | 2 | Clearfield | 3 | 2017-02-13 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
38 | 38 | 85076 | -- | #REF! | 2 | Clearfield | 3 | 2016-07-22 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
39 | 39 | 85079 | -- | #REF! | 2 | Clearfield | 2 | 2017-02-13 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
40 | 40 | 93323 | -- | #REF! | 2 | Clearfield | 2 | 2017-02-13 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
41 | 41 | 93372 | -- | #REF! | 2 | Clearfield | 6 | 2016-07-22 | #REF! | #REF! | [6 empty] | 5 |  | #REF! | #REF! | #REF! | #REF! | #REF!
42 | 42 | 88626 | -- | #REF! | 2 | Clearfield | 2 | 2017-02-13 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
43 | 43 | 0 | -- | #REF! | 2 | Clearfield | 1 | 2016-08-22 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
44 | 44 | 3571 | -- | #REF! | 2 | Clearfield | 7 | 2016-06-06 | #REF! | #REF! | [6 empty] | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
45 | 45 | 85119 | -- | #REF! | 2 | Clearfield | 4 | 2016-07-12 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
46 | 46 | 91510 | -- | #REF! | 2 | Clinton | 4 | 2017-02-13 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
47 | 47 | 69040 | -- | #REF! | 2 | Clinton | 5 | 2016-06-27 | #REF! | #REF! | [6 empty] | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
48 | 48 | 85152 | -- | #REF! | 2 | Elk | 7 | 2016-07-18 | #REF! | #REF! | [6 empty] | 3 | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
49 | 49 | 69088 | -- | #REF! | 2 | Elk | 5 | 2016-07-08 | #REF! | #REF! | [6 empty] | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
50 | 50 | 88185 | -- | #REF! | 2 | Elk | 6 | 2016-07-22 | #REF! | #REF! | [6 empty] | 3 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
51 | 51 | 88195 | -- | #REF! | 2 | Juniata | 2 | 2017-02-13 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
52 | 52 | 4194 | -- | #REF! | 2 | Juniata | 1 | 2017-06-06 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
53 | 53 | 4214 | -- | #REF! | 2 | Juniata | 2 | 2017-05-22 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
54 | 54 | 4218 | -- | #REF! | 2 | Juniata | 4 | 2017-06-13 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
55 | 55 | 81508 | -- | #REF! | 2 | Juniata | 3 | 2016-06-17 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
56 | 56 | 91518 | -- | #REF! | 2 | Juniata | 3 | 2017-04-03 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
57 | 57 | 78606 | -- | #REF! | 2 | McKean | 4 | 2017-03-21 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
58 | 58 | 78605 | -- | #REF! | 2 | McKean | 6 | 2017-03-21 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
59 | 59 | 4344 | -- | #REF! | 2 | McKean | 1 | 2017-05-22 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
60 | 60 | 88664 | -- | #REF! | 2 | McKean | 4 | 2016-07-18 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
61 | 61 | 88183 | -- | #REF! | 2 | McKean | 3 | 2017-03-06 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
62 | 62 | 85215 | -- | #REF! | 2 | McKean | 3 | 2016-07-22 | #REF! | #REF! | [6 empty] | 1 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
63 | 63 | 4341 | -- | #REF! | 2 | McKean | 3 | 2017-05-18 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
64 | 64 | 85259 | -- | #REF! | 2 | McKean | 4 | 2017-06-19 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
65 | 65 | 85234 | -- | #REF! | 2 | McKean | 3 | 2017-03-21 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
66 | 66 | 4336 | -- | #REF! | 2 | McKean | 4 | 2017-03-21 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
67 | 67 | 85237 | -- | #REF! | 2 | McKean | 3 | 2017-06-16 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
68 | 68 | 4340 | -- | #REF! | 2 | McKean | 6 | 2016-08-12 | #REF! | #REF! | [6 empty] | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
69 | 69 | 88630 | -- | #REF! | 2 | McKean | 7 | 2016-07-18 | #REF! | #REF! | [6 empty] | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
70 | 70 | 68965 | -- | #REF! | 2 | McKean | 5 | 2016-08-12 | #REF! | #REF! | [6 empty] | 3 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
71 | 71 | 4486 | -- | #REF! | 2 | McKean | 6 | 2016-07-08 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
72 | 72 | 78611 | -- | #REF! | 2 | McKean | 2 | 2017-05-22 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
73 | 73 | 93322 | -- | #REF! | 2 | McKean | 4 | 2016-08-10 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
74 | 74 | 4642 | -- | #REF! | 2 | Mifflin | 3 | 2017-03-16 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
75 | 75 | 85297 | -- | #REF! | 2 | Mifflin | 3 | 2017-06-12 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
76 | 76 | 4676 | -- | #REF! | 2 | Mifflin | 3 | 2017-05-26 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
77 | 77 | 4677 | -- | #REF! | 2 | Mifflin | 1 | 2017-06-01 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
78 | 78 | 85275 | -- | #REF! | 2 | Mifflin | 4 | 2016-07-22 | #REF! | #REF! | [6 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
79 | 79 | 88640 | -- | #REF! | 2 | Potter | 4 | 2017-05-30 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
80 | 80 | 69501 | -- | #REF! | 2 | Potter | 2 | 2017-03-21 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
81 | 81 | 93375 | -- | #REF! | 2 | Potter | 5 | 2016-07-22 | #REF! | #REF! | [6 empty] | 3 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
82 | 82 | 85309 | -- | #REF! | 2 | Potter | 3 | 2017-04-10 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
83 | 83 | 4805 | -- | #REF! | 2 | Potter | 7 | 2016-07-22 | #REF! | #REF! | [6 empty] | 2 | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
84 | 84 | 4897 | -- | #REF! | 2 | Potter | 5 | 2016-06-27 | #REF! | #REF! | [6 empty] | 3 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
85 | 85 | 4898 | -- | #REF! | 2 | Potter | 5 | 2016-07-05 | #REF! | #REF! | [6 empty] | 3 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
86 | 86 | 4899 | -- | #REF! | 2 | Potter | 2 | 2017-06-15 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
87 | 87 | 93373 | -- | #REF! | 2 | Potter | 1 | 2017-05-23 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
88 | 88 | 85402 | -- | #REF! | 2 | Potter | 4 | 2017-05-25 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
89 | 89 | 83457 | -- | #REF! | 3 | Bradford | 5 | 2016-06-13 | #REF! | #REF! | [6 empty] | 3 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
90 | 90 | 99281 | Y | #REF! | 3 | Bradford | 2 | 2015-07-16 | #REF! | #REF! |  |  |  | 1 | 1 |  | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
91 | 91 | 5038 | -- | #REF! | 3 | Bradford | 5 | 2016-06-17 | #REF! | #REF! | [6 empty] | 4 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
92 | 92 | 5093 | Y | #REF! | 3 | Bradford | 3 | 06-01-15 A | #REF! | #REF! |  |  |  | 3 |  |  | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
93 | 93 | 79247 | -- | #REF! | 3 | Bradford | 2 | 2016-09-13 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
94 | 94 | 76863 | Y | #REF! | 3 | Bradford | 3 | 2015-10-05 | #REF! | #REF! | 2 |  |  | 1 |  |  | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
95 | 95 | 5210 | Y | #REF! | 3 | Bradford | 2 | 2015-07-22 | #REF! | #REF! | 1 |  |  |  | 1 |  | 1 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
96 | 96 | 5039 | Y | #REF! | 3 | Bradford | 3 | 2015-08-05 | #REF! | #REF! | 1 |  |  | 2 |  |  | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
97 | 97 | 5208 | Y | #REF! | 3 | Bradford | 2 | 2016-03-16 | #REF! | #REF! |  |  |  | 1 | 1 |  | 1 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
98 | 98 | 5215 | Y | #REF! | 3 | Bradford | 2 | 2016-04-18 | #REF! | #REF! |  |  |  |  | 2 |  |  | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
99 | 99 | 98535 | -- | #REF! | 3 | Bradford | 1 | 2017-08-01 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
100 | 100 | 5218 | -- | #REF! | 3 | Bradford | 3 | 2016-08-08 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
101 | 101 | 5589 | -- | #REF! | 3 | Columbia | 4 | 2016-08-11 | #REF! | #REF! | [6 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
102 | 102 | 98939 | Y | #REF! | 3 | Columbia | 8 | 2015-09-18 | #REF! | #REF! |  |  |  | 8 |  |  | 8 |  | #REF! | #REF! | #REF! | #REF! | #REF!
103 | 103 | 5578 | Y | #REF! | 3 | Columbia | 1 | 2015-07-16 | #REF! | #REF! |  |  |  |  | 1 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
104 | 104 | 78822 | Y | #REF! | 3 | Columbia | 2 | 2015-07-22 | #REF! | #REF! |  |  |  | 2 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
105 | 106 | 91436 | -- | #REF! | 3 | Lycoming | 2 | 2017-02-21 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
106 | 107 | 6049 | Y | #REF! | 3 | Lycoming | 3 | 2015-07-20 | #REF! | #REF! |  |  |  | 3 |  |  | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
107 | 108 | 6023 | -- | #REF! | 3 | Lycoming | 2 | 2016-07-21 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
108 | 109 | 6145 | -- | #REF! | 3 | Lycoming | 3 | 2016-05-31 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
109 | 110 | 6045 | -- | #REF! | 3 | Lycoming | 2 | 2017-06-01 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
110 | 111 | 6054 | -- | #REF! | 3 | Lycoming | 5 | 2016-07-08 | #REF! | #REF! | [6 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
111 | 112 | 6057 | Y | #REF! | 3 | Lycoming | 3 | 2015-08-31 | #REF! | #REF! | 3 | [5 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
112 | 113 | 6052 | -- | #REF! | 3 | Lycoming | 2 | 2017-06-27 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
113 | 114 | 74022 | Y | #REF! | 3 | Lycoming | 2 | 2015-07-22 | #REF! | #REF! |  |  |  | 2 |  |  | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
114 | 115 | 6144 | -- | #REF! | 3 | Lycoming | 2 | 2017-08-01 | #REF! | #REF! | [6 empty] | 1 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
115 | 116 | 6387 | -- | #REF! | 3 | Montour | 3 | 2016-05-12 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
116 | 117 | 6381 | -- | #REF! | 3 | Montour | 1 | 2017-08-01 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
117 | 118 | 74037 | Y | #REF! | 3 | Montour | 4 | 2015-07-16 | #REF! | #REF! |  |  |  | 4 |  |  | 4 |  | #REF! | #REF! | #REF! | #REF! | #REF!
118 | 119 | 97586 | -- | #REF! | 3 | Northumberland | 2 | 2017-07-24 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
119 | 120 | 6669 | -- | #REF! | 3 | Northumberland | 3 | 2016-08-11 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
120 | 121 | 79230 | -- | #REF! | 3 | Northumberland | 1 | 2017-08-01 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
121 | 122 | 6603 | -- | #REF! | 3 | Northumberland | 3 | 2016-06-14 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
122 | 123 | 88047 | -- | #REF! | 3 | Northumberland | 2 | 2017-05-25 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
123 | 124 | 88799 | -- | #REF! | 3 | Snyder | 7 | 2016-08-11 | #REF! | #REF! | [6 empty] | 1 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
124 | 125 | 89977 | -- | #REF! | 3 | Sullivan | 2 | 2016-12-12 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
125 | 126 | 7021 | Y | #REF! | 3 | Sullivan | 3 | 2015-08-03 | #REF! | #REF! |  |  |  | 3 |  |  | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
126 | 127 | 7009 | -- | #REF! | 3 | Tioga | 1 | 2016-11-28 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
127 | 128 | 7326 | -- | #REF! | 3 | Tioga | 4 | 2016-06-27 | #REF! | #REF! | [6 empty] | 2 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
128 | 129 | 7251 | Y | #REF! | 3 | Tioga | 4 | 2015-07-13 | #REF! | #REF! | 3 |  |  |  | 1 |  | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
129 | 130 | 87929 | -- | #REF! | 3 | Tioga | 3 | 2016-08-11 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
130 | 131 | 79055 | Y | #REF! | 3 | Tioga | 4 | 2015-08-06 | #REF! | #REF! | 2 |  |  | 1 | 1 |  | 4 |  | #REF! | #REF! | #REF! | #REF! | #REF!
131 | 132 | 7136 | Y | #REF! | 3 | Tioga | 5 | 2015-09-25 | #REF! | #REF! | 3 |  |  |  | 2 |  | 3 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
132 | 133 | 7347 | Y | #REF! | 3 | Tioga | 2 | 2015-07-30 | #REF! | #REF! | 2 | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
133 | 134 | 83470 | -- | #REF! | 3 | Tioga | 2 | 2016-08-03 | #REF! | #REF! | [6 empty] | 1 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
134 | 135 | 7542 | -- | #REF! | 3 | Union | 2 | 2016-07-11 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
135 | 136 | 7542 | -- | #REF! | 3 | Union | 2 | 2016-07-11 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
136 | 137 | 83478 | Y | #REF! | 3 | Union | 3 | 2015-08-10 | #REF! | #REF! | 2 |  |  |  | 1 |  | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
137 | 138 | 74043 | Y | #REF! | 3 | Union | 7 | 2016-06-20 | #REF! | #REF! |  |  |  | 6 | 1 |  | 6 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
138 | 139 | 96689 | -- | #REF! | 4 | Lackawanna | 5 | 2016-05-27 | #REF! | #REF! | [7 empty] | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
139 | 140 | 67364 | -- | #REF! | 4 | Luzerne | 2 | 2016-06-17 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
140 | 141 | 97506 | -- | #REF! | 4 | Luzerne | 1 | 2016-06-24 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
141 | 142 | 96726 | Y | #REF! | 4 | Pike | 14 | 06-29-15 A | #REF! | #REF! |  |  |  | 14 |  |  | 14 |  | #REF! | #REF! | #REF! | #REF! | #REF!
142 | 143 | 67514 | -- | #REF! | 4 | Pike | 2 | 2016-05-26 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
143 | 144 | 96737 | -- | #REF! | 4 | Susquehanna | 2 | 2016-06-17 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
144 | 145 | 89023 | -- | #REF! | 4 | Susquehanna | 1 | 2016-03-25 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
145 | 146 | 9719 | Y | #REF! | 4 | Susquehanna | 5 | 2015-08-07 | #REF! | #REF! |  |  |  | 4 | 1 |  | 5 |  | #REF! | #REF! | #REF! | #REF! | #REF!
146 | 147 | 79572 | -- | #REF! | 4 | Susquehanna | 2 | 2016-05-02 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
147 | 148 | 9656 | -- | #REF! | 4 | Susquehanna | 1 | 2017-05-30 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
148 | 149 | 96729 | -- | #REF! | 4 | Susquehanna | 2 | 2016-05-20 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
149 | 150 | 100550 | -- | #REF! | 4 | Susquehanna | 1 | 2017-05-30 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
150 | 151 | 85782 | Y | #REF! | 4 | Susquehanna | 2 | 2015-07-08 | #REF! | #REF! |  |  |  |  | 2 |  | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
151 | 152 | 96734 | -- | #REF! | 4 | Susquehanna | 3 | 2016-05-20 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
152 | 153 | 96727 | Y | #REF! | 4 | Susquehanna | 16 | 2015-07-20 | #REF! | #REF! |  |  |  | 16 |  |  | 16 |  | #REF! | #REF! | #REF! | #REF! | #REF!
153 | 154 | 9679 | -- | #REF! | 4 | Susquehanna | 1 | 2017-05-30 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
154 | 155 | 96736 | -- | #REF! | 4 | Susquehanna | 1 | 2016-08-08 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
155 | 156 | 68876 | -- | #REF! | 4 | Wayne | 3 | 2016-05-20 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
156 | 157 | 9969 | -- | #REF! | 4 | Wayne | 2 | 2016-08-25 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
157 | 158 | 68917 | Y | #REF! | 4 | Wayne | 3 | 2015-08-17 | #REF! | #REF! |  |  |  | 2 | 1 |  | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
158 | 159 | 68927 | Y | #REF! | 4 | Wayne | 7 | 2015-08-13 | #REF! | #REF! |  |  |  | 5 | 2 |  | 7 |  | #REF! | #REF! | #REF! | #REF! | #REF!
159 | 160 | 67584 | -- | #REF! | 4 | Wayne | 2 | 2016-08-01 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
160 | 161 | 56752 | Y | #REF! | 4 | Wayne | 2 | 2015-08-13 | #REF! | #REF! |  |  |  |  | 2 |  | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
161 | 162 | 79580 | Y | #REF! | 4 | Wayne | 15 | 2015-07-01 | #REF! | #REF! |  |  |  | 15 |  |  | 15 |  | #REF! | #REF! | #REF! | #REF! | #REF!
162 | 163 | 9978 | -- | #REF! | 4 | Wayne | 1 | 2016-07-05 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
163 | 164 | 10230 | -- | #REF! | 4 | Wyoming | 2 | 2016-08-18 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
164 | 165 | 10243 | -- | #REF! | 4 | Wyoming | 1 | 2016-08-15 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
165 | 166 | 68786 | Y | #REF! | 4 | Wyoming | 5 | 2015-08-06 | #REF! | #REF! |  |  |  | 3 | 2 |  | 5 |  | #REF! | #REF! | #REF! | #REF! | #REF!
166 | 167 | 68806 | Y | #REF! | 4 | Wyoming | 7 | 2015-08-03 | #REF! | #REF! |  |  |  | 6 | 1 |  | 7 |  | #REF! | #REF! | #REF! | #REF! | #REF!
167 | 168 | 79078 | -- | #REF! | 5 | Berks | 6 | 2016-08-01 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
168 | 169 | 78877 | -- | #REF! | 5 | Berks | 3 | 2016-06-20 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
169 | 170 | 78889 | -- | #REF! | 5 | Berks | 4 | 2016-08-22 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
170 | 171 | 85635 | -- | #REF! | 5 | Berks | 2 | 2016-08-15 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
171 | 172 | 79081 | -- | #REF! | 5 | Berks | 6 | 2016-06-01 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
172 | 173 | 85764 | Y | #REF! | 5 | Carbon | 6 | 2016-03-07 | #REF! | #REF! | 4 |  |  |  | 2 |  | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
173 | 174 | 85762 | -- | #REF! | 5 | Carbon | 2 | 2017-06-05 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
174 | 175 | 85693 | -- | #REF! | 5 | Lehigh | 8 | 2016-11-01 | #REF! | #REF! | [7 empty] | 6 | #REF! | #REF! | #REF! | #REF! | #REF!
175 | 176 | 89633 | -- | #REF! | 5 | Lehigh | 5 | 2017-03-09 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
176 | 177 | 85683 | -- | #REF! | 5 | Lehigh | 5 | 2017-05-22 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
177 | 178 | 89639 | -- | #REF! | 5 | Lehigh | 6 | 2016-06-17 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
178 | 179 | 85811 | -- | #REF! | 5 | Monroe | 5 | 2016-05-26 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
179 | 180 | 91680 | Y | #REF! | 5 | Monroe | 1 | 2016-03-08 | #REF! | #REF! |  |  |  |  | 1 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
180 | 181 | 79157 | Y | #REF! | 5 | Monroe | 1 | 2015-07-23 | #REF! | #REF! |  |  |  |  | 1 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
181 | 182 | 79158 | Y | #REF! | 5 | Monroe | 9 | 2015-08-03 | #REF! | #REF! |  |  |  | 7 | 2 |  | 7 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
182 | 183 | 11649 | Y | #REF! | 5 | Monroe | 1 | 2015-07-16 | #REF! | #REF! |  |  |  |  | 1 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
183 | 184 | 11730 | Y | #REF! | 5 | Monroe | 6 | 2015-07-24 | #REF! | #REF! |  |  | 2 | 4 |  |  | 6 |  | #REF! | #REF! | #REF! | #REF! | #REF!
184 | 185 | 96445 | Y | #REF! | 5 | Monroe | 2 | 2015-08-26 | #REF! | #REF! |  |  |  | 2 |  |  | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
185 | 186 | 85879 | Y | #REF! | 5 | Monroe | 4 | 2015-07-20 | #REF! | #REF! | 1 |  |  |  | 3 |  | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
186 | 187 | 89628 | Y | #REF! | 5 | Monroe | 8 | 2015-07-24 | #REF! | #REF! |  |  |  | 8 |  |  | 8 |  | #REF! | #REF! | #REF! | #REF! | #REF!
187 | 188 | 79204 | Y | #REF! | 5 | Monroe | 4 | 2016-03-08 | #REF! | #REF! |  |  |  | 4 |  |  | 4 |  | #REF! | #REF! | #REF! | #REF! | #REF!
188 | 189 | 79170 | Y | #REF! | 5 | Monroe | 1 | 2016-06-08 | #REF! | #REF! |  |  |  |  | 1 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
189 | 190 | 76368 | Y | #REF! | 5 | Monroe | 6 | 2015-12-09 | #REF! | #REF! | 4 |  |  |  | 2 |  | 4 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
190 | 191 | 96447 | Y | #REF! | 5 | Monroe | 1 | 2015-10-07 | #REF! | #REF! |  |  |  |  | 1 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
191 | 192 | 11758 | Y | #REF! | 5 | Monroe | 5 | 2015-08-07 | #REF! | #REF! |  |  |  | 5 |  |  | 5 |  | #REF! | #REF! | #REF! | #REF! | #REF!
192 | 194 | 79185 | Y | #REF! | 5 | Monroe | 5 | 2015-07-21 | #REF! | #REF! |  |  |  | 5 |  |  | 5 |  | #REF! | #REF! | #REF! | #REF! | #REF!
193 | 195 | 85849 | Y | #REF! | 5 | Monroe | 5 | 2016-04-28 | #REF! | #REF! |  |  |  | 5 |  |  | 5 |  | #REF! | #REF! | #REF! | #REF! | #REF!
194 | 196 | 79187 | Y | #REF! | 5 | Monroe | 3 | 2016-03-08 | #REF! | #REF! | 3 | [5 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
195 | 197 | 99555 | -- | #REF! | 5 | Northampton | 4 | 2016-06-06 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
196 | 198 | 104632 | -- | #REF! | 5 | Northampton | 2 | 2017-03-06 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
197 | 201 | 85947 | -- | #REF! | 5 | Northampton | 1 | 2016-06-17 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
198 | 202 | 67256 | -- | #REF! | 5 | Northampton | 2 | 2016-06-27 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
199 | 203 | 12098 | -- | #REF! | 5 | Northampton | 5 | 2017-05-11 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
200 | 204 | 12717 | Y | #REF! | 5 | Schuylkill | 2 | 2015-07-14 | #REF! | #REF! |  |  |  | 2 |  |  | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
201 | 205 | 99559 | Y | #REF! | 5 | Schuylkill | 2 | 2015-09-15 | #REF! | #REF! |  |  |  | 2 |  |  | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
202 | 206 | 12710 | Y | #REF! | 5 | Schuylkill | 2 | 2015-09-14 | #REF! | #REF! |  |  |  | 2 |  |  | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
203 | 207 | 85810 | Y | #REF! | 5 | Schuylkill | 5 | 2016-02-17 | #REF! | #REF! | 3 |  |  |  | 2 |  | 3 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
204 | 208 | 85724 | Y | #REF! | 5 | Schuylkill | 3 | 2015-07-20 | #REF! | #REF! |  |  |  | 3 |  |  | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
205 | 209 | 47695 | Y | #REF! | 5 | Schuylkill | 4 | 2015-08-24 | #REF! | #REF! |  |  |  | 3 | 1 |  | 4 |  | #REF! | #REF! | #REF! | #REF! | #REF!
206 | 210 | 12522 | Y | #REF! | 5 | Schuylkill | 2 | 2015-07-20 | #REF! | #REF! |  | 1 |  | 1 |  |  | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
207 | 211 | 56830 | -- | #REF! | 6 | Bucks | 2 | 2017-04-03 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
208 | 212 | 81284 | -- | #REF! | 6 | Chester | 1 | 2017-03-06 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
209 | 213 | 86306 | -- | #REF! | 6 | Chester | 1 | 2016-08-31 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
210 | 214 | 15232 | -- | #REF! | 6 | Delaware | 4 | 2016-08-04 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
211 | 215 | 102315 | -- | #REF! | 6 | Montgomery | 2 | 2017-03-24 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
212 | 216 | 102218 | -- | #REF! | 6 | Montgomery | 3 | 2017-03-08 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
213 | 217 | 86343 | -- | #REF! | 6 | Montgomery | 4 | 2017-03-24 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
214 | 218 | 67373 | -- | #REF! | 6 | Montgomery | 3 | 2016-08-31 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
215 | 219 | 81290 | -- | #REF! | 6 | Montgomery | 2 | 2016-07-05 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
216 | 220 | 87428 | -- | #REF! | 8 | Adams | 6 | 2017-04-03 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
217 | 221 | 87427 | -- | #REF! | 8 | Adams | 6 | 2016-08-15 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
218 | 222 | 87417 | -- | #REF! | 8 | Adams | 3 | 2016-07-11 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
219 | 223 | 87673 | -- | #REF! | 8 | Adams | 4 | 2017-03-21 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
220 | 224 | 18051 | -- | #REF! | 8 | Adams | 5 | 2016-06-17 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
221 | 225 | 99774 | -- | #REF! | 8 | Adams | 9 | 2016-06-16 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
222 | 226 | 87436 | -- | #REF! | 8 | Adams | 5 | 2017-08-01 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
223 | 227 | 87434 | -- | #REF! | 8 | Adams | 1 | 2016-06-17 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
224 | 228 | 18146 | -- | #REF! | 8 | Adams | 3 | 2017-06-05 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
225 | 229 | 87676 | -- | #REF! | 8 | Adams | 3 | 2016-06-22 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
226 | 230 | 87671 | -- | #REF! | 8 | Adams | 1 | 2017-03-06 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
227 | 231 | 74951 | -- | #REF! | 8 | Adams | 5 | 2016-05-25 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
228 | 232 | 87675 | -- | #REF! | 8 | Adams | 4 | 2017-05-30 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
229 | 233 | 87437 | -- | #REF! | 8 | Adams | 4 | 2017-06-01 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
230 | 234 | 87438 | -- | #REF! | 8 | Adams | 1 | 2017-05-26 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
231 | 235 | 90784 | -- | #REF! | 8 | Adams | 2 | 2017-05-30 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
232 | 236 | 90694 | -- | #REF! | 8 | Cumberland | 6 | 2017-03-13 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
233 | 237 | 87424 | -- | #REF! | 8 | Cumberland | 3 | 2017-03-21 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
234 | 238 | 90695 | -- | #REF! | 8 | Cumberland | 2 | 2017-08-21 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
235 | 239 | 89274 | -- | #REF! | 8 | Cumberland | 4 | 2017-02-10 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
236 | 240 | 74054 | -- | #REF! | 8 | Cumberland | 3 | 2017-05-11 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
237 | 241 | 90739 | -- | #REF! | 8 | Cumberland | 1 | 2017-05-31 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
238 | 242 | 74055 | -- | #REF! | 8 | Cumberland | 4 | 2017-05-30 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
239 | 243 | 90769 | -- | #REF! | 8 | Cumberland | 1 | 2017-05-30 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
240 | 244 | 90770 | -- | #REF! | 8 | Cumberland | 4 | 2017-08-14 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
241 | 245 | 100078 | -- | #REF! | 8 | Dauphin | 3 | 2016-08-18 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
242 | 246 | 47519 | -- | #REF! | 8 | Dauphin | 5 | 2016-08-01 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
243 | 247 | 87457 | -- | #REF! | 8 | Dauphin | 2 | 2016-07-05 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
244 | 248 | 87686 | -- | #REF! | 8 | Franklin | 5 | 2017-08-07 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
245 | 249 | 63173 | -- | #REF! | 8 | Franklin | 1 | 2016-05-17 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
246 | 250 | 87683 | -- | #REF! | 8 | Franklin | 5 | 2017-05-11 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
247 | 251 | 78710 | -- | #REF! | 8 | Franklin | 1 | 2017-06-08 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
248 | 252 | 78708 | -- | #REF! | 8 | Franklin | 3 | 2016-07-11 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
249 | 253 | 19965 | -- | #REF! | 8 | Lancaster | 4 | 2016-06-07 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
250 | 254 | 87315 | -- | #REF! | 8 | Lancaster | 2 | 2017-03-21 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
251 | 255 | 87316 | -- | #REF! | 8 | Lancaster | 3 | 2016-06-17 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
252 | 256 | 87536 | -- | #REF! | 8 | Lancaster | 3 | 2017-05-30 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
253 | 257 | 87554 | -- | #REF! | 8 | Lancaster | 2 | 2016-08-18 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
254 | 258 | 19915 | -- | #REF! | 8 | Lancaster | 4 | 2017-05-11 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
255 | 259 | 87505 | -- | #REF! | 8 | Lancaster | 6 | 2017-03-08 | #REF! | #REF! | [7 empty] | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
256 | 260 | 91194 | -- | #REF! | 8 | Lancaster | 1 | 2017-05-31 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
257 | 261 | 78868 | -- | #REF! | 8 | Lancaster | 3 | 2016-06-22 | #REF! | #REF! | [6 empty] | 1 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
258 | 262 | 91266 | -- | #REF! | 8 | Lancaster | 4 | 2017-04-03 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
259 | 263 | 87521 | -- | #REF! | 8 | Lancaster | 3 | 2017-05-30 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
260 | 264 | 74958 | -- | #REF! | 8 | Lancaster | 1 | 2016-07-11 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
261 | 265 | 19927 | -- | #REF! | 8 | Lancaster | 3 | 2016-08-03 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
262 | 266 | 100523 | -- | #REF! | 8 | Lancaster | 2 | 2017-07-10 | #REF! | #REF! | [6 empty] | 1 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
263 | 267 | 63230 | -- | #REF! | 8 | Lancaster | 2 | 2017-08-31 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
264 | 268 | 20124 | -- | #REF! | 8 | Lancaster | 1 | 2016-08-03 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
265 | 269 | 87706 | -- | #REF! | 8 | Lancaster | 2 | 2017-08-01 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
266 | 270 | 91323 | -- | #REF! | 8 | Lancaster | 1 | 2017-08-01 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
267 | 271 | 87515 | -- | #REF! | 8 | Lancaster | 5 | 2016-08-03 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
268 | 272 | 87566 | -- | #REF! | 8 | Lancaster | 2 | 2016-05-17 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
269 | 273 | 91324 | -- | #REF! | 8 | Lancaster | 3 | 2017-06-12 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
270 | 274 | 87516 | -- | #REF! | 8 | Lancaster | 2 | 2016-08-03 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
271 | 275 | 20123 | -- | #REF! | 8 | Lancaster | 1 | 2017-07-31 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
272 | 276 | 87562 | -- | #REF! | 8 | Lancaster | 1 | 2017-08-01 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
273 | 277 | 91108 | -- | #REF! | 8 | Lancaster | 1 | 2017-06-01 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
274 | 278 | 19964 | -- | #REF! | 8 | Lancaster | 2 | 2016-05-12 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
275 | 279 | 87518 | -- | #REF! | 8 | Lancaster | 2 | 2016-10-19 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
276 | 280 | 87501 | -- | #REF! | 8 | Lancaster | 1 | 2016-08-05 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
277 | 281 | 19812 | -- | #REF! | 8 | Lancaster | 3 | 2017-06-26 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
278 | 282 | 63229 | -- | #REF! | 8 | Lancaster | 3 | 2016-08-03 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
279 | 283 | 20151 | -- | #REF! | 8 | Lancaster | 2 | 2017-06-08 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
280 | 284 | 91352 | -- | #REF! | 8 | Lebanon | 1 | 2017-04-03 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
281 | 285 | 87462 | -- | #REF! | 8 | Perry | 5 | 2017-04-14 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
282 | 286 | 93582 | -- | #REF! | 8 | Perry | 1 | 2017-05-26 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
283 | 287 | 79054 | -- | #REF! | 8 | Perry | 3 | 2017-05-26 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
284 | 288 | 73961 | -- | #REF! | 8 | Perry | 2 | 2017-05-25 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
285 | 289 | 87465 | -- | #REF! | 8 | Perry | 2 | 2017-05-30 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
286 | 290 | 90716 | -- | #REF! | 8 | Perry | 2 | 2016-05-31 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
287 | 291 | 87491 | -- | #REF! | 8 | Perry | 2 | 2016-08-03 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
288 | 292 | 101098 | -- | #REF! | 8 | Perry | 1 | 2017-07-24 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
289 | 293 | 79042 | -- | #REF! | 8 | Perry | 3 | 2016-08-03 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
290 | 294 | 79047 | -- | #REF! | 8 | Perry | 2 | 2017-05-30 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
291 | 295 | 91353 | -- | #REF! | 8 | York | 3 | 2017-03-20 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
292 | 296 | 87693 | -- | #REF! | 8 | York | 3 | 2016-08-05 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
293 | 297 | 91191 | -- | #REF! | 8 | York | 7 | 2017-06-08 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
294 | 298 | 78860 | -- | #REF! | 8 | York | 5 | 2017-05-25 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
295 | 299 | 87551 | -- | #REF! | 8 | York | 4 | 2017-07-24 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
296 | 300 | 78878 | -- | #REF! | 8 | York | 5 | 2016-05-31 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
297 | 301 | 78896 | -- | #REF! | 8 | York | 4 | 2016-08-01 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
298 | 302 | 87695 | -- | #REF! | 8 | York | 2 | 2016-08-01 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
299 | 303 | 91367 | -- | #REF! | 8 | York | 4 | 2017-08-04 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
300 | 304 | 87596 | -- | #REF! | 8 | York | 3 | 2016-06-17 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
301 | 305 | 87595 | -- | #REF! | 8 | York | 3 | 2017-07-28 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
302 | 306 | 74944 | -- | #REF! | 8 | York | 8 | 2016-07-22 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
303 | 307 | 83428 | -- | #REF! | 8 | York | 4 | 2016-08-03 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
304 | 308 | 90222 | -- | #REF! | 8 | York | 3 | 2016-07-18 | #REF! | #REF! | [6 empty] | 1 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
305 | 309 | 91192 | -- | #REF! | 8 | York | 4 | 2017-07-28 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
306 | 310 | 88114 | -- | #REF! | 9 | Bedford | 2 | 2016-05-23 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
307 | 311 | 21558 | -- | #REF! | 9 | Bedford | 1 | 2016-06-17 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
308 | 312 | 21563 | -- | #REF! | 9 | Bedford | 3 | 2016-03-25 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
309 | 313 | 21455 | -- | #REF! | 9 | Bedford | 3 | 2016-04-15 | #REF! | #REF! | [6 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
310 | 314 | 88121 | -- | #REF! | 9 | Bedford | 5 | 2016-05-23 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
311 | 315 | 21596 | -- | #REF! | 9 | Bedford | 2 | 2017-05-30 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
312 | 316 | 21552 | -- | #REF! | 9 | Bedford | 2 | 2016-07-05 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
313 | 317 | 21600 | -- | #REF! | 9 | Bedford | 2 | 2016-05-31 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
314 | 318 | 74424 | -- | #REF! | 9 | Bedford | 3 | 2017-05-30 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
315 | 319 | 22107 | -- | #REF! | 9 | Blair | 2 | 2017-07-11 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
316 | 320 | 74376 | -- | #REF! | 9 | Blair | 5 | 2016-06-28 | #REF! | #REF! | [6 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
317 | 321 | 21957 | -- | #REF! | 9 | Blair | 3 | 2017-03-20 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
318 | 322 | 21961 | -- | #REF! | 9 | Blair | 1 | 2017-07-13 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
319 | 323 | 21967 | -- | #REF! | 9 | Blair | 6 | 2016-06-17 | #REF! | #REF! | [6 empty] | 2 | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
320 | 324 | 22626 | -- | #REF! | 9 | Cambria | 3 | 2016-06-17 | #REF! | #REF! | [6 empty] | 2 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
321 | 325 | 22627 | -- | #REF! | 9 | Cambria | 6 | 2016-05-23 | #REF! | #REF! | [6 empty] | 1 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
322 | 326 | 22444 | -- | #REF! | 9 | Cambria | 4 | 2016-07-08 | #REF! | #REF! | [6 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
323 | 327 | 22797 | -- | #REF! | 9 | Fulton | 2 | 2017-05-11 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
324 | 328 | 22798 | -- | #REF! | 9 | Fulton | 3 | 2016-08-22 | #REF! | #REF! | [6 empty] | 2 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
325 | 329 | 22825 | -- | #REF! | 9 | Fulton | 2 | 2016-03-25 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
326 | 330 | 22826 | -- | #REF! | 9 | Fulton | 3 | 2016-03-25 | #REF! | #REF! | [6 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
327 | 331 | 22827 | -- | #REF! | 9 | Fulton | 5 | 2016-05-23 | #REF! | #REF! | [6 empty] | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
328 | 332 | 22832 | -- | #REF! | 9 | Fulton | 4 | 2017-04-05 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
329 | 333 | 88142 | -- | #REF! | 9 | Fulton | 3 | 2016-08-11 | #REF! | #REF! | [6 empty] | 2 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
330 | 334 | 22837 | -- | #REF! | 9 | Fulton | 4 | 2016-07-08 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
331 | 335 | 74433 | -- | #REF! | 9 | Huntingdon | 2 | 2017-03-21 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
332 | 336 | 23030 | -- | #REF! | 9 | Huntingdon | 3 | 2016-04-25 | #REF! | #REF! | [6 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
333 | 337 | 22980 | -- | #REF! | 9 | Huntingdon | 2 | 2017-03-21 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
334 | 338 | 23039 | -- | #REF! | 9 | Huntingdon | 4 | 2016-06-08 | #REF! | #REF! | [6 empty] | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
335 | 339 | 23038 | -- | #REF! | 9 | Huntingdon | 5 | 2016-05-19 | #REF! | #REF! | [6 empty] | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
336 | 340 | 23058 | -- | #REF! | 9 | Huntingdon | 1 | 2017-05-31 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
337 | 341 | 23114 | -- | #REF! | 9 | Huntingdon | 2 | 2016-06-20 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
338 | 342 | 74449 | -- | #REF! | 9 | Huntingdon | 1 | 2017-05-11 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
339 | 343 | 23116 | -- | #REF! | 9 | Huntingdon | 1 | 2017-05-11 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
340 | 344 | 88158 | -- | #REF! | 9 | Somerset | 4 | 2016-06-17 | #REF! | #REF! | [6 empty] | 2 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
341 | 345 | 92698 | -- | #REF! | 9 | Somerset | 4 | 2016-06-17 | #REF! | #REF! | [6 empty] | 1 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
342 | 346 | 23517 | -- | #REF! | 9 | Somerset | 1 | 2017-03-21 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
343 | 347 | 23586 | -- | #REF! | 9 | Somerset | 3 | 2016-07-06 | #REF! | #REF! | [6 empty] | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
344 | 348 | 23410 | -- | #REF! | 9 | Somerset | 3 | 2016-05-23 | #REF! | #REF! | [6 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
345 | 349 | 74446 | -- | #REF! | 9 | Somerset | 3 | 2016-05-16 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
346 | 350 | 23516 | -- | #REF! | 9 | Somerset | 1 | 2017-05-22 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
347 | 351 | 23571 | -- | #REF! | 9 | Somerset | 1 | 2017-05-30 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
348 | 352 | 23588 | -- | #REF! | 9 | Somerset | 1 | 2017-06-05 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
349 | 353 | 74467 | -- | #REF! | 9 | Somerset | 1 | 2017-08-01 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
350 | 354 | 23428 | -- | #REF! | 9 | Somerset | 3 | 2016-04-14 | #REF! | #REF! | [6 empty] | 2 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
351 | 355 | 23549 | -- | #REF! | 9 | Somerset | 2 | 2016-07-18 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
352 | 356 | 23454 | -- | #REF! | 9 | Somerset | 1 | 2017-08-01 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
353 | 357 | 23601 | -- | #REF! | 9 | Somerset | 2 | 2017-08-01 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
354 | 358 | 83197 | -- | #REF! | 10 | Armstrong | 4 | 2016-06-20 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
355 | 359 | 24085 | Y | #REF! | 10 | Armstrong | 4 | 2015-07-16 | #REF! | #REF! |  | 4 |  |  |  |  | 4 |  | #REF! | #REF! | #REF! | #REF! | #REF!
356 | 360 | 79606 | Y | #REF! | 10 | Armstrong | 5 | 2015-07-22 | #REF! | #REF! |  |  |  | 4 |  |  | 3 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
357 | 361 | 24000 | -- | #REF! | 10 | Armstrong | 6 | 2017-05-01 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
358 | 362 | 83252 | -- | #REF! | 10 | Armstrong | 3 | 2017-02-24 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
359 | 363 | 74202 | -- | #REF! | 10 | Armstrong | 3 | 2017-05-30 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
360 | 364 | 24023 | -- | #REF! | 10 | Armstrong | 6 | 2016-05-20 | #REF! | #REF! | [6 empty] | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
361 | 365 | 24018 | -- | #REF! | 10 | Armstrong | 6 | 2016-05-31 | #REF! | #REF! | [6 empty] | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
362 | 366 | 24153 | Y | #REF! | 10 | Armstrong | 6 | 2015-07-20 | #REF! | #REF! |  |  |  | 2 | 3 |  | 2 | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
363 | 367 | 83284 | Y | #REF! | 10 | Armstrong | 7 | 2015-07-16 | #REF! | #REF! |  | 4 |  | 1 |  | 2 | 4 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
364 | 368 | 98070 | -- | #REF! | 10 | Armstrong | 4 | 2017-03-01 | #REF! | #REF! | [6 empty] | 1 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
365 | 369 | 24806 | Y | #REF! | 10 | Butler | 8 | 2015-07-20 | #REF! | #REF! | 1 | 4 |  | 1 | 2 |  | 5 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
366 | 370 | 24757 | -- | #REF! | 10 | Butler | 1 | 2017-05-30 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
367 | 371 | 24667 | Y | #REF! | 10 | Butler | 8 | 2015-08-03 | #REF! | #REF! |  | 2 |  | 6 |  |  | 6 | 2 | #REF! |  | #REF! | #REF! | #REF!
368 | 372 | 24779 | -- | #REF! | 10 | Butler | 1 | 2017-06-01 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
369 | 373 | 78002 | Y | #REF! | 10 | Butler | 8 | 06-22-15 A | #REF! | #REF! | 3 | 3 |  |  | 2 |  | 4 | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
370 | 374 | 83332 | -- | #REF! | 10 | Butler | 1 | 2016-08-05 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
371 | 375 | 24703 | -- | #REF! | 10 | Butler | 2 | 2016-07-08 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
372 | 376 | 83335 | Y | #REF! | 10 | Butler | 2 | 06-24-15 A | #REF! | #REF! |  |  |  |  | 2 |  | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
373 | 377 | 77989 | -- | #REF! | 10 | Butler | 2 | 2017-03-06 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
374 | 378 | 89967 | -- | #REF! | 10 | Butler | 1 | 2016-05-19 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
375 | 379 | 24710 | -- | #REF! | 10 | Butler | 3 | 2017-04-11 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
376 | 380 | 83229 | -- | #REF! | 10 | Clarion | 4 | 2016-06-08 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
377 | 381 | 83232 | -- | #REF! | 10 | Clarion | 3 | 2016-06-16 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
378 | 382 | 83234 | -- | #REF! | 10 | Clarion | 4 | 2016-06-17 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
379 | 383 | 25221 | -- | #REF! | 10 | Clarion | 3 | 2017-05-11 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
380 | 384 | 83241 | -- | #REF! | 10 | Clarion | 3 | 2017-07-24 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
381 | 385 | 83256 | -- | #REF! | 10 | Clarion | 5 | 2017-05-26 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
382 | 386 | 83293 | -- | #REF! | 10 | Indiana | 3 | 2017-05-22 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
383 | 387 | 95851 | -- | #REF! | 10 | Indiana | 1 | 2016-06-17 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
384 | 388 | 25780 | -- | #REF! | 10 | Indiana | 2 | 2016-05-26 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
385 | 389 | 25584 | -- | #REF! | 10 | Indiana | 3 | 2017-07-24 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
386 | 390 | 78120 | -- | #REF! | 10 | Indiana | 2 | 2017-05-11 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
387 | 391 | 83282 | -- | #REF! | 10 | Jefferson | 3 | 2016-06-17 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
388 | 392 | 83312 | -- | #REF! | 10 | Jefferson | 3 | 2017-05-30 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
389 | 393 | 26151 | -- | #REF! | 10 | Jefferson | 1 | 2017-07-24 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
390 | 394 | 26069 | -- | #REF! | 10 | Jefferson | 3 | 2017-05-26 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
391 | 395 | 83343 | -- | #REF! | 10 | Jefferson | 3 | 2017-05-26 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
392 | 396 | 62523 | -- | #REF! | 11 | Allegheny | 7 | 2016-07-11 | #REF! | #REF! | [6 empty] | 5 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
393 | 397 | 27272 | -- | #REF! | 11 | Allegheny | 2 | 2016-05-20 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
394 | 398 | 28154 | -- | #REF! | 11 | Allegheny | 4 | 2016-06-24 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
395 | 399 | 73522 | -- | #REF! | 11 | Allegheny | 6 | 2017-02-13 | #REF! | #REF! | [7 empty] | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
396 | 402 | 37590 | -- | #REF! | 11 | Allegheny | 3 | 2016-06-17 | #REF! | #REF! | [6 empty] | 1 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
397 | 403 | 28597 | -- | #REF! | 11 | Allegheny | 4 | 2016-05-19 | #REF! | #REF! | [6 empty] | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
398 | 404 | 63321 | -- | #REF! | 11 | Allegheny | 2 | 2017-02-24 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
399 | 405 | 63324 | Y | #REF! | 11 | Allegheny | 6 | 2015-07-22 | #REF! | #REF! |  |  |  |  | 5 |  | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
400 | 406 | 78185 | -- | #REF! | 11 | Allegheny | 6 | 2016-04-04 | #REF! | #REF! | [6 empty] | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
401 | 407 | 27185 | -- | #REF! | 11 | Allegheny | 5 | 2017-02-16 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
402 | 408 | 27188 | -- | #REF! | 11 | Allegheny | 5 | 2017-05-22 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
403 | 409 | 28128 | -- | #REF! | 11 | Allegheny | 6 | 2017-04-03 | #REF! | #REF! | [7 empty] | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
404 | 410 | 78220 | -- | #REF! | 11 | Allegheny | 2 | 2016-07-07 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
405 | 411 | 89100 | -- | #REF! | 11 | Allegheny | 4 | 2016-07-11 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
406 | 412 | 63342 | Y | #REF! | 11 | Allegheny | 6 | 2016-05-23 | #REF! | #REF! |  |  |  | 1 | 3 | 2 | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
407 | 413 | 28603 | -- | #REF! | 11 | Allegheny | 1 | 2016-09-02 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
408 | 414 | 63343 | Y | #REF! | 11 | Allegheny | 8 | 2016-05-26 | #REF! | #REF! | 1 | 1 |  | 1 | 4 | 1 | 3 | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
409 | 415 | 63344 | Y | #REF! | 11 | Allegheny | 6 | 2015-07-16 | #REF! | #REF! |  |  |  | 2 | 4 |  | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
410 | 416 | 78223 | Y | #REF! | 11 | Allegheny | 6 | 2015-08-05 | #REF! | #REF! | 1 |  |  | 2 | 3 |  | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
411 | 417 | 99687 | -- | #REF! | 11 | Allegheny | 4 | 2017-05-22 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
412 | 418 | 27287 | Y | #REF! | 11 | Allegheny | 6 | 2016-04-04 | #REF! | #REF! | 2 |  |  | 2 | 2 |  | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
413 | 419 | 63356 | Y | #REF! | 11 | Allegheny | 6 | 2015-08-03 | #REF! | #REF! |  |  |  |  | 5 |  | 5 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
414 | 420 | 63513 | Y | #REF! | 11 | Allegheny | 9 | 2015-08-06 | #REF! | #REF! |  |  |  | 6 | 2 | 1 | 7 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
415 | 421 | 28607 | -- | #REF! | 11 | Allegheny | 5 | 2016-04-04 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
416 | 422 | 62174 | Y | #REF! | 11 | Allegheny | 2 | 2016-05-23 | #REF! | #REF! |  |  |  | 2 |  |  | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
417 | 423 | 26417 | -- | #REF! | 11 | Allegheny | 4 | 2016-06-17 | #REF! | #REF! | [6 empty] | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
418 | 424 | 73045 | -- | #REF! | 11 | Allegheny | 6 | 2016-04-22 | #REF! | #REF! | [6 empty] | 1 | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
419 | 425 | 27451 | -- | #REF! | 11 | Allegheny | 7 | 2016-04-20 | #REF! | #REF! | [6 empty] | 2 | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
420 | 426 | 99665 | -- | #REF! | 11 | Allegheny | 3 | 2016-06-17 | #REF! | #REF! | [6 empty] | 1 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
421 | 427 | 78224 | -- | #REF! | 11 | Allegheny | 6 | 2016-04-20 | #REF! | #REF! | [6 empty] | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
422 | 428 | 99670 | -- | #REF! | 11 | Allegheny | 2 | 2017-05-22 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
423 | 429 | 63529 | -- | #REF! | 11 | Allegheny | 5 | 2017-02-16 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
424 | 430 | 78271 | -- | #REF! | 11 | Allegheny | 7 | 2016-05-31 | #REF! | #REF! | [6 empty] | 4 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
425 | 431 | 63547 | Y | #REF! | 11 | Allegheny | 6 | 2015-09-01 | #REF! | #REF! |  |  |  |  | 6 |  | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
426 | 432 | 74324 | -- | #REF! | 11 | Allegheny | 4 | 2016-05-19 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
427 | 433 | 27419 | Y | #REF! | 11 | Allegheny | 13 | 2016-02-17 | #REF! | #REF! |  |  |  | 4 | 2 |  | 6 | 7 | #REF! | #REF! | #REF! | #REF! | #REF!
428 | 434 | 89124 | -- | #REF! | 11 | Allegheny | 6 | 2016-06-17 | #REF! | #REF! | [7 empty] | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
429 | 435 | 27275 | -- | #REF! | 11 | Allegheny | 4 | 2017-07-28 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
430 | 436 | 63557 | Y | #REF! | 11 | Allegheny | 10 | 2015-08-07 | #REF! | #REF! |  |  |  | 7 | 3 |  | 5 | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
431 | 437 | 27436 | -- | #REF! | 11 | Allegheny | 3 | 2016-06-16 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
432 | 438 | 28446 | Y | #REF! | 11 | Allegheny | 6 | 2015-09-21 | #REF! | #REF! |  |  |  | 3 | 2 | 1 | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
433 | 439 | 27386 | -- | #REF! | 11 | Allegheny | 3 | 2016-06-17 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
434 | 440 | 28136 | -- | #REF! | 11 | Allegheny | 5 | 2016-07-11 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
435 | 441 | 27454 | -- | #REF! | 11 | Allegheny | 2 | 2016-06-22 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
436 | 442 | 27430 | -- | #REF! | 11 | Allegheny | 7 | 2016-04-06 | #REF! | #REF! | [6 empty] | 3 | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
437 | 443 | 27429 | -- | #REF! | 11 | Allegheny | 5 | 2016-06-17 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
438 | 444 | 89079 | -- | #REF! | 11 | Allegheny | 4 | 2016-05-23 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
439 | 445 | 78407 | -- | #REF! | 11 | Allegheny | 4 | 2017-05-22 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
440 | 446 | 74338 | Y | #REF! | 11 | Allegheny | 6 | 2015-08-07 | #REF! | #REF! | 3 |  |  | 3 |  |  | 3 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
441 | 447 | 78413 | -- | #REF! | 11 | Allegheny | 1 | 2016-07-14 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
442 | 448 | 78414 | -- | #REF! | 11 | Allegheny | 1 | 2017-02-21 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
443 | 449 | 78416 | -- | #REF! | 11 | Allegheny | 4 | 2016-07-08 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
444 | 450 | 78417 | -- | #REF! | 11 | Allegheny | 3 | 2016-05-19 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
445 | 451 | 70804 | -- | #REF! | 11 | Beaver | 2 | 2017-06-06 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
446 | 452 | 28944 | -- | #REF! | 11 | Beaver | 1 | 2017-05-22 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
447 | 453 | 93613 | -- | #REF! | 11 | Beaver | 6 | 2016-05-25 | #REF! | #REF! | [7 empty] | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
448 | 454 | 80062 | -- | #REF! | 11 | Beaver | 3 | 2017-05-11 | #REF! | #REF! | [6 empty] | 1 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
449 | 455 | 69069 | -- | #REF! | 11 | Beaver | 2 | 2017-04-24 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
450 | 456 | 67378 | -- | #REF! | 11 | Beaver | 2 | 2017-04-24 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
451 | 457 | 70805 | -- | #REF! | 11 | Beaver | 1 | 2016-05-20 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
452 | 458 | 70807 | -- | #REF! | 11 | Beaver | 3 | 2016-05-19 | #REF! | #REF! | [6 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
453 | 459 | 89058 | -- | #REF! | 11 | Beaver | 1 | 2016-06-08 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
454 | 460 | 99793 | -- | #REF! | 11 | Beaver | 1 | 2016-05-31 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
455 | 461 | 29062 | -- | #REF! | 11 | Beaver | 1 | 2017-05-30 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
456 | 462 | 78310 | -- | #REF! | 11 | Beaver | 1 | 2017-03-06 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
457 | 463 | 99794 | -- | #REF! | 11 | Beaver | 3 | 2016-08-15 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
458 | 464 | 78313 | -- | #REF! | 11 | Beaver | 1 | 2017-04-24 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
459 | 465 | 29374 | -- | #REF! | 11 | Lawrence | 3 | 2017-05-26 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
460 | 466 | 78362 | -- | #REF! | 11 | Lawrence | 1 | 2016-07-05 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
461 | 467 | 29534 | -- | #REF! | 11 | Lawrence | 2 | 2017-04-24 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
462 | 468 | 78318 | -- | #REF! | 11 | Lawrence | 1 | 2017-04-03 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
463 | 469 | 89094 | -- | #REF! | 11 | Lawrence | 3 | 2017-04-24 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
464 | 470 | 78370 | -- | #REF! | 11 | Lawrence | 2 | 2017-05-22 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
465 | 471 | 69103 | -- | #REF! | 11 | Lawrence | 3 | 2016-06-08 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
466 | 472 | 78374 | -- | #REF! | 11 | Lawrence | 1 | 2017-03-01 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
467 | 473 | 69231 | -- | #REF! | 11 | Lawrence | 5 | 2017-07-24 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
468 | 474 | 78378 | -- | #REF! | 11 | Lawrence | 1 | 2016-07-08 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
469 | 475 | 99796 | -- | #REF! | 11 | Lawrence | 2 | 2017-05-11 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
470 | 476 | 29321 | -- | #REF! | 11 | Lawrence | 4 | 2016-08-03 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
471 | 477 | 29387 | -- | #REF! | 11 | Lawrence | 1 | 2016-08-15 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
472 | 478 | 99798 | -- | #REF! | 11 | Lawrence | 2 | 2017-04-24 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
473 | 479 | 29525 | -- | #REF! | 11 | Lawrence | 4 | 2017-05-11 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
474 | 480 | 99797 | -- | #REF! | 11 | Lawrence | 3 | 2017-03-20 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
475 | 481 | 29549 | -- | #REF! | 11 | Lawrence | 4 | 2017-04-24 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
476 | 482 | 80677 | -- | #REF! | 11 | Lawrence | 1 | 2016-05-20 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
477 | 483 | 51503 | -- | #REF! | 12 | Fayette | 3 | 2016-05-19 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
478 | 484 | 51484 | -- | #REF! | 12 | Fayette | 4 | 2017-05-23 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
479 | 485 | 74174 | -- | #REF! | 12 | Fayette | 4 | 2017-06-05 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
480 | 486 | 74176 | -- | #REF! | 12 | Fayette | 4 | 2017-04-10 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
481 | 487 | 81961 | -- | #REF! | 12 | Fayette | 1 | 2017-06-09 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
482 | 488 | 29781 | -- | #REF! | 12 | Fayette | 1 | 2016-08-05 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
483 | 489 | 69229 | -- | #REF! | 12 | Fayette | 5 | 2016-07-08 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
484 | 490 | 74345 | -- | #REF! | 12 | Fayette | 2 | 2017-06-12 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
485 | 491 | 76009 | -- | #REF! | 12 | Fayette | 2 | 2017-02-27 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
486 | 492 | 76012 | -- | #REF! | 12 | Fayette | 3 | 2016-07-08 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
487 | 493 | 29820 | -- | #REF! | 12 | Fayette | 4 | 2016-03-14 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
488 | 494 | 90965 | -- | #REF! | 12 | Fayette | 1 | 2017-09-05 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
489 | 495 | 89075 | -- | #REF! | 12 | Fayette | 2 | 2017-05-15 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
490 | 496 | 29823 | -- | #REF! | 12 | Fayette | 1 | 2017-05-30 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
491 | 497 | 29926 | -- | #REF! | 12 | Fayette | 4 | 2016-07-01 | #REF! | #REF! | [6 empty] | 2 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
492 | 498 | 29893 | -- | #REF! | 12 | Fayette | 2 | 2016-05-09 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
493 | 499 | 74184 | -- | #REF! | 12 | Fayette | 4 | 2016-08-05 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
494 | 500 | 74189 | -- | #REF! | 12 | Fayette | 1 | 2016-08-22 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
495 | 501 | 79325 | -- | #REF! | 12 | Fayette | 2 | 2017-05-16 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
496 | 502 | 79328 | -- | #REF! | 12 | Fayette | 1 | 2017-07-26 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
497 | 503 | 79337 | -- | #REF! | 12 | Fayette | 2 | 2016-09-06 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
498 | 504 | 79340 | -- | #REF! | 12 | Greene | 3 | 2016-04-04 | #REF! | #REF! | [6 empty] | 1 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
499 | 505 | 79342 | -- | #REF! | 12 | Greene | 2 | 2017-02-06 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
500 | 506 | 30291 | -- | #REF! | 12 | Greene | 6 | 2016-05-20 | #REF! | #REF! | [6 empty] | 2 | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
501 | 507 | 76037 | -- | #REF! | 12 | Greene | 6 | 2016-05-17 | #REF! | #REF! | [6 empty] | 1 | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
502 | 508 | 89031 | -- | #REF! | 12 | Greene | 6 | 2016-05-19 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
503 | 509 | 74203 | -- | #REF! | 12 | Greene | 1 | 2016-07-25 | #REF! | #REF! | [6 empty] | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
504 | 510 | 30335 | -- | #REF! | 12 | Greene | 6 | 2016-07-18 | #REF! | #REF! | [6 empty] | 1 | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
505 | 511 | 79353 | -- | #REF! | 12 | Greene | 4 | 2016-07-18 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
506 | 512 | 30289 | -- | #REF! | 12 | Greene | 3 | 2017-03-16 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
507 | 513 | 79356 | -- | #REF! | 12 | Greene | 5 | 2017-04-03 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
508 | 514 | 79357 | -- | #REF! | 12 | Greene | 4 | 2016-06-17 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
509 | 515 | 88079 | -- | #REF! | 12 | Greene | 4 | 2016-05-19 | #REF! | #REF! | [6 empty] | 1 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
510 | 516 | 30231 | -- | #REF! | 12 | Greene | 3 | 2016-05-16 | #REF! | #REF! | [6 empty] | 1 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
511 | 517 | 30975 | -- | #REF! | 12 | Washington | 2 | 2016-07-05 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
512 | 518 | 30639 | -- | #REF! | 12 | Washington | 4 | 2016-05-23 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
513 | 519 | 30997 | -- | #REF! | 12 | Washington | 4 | 2017-02-21 | #REF! | #REF! | [7 empty] | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
514 | 520 | 73058 | -- | #REF! | 12 | Washington | 5 | 2016-06-23 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
515 | 521 | 89048 | -- | #REF! | 12 | Washington | 2 | 2016-06-27 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
516 | 522 | 88078 | -- | #REF! | 12 | Washington | 2 | 2016-05-19 | #REF! | #REF! | [6 empty] | 1 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
517 | 523 | 76062 | -- | #REF! | 12 | Washington | 8 | 2016-05-23 | #REF! | #REF! | [6 empty] | 3 | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
518 | 524 | 30813 | -- | #REF! | 12 | Washington | 2 | 2017-07-28 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
519 | 525 | 31155 | -- | #REF! | 12 | Washington | 2 | 2016-08-05 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
520 | 526 | 98374 | -- | #REF! | 12 | Washington | 2 | 2016-08-15 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
521 | 527 | 76072 | -- | #REF! | 12 | Washington | 3 | 2017-07-28 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
522 | 528 | 98377 | -- | #REF! | 12 | Washington | 4 | 2016-07-25 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
523 | 529 | 89142 | -- | #REF! | 12 | Washington | 1 | 2017-02-08 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
524 | 530 | 98864 | -- | #REF! | 12 | Washington | 3 | 2017-02-13 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
525 | 531 | 51507 | -- | #REF! | 12 | Washington | 4 | 2016-05-17 | #REF! | #REF! | [6 empty] | 1 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
526 | 532 | 31157 | -- | #REF! | 12 | Washington | 5 | 2016-07-11 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
527 | 533 | 81841 | -- | #REF! | 12 | Washington | 2 | 2017-05-25 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
528 | 534 | 30715 | -- | #REF! | 12 | Washington | 4 | 2017-05-04 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
529 | 535 | 30881 | -- | #REF! | 12 | Washington | 1 | 2016-08-05 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
530 | 536 | 31146 | -- | #REF! | 12 | Washington | 1 | 2016-06-17 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
531 | 537 | 30552 | -- | #REF! | 12 | Washington | 1 | 2017-07-28 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
532 | 538 | 30702 | -- | #REF! | 12 | Washington | 2 | 2016-08-05 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
533 | 539 | 81846 | -- | #REF! | 12 | Washington | 1 | 2017-07-24 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
534 | 540 | 30635 | -- | #REF! | 12 | Washington | 1 | 2017-03-03 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
535 | 541 | 32045 | -- | #REF! | 12 | Westmoreland | 2 | 2016-05-23 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
536 | 542 | 76089 | Y | #REF! | 12 | Westmoreland | 1 | 2015-07-24 | #REF! | #REF! |  |  |  | 1 |  |  | 1 |  | #REF! | #REF! | #REF! | #REF! | #REF!
537 | 543 | 79402 | -- | #REF! | 12 | Westmoreland | 5 | 2017-03-22 | #REF! | #REF! | [7 empty] | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
538 | 544 | 31601 | Y | #REF! | 12 | Westmoreland | 1 | 2015-08-05 | #REF! | #REF! |  |  |  |  | 1 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
539 | 545 | 74418 | Y | #REF! | 12 | Westmoreland | 2 | 2015-07-16 | #REF! | #REF! |  |  |  | 2 |  |  | 2 |  | #REF! | #REF! | #REF! | #REF! | #REF!
540 | 546 | 31826 | Y | #REF! | 12 | Westmoreland | 3 | 2016-04-18 | #REF! | #REF! | 3 | [5 empty] | 3 |  | #REF! | #REF! | #REF! | #REF! | #REF!
541 | 547 | 31614 | Y | #REF! | 12 | Westmoreland | 4 | 06-22-15 A | #REF! | #REF! | 1 |  |  |  | 3 |  | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
542 | 548 | 76121 | -- | #REF! | 12 | Westmoreland | 7 | 2016-05-23 | #REF! | #REF! | [6 empty] | 4 | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
543 | 549 | 76122 | Y | #REF! | 12 | Westmoreland | 4 | 2015-07-16 | #REF! | #REF! | 2 |  |  | 2 |  |  | 4 |  | #REF! | #REF! | #REF! | #REF! | #REF!
544 | 550 | 98633 | -- | #REF! | 12 | Westmoreland | 2 | 2016-05-16 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
545 | 551 | 31972 | -- | #REF! | 12 | Westmoreland | 1 | 2016-08-04 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
546 | 552 | 31611 | Y | #REF! | 12 | Westmoreland | 4 | 2016-06-27 | #REF! | #REF! | 2 |  |  | 1 |  |  | 3 | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
547 | 553 | 89037 | -- | #REF! | 12 | Westmoreland | 2 | 2017-05-04 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
548 | 554 | 31304 | Y | #REF! | 12 | Westmoreland | 1 | 2015-07-30 | #REF! | #REF! |  |  |  |  | 1 |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF!
549 | 555 | 79404 | -- | #REF! | 12 | Westmoreland | 4 | 2017-04-13 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
550 | 556 | 79418 | Y | #REF! | 12 | Westmoreland | 5 | 2015-08-17 | #REF! | #REF! | 1 |  |  | 3 | 1 |  | 3 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
551 | 557 | 79419 | -- | #REF! | 12 | Westmoreland | 3 | 2016-06-10 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
552 | 558 | 31699 | -- | #REF! | 12 | Westmoreland | 5 | 2017-03-06 | #REF! | #REF! | [7 empty] | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
553 | 559 | 91189 | Y | #REF! | 12 | Westmoreland | 5 | 2015-08-11 | #REF! | #REF! | 3 |  |  | 1 |  |  | 3 | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
554 | 560 | 89049 | -- | #REF! | 12 | Westmoreland | 5 | 2017-04-24 | #REF! | #REF! | [7 empty] | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
555 | 561 | 81636 | -- | #REF! | 12 | Fayette | 2 | 2017-07-24 | #REF! | #REF! | [7 empty] | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
556 | 562 | 79326 | -- | #REF! | 12 | Fayette | 2 | 2017-02-24 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
557 | 563 | 74190 | -- | #REF! | 12 | Fayette | 2 | 2016-08-05 | #REF! | #REF! | [7 empty] | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
558 | 564 | 102789 | -- | #REF! | 8 | Cumberland | 1 | 2017-04-17 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
| 558 | [5 empty] | 1844 |  |  |  | 26 | 7 | 1 | 57 | 48 | 5 | 181 | 374 | 0 | #REF! | #REF! | #REF! | 0
Formulas:
Construction Start = LOOKUP(Table5[[#This Row],[JV Number]],Table4[JV '#],Table4[Construction Start Dates])

## PA One Call Summary
JV # | CJV Region | ECB | PA One Call Serial Number | PA One Call Request Date | ***PLEASE NOTE THESE ARE CALCULATED COLUMNS. DO NOT ENTER DATA HERE. ENTER DATE IN "UTILITY TRACKING LOG".
1 | #REF! | -- | 20150351072 | #REF!
2 | #REF! | -- | 20150341823 | #REF!
3 | #REF! | -- | 20151473198 | #REF!
4 | #REF! | -- | 20143580160 | #REF!
5 | #REF! | -- | 20150161005 | #REF!
6 | #REF! | -- | 20150350248 | #REF!
7 | #REF! | -- | 20150340926 | #REF!
8 | #REF! | -- | 20151473231 | #REF!
9 | #REF! | -- | 20150410270 | #REF!
10 | #REF! | -- | 20150161022 | #REF!
11 | #REF! | -- | 20151472691 | #REF!
12 | #REF! | -- | 20150330199 | #REF!
13 | #REF! | -- | 20151473445 | #REF!
14 | #REF! | -- | 20150330486 | #REF!
15 | #REF! | -- | 20151472948 | #REF!
16 | #REF! | -- | 20150330512 | #REF!
17 | #REF! | -- | 20151471285, 20151471286 | #REF!
18 | #REF! | -- | 20150411787 | #REF!
19 | #REF! | -- | 20150340910 | #REF!
20 | #REF! | -- | 20151472392 | #REF!
21 | #REF! | -- | 20150340945 | #REF!
22 | #REF! | -- | 20151473333, 20151473334 | #REF!
23 | #REF! | -- | 20151471561 | #REF!
24 | #REF! | -- | 20143571624 | #REF!
25 | #REF! | -- | 20150541259 | #REF!
26 | #REF! | -- | 20150541283 | #REF!
27 | #REF! | -- | 20150541322 | #REF!
28 | #REF! | -- | 20150541685 | #REF!
29 | #REF! | -- | 20150541711 | #REF!
30 | #REF! | -- | 20143580136 | #REF!
31 | #REF! | -- | 20150541337 | #REF!
32 | #REF! | -- | 20150161081 | #REF!
33 | #REF! | -- | 20150541356 | #REF!
34 | #REF! | -- | 20150541697 | #REF!
35 | #REF! | -- | 20150161095, 20150161097 | #REF!
36 | #REF! | -- | 20143580396 | #REF!
37 | #REF! | -- | 20150712670 | #REF!
38 | #REF! | -- | 20150541754 | #REF!
39 | #REF! | -- | 20150752974 | #REF!
40 | #REF! | -- | 20150752912 | #REF!
41 | #REF! | -- | 20150680973 | #REF!
42 | #REF! | -- | 20150752439 | #REF!
43 | #REF! | -- | 20150682136 | #REF!
44 | #REF! | -- | 20143580324 | #REF!
45 | #REF! | -- | 20150541736 | #REF!
46 | #REF! | -- | 20150752547 | #REF!
47 | #REF! | -- | 20143580327 | #REF!
48 | #REF! | -- | 20150161105 | #REF!
49 | #REF! | -- | 20143580336 | #REF!
50 | #REF! | -- | 20150681014/ 20150681015 | #REF!
51 | #REF! | -- | 20150761133 | #REF!
52 | #REF! | -- | 20151470384 | #REF!
53 | #REF! | -- | 20151463303 | #REF!
54 | #REF! | -- | 20151473006 | #REF!
55 | #REF! | -- | 20150681042 | #REF!
56 | #REF! | -- | 20150781847 | #REF!
57 | #REF! | -- | 20150761183 | #REF!
58 | #REF! | -- | 20150761206 | #REF!
59 | #REF! | -- | 20150401604 | #REF!
60 | #REF! | -- | 20150640316 | 2015-03-06
61 | #REF! | -- | 20150762216 | #REF!
62 | #REF! | -- | 20150401238 | #REF!
63 | #REF! | -- | 20150401268 | #REF!
64 | #REF! | -- | 20150401536 | #REF!
65 | #REF! | -- | 20150401631 | #REF!
66 | #REF! | -- | 20150762617 | #REF!
67 | #REF! | -- | 20150401777 | #REF!
68 | #REF! | -- | 20150641226 | 2015-03-06
69 | #REF! | -- | 20143580408 | #REF!
70 | #REF! | -- | 20150681611 | #REF!
71 | #REF! | -- | 20143580345 | #REF!
72 | #REF! | -- | 20150401781 | #REF!
73 | #REF! | -- | 20150682166 | #REF!
74 | #REF! | -- | 20150441409 | #REF!
75 | #REF! | -- | 20151473141 | #REF!
76 | #REF! | -- | 20151470677 | #REF!
77 | #REF! | -- | 20151470863 | #REF!
78 | #REF! | -- | 20150401857 | #REF!
79 | #REF! | -- | 20151472488 | #REF!
80 | #REF! | -- | 20150762632 | #REF!
81 | #REF! | -- | 20150640336 | 2015-03-06
82 | #REF! | -- | 20151471351 | #REF!
83 | #REF! | -- | 20150640366 | 2015-03-06
84 | #REF! | -- | 20143580428 | #REF!
85 | #REF! | -- | 20150161136 | #REF!
86 | #REF! | -- | 20151473258 | #REF!
87 | #REF! | -- | 20151463369 | #REF!
88 | #REF! | -- | 20151471424 | #REF!
89 | #REF! | -- | 20150501485 | #REF!
90 | #REF! | Y | 20140270636 | #REF!
91 | #REF! | -- | 20143580167 | #REF!
92 | #REF! | Y | 20140231230 | #REF!
93 | #REF! | -- | 20150501470 | #REF!
94 | #REF! | Y | 20121810773 | #REF!
95 | #REF! | Y | 20123382078 | #REF!
96 | #REF! | Y | 20102561704 | #REF!
97 | #REF! | Y | 20140230920 | #REF!
98 | #REF! | Y | 20140230925 | #REF!
99 | #REF! | -- | 2015561535 | #REF!
100 | #REF! | -- | 20150501494 | #REF!
101 | #REF! | -- | 20150510819 | #REF!
102 | #REF! | Y | 20140270413 | #REF!
103 | #REF! | Y | 20140270447 | #REF!
104 | #REF! | Y | 20140271013, 20140271014 | #REF!
106 | #REF! | -- | 20150540536 | #REF!
107 | #REF! | Y | 20102520477 | #REF!
108 | #REF! | -- | 20150510827 | #REF!
109 | #REF! | -- | 20150161147 | #REF!
110 | #REF! | -- | 20150510840 | #REF!
111 | #REF! | -- | 20150161160 | #REF!
112 | #REF! | Y | 20130590226 | #REF!
113 | #REF! | -- | 20150540567 | #REF!
114 | #REF! | Y | 20121721769, 20121721770 | #REF!
115 | #REF! | -- | 20150540589 | #REF!
116 | #REF! | -- | 20143571637 | #REF!
117 | #REF! | -- | 20150540599 | #REF!
118 | #REF! | Y | 20130310595 | #REF!
119 | #REF! | -- | 20150510365 | #REF!
120 | #REF! | -- | 20151412504 | #REF!
121 | #REF! | -- | 20150510353 | #REF!
122 | #REF! | -- | 20150161786 | #REF!
123 | #REF! | -- | 20150540865 | #REF!
124 | #REF! | -- | 20150510372 | #REF!
125 | #REF! | -- | 20150510439 | #REF!
126 | #REF! | Y | 20140621066 | #REF!
127 | #REF! | -- | 20150540906 | #REF!
128 | #REF! | -- | 20150540886 | #REF!
129 | #REF! | Y | 20120531621 | #REF!
130 | #REF! | -- | 20150540876 | #REF!
131 | #REF! | Y | 20102730430 | #REF!
132 | #REF! | Y | 20120531574 | #REF!
133 | #REF! | Y | 20130461235 | #REF!
134 | #REF! | -- | 20150510450 | #REF!
135 | #REF! | -- | 20150161176, 20150161177 | #REF!
136 | #REF! | -- | 20150540916, 20150540917 | #REF!
137 | #REF! | Y | 20113201954, 20113201955 | #REF!
138 | #REF! | Y | 20102451630 | #REF!
139 | #REF! | -- | 20143521244 | #REF!
140 | #REF! | -- | 20150420607 | #REF!
141 | #REF! | -- | 20150420631 | #REF!
142 | #REF! | Y | 20140730431 | #REF!
143 | #REF! | -- | 20143580171 | #REF!
144 | #REF! | -- | 20150420639 | #REF!
145 | #REF! | -- | 20143561405 | #REF!
146 | #REF! | Y | 20140701600 | #REF!
147 | #REF! | -- | 20143580177 | #REF!
148 | #REF! | -- | 20151410438 | #REF!
149 | #REF! | -- | 20143580198 | #REF!
150 | #REF! | -- | 20151411254 | #REF!
151 | #REF! | Y | 20140701622 | #REF!
152 | #REF! | -- | 20143580483 | #REF!
153 | #REF! | Y | 20140730587 | #REF!
154 | #REF! | -- | 20151411354 | #REF!
155 | #REF! | -- | 20150420650 | #REF!
156 | #REF! | -- | 20143580183 | #REF!
157 | #REF! | -- | 20150420657 | #REF!
158 | #REF! | Y | 20140730520 | #REF!
159 | #REF! | Y | 20140730487 | #REF!
160 | #REF! | -- | 20140872316 | #REF!
161 | #REF! | Y | 20150271472 | #REF!
162 | #REF! | Y | 20140730634 | #REF!
163 | #REF! | -- | 20151671802 | #REF!
164 | #REF! | -- | 20150682207 | #REF!
165 | #REF! | -- | 20150701251 | #REF!
166 | #REF! | Y | 20140701940 | #REF!
167 | #REF! | Y | 20140701917 | #REF!
168 | #REF! | -- | 20150271473 | #REF!
169 | #REF! | -- | 20150161804 | #REF!
170 | #REF! | -- | - | #REF!
171 | #REF! | -- | 20150682225 | #REF!
172 | #REF! | -- | 20150161811 | #REF!
173 | #REF! | Y | 20140660634, 20140761455 | #REF!
174 | #REF! | -- | 20150762133 | #REF!
175 | #REF! | -- | 20150261292, 20150261293 | #REF!
176 | #REF! | -- | 20150751362 | #REF!
177 | #REF! | -- | 20143580203 | #REF!
178 | #REF! | -- | - | #REF!
179 | #REF! | -- | 20143561422 | #REF!
180 | #REF! | Y | 20140730675 | #REF!
181 | #REF! | Y | 20140310616, 20140630216 | #REF!
182 | #REF! | Y | 20140281453, 20140691002 | #REF!
183 | #REF! | Y | 20140240189, 20140691204 | #REF!
184 | #REF! | Y | 20140281480 | #REF!
185 | #REF! | Y | 20140240157 | #REF!
186 | #REF! | Y | 20140170608, 20140691602 | #REF!
187 | #REF! | Y | 20140691482, 20140691602, 20140720024, 20140170626 | #REF!
188 | #REF! | Y | 20140170663, 20140680050 | #REF!
189 | #REF! | Y | 20140630317 | #REF!
190 | #REF! | Y | 20130561832, 20130561993 | #REF!
191 | #REF! | Y | 20140511410 | #REF!
192 | #REF! | Y | 20140310593 | #REF!
194 | #REF! | Y | 20092382122 | #REF!
195 | #REF! | Y | 20140240144, 20140720024 | #REF!
196 | #REF! | Y | 20140240265 | #REF!
197 | #REF! | -- | 20150161793 | #REF!
198 | #REF! | -- | 20151412643 | #REF!
201 | #REF! | -- | 20150681634 | #REF!
202 | #REF! | -- | 20150261297 | #REF!
203 | #REF! | -- | 20150781905 | #REF!
204 | #REF! | Y | 20140690621, 20140761583 | #REF!
205 | #REF! | Y | 20140690644 | #REF!
206 | #REF! | Y | 20140690673 | #REF!
207 | #REF! | Y | 20140761698 | #REF!
208 | #REF! | Y | 20130300901, 20140131742, 20140761803 | #REF!
209 | #REF! | Y | 20140161218, 20140761890 | #REF!
210 | #REF! | Y | 20140131714, 20140761993 | #REF!
211 | #REF! | -- | 20143580217 | #REF!
212 | #REF! | -- | 20150712604 | #REF!
213 | #REF! | -- | 20150682247 | #REF!
214 | #REF! | -- | 20150271475 | #REF!
215 | #REF! | -- | 20150751388 | #REF!
216 | #REF! | -- | 20150751415 | #REF!
217 | #REF! | -- | 20150751452 | #REF!
218 | #REF! | -- | 20150701229 | #REF!
219 | #REF! | -- | 20143571505 | #REF!
220 | #REF! | -- | 20150681661/ 20150681662 | #REF!
221 | #REF! | -- | 20150261301 | #REF!
222 | #REF! | -- | 20150261305, 20150261306 | #REF!
223 | #REF! | -- | 20150712635/ 20150712636 | #REF!
224 | #REF! | -- | 20150161850 | #REF!
225 | #REF! | -- | 20150170124 | #REF!
226 | #REF! | -- | 20150762657/ 20150762658 | #REF!
227 | #REF! | -- | 20150170126 | #REF!
228 | #REF! | -- | 20151412879 | #REF!
229 | #REF! | -- | 20150261308, 20150261307 | #REF!
230 | #REF! | -- | 20150762107/ 20150762108 | #REF!
231 | #REF! | -- | 20143580152 | #REF!
232 | #REF! | -- | 20151412034 | #REF!
233 | #REF! | -- | 20151411415 | #REF!
234 | #REF! | -- | 20150161834 | #REF!
235 | #REF! | -- | 20150712651 | #REF!
236 | #REF! | -- | 20150721703 | #REF!
237 | #REF! | -- | 20150721733 | #REF!
238 | #REF! | -- | 20151671682 | #REF!
239 | #REF! | -- | 20150721759 / 20150721760 | #REF!
240 | #REF! | -- | 20150781279 | #REF!
241 | #REF! | -- | 20150762150 /20150762160 | #REF!
242 | #REF! | -- | 20151411466 | #REF!
243 | #REF! | -- | 20151412188, 20151412224 | #REF!
244 | #REF! | -- | 20151420686 | #REF!
245 | #REF! | -- | 20150701189 | #REF!
246 | #REF! | -- | 20150271477 | #REF!
247 | #REF! | -- | 20150261309 | #REF!
248 | #REF! | -- | 20150781288 | #REF!
249 | #REF! | -- | 20143580224 | #REF!
250 | #REF! | -- | 20150781297/ 20150781298 | #REF!
251 | #REF! | -- | 20151411926 | #REF!
252 | #REF! | -- | 20150261312 | #REF!
253 | #REF! | -- | 20143580433, 20143580434 | #REF!
254 | #REF! | -- | 20150721780 | #REF!
255 | #REF! | -- | 20150681684/ 20150681685 | #REF!
256 | #REF! | -- | 20150781953 | #REF!
257 | #REF! | -- | 20150271480 | #REF!
258 | #REF! | -- | 20151462579 | #REF!
259 | #REF! | -- | 20150722077 /20150722078/ 20150722079 | #REF!
260 | #REF! | -- | 20150761153 | #REF!
261 | #REF! | -- | 20143580443 | #REF!
262 | #REF! | -- | 20143571514 | #REF!
263 | #REF! | -- | 20151671723 | #REF!
264 | #REF! | -- | 20150261320 | #REF!
265 | #REF! | -- | 20150271482 | #REF!
266 | #REF! | -- | 20151471484 | #REF!
267 | #REF! | -- | 20151472602 | #REF!
268 | #REF! | -- | 20150271484 | #REF!
269 | #REF! | -- | 20151470444 | #REF!
270 | #REF! | -- | 20151470509, 20151470510 | #REF!
271 | #REF! | -- | 20150271485 | #REF!
272 | #REF! | -- | 20143561430 | #REF!
273 | #REF! | -- | 20150762193 | #REF!
274 | #REF! | -- | 20150641242 | 2015-03-06
275 | #REF! | -- | 20150781883 | #REF!
276 | #REF! | -- | 20151470950 | #REF!
277 | #REF! | -- | 20151463220 | #REF!
278 | #REF! | -- | 20143571656 | #REF!
279 | #REF! | -- | 20150641265 | 2015-03-06
280 | #REF! | -- | 20143571667, 20143571668 | #REF!
281 | #REF! | -- | 20150752891 | #REF!
282 | #REF! | -- | 20150420402 | #REF!
283 | #REF! | -- | 20150762649 | #REF!
284 | #REF! | -- | 20143571525 | #REF!
285 | #REF! | -- | 20150752474 | #REF!
286 | #REF! | -- | 20151410849 | #REF!
287 | #REF! | -- | 20151410975 | #REF!
288 | #REF! | -- | 20150751481 | #REF!
289 | #REF! | -- | 20151410885 | #REF!
290 | #REF! | -- | 20150161237 | #REF!
291 | #REF! | -- | 20150420413 | #REF!
292 | #REF! | -- | 20151421242 | #REF!
293 | #REF! | -- | 20150420431 | #REF!
294 | #REF! | -- | 20151412690 | #REF!
295 | #REF! | -- | 20150752367 | #REF!
296 | #REF! | -- | 20143571677 | #REF!
297 | #REF! | -- | 20151463749, 20151463750 | #REF!
298 | #REF! | -- | 20150752392 | #REF!
299 | #REF! | -- | 20150781928/ 20150781929 | #REF!
300 | #REF! | -- | 20150161784 | #REF!
301 | #REF! | -- | 20150420444, 20150420445 | #REF!
302 | #REF! | -- | 20150681692 | #REF!
303 | #REF! | -- | 201514200645 | #REF!
304 | #REF! | -- | 20150261323, 20150261324 | #REF!
305 | #REF! | -- | 20151420309 | #REF!
306 | #REF! | -- | 20150261329, 20150261330 | #REF!
307 | #REF! | -- | 20150420589 | #REF!
308 | #REF! | -- | 20150271466, 20150271467, 20150271468, 20150271469 | #REF!
309 | #REF! | -- | 20151420609, 20151420610 | #REF!
310 | #REF! | -- | 20150161798 | #REF!
311 | #REF! | -- | 20150380175 | #REF!
312 | #REF! | -- | 20143561437 | #REF!
313 | #REF! | -- | 20143561445 | #REF!
314 | #REF! | -- | 20143561454 | #REF!
315 | #REF! | -- | 20150411932 | #REF!
316 | #REF! | -- | 20150411927 | #REF!
317 | #REF! | -- | 20143580298 | #REF!
318 | #REF! | -- | 20150411937 | #REF!
319 | #REF! | -- | 20150411944 | #REF!
320 | #REF! | -- | 20143580307 | #REF!
321 | #REF! | -- | 20150411939 | #REF!
322 | #REF! | -- | 20150491178 | #REF!
323 | #REF! | -- | 20150161831 | #REF!
324 | #REF! | -- | 20150161836 | #REF!
325 | #REF! | -- | 20143561462 | #REF!
326 | #REF! | -- | 20150491142 | #REF!
327 | #REF! | -- | 20150501070 | #REF!
328 | #REF! | -- | 20150500720/20151811319 | #REF!
329 | #REF! | -- | 20143561474 | #REF!
330 | #REF! | -- | 20143571735 | #REF!
331 | #REF! | -- | 20143571746 | #REF!
332 | #REF! | -- | 20150501099 | #REF!
333 | #REF! | -- | 20150500707 | #REF!
334 | #REF! | -- | 20150500694 | #REF!
335 | #REF! | -- | 20150501134 | #REF!
336 | #REF! | -- | 20143571761 | #REF!
337 | #REF! | -- | 20150501356 | #REF!
338 | #REF! | -- | 20143580417 | #REF!
339 | #REF! | -- | 20143580425 | #REF!
340 | #REF! | -- | 20150501378 | #REF!
341 | #REF! | -- | 20150501112 | #REF!
342 | #REF! | -- | 20150501361 | #REF!
343 | #REF! | -- | 20150501372 | #REF!
344 | #REF! | -- | 20150161848, 20150161849 | #REF!
345 | #REF! | -- | 20150170057, 20150170058 | #REF!
346 | #REF! | -- | 20150501388, 20150501389 | #REF!
347 | #REF! | -- | 20143580432 | #REF!
348 | #REF! | -- | 20143571775 | #REF!
349 | #REF! | -- | 20143580320 | #REF!
350 | #REF! | -- | 20150501450, 20150501451 | #REF!
351 | #REF! | -- | 20150501474 | #REF!
352 | #REF! | -- | 20150501481 | #REF!
353 | #REF! | -- | 20150501491, 20150501492 | #REF!
354 | #REF! | -- | 20143580119 | #REF!
355 | #REF! | -- | 20143580311 | #REF!
356 | #REF! | -- | 20150501506 | #REF!
357 | #REF! | -- | 20150501439 | #REF!
358 | #REF! | -- | 20150330208 | #REF!
359 | #REF! | Y | 0 | #REF!
360 | #REF! | Y | 20130341535 | #REF!
361 | #REF! | -- | 20150410282 | #REF!
362 | #REF! | -- | 20150341109 | #REF!
363 | #REF! | -- | 20151412971 | #REF!
364 | #REF! | -- | 20143580317 | #REF!
365 | #REF! | -- | 20143580322 | #REF!
366 | #REF! | Y | 20140221432 | #REF!
367 | #REF! | Y | 20140221433 | #REF!
368 | #REF! | -- | 20150420541 | #REF!
369 | #REF! | Y | 20140510738 | #REF!
370 | #REF! | -- | 20151413015 | #REF!
371 | #REF! | Y | 20140510756 | #REF!
372 | #REF! | -- | 20151422492 | #REF!
373 | #REF! | Y | 20140371912 | #REF!
374 | #REF! | -- | 20150300985 | #REF!
375 | #REF! | -- | 20143571422 | #REF!
376 | #REF! | Y | 20140510700 | #REF!
377 | #REF! | -- | 20151420256 | #REF!
378 | #REF! | -- | 20143580231 | #REF!
379 | #REF! | -- | 20150341137 | #REF!
380 | #REF! | -- | 20150330217 | #REF!
381 | #REF! | -- | 20150330310 | #REF!
382 | #REF! | -- | 20150330289 | #REF!
383 | #REF! | -- | 20150341764, 20150341774 | #REF!
384 | #REF! | -- | 20151461574 | #REF!
385 | #REF! | -- | 20151413050 | #REF!
386 | #REF! | -- | 20151421304 | #REF!
387 | #REF! | -- | 20150330361 | #REF!
388 | #REF! | -- | 20143580238 | #REF!
389 | #REF! | -- | 20151462676 | #REF!
390 | #REF! | -- | 20150350459 | #REF!
391 | #REF! | -- | 20150170060 | #REF!
392 | #REF! | -- | 20151420341, 20151420342 | #REF!
393 | #REF! | -- | 20151462771 | #REF!
394 | #REF! | -- | 20151420498 | #REF!
395 | #REF! | -- | 20151420538, 20151420539 | #REF!
396 | #REF! | -- | 20150420290 | #REF!
397 | #REF! | -- | 20150161192 | #REF!
398 | #REF! | -- | 20150420382 | #REF!
399 | #REF! | -- | 20150420486, 20150420487 | #REF!
402 | #REF! | -- | 20143580439 | #REF!
403 | #REF! | -- | 20143580328 | #REF!
404 | #REF! | -- | 20150341089 | #REF!
405 | #REF! | Y | 20140162107 | #REF!
406 | #REF! | -- | 20143580332 | #REF!
407 | #REF! | -- | 20143580503 | #REF!
408 | #REF! | -- | 20150411801 | #REF!
409 | #REF! | -- | 20150350272 | #REF!
410 | #REF! | -- | 20150301463 | #REF!
411 | #REF! | -- | 20150301475 | #REF!
412 | #REF! | Y | 20140162112 | #REF!
413 | #REF! | -- | 20150330137 | #REF!
414 | #REF! | Y | 20133610627 | #REF!
415 | #REF! | Y | 20121380869 | #REF!
416 | #REF! | Y | 20140162094 | #REF!
417 | #REF! | -- | 20150411810 | #REF!
418 | #REF! | Y | 20140162109 | #REF!
419 | #REF! | Y | 20140371911 | #REF!
420 | #REF! | Y | 20140410780, 20140371909 | #REF!
421 | #REF! | -- | 20143580442 | #REF!
422 | #REF! | Y | 20133390194 | #REF!
423 | #REF! | -- | 20150161751, 20150161752 | #REF!
424 | #REF! | -- | 20143580340 | #REF!
425 | #REF! | -- | 20150170073 | #REF!
426 | #REF! | -- | 20150161794 | #REF!
427 | #REF! | -- | 20150170076, 20150170077 | #REF!
428 | #REF! | -- | 20150411843 | #REF!
429 | #REF! | -- | 20143571433 | #REF!
430 | #REF! | -- | 20150161783 | #REF!
431 | #REF! | Y | 0 | #REF!
432 | #REF! | -- | 20150170081, 20150170082 | #REF!
433 | #REF! | Y | 20140162146 | #REF!
434 | #REF! | -- | 20150170083 | #REF!
435 | #REF! | -- | 20151471652 | #REF!
436 | #REF! | Y | 0 | #REF!
437 | #REF! | -- | 20150161202 | #REF!
438 | #REF! | Y | 20133390204 | #REF!
439 | #REF! | -- | 20150170090 | #REF!
440 | #REF! | -- | 20150341098 | #REF!
441 | #REF! | -- | 20150301240 | #REF!
442 | #REF! | -- | 20150170118, 20150170119 | #REF!
443 | #REF! | -- | 20150161724 | #REF!
444 | #REF! | -- | 20150170120, 20150170121 | #REF!
445 | #REF! | -- | 20150420669 | #REF!
446 | #REF! | Y | 20140162092 | #REF!
447 | #REF! | -- | 20150340804 | #REF!
448 | #REF! | -- | 20150340889 | #REF!
449 | #REF! | -- | 20150301286 | #REF!
450 | #REF! | -- | 20150170123 | #REF!
451 | #REF! | -- | 20151472773 | #REF!
452 | #REF! | -- | 20151470662 | #REF!
453 | #REF! | -- | 20150170125 | #REF!
454 | #REF! | -- | 20150350331 | #REF!
455 | #REF! | -- | 20150341801 | #REF!
456 | #REF! | -- | 20150341820 | #REF!
457 | #REF! | -- | 20143580299 | #REF!
458 | #REF! | -- | 20143570586 | #REF!
459 | #REF! | -- | 20150161766 | #REF!
460 | #REF! | -- | 20150161774 | #REF!
461 | #REF! | -- | 20151471730 | #REF!
462 | #REF! | -- | 20151472898, 20151472899 | #REF!
463 | #REF! | -- | 20150330155 | #REF!
464 | #REF! | -- | 20150620724 | #REF!
465 | #REF! | -- | 20151470992 | #REF!
466 | #REF! | -- | 20151411253 | #REF!
467 | #REF! | -- | 20150351122 | #REF!
468 | #REF! | -- | 20150411766 | #REF!
469 | #REF! | -- | 20150420614 | #REF!
470 | #REF! | -- | 20151471060 | #REF!
471 | #REF! | -- | 20150161711 | #REF!
472 | #REF! | -- | 20150411781 | #REF!
473 | #REF! | -- | 20150351122, 20151471110 | #REF!
474 | #REF! | -- | 20150341698 | #REF!
475 | #REF! | -- | 20150350479 | #REF!
476 | #REF! | -- | 20150291606 | #REF!
477 | #REF! | -- | 20150330166 | #REF!
478 | #REF! | -- | 20150351748 20150351749 | #REF!
479 | #REF! | -- | 20150341785 | #REF!
480 | #REF! | -- | 20150420644 | #REF!
481 | #REF! | -- | 20150361529 | #REF!
482 | #REF! | -- | 20143571138 | #REF!
483 | #REF! | -- | 20143571450, 20143571452 | #REF!
484 | #REF! | -- | 20143580452 | #REF!
485 | #REF! | -- | 20151461291 | #REF!
486 | #REF! | -- | 20150350447 | #REF!
487 | #REF! | -- | 20151422555 | #REF!
488 | #REF! | -- | 20150281894 | #REF!
489 | #REF! | -- | 20150291510 | #REF!
490 | #REF! | -- | 20151461419, 20151461420 | #REF!
491 | #REF! | -- | 20150341153 20150341154 | #REF!
492 | #REF! | -- | 20143580347, 20143580348 | #REF!
493 | #REF! | -- | 20143571183 | #REF!
494 | #REF! | -- | 20151463422 | #REF!
495 | #REF! | -- | 20151412100 | #REF!
496 | #REF! | -- | 20151461674 | #REF!
497 | #REF! | -- | 20143580467, 20143580470 | #REF!
498 | #REF! | -- | 20143571250 | #REF!
499 | #REF! | -- | 20150291578 | #REF!
500 | #REF! | -- | 20150301307 | #REF!
501 | #REF! | -- | 20150411739 | #REF!
502 | #REF! | -- | 20151462809 | #REF!
503 | #REF! | -- | 20150301378 | #REF!
504 | #REF! | -- | 20143571263 | #REF!
505 | #REF! | -- | 20150411755 | #REF!
506 | #REF! | -- | 20143571273 | #REF!
507 | #REF! | -- | 20143571371 | #REF!
508 | #REF! | -- | 20143580303, 20143580304 | #REF!
509 | #REF! | -- | 20150420316 | #REF!
510 | #REF! | -- | 20150291598, 20150291599 | #REF!
511 | #REF! | -- | 20150330424 | #REF!
512 | #REF! | -- | 20143580312 | #REF!
513 | #REF! | -- | 20150341683 | #REF!
514 | #REF! | -- | 20150161837 | #REF!
515 | #REF! | -- | 20143571385 | #REF!
516 | #REF! | -- | 20143571401 | #REF!
517 | #REF! | -- | 20150350499 | #REF!
518 | #REF! | -- | 20150161840 | #REF!
519 | #REF! | -- | 20150341717 20150341718 | #REF!
520 | #REF! | -- | 20150291622 | #REF!
521 | #REF! | -- | 20150330537 | #REF!
522 | #REF! | -- | 20143580124, 20143580125 | #REF!
523 | #REF! | -- | 20150161845 | #REF!
524 | #REF! | -- | 20151461752 | #REF!
525 | #REF! | -- | 20150301020 | #REF!
526 | #REF! | -- | 20150330178 | #REF!
527 | #REF! | -- | 20151461810 | #REF!
528 | #REF! | -- | 20150301451 | #REF!
529 | #REF! | -- | 20143580131 | #REF!
530 | #REF! | -- | 20150330391 | #REF!
531 | #REF! | -- | 20150161815 | #REF!
532 | #REF! | -- | 20150301127 | #REF!
533 | #REF! | -- | 20151420569 | #REF!
534 | #REF! | -- | 20151412755 | #REF!
535 | #REF! | -- | 20150330097 | #REF!
536 | #REF! | -- | 20150161847 | #REF!
537 | #REF! | -- | 20151462383 | #REF!
538 | #REF! | -- | 20150330108 | #REF!
539 | #REF! | -- | 20151463040 | #REF!
540 | #REF! | -- | 20150351050 20150351051 | #REF!
541 | #REF! | -- | 20150161856, 20150161857 | #REF!
542 | #REF! | Y | 20140660772 | #REF!
543 | #REF! | -- | 20150341825 | #REF!
544 | #REF! | Y | 20140660772 | #REF!
545 | #REF! | Y | 0 | #REF!
546 | #REF! | Y | 20140570767 | #REF!
547 | #REF! | Y | 20140570765 | #REF!
548 | #REF! | -- | 20150161833 | #REF!
549 | #REF! | Y | 20140570776 | #REF!
550 | #REF! | -- | 20143571496 | #REF!
551 | #REF! | -- | 20150301149 | #REF!
552 | #REF! | Y | 20140570776 | #REF!
553 | #REF! | -- | 20151412821 | #REF!
554 | #REF! | Y | 20140661426 | #REF!
555 | #REF! | -- | 20150361577 | #REF!
556 | #REF! | Y | 20140631600 | #REF!
557 | #REF! | -- | 20150161835 | #REF!
558 | #REF! | -- | 20151461534 | #REF!
559 | #REF! | Y | 0 | #REF!
560 | #REF! | -- | 20150410236 | #REF!
561 | #REF! | -- | 20151462477 | #REF!
562 | #REF! | -- | 20150341666 | #REF!
563 | #REF! | -- | 20150301334 | #REF!
564 | #REF! | -- | 20151410994 | #REF!
558 |  |  | 553 | 6

## Schedule Dump
Dump from Josh's Schedule Spreadsheets
| ↓ | ↓
JV # | NTP3 Issue Dates Per CPM Schedule | Construction Start Dates | 7/15 CPM Update ← | ***PLEASE NOTE THESE ARE ALL CALCULATED COLUMNS. DO NOT ENTER DATA HERE. ENTER DATA IN "UTILITY TRACKING LOG". | PBS-02R3 | If negative then construction date advanced
1 | 2016-11-14 | 2017-05-11 |  |  | 2017-05-11 | 0
2 | 2016-08-01 | 2016-08-08 |  |  | 2016-08-01 | 7
3 | 2017-03-06 | 2017-07-10 |  |  | 2017-07-10 | 0
4 | 2016-02-25 | 2016-05-13 |  |  | 2016-05-12 | 1
5 | 2016-04-04 | 2016-05-23 |  |  | 2016-05-23 | 0
6 | 2016-10-03 | 2017-03-27 |  |  | 2017-03-27 | 0
7 | 2016-08-01 | 2016-08-18 |  |  | 2016-08-01 | 17
8 | 2017-03-06 | 2017-09-08 |  |  | 2017-09-08 | 0
9 | 2016-10-31 | 2017-03-27 |  |  | 2017-03-27 | 0
10 | 2016-04-04 | 2016-06-17 |  |  | 2016-05-23 | 25
11 | 2017-01-31 | 2017-06-05 |  |  | 2017-06-05 | 0
12 | 2016-05-05 | 2016-05-23 |  |  | 2016-05-23 | 0
13 | 2017-03-30 | 2017-08-21 |  |  | 2017-08-21 | 0
14 | 2016-10-03 | 2017-02-24 |  |  | 2017-02-24 | 0
15 | 2017-01-31 | 2017-05-30 |  |  | 2017-05-30 | 0
16 | 2016-10-17 | 2017-02-24 |  |  | 2017-02-24 | 0
17 | 2017-01-04 | 2017-06-01 |  |  | 2017-06-01 | 0
18 | 2016-11-16 | 2017-02-21 |  |  | 2017-02-21 | 0
19 | 2016-10-03 | 2017-03-08 |  |  | 2017-03-08 | 0
20 | 2017-01-17 | 2017-06-02 |  |  | 2017-06-02 | 0
21 | 2016-08-01 | 2016-08-18 |  |  | 2016-08-01 | 17
22 | 2017-03-22 | 2017-08-21 |  |  | 2017-08-21 | 0
23 | 2017-01-03 | 2017-05-18 |  |  | 2017-05-18 | 0
24 | 2016-02-25 | 2016-05-12 |  |  | 2016-03-21 | 52
25 | 2017-03-30 | 2017-05-12 |  |  | 2017-05-12 | 0
26 | 2016-12-16 | 2017-06-13 |  |  | 2017-06-13 | 0
27 | 2016-12-16 | 2017-02-13 |  |  | 2017-02-13 | 0
28 | 2016-12-20 | 2017-05-11 |  |  | 2017-05-11 | 0
29 | 2017-03-22 | 2017-08-01 |  |  | 2017-08-01 | 0
30 | 2017-03-20 | 2017-08-03 |  |  | 2017-08-03 | 0
31 | 2016-09-01 | 2017-02-13 |  |  | 2017-02-13 | 0
32 | 2016-04-04 | 2016-04-07 |  |  | 2016-04-04 | 3
33 | 2016-09-01 | 2017-02-13 |  |  | 2017-02-13 | 0
34 | 2016-12-20 | 2017-05-11 |  |  | 2017-05-11 | 0
35 | 2016-04-11 | 2016-06-08 |  |  | 2016-04-11 | 58
36 | 2016-03-07 | 2016-04-14 |  |  | 2016-04-14 | 0
37 | 2016-09-01 | 2017-02-13 |  |  | 2017-02-13 | 0
38 | 2016-05-23 | 2016-07-22 |  |  | 2016-05-23 | 60
39 | 2016-09-20 | 2017-02-13 |  |  | 2017-02-13 | 0
40 | 2016-09-20 | 2017-02-13 |  |  | 2017-02-13 | 0
41 | 2016-05-23 | 2016-07-22 |  |  | 2016-05-23 | 60
42 | 2016-09-01 | 2017-02-13 |  |  | 2017-02-13 | 0
43 | 2016-08-01 | 2016-08-22 |  |  | 2016-08-08 | 14
44 | 2016-04-25 | 2016-06-06 |  |  | 2016-05-27 | 10
45 | 2016-05-16 | 2016-07-12 |  |  | 2016-06-01 | 41
46 | 2016-09-20 | 2017-02-13 |  |  | 2017-02-13 | 0
47 | 2016-04-25 | 2016-06-27 |  |  | 2016-05-20 | 38
48 | 2016-05-02 | 2016-07-18 |  |  | 2016-05-12 | 67
49 | 2016-04-19 | 2016-07-08 |  |  | 2016-05-23 | 46
50 | 2016-05-18 | 2016-07-22 |  |  | 2016-05-23 | 60
51 | 2016-09-20 | 2017-02-13 |  |  | 2017-02-13 | 0
52 | 2017-01-17 | 2017-06-06 |  |  | 2017-06-06 | 0
53 | 2016-12-21 | 2017-05-22 |  |  | 2017-05-22 | 0
54 | 2017-03-06 | 2017-06-13 |  |  | 2017-06-13 | 0
55 | 2016-03-29 | 2016-06-17 |  |  | 2016-03-29 | 80
56 | 2016-10-19 | 2017-04-03 |  |  | 2017-04-03 | 0
57 | 2016-09-20 | 2017-03-21 |  |  | 2017-03-21 | 0
58 | 2016-09-20 | 2017-03-21 |  |  | 2017-03-21 | 0
59 | 2017-01-17 | 2017-05-22 |  |  | 2017-05-22 | 0
60 | 2016-05-23 | 2016-07-18 |  |  | 2016-06-14 | 34
61 | 2016-09-20 | 2017-03-06 |  |  | 2017-03-06 | 0
62 | 2016-05-23 | 2016-07-22 |  |  | 2016-05-23 | 60
63 | 2016-12-20 | 2017-05-18 |  |  | 2017-05-18 | 0
64 | 2016-12-20 | 2017-06-19 |  |  | 2017-06-19 | 0
65 | 2017-01-03 | 2017-03-21 |  |  | 2017-03-21 | 0
66 | 2016-09-20 | 2017-03-21 |  |  | 2017-03-21 | 0
67 | 2017-01-17 | 2017-06-16 |  |  | 2017-06-16 | 0
68 | 2016-08-01 | 2016-08-12 |  |  | 2016-08-12 | 0
69 | 2016-08-01 | 2016-07-18 |  |  | 2016-08-01 | -14
70 | 2016-08-01 | 2016-08-12 |  |  | 2016-08-12 | 0
71 | 2016-04-19 | 2016-07-08 |  |  | 2016-05-23 | 46
72 | 2017-01-17 | 2017-05-22 |  |  | 2017-05-22 | 0
73 | 2016-08-01 | 2016-08-10 |  |  | 2016-08-08 | 2
74 | 2016-11-30 | 2017-03-16 |  |  | 2017-03-16 | 0
75 | 2017-03-06 | 2017-06-12 |  |  | 2017-06-12 | 0
76 | 2017-01-17 | 2017-05-26 |  |  | 2017-05-26 | 0
77 | 2017-01-17 | 2017-06-01 |  |  | 2017-06-01 | 0
78 | 2016-05-16 | 2016-07-22 |  |  | 2016-06-21 | 31
79 | 2017-01-31 | 2017-05-30 |  |  | 2017-05-30 | 0
80 | 2016-09-20 | 2017-03-21 |  |  | 2017-03-21 | 0
81 | 2016-05-30 | 2016-07-22 |  |  | 2016-05-31 | 52
82 | 2017-01-17 | 2017-04-10 |  |  | 2017-04-10 | 0
83 | 2016-05-30 | 2016-07-22 |  |  | 2016-05-31 | 52
84 | 2016-03-23 | 2016-06-27 |  |  | 2016-03-23 | 96
85 | 2016-05-02 | 2016-07-05 |  |  | 2016-05-16 | 50
86 | 2017-03-06 | 2017-06-15 |  |  | 2017-06-15 | 0
87 | 2016-12-21 | 2017-05-23 |  |  | 2017-05-23 | 0
88 | 2017-02-01 | 2017-05-25 |  |  | 2017-05-25 | 0
89 | 2016-04-05 | 2016-06-13 |  |  | 2016-04-06 | 68
90 | 2015-06-18 | 2015-07-16 |  |  | 2015-06-11 | 35
91 | 2016-06-30 | 2016-06-17 |  |  | 2016-06-30 | -13
92 | 2015-05-14 | 06-01-15 A |  |  | 2015-05-28 | #VALUE!
93 | 2016-08-01 | 2016-09-13 |  |  | 2016-09-13 | 0
94 | 2015-06-24 | 2015-10-05 |  |  | 2015-06-18 | 109
95 | 2015-07-01 | 2015-07-22 |  |  | 2015-07-08 | 14
96 | 2015-07-24 | 2015-08-05 |  |  | 2015-07-31 | 5
97 | 2015-07-24 | 2016-03-16 |  |  | 2015-07-31 | 229
98 | 2015-07-08 | 2016-04-18 |  |  | 2015-07-27 | 266
99 | 2017-02-06 | 2017-08-01 |  |  | 2017-08-01 | 0
100 | 2016-08-01 | 2016-08-08 |  |  | 2016-08-08 | 0
101 | 2016-07-04 | 2016-08-11 |  |  | 2016-08-08 | 3
102 | 2015-08-11 | 2015-09-18 |  |  | 2015-08-27 | 22
103 | 2015-07-03 | 2015-07-16 |  |  | 2015-07-10 | 6
104 | 2015-06-12 | 2015-07-22 |  |  | 2015-06-19 | 33
106 | 2016-12-06 | 2017-02-21 |  |  | 2017-02-21 | 0
107 | 2015-06-23 | 2015-07-20 |  |  | 2015-06-30 | 20
108 | 2016-07-04 | 2016-07-21 |  |  | 2016-07-12 | 9
109 | 2016-03-31 | 2016-05-31 |  |  | 2016-05-31 | 0
110 | 2016-11-30 | 2017-06-01 |  |  | 2017-06-01 | 0
111 | 2016-05-30 | 2016-07-08 |  |  | 2016-06-01 | 37
112 | 2015-07-20 | 2015-08-31 |  |  | 2015-07-27 | 35
113 | 2017-01-05 | 2017-06-27 |  |  | 2017-06-27 | 0
114 | 2015-05-29 | 2015-07-22 |  |  | 2015-05-26 | 57
115 | 2017-02-06 | 2017-08-01 |  |  | 2017-08-01 | 0
116 | 2016-02-25 | 2016-05-12 |  |  | 2016-03-21 | 52
117 | 2017-02-06 | 2017-08-01 |  |  | 2017-08-01 | 0
118 | 2015-06-23 | 2015-07-16 |  |  | 2015-06-30 | 16
119 | 2017-03-06 | 2017-07-24 |  |  | 2017-07-24 | 0
120 | 2016-07-04 | 2016-08-11 |  |  | 2016-08-08 | 3
121 | 2017-02-06 | 2017-08-01 |  |  | 2017-08-01 | 0
122 | 2016-05-02 | 2016-06-14 |  |  | 2016-06-14 | 0
123 | 2016-11-02 | 2017-05-25 |  |  | 2017-05-25 | 0
124 | 2016-07-04 | 2016-08-11 |  |  | 2016-08-08 | 3
125 | 2016-10-31 | 2016-12-12 |  |  | 2016-12-12 | 0
126 | 2015-07-07 | 2015-08-03 |  |  | 2015-07-28 | 6
127 | 2016-10-31 | 2016-11-28 |  |  | 2016-11-28 | 0
128 | 2016-05-02 | 2016-06-27 |  |  | 2016-05-23 | 35
129 | 2015-05-20 | 2015-07-13 |  |  | 2015-06-01 | 42
130 | 2016-08-01 | 2016-08-11 |  |  | 2016-08-08 | 3
131 | 2015-09-23 | 2015-08-06 |  |  | 2016-03-14 | -221
132 | 2015-08-05 | 2015-09-25 |  |  | 2015-08-13 | 43
133 | 2015-08-05 | 2015-07-30 |  |  | 2015-08-13 | -14
134 | 2016-07-04 | 2016-08-03 |  |  | 2016-08-03 | 0
135 | 2016-05-31 | 2016-07-11 |  |  | 2016-06-27 | 14
136 | 2016-06-02 | 2016-07-11 |  |  | 2016-06-02 | 39
137 | 2015-07-29 | 2015-08-10 |  |  | 2015-08-06 | 4
138 | 2015-07-23 | 2016-06-20 |  |  | 2015-07-30 | 326
139 | 2016-02-25 | 2016-05-27 |  |  | 2016-03-14 | 74
140 | 2016-03-31 | 2016-06-17 |  |  | 2016-03-31 | 78
141 | 2016-03-31 | 2016-06-24 |  |  | 2016-03-31 | 85
142 | 2015-05-13 | 06-29-15 A |  |  | 2015-06-09 | #VALUE!
143 | 2016-02-25 | 2016-05-26 |  |  | 2016-02-25 | 91
144 | 2016-05-02 | 2016-06-17 |  |  | 2016-05-23 | 25
145 | 2016-05-31 | 2016-03-25 |  |  | 2016-05-31 | -67
146 | 2015-06-23 | 2015-08-07 |  |  | 2015-07-02 | 36
147 | 2016-03-02 | 2016-05-02 |  |  | 2016-04-11 | 21
148 | 2016-11-02 | 2017-05-30 |  |  | 2017-05-30 | 0
149 | 2016-03-11 | 2016-05-20 |  |  | 2016-05-20 | 0
150 | 2016-10-31 | 2017-05-30 |  |  | 2017-05-30 | 0
151 | 2015-06-09 | 2015-07-08 |  |  | 2015-06-02 | 36
152 | 2016-03-11 | 2016-05-20 |  |  | 2016-05-20 | 0
153 | 2015-06-09 | 2015-07-20 |  |  | 2015-06-02 | 48
154 | 2016-11-30 | 2017-05-30 |  |  | 2017-05-30 | 0
155 | 2016-08-01 | 2016-08-08 |  |  | 2016-08-08 | 0
156 | 2016-03-11 | 2016-05-20 |  |  | 2016-05-20 | 0
157 | 2016-08-01 | 2016-08-25 |  |  | 2016-08-15 | 10
158 | 2015-06-17 | 2015-08-17 |  |  | 2015-06-24 | 54
159 | 2015-07-14 | 2015-08-13 |  |  | 2015-08-06 | 7
160 | 2016-07-04 | 2016-08-01 |  |  | 2016-08-01 | 0
161 | 2015-07-14 | 2015-08-13 |  |  | 2015-08-06 | 7
162 | 2015-05-14 | 2015-07-01 |  |  | 2015-05-18 | 44
163 | 2016-06-02 | 2016-07-05 |  |  | 2016-06-02 | 33
164 | 2016-08-01 | 2016-08-18 |  |  | 2016-08-12 | 6
165 | 2016-08-01 | 2016-08-15 |  |  | 2016-08-15 | 0
166 | 2015-07-10 | 2015-08-06 |  |  | 2015-08-06 | 0
167 | 2015-07-23 | 2015-08-03 |  |  | 2015-07-30 | 4
168 | 2016-07-04 | 2016-08-01 |  |  | 2016-08-01 | 0
169 | 2016-04-20 | 2016-06-20 |  |  | 2016-04-20 | 61
170 | 2016-02-29 | 2016-08-22 |  |  | 2016-03-14 | 161
171 | 2016-08-01 | 2016-08-15 |  |  | 2016-08-15 | 0
172 | 2016-04-04 | 2016-06-01 |  |  | 2016-05-24 | 8
173 | 2015-06-15 | 2016-03-07 |  |  | 2015-06-15 | 266
174 | 2016-10-03 | 2017-06-05 |  |  | 2017-06-05 | 0
175 | 2016-08-15 | 2016-11-01 |  |  | 2016-11-01 | 0
176 | 2016-09-01 | 2017-03-09 |  |  | 2017-03-09 | 0
177 | 2017-01-05 | 2017-05-22 |  |  | 2017-05-22 | 0
178 | 2016-03-29 | 2016-06-17 |  |  | 2016-03-29 | 80
179 | 2016-02-26 | 2016-05-26 |  |  | 2016-03-18 | 69
180 | 2015-08-07 | 2016-03-08 |  |  | 2016-03-08 | 0
181 | 2015-07-07 | 2015-07-23 |  |  | 2015-08-17 | -25
182 | 2015-05-13 | 2015-08-03 |  |  | 2015-05-06 | 89
183 | 2015-06-09 | 2015-07-16 |  |  | 2015-06-02 | 44
184 | 2015-06-02 | 2015-07-24 |  |  | 2015-06-02 | 52
185 | 2015-07-21 | 2015-08-26 |  |  | 2015-07-28 | 29
186 | 2015-06-09 | 2015-07-20 |  |  | 2015-06-02 | 48
187 | 2015-06-23 | 2015-07-24 |  |  | 2015-06-16 | 38
188 | 2015-07-22 | 2016-03-08 |  |  | 2016-03-08 | 0
189 | 2015-09-15 | 2016-06-08 |  |  | 2016-06-08 | 0
190 | 2015-07-15 | 2015-12-09 |  |  | 2015-12-15 | -6
191 | 2015-07-21 | 2015-10-07 |  |  | 2015-07-28 | 71
192 | 2015-07-28 | 2015-08-07 |  |  | 2015-08-04 | 3
194 | 2015-06-30 | 2015-07-21 |  |  | 2015-06-24 | 27
195 | 2015-08-03 | 2016-04-28 |  |  | 2015-08-27 | 245
196 | 2015-08-03 | 2016-03-08 |  |  | 2016-03-08 | 0
197 | 2016-03-18 | 2016-06-06 |  |  | 2016-03-18 | 80
198 | 2016-11-21 | 2017-03-06 |  |  | 2017-03-06 | 0
201 | 2016-05-02 | 2016-06-17 |  |  | 2016-05-24 | 24
202 | 2016-05-03 | 2016-06-27 |  |  | 2016-06-21 | 6
203 | 2016-11-02 | 2017-05-11 |  |  | 2017-05-11 | 0
204 | 2015-05-29 | 2015-07-14 |  |  | 2015-05-22 | 53
205 | 2015-08-05 | 2015-09-15 |  |  | 2015-08-06 | 40
206 | 2015-08-11 | 2015-09-14 |  |  | 2015-09-01 | 13
207 | 2015-08-10 | 2016-02-17 |  |  | 2016-02-17 | 0
208 | 2015-06-24 | 2015-07-20 |  |  | 2015-06-18 | 32
209 | 2015-07-01 | 2015-08-24 |  |  | 2015-07-08 | 47
210 | 2015-05-14 | 2015-07-20 |  |  | 2015-05-26 | 55
211 | 2017-01-31 | 2017-04-03 |  |  | 2017-04-03 | 0
212 | 2016-10-03 | 2017-03-06 |  |  | 2017-03-06 | 0
213 | 2016-08-01 | 2016-08-31 |  |  | 2016-08-31 | 0
214 | 2016-06-30 | 2016-08-04 |  |  | 2016-08-04 | 0
215 | 2016-09-01 | 2017-03-24 |  |  | 2017-03-24 | 0
216 | 2016-09-01 | 2017-03-08 |  |  | 2017-03-08 | 0
217 | 2016-08-31 | 2017-03-24 |  |  | 2017-03-24 | 0
218 | 2016-08-01 | 2016-08-31 |  |  | 2016-08-31 | 0
219 | 2016-04-14 | 2016-07-05 |  |  | 2016-05-03 | 63
220 | 2017-01-02 | 2017-04-03 |  |  | 2017-04-03 | 0
221 | 2016-05-30 | 2016-08-15 |  |  | 2016-05-31 | 76
222 | 2016-05-18 | 2016-07-11 |  |  | 2016-05-23 | 49
223 | 2016-08-31 | 2017-03-21 |  |  | 2017-03-21 | 0
224 | 2016-04-19 | 2016-06-17 |  |  | 2016-05-23 | 25
225 | 2016-04-19 | 2016-06-16 |  |  | 2016-05-27 | 20
226 | 2017-02-13 | 2017-08-01 |  |  | 2017-08-01 | 0
227 | 2016-04-19 | 2016-06-17 |  |  | 2016-05-27 | 21
228 | 2017-01-16 | 2017-06-05 |  |  | 2017-06-05 | 0
229 | 2016-06-02 | 2016-06-22 |  |  | 2016-06-06 | 16
230 | 2016-10-05 | 2017-03-06 |  |  | 2017-03-06 | 0
231 | 2016-02-29 | 2016-05-25 |  |  | 2016-04-12 | 43
232 | 2016-12-19 | 2017-05-30 |  |  | 2017-05-30 | 0
233 | 2017-01-05 | 2017-06-01 |  |  | 2017-06-01 | 0
234 | 2016-12-05 | 2017-05-26 |  |  | 2017-05-26 | 0
235 | 2016-12-16 | 2017-05-30 |  |  | 2017-05-30 | 0
236 | 2016-08-31 | 2017-03-13 |  |  | 2017-03-13 | 0
237 | 2016-12-16 | 2017-03-21 |  |  | 2017-03-21 | 0
238 | 2016-10-27 | 2017-08-21 |  |  | 2017-08-21 | 0
239 | 2016-09-01 | 2017-02-10 |  |  | 2017-02-10 | 0
240 | 2016-11-01 | 2017-05-11 |  |  | 2017-05-11 | 0
241 | 2017-01-17 | 2017-05-31 |  |  | 2017-05-31 | 0
242 | 2017-01-04 | 2017-05-30 |  |  | 2017-05-30 | 0
243 | 2016-11-30 | 2017-05-30 |  |  | 2017-05-30 | 0
244 | 2017-03-16 | 2017-08-14 |  |  | 2017-08-14 | 0
245 | 2016-08-01 | 2016-08-18 |  |  | 2016-08-15 | 3
246 | 2016-06-02 | 2016-08-01 |  |  | 2016-08-01 | 0
247 | 2016-06-01 | 2016-07-05 |  |  | 2016-06-01 | 34
248 | 2016-12-20 | 2017-08-07 |  |  | 2017-08-07 | 0
249 | 2016-03-16 | 2016-05-17 |  |  | 2016-05-13 | 4
250 | 2016-11-02 | 2017-05-11 |  |  | 2017-05-11 | 0
251 | 2017-01-05 | 2017-06-08 |  |  | 2017-06-08 | 0
252 | 2016-06-02 | 2016-07-11 |  |  | 2016-06-02 | 39
253 | 2016-04-11 | 2016-06-07 |  |  | 2016-05-20 | 18
254 | 2016-08-31 | 2017-03-21 |  |  | 2017-03-21 | 0
255 | 2016-05-02 | 2016-06-17 |  |  | 2016-05-23 | 25
256 | 2016-11-02 | 2017-05-30 |  |  | 2017-05-30 | 0
257 | 2016-07-04 | 2016-08-18 |  |  | 2016-08-01 | 17
258 | 2016-11-01 | 2017-05-11 |  |  | 2017-05-11 | 0
259 | 2016-09-01 | 2017-03-08 |  |  | 2017-03-08 | 0
260 | 2017-01-17 | 2017-05-31 |  |  | 2017-05-31 | 0
261 | 2016-04-25 | 2016-06-22 |  |  | 2016-05-20 | 33
262 | 2016-10-03 | 2017-04-03 |  |  | 2017-04-03 | 0
263 | 2017-01-05 | 2017-05-30 |  |  | 2017-05-30 | 0
264 | 2016-06-02 | 2016-07-11 |  |  | 2016-06-02 | 39
265 | 2016-07-04 | 2016-08-03 |  |  | 2016-08-03 | 0
266 | 2017-03-06 | 2017-07-10 |  |  | 2017-07-10 | 0
267 | 2017-03-30 | 2017-08-31 |  |  | 2017-08-31 | 0
268 | 2016-07-04 | 2016-08-03 |  |  | 2016-08-03 | 0
269 | 2017-02-06 | 2017-08-01 |  |  | 2017-08-01 | 0
270 | 2017-02-06 | 2017-08-01 |  |  | 2017-08-01 | 0
271 | 2016-06-30 | 2016-08-03 |  |  | 2016-08-03 | 0
272 | 2016-02-25 | 2016-05-17 |  |  | 2016-04-12 | 35
273 | 2017-01-17 | 2017-06-12 |  |  | 2017-06-12 | 0
274 | 2016-07-04 | 2016-08-03 |  |  | 2016-08-03 | 0
275 | 2017-02-16 | 2017-07-31 |  |  | 2017-07-31 | 0
276 | 2017-02-06 | 2017-08-01 |  |  | 2017-08-01 | 0
277 | 2016-12-05 | 2017-06-01 |  |  | 2017-06-01 | 0
278 | 2016-02-25 | 2016-05-12 |  |  | 2016-04-12 | 30
279 | 2016-06-30 | 2016-10-19 |  |  | 2016-08-03 | 77
280 | 2016-02-29 | 2016-08-05 |  |  | 2016-04-12 | 115
281 | 2017-01-17 | 2017-06-26 |  |  | 2017-06-26 | 0
282 | 2016-07-04 | 2016-08-03 |  |  | 2016-08-03 | 0
283 | 2017-01-17 | 2017-06-08 |  |  | 2017-06-08 | 0
284 | 2016-10-03 | 2017-04-03 |  |  | 2017-04-03 | 0
285 | 2016-10-03 | 2017-04-14 |  |  | 2017-04-14 | 0
286 | 2016-10-31 | 2017-05-26 |  |  | 2017-05-26 | 0
287 | 2016-10-31 | 2017-05-26 |  |  | 2017-05-26 | 0
288 | 2016-12-16 | 2017-05-25 |  |  | 2017-05-25 | 0
289 | 2016-11-02 | 2017-05-30 |  |  | 2017-05-30 | 0
290 | 2016-04-04 | 2016-05-31 |  |  | 2016-05-31 | 0
291 | 2016-07-04 | 2016-08-03 |  |  | 2016-08-03 | 0
292 | 2017-03-22 | 2017-07-24 |  |  | 2017-07-24 | 0
293 | 2016-07-04 | 2016-08-03 |  |  | 2016-08-03 | 0
294 | 2017-01-05 | 2017-05-30 |  |  | 2017-05-30 | 0
295 | 2016-12-16 | 2017-03-20 |  |  | 2017-03-20 | 0
296 | 2016-02-25 | 2016-08-05 |  |  | 2016-04-12 | 115
297 | 2017-01-05 | 2017-06-08 |  |  | 2017-06-08 | 0
298 | 2016-12-15 | 2017-05-25 |  |  | 2017-05-25 | 0
299 | 2017-02-16 | 2017-07-24 |  |  | 2017-07-24 | 0
300 | 2016-04-04 | 2016-05-31 |  |  | 2016-05-31 | 0
301 | 2016-06-02 | 2016-08-01 |  |  | 2016-06-02 | 60
302 | 2016-06-29 | 2016-08-01 |  |  | 2016-06-29 | 33
303 | 2017-03-06 | 2017-08-04 |  |  | 2017-08-04 | 0
304 | 2016-06-01 | 2016-06-17 |  |  | 2016-06-01 | 16
305 | 2017-02-06 | 2017-07-28 |  |  | 2017-07-28 | 0
306 | 2016-05-30 | 2016-07-22 |  |  | 2016-05-31 | 52
307 | 2016-07-04 | 2016-08-03 |  |  | 2016-08-03 | 0
308 | 2016-05-30 | 2016-07-18 |  |  | 2016-06-06 | 42
309 | 2017-02-06 | 2017-07-28 |  |  | 2017-07-28 | 0
310 | 2016-05-02 | 2016-05-23 |  |  | 2016-05-16 | 7
311 | 2016-03-14 | 2016-06-17 |  |  | 2016-03-21 | 88
312 | 2016-02-24 | 2016-03-25 |  |  | 2016-03-25 | 0
313 | 2016-02-25 | 2016-04-15 |  |  | 2016-03-25 | 21
314 | 2016-02-25 | 2016-05-23 |  |  | 2016-05-23 | 0
315 | 2016-10-31 | 2017-05-30 |  |  | 2017-05-30 | 0
316 | 2016-05-03 | 2016-07-05 |  |  | 2016-05-03 | 63
317 | 2016-03-02 | 2016-05-31 |  |  | 2016-05-31 | 0
318 | 2016-10-31 | 2017-05-30 |  |  | 2017-05-30 | 0
319 | 2017-01-05 | 2017-07-11 |  |  | 2017-07-11 | 0
320 | 2016-06-30 | 2016-06-28 |  |  | 2016-06-30 | -2
321 | 2016-10-11 | 2017-03-20 |  |  | 2017-03-20 | 0
322 | 2017-01-05 | 2017-07-13 |  |  | 2017-07-13 | 0
323 | 2016-05-02 | 2016-06-17 |  |  | 2016-06-14 | 3
324 | 2016-05-02 | 2016-06-17 |  |  | 2016-05-31 | 17
325 | 2016-02-25 | 2016-05-23 |  |  | 2016-05-23 | 0
326 | 2016-05-31 | 2016-07-08 |  |  | 2016-05-31 | 38
327 | 2016-11-02 | 2017-05-11 |  |  | 2017-05-11 | 0
328 | 2016-08-02 | 2016-08-22 |  |  | 2016-08-02 | 20
329 | 2016-01-25 | 2016-03-25 |  |  | 2016-03-25 | 0
330 | 2016-01-25 | 2016-03-25 |  |  | 2016-03-25 | 0
331 | 2016-02-25 | 2016-05-23 |  |  | 2016-05-23 | 0
332 | 2016-10-18 | 2017-04-05 |  |  | 2017-04-05 | 0
333 | 2016-08-01 | 2016-08-11 |  |  | 2016-08-08 | 3
334 | 2016-06-02 | 2016-07-08 |  |  | 2016-06-08 | 30
335 | 2016-08-01 | 2017-03-21 |  |  | 2017-03-21 | 0
336 | 2016-02-25 | 2016-04-25 |  |  | 2016-03-25 | 31
337 | 2016-08-01 | 2017-03-21 |  |  | 2017-03-21 | 0
338 | 2016-03-07 | 2016-06-08 |  |  | 2016-05-23 | 16
339 | 2016-03-07 | 2016-05-19 |  |  | 2016-03-25 | 55
340 | 2016-11-30 | 2017-05-31 |  |  | 2017-05-31 | 0
341 | 2016-06-01 | 2016-06-20 |  |  | 2016-06-01 | 19
342 | 2016-11-02 | 2017-05-11 |  |  | 2017-05-11 | 0
343 | 2016-11-02 | 2017-05-11 |  |  | 2017-05-11 | 0
344 | 2016-05-02 | 2016-06-17 |  |  | 2016-05-12 | 36
345 | 2016-05-02 | 2016-06-17 |  |  | 2016-05-12 | 36
346 | 2016-08-01 | 2017-03-21 |  |  | 2017-03-21 | 0
347 | 2016-03-10 | 2016-07-06 |  |  | 2016-05-23 | 44
348 | 2016-02-25 | 2016-05-23 |  |  | 2016-05-23 | 0
349 | 2016-02-24 | 2016-05-16 |  |  | 2016-04-14 | 32
350 | 2016-11-21 | 2017-05-22 |  |  | 2017-05-22 | 0
351 | 2016-10-31 | 2017-05-30 |  |  | 2017-05-30 | 0
352 | 2016-12-01 | 2017-06-05 |  |  | 2017-06-05 | 0
353 | 2017-02-06 | 2017-08-01 |  |  | 2017-08-01 | 0
354 | 2016-08-01 | 2016-04-14 |  |  | 2016-08-01 | -109
355 | 2016-05-31 | 2016-07-18 |  |  | 2016-05-31 | 48
356 | 2017-02-06 | 2017-08-01 |  |  | 2017-08-01 | 0
357 | 2017-03-06 | 2017-08-01 |  |  | 2017-08-01 | 0
358 | 2016-03-29 | 2016-06-20 |  |  | 2016-03-29 | 83
359 | 2015-05-21 | 2015-07-16 |  |  | 2015-05-21 | 56
360 | 2015-06-17 | 2015-07-22 |  |  | 2015-06-24 | 28
361 | 2016-11-21 | 2017-05-01 |  |  | 2017-05-01 | 0
362 | 2016-09-05 | 2017-02-24 |  |  | 2017-02-24 | 0
363 | 2016-12-06 | 2017-05-30 |  |  | 2017-05-30 | 0
364 | 2016-03-07 | 2016-05-20 |  |  | 2016-05-20 | 0
365 | 2016-03-07 | 2016-05-31 |  |  | 2016-05-20 | 11
366 | 2015-06-02 | 2015-07-20 |  |  | 2015-05-26 | 55
367 | 2015-05-14 | 2015-07-16 |  |  | 2015-05-28 | 49
368 | 2016-08-31 | 2017-03-01 |  |  | 2017-03-01 | 0
369 | 2015-06-24 | 2015-07-20 |  |  | 2015-06-18 | 32
370 | 2017-01-05 | 2017-05-30 |  |  | 2017-05-30 | 0
371 | 2015-07-01 | 2015-08-03 |  |  | 2015-07-13 | 21
372 | 2017-01-03 | 2017-06-01 |  |  | 2017-06-01 | 0
373 | 2015-05-14 | 06-22-15 A |  |  | 2015-06-03 | #VALUE!
374 | 2016-06-02 | 2016-08-05 |  |  | 2016-08-08 | -3
375 | 2016-07-01 | 2016-07-08 |  |  | 2016-07-01 | 7
376 | 2015-05-14 | 06-24-15 A |  |  | 2015-06-01 | #VALUE!
377 | 2016-12-20 | 2017-03-06 |  |  | 2017-03-06 | 0
378 | 2016-02-25 | 2016-05-19 |  |  | 2016-05-12 | 7
379 | 2016-10-05 | 2017-04-11 |  |  | 2017-04-11 | 0
380 | 2016-03-29 | 2016-06-08 |  |  | 2016-03-29 | 71
381 | 2016-03-29 | 2016-06-16 |  |  | 2016-03-29 | 79
382 | 2016-03-29 | 2016-06-17 |  |  | 2016-03-29 | 80
383 | 2016-10-03 | 2017-05-11 |  |  | 2017-05-11 | 0
384 | 2017-02-06 | 2017-07-24 |  |  | 2017-07-24 | 0
385 | 2017-01-05 | 2017-05-26 |  |  | 2017-05-26 | 0
386 | 2016-12-12 | 2017-05-22 |  |  | 2017-05-22 | 0
387 | 2016-03-29 | 2016-06-17 |  |  | 2016-03-29 | 80
388 | 2016-03-07 | 2016-05-26 |  |  | 2016-05-20 | 6
389 | 2017-03-06 | 2017-07-24 |  |  | 2017-07-24 | 0
390 | 2016-11-02 | 2017-05-11 |  |  | 2017-05-11 | 0
391 | 2016-04-04 | 2016-06-17 |  |  | 2016-05-31 | 17
392 | 2017-01-05 | 2017-05-30 |  |  | 2017-05-30 | 0
393 | 2017-03-06 | 2017-07-24 |  |  | 2017-07-24 | 0
394 | 2016-12-06 | 2017-05-26 |  |  | 2017-05-26 | 0
395 | 2017-01-05 | 2017-05-26 |  |  | 2017-05-26 | 0
396 | 2016-06-16 | 2016-07-11 |  |  | 2016-07-11 | 0
397 | 2016-03-30 | 2016-05-20 |  |  | 2016-05-20 | 0
398 | 2016-05-16 | 2016-06-24 |  |  | 2016-05-16 | 39
399 | 2016-08-01 | 2017-02-13 |  |  | 2017-02-13 | 0
402 | 2016-01-25 | 2016-06-17 |  |  | 2016-03-23 | 86
403 | 2016-01-25 | 2016-05-19 |  |  | 2016-03-23 | 57
404 | 2016-10-05 | 2017-02-24 |  |  | 2017-02-24 | 0
405 | 2015-07-03 | 2015-07-22 |  |  | 2015-07-21 | 1
406 | 2016-02-25 | 2016-04-04 |  |  | 2016-03-23 | 12
407 | 2016-09-05 | 2017-02-16 |  |  | 2017-02-16 | 0
408 | 2016-12-01 | 2017-05-22 |  |  | 2017-05-22 | 0
409 | 2016-10-17 | 2017-04-03 |  |  | 2017-04-03 | 0
410 | 2016-05-16 | 2016-07-07 |  |  | 2016-06-14 | 23
411 | 2016-06-01 | 2016-07-11 |  |  | 2016-06-01 | 40
412 | 2015-07-01 | 2016-05-23 |  |  | 2015-07-08 | 320
413 | 2016-07-04 | 2016-09-02 |  |  | 2016-09-02 | 0
414 | 2015-06-18 | 2016-05-26 |  |  | 2015-06-11 | 350
415 | 2015-07-24 | 2015-07-16 |  |  | 2015-07-31 | -15
416 | 2015-07-21 | 2015-08-05 |  |  | 2016-03-14 | -222
417 | 2016-12-01 | 2017-05-22 |  |  | 2017-05-22 | 0
418 | 2015-07-30 | 2016-04-04 |  |  | 2015-08-07 | 241
419 | 2015-07-24 | 2015-08-03 |  |  | 2015-07-31 | 3
420 | 2015-08-04 | 2015-08-06 |  |  | 2015-08-11 | -5
421 | 2016-02-25 | 2016-04-04 |  |  | 2016-03-23 | 12
422 | 2015-05-14 | 2016-05-23 |  |  | 2015-06-03 | 355
423 | 2016-05-31 | 2016-06-17 |  |  | 2016-05-31 | 17
424 | 2016-01-25 | 2016-04-22 |  |  | 2016-03-23 | 30
425 | 2016-02-25 | 2016-04-20 |  |  | 2016-04-20 | 0
426 | 2016-05-31 | 2016-06-17 |  |  | 2016-05-31 | 17
427 | 2016-02-25 | 2016-04-20 |  |  | 2016-04-20 | 0
428 | 2016-12-01 | 2017-05-22 |  |  | 2017-05-22 | 0
429 | 2016-03-10 | 2017-02-16 |  |  | 2016-03-10 | 343
430 | 2016-05-31 | 2016-05-31 |  |  | 2016-05-31 | 0
431 | 2015-06-11 | 2015-09-01 |  |  | 2015-06-04 | 89
432 | 2016-02-25 | 2016-05-19 |  |  | 2016-04-20 | 29
433 | 2015-07-29 | 2016-02-17 |  |  | 2016-02-17 | 0
434 | 2016-02-25 | 2016-06-17 |  |  | 2016-04-20 | 58
435 | 2017-01-03 | 2017-07-28 |  |  | 2017-07-28 | 0
436 | 2015-07-14 | 2015-08-07 |  |  | 2015-07-21 | 17
437 | 2016-03-14 | 2016-06-16 |  |  | 2016-05-20 | 27
438 | 2015-07-29 | 2015-09-21 |  |  | 2015-08-07 | 45
439 | 2016-02-25 | 2016-06-17 |  |  | 2016-04-20 | 58
440 | 2016-06-30 | 2016-07-11 |  |  | 2016-06-30 | 11
441 | 2016-05-16 | 2016-06-22 |  |  | 2016-06-14 | 8
442 | 2016-02-25 | 2016-04-06 |  |  | 2016-03-07 | 30
443 | 2016-07-13 | 2016-06-17 |  |  | 2016-07-13 | -26
444 | 2016-02-25 | 2016-05-23 |  |  | 2016-04-20 | 33
445 | 2016-12-01 | 2017-05-22 |  |  | 2017-05-22 | 0
446 | 2015-07-10 | 2015-08-07 |  |  | 2015-08-07 | 0
447 | 2016-05-17 | 2016-07-14 |  |  | 2016-05-17 | 58
448 | 2016-10-03 | 2017-02-21 |  |  | 2017-02-21 | 0
449 | 2016-06-30 | 2016-07-08 |  |  | 2016-06-30 | 8
450 | 2016-02-25 | 2016-05-19 |  |  | 2016-04-20 | 29
451 | 2017-01-31 | 2017-06-06 |  |  | 2017-06-06 | 0
452 | 2016-12-01 | 2017-05-22 |  |  | 2017-05-22 | 0
453 | 2016-02-25 | 2016-05-25 |  |  | 2016-04-20 | 35
454 | 2016-11-02 | 2017-05-11 |  |  | 2017-05-11 | 0
455 | 2016-10-24 | 2017-04-24 |  |  | 2017-04-24 | 0
456 | 2016-10-17 | 2017-04-24 |  |  | 2017-04-24 | 0
457 | 2016-03-07 | 2016-05-20 |  |  | 2016-05-20 | 0
458 | 2016-02-25 | 2016-05-19 |  |  | 2016-02-25 | 84
459 | 2016-04-04 | 2016-06-08 |  |  | 2016-05-23 | 16
460 | 2016-04-04 | 2016-05-31 |  |  | 2016-05-31 | 0
461 | 2017-02-02 | 2017-05-30 |  |  | 2017-05-30 | 0
462 | 2017-02-06 | 2017-03-06 |  |  | 2017-03-06 | 0
463 | 2016-07-04 | 2016-08-15 |  |  | 2016-08-08 | 7
464 | 2016-10-17 | 2017-04-24 |  |  | 2017-04-24 | 0
465 | 2017-01-05 | 2017-05-26 |  |  | 2017-05-26 | 0
466 | 2016-05-02 | 2016-07-05 |  |  | 2016-05-23 | 43
467 | 2016-10-17 | 2017-04-24 |  |  | 2017-04-24 | 0
468 | 2016-11-21 | 2017-04-03 |  |  | 2017-04-03 | 0
469 | 2016-10-17 | 2017-04-24 |  |  | 2017-04-24 | 0
470 | 2017-01-05 | 2017-05-22 |  |  | 2017-05-22 | 0
471 | 2016-03-30 | 2016-06-08 |  |  | 2016-05-16 | 23
472 | 2016-11-21 | 2017-03-01 |  |  | 2017-03-01 | 0
473 | 2017-01-05 | 2017-07-24 |  |  | 2017-07-24 | 0
474 | 2016-06-30 | 2016-07-08 |  |  | 2016-06-30 | 8
475 | 2016-11-02 | 2017-05-11 |  |  | 2017-05-11 | 0
476 | 2016-06-02 | 2016-08-03 |  |  | 2016-08-03 | 0
477 | 2016-07-04 | 2016-08-15 |  |  | 2016-08-08 | 7
478 | 2016-10-17 | 2017-04-24 |  |  | 2017-04-24 | 0
479 | 2016-10-04 | 2017-05-11 |  |  | 2017-05-11 | 0
480 | 2016-10-17 | 2017-03-20 |  |  | 2017-03-20 | 0
481 | 2016-10-17 | 2017-04-24 |  |  | 2017-04-24 | 0
482 | 2016-02-25 | 2016-05-20 |  |  | 2016-02-25 | 85
483 | 2016-04-04 | 2016-05-19 |  |  | 2016-04-04 | 45
484 | 2016-12-20 | 2017-05-23 |  |  | 2017-05-23 | 0
485 | 2017-01-17 | 2017-06-05 |  |  | 2017-06-05 | 0
486 | 2016-10-17 | 2017-04-10 |  |  | 2017-04-10 | 0
487 | 2017-01-03 | 2017-06-09 |  |  | 2017-06-09 | 0
488 | 2016-06-02 | 2016-08-05 |  |  | 2016-08-08 | -3
489 | 2016-06-02 | 2016-07-08 |  |  | 2016-06-02 | 36
490 | 2017-02-02 | 2017-06-12 |  |  | 2017-06-12 | 0
491 | 2016-09-05 | 2017-02-27 |  |  | 2017-02-27 | 0
492 | 2016-06-30 | 2016-07-08 |  |  | 2016-06-30 | 8
493 | 2016-01-25 | 2016-03-14 |  |  | 2016-02-15 | 28
494 | 2017-03-16 | 2017-09-05 |  |  | 2017-09-05 | 0
495 | 2016-12-01 | 2017-05-15 |  |  | 2017-05-15 | 0
496 | 2017-01-31 | 2017-05-30 |  |  | 2017-05-30 | 0
497 | 2016-04-25 | 2016-07-01 |  |  | 2016-05-23 | 39
498 | 2016-01-25 | 2016-05-09 |  |  | 2016-02-15 | 84
499 | 2016-06-02 | 2016-08-05 |  |  | 2016-08-08 | -3
500 | 2016-08-01 | 2016-08-22 |  |  | 2016-08-22 | 0
501 | 2016-11-30 | 2017-05-16 |  |  | 2017-05-16 | 0
502 | 2017-03-06 | 2017-07-26 |  |  | 2017-07-26 | 0
503 | 2016-08-01 | 2016-09-06 |  |  | 2016-09-06 | 0
504 | 2016-02-25 | 2016-04-04 |  |  | 2016-02-25 | 39
505 | 2016-11-21 | 2017-02-06 |  |  | 2017-02-06 | 0
506 | 2016-01-25 | 2016-05-20 |  |  | 2016-03-25 | 56
507 | 2016-02-25 | 2016-05-17 |  |  | 2016-03-25 | 53
508 | 2016-03-07 | 2016-05-19 |  |  | 2016-03-16 | 64
509 | 2016-06-29 | 2016-07-25 |  |  | 2016-06-29 | 26
510 | 2016-05-31 | 2016-07-18 |  |  | 2016-05-31 | 48
511 | 2016-05-31 | 2016-07-18 |  |  | 2016-05-31 | 48
512 | 2016-11-02 | 2017-03-16 |  |  | 2017-03-16 | 0
513 | 2016-09-05 | 2017-04-03 |  |  | 2017-04-03 | 0
514 | 2016-05-30 | 2016-06-17 |  |  | 2016-05-31 | 17
515 | 2016-02-25 | 2016-05-19 |  |  | 2016-03-25 | 55
516 | 2016-02-25 | 2016-05-16 |  |  | 2016-03-25 | 52
517 | 2016-05-02 | 2016-07-05 |  |  | 2016-05-02 | 64
518 | 2016-05-02 | 2016-05-23 |  |  | 2016-05-23 | 0
519 | 2016-09-05 | 2017-02-21 |  |  | 2017-02-21 | 0
520 | 2016-05-03 | 2016-06-23 |  |  | 2016-05-03 | 51
521 | 2016-05-02 | 2016-06-27 |  |  | 2016-05-23 | 35
522 | 2016-02-25 | 2016-05-19 |  |  | 2016-03-25 | 55
523 | 2016-05-02 | 2016-05-23 |  |  | 2016-05-23 | 0
524 | 2017-02-06 | 2017-07-28 |  |  | 2017-07-28 | 0
525 | 2016-06-02 | 2016-08-05 |  |  | 2016-08-08 | -3
526 | 2016-08-01 | 2016-08-15 |  |  | 2016-08-10 | 5
527 | 2017-02-06 | 2017-07-28 |  |  | 2017-07-28 | 0
528 | 2016-07-04 | 2016-07-25 |  |  | 2016-07-25 | 0
529 | 2016-02-29 | 2017-02-08 |  |  | 2016-03-25 | 320
530 | 2016-08-01 | 2017-02-13 |  |  | 2017-02-13 | 0
531 | 2016-02-29 | 2016-05-17 |  |  | 2016-04-15 | 32
532 | 2016-06-02 | 2016-07-11 |  |  | 2016-06-02 | 39
533 | 2017-01-05 | 2017-05-25 |  |  | 2017-05-25 | 0
534 | 2016-12-05 | 2017-05-04 |  |  | 2017-05-04 | 0
535 | 2016-07-04 | 2016-08-05 |  |  | 2016-08-08 | -3
536 | 2016-05-02 | 2016-06-17 |  |  | 2016-05-23 | 25
537 | 2017-02-06 | 2017-07-28 |  |  | 2017-07-28 | 0
538 | 2016-07-04 | 2016-08-05 |  |  | 2016-08-08 | -3
539 | 2017-03-06 | 2017-07-24 |  |  | 2017-07-24 | 0
540 | 2017-02-20 | 2017-03-03 |  |  | 2017-03-03 | 0
541 | 2016-05-02 | 2016-05-23 |  |  | 2016-05-23 | 0
542 | 2015-07-01 | 2015-07-24 |  |  | 2015-06-24 | 30
543 | 2016-10-17 | 2017-03-22 |  |  | 2017-03-22 | 0
544 | 2015-09-17 | 2015-08-05 |  |  | 2016-03-07 | -215
545 | 2015-06-29 | 2015-07-16 |  |  | 2015-06-22 | 24
546 | 2015-07-29 | 2016-04-18 |  |  | 2015-08-10 | 252
547 | 2015-05-29 | 06-22-15 A |  |  | 2015-05-26 | #VALUE!
548 | 2016-03-30 | 2016-05-23 |  |  | 2016-05-23 | 0
549 | 2015-06-24 | 2015-07-16 |  |  | 2015-06-18 | 28
550 | 2016-04-11 | 2016-05-16 |  |  | 2016-04-11 | 35
551 | 2016-06-02 | 2016-08-04 |  |  | 2016-08-03 | 1
552 | 2015-06-29 | 2016-06-27 |  |  | 2015-06-30 | 363
553 | 2016-12-05 | 2017-05-04 |  |  | 2017-05-04 | 0
554 | 2015-07-24 | 2015-07-30 |  |  | 2015-07-31 | -1
555 | 2016-11-07 | 2017-04-13 |  |  | 2017-04-13 | 0
556 | 2015-07-21 | 2015-08-17 |  |  | 2015-07-28 | 20
557 | 2016-03-30 | 2016-06-10 |  |  | 2016-05-23 | 18
558 | 2017-02-01 | 2017-03-06 |  |  | 2017-03-06 | 0
559 | 2015-07-14 | 2015-08-11 |  |  | 2015-08-07 | 4
560 | 2016-11-14 | 2017-04-24 |  |  | 2017-04-24 | 0
561 | 2017-03-06 | 2017-07-24 |  |  | 2017-07-24 | 0
562 | 2016-09-05 | 2017-02-24 |  |  | 2017-02-24 | 0
563 | 2016-06-29 | 2016-08-05 |  |  | 2016-08-08 | -3
564 | 2016-12-01 | 2017-04-17 |  |  | 2017-04-17 | 0
558

## Map
JV Number | Early Completion Bridge | Region | District | County | Latitude | Longitude | Requires Clearing | Requires Stakeout | Requires Earthwork | Requires Guiderail Adjustment | Requires Other Action
1 | -- | #REF! | 1 | Crawford | 41.6151 | -80.2379 | #REF! | #REF! | #REF! | #REF! | #REF!
2 | -- | #REF! | 1 | Crawford | 41.7962 | -80.0781 | #REF! | #REF! | #REF! | #REF! | #REF!
3 | -- | #REF! | 1 | Crawford | 41.6021 | -80.4312 | #REF! | #REF! | #REF! | #REF! | #REF!
4 | -- | #REF! | 1 | Crawford | 41.7483 | -79.9407 | #REF! | #REF! | #REF! | #REF! | #REF!
5 | -- | #REF! | 1 | Crawford | 41.6514 | -79.7261 | #REF! | #REF! | #REF! | #REF! | #REF!
6 | -- | #REF! | 1 | Crawford | 41.7519 | -80.0878 | #REF! | #REF! | #REF! | #REF! | #REF!
7 | -- | #REF! | 1 | Crawford | 41.7327 | -80.1616 | #REF! | #REF! | #REF! | #REF! | #REF!
8 | -- | #REF! | 1 | Erie | 42.0566 | -80.1481 | #REF! | #REF! | #REF! | #REF! | #REF!
9 | -- | #REF! | 1 | Forest | 41.5088 | -79.4497 | #REF! | #REF! | #REF! | #REF! | #REF!
10 | -- | #REF! | 1 | Forest | 41.5867 | -79.3548 | #REF! | #REF! | #REF! | #REF! | #REF!
11 | -- | #REF! | 1 | Forest | 41.5858 | -79.3397 | #REF! | #REF! | #REF! | #REF! | #REF!
12 | -- | #REF! | 1 | Forest | 41.5849 | -79.317 | #REF! | #REF! | #REF! | #REF! | #REF!
13 | -- | #REF! | 1 | Mercer | 41.4087 | -80.0752 | #REF! | #REF! | #REF! | #REF! | #REF!
14 | -- | #REF! | 1 | Mercer | 41.1918 | -80.3903 | #REF! | #REF! | #REF! | #REF! | #REF!
15 | -- | #REF! | 1 | Mercer | 41.246 | -80.3028 | #REF! | #REF! | #REF! | #REF! | #REF!
16 | -- | #REF! | 1 | Venango | 41.5748 | -79.8654 | #REF! | #REF! | #REF! | #REF! | #REF!
17 | -- | #REF! | 1 | Venango | 41.3135 | -79.7238 | #REF! | #REF! | #REF! | #REF! | #REF!
18 | -- | #REF! | 1 | Warren | 41.8386 | -79.3614 | #REF! | #REF! | #REF! | #REF! | #REF!
19 | -- | #REF! | 1 | Warren | 41.8471 | -79.3363 | #REF! | #REF! | #REF! | #REF! | #REF!
20 | -- | #REF! | 1 | Warren | 41.7256 | -79.0548 | #REF! | #REF! | #REF! | #REF! | #REF!
21 | -- | #REF! | 1 | Warren | 41.904 | -79.3447 | #REF! | #REF! | #REF! | #REF! | #REF!
22 | -- | #REF! | 1 | Warren | 41.68 | -79.4221 | #REF! | #REF! | #REF! | #REF! | #REF!
23 | -- | #REF! | 1 | Warren | 41.9515 | -79.4433 | #REF! | #REF! | #REF! | #REF! | #REF!
24 | -- | #REF! | 1 | Warren | 41.846 | -79.5687 | #REF! | #REF! | #REF! | #REF! | #REF!
25 | -- | #REF! | 2 | Cameron | 41.4708 | -78.3911 | #REF! | #REF! | #REF! | #REF! | #REF!
26 | -- | #REF! | 2 | Centre | 40.899 | -77.3573 | #REF! | #REF! | #REF! | #REF! | #REF!
27 | -- | #REF! | 2 | Centre | 40.9243 | -77.78 | #REF! | #REF! | #REF! | #REF! | #REF!
28 | -- | #REF! | 2 | Centre | 40.9992 | -77.8114 | #REF! | #REF! | #REF! | #REF! | #REF!
29 | -- | #REF! | 2 | Centre | 41.0091 | -77.7908 | #REF! | #REF! | #REF! | #REF! | #REF!
30 | -- | #REF! | 2 | Centre | 40.8819 | -77.4198 | #REF! | #REF! | #REF! | #REF! | #REF!
31 | -- | #REF! | 2 | Centre | 40.8018 | -78.0516 | #REF! | #REF! | #REF! | #REF! | #REF!
32 | -- | #REF! | 2 | Centre | 40.8126 | -78.0397 | #REF! | #REF! | #REF! | #REF! | #REF!
33 | -- | #REF! | 2 | Centre | 40.9064 | -77.8772 | #REF! | #REF! | #REF! | #REF! | #REF!
34 | -- | #REF! | 2 | Centre | 41.0538 | -77.9439 | #REF! | #REF! | #REF! | #REF! | #REF!
35 | -- | #REF! | 2 | Centre | 40.955 | -78.1702 | #REF! | #REF! | #REF! | #REF! | #REF!
36 | -- | #REF! | 2 | Clearfield | 40.9315 | -78.2242 | #REF! | #REF! | #REF! | #REF! | #REF!
37 | -- | #REF! | 2 | Clearfield | 40.8848 | -78.7566 | #REF! | #REF! | #REF! | #REF! | #REF!
38 | -- | #REF! | 2 | Clearfield | 40.9094 | -78.6707 | #REF! | #REF! | #REF! | #REF! | #REF!
39 | -- | #REF! | 2 | Clearfield | 40.9303 | -78.6468 | #REF! | #REF! | #REF! | #REF! | #REF!
40 | -- | #REF! | 2 | Clearfield | 40.9311 | -78.6461 | #REF! | #REF! | #REF! | #REF! | #REF!
41 | -- | #REF! | 2 | Clearfield | 41.1896 | -78.6015 | #REF! | #REF! | #REF! | #REF! | #REF!
42 | -- | #REF! | 2 | Clearfield | 41.2422 | -78.5402 | #REF! | #REF! | #REF! | #REF! | #REF!
43 | -- | #REF! | 2 | Clearfield | 40.9375 | -78.2029 | #REF! | #REF! | #REF! | #REF! | #REF!
44 | -- | #REF! | 2 | Clearfield | 40.9302 | -78.2797 | #REF! | #REF! | #REF! | #REF! | #REF!
45 | -- | #REF! | 2 | Clearfield | 41.0036 | -78.7869 | #REF! | #REF! | #REF! | #REF! | #REF!
46 | -- | #REF! | 2 | Clinton | 41.09 | -77.5362 | #REF! | #REF! | #REF! | #REF! | #REF!
47 | -- | #REF! | 2 | Clinton | 41.0855 | -77.4653 | #REF! | #REF! | #REF! | #REF! | #REF!
48 | -- | #REF! | 2 | Elk | 41.428 | -78.5329 | #REF! | #REF! | #REF! | #REF! | #REF!
49 | -- | #REF! | 2 | Elk | 41.2603 | -78.7261 | #REF! | #REF! | #REF! | #REF! | #REF!
50 | -- | #REF! | 2 | Elk | 41.4792 | -78.6697 | #REF! | #REF! | #REF! | #REF! | #REF!
51 | -- | #REF! | 2 | Juniata | 40.6347 | -77.2779 | #REF! | #REF! | #REF! | #REF! | #REF!
52 | -- | #REF! | 2 | Juniata | 40.3722 | -77.6006 | #REF! | #REF! | #REF! | #REF! | #REF!
53 | -- | #REF! | 2 | Juniata | 40.5937 | -77.3999 | #REF! | #REF! | #REF! | #REF! | #REF!
54 | -- | #REF! | 2 | Juniata | 40.637 | -77.2754 | #REF! | #REF! | #REF! | #REF! | #REF!
55 | -- | #REF! | 2 | Juniata | 40.5835 | -77.2954 | #REF! | #REF! | #REF! | #REF! | #REF!
56 | -- | #REF! | 2 | Juniata | 40.6119 | -77.3132 | #REF! | #REF! | #REF! | #REF! | #REF!
57 | -- | #REF! | 2 | McKean | 41.7052 | -78.5921 | #REF! | #REF! | #REF! | #REF! | #REF!
58 | -- | #REF! | 2 | McKean | 41.7302 | -78.5416 | #REF! | #REF! | #REF! | #REF! | #REF!
59 | -- | #REF! | 2 | McKean | 41.6341 | -78.3574 | #REF! | #REF! | #REF! | #REF! | #REF!
60 | -- | #REF! | 2 | McKean | 41.802 | -78.5643 | #REF! | #REF! | #REF! | #REF! | #REF!
61 | -- | #REF! | 2 | McKean | 41.7083 | -78.2148 | #REF! | #REF! | #REF! | #REF! | #REF!
62 | -- | #REF! | 2 | McKean | 41.8326 | -78.2963 | #REF! | #REF! | #REF! | #REF! | #REF!
63 | -- | #REF! | 2 | McKean | 41.8788 | -78.349 | #REF! | #REF! | #REF! | #REF! | #REF!
64 | -- | #REF! | 2 | McKean | 41.8892 | -78.352 | #REF! | #REF! | #REF! | #REF! | #REF!
65 | -- | #REF! | 2 | McKean | 41.9716 | -78.5844 | #REF! | #REF! | #REF! | #REF! | #REF!
66 | -- | #REF! | 2 | McKean | 41.9716 | -78.5741 | #REF! | #REF! | #REF! | #REF! | #REF!
67 | -- | #REF! | 2 | McKean | 41.9784 | -78.5575 | #REF! | #REF! | #REF! | #REF! | #REF!
68 | -- | #REF! | 2 | McKean | 41.9044 | -78.6613 | #REF! | #REF! | #REF! | #REF! | #REF!
69 | -- | #REF! | 2 | McKean | 41.9055 | -78.6575 | #REF! | #REF! | #REF! | #REF! | #REF!
70 | -- | #REF! | 2 | McKean | 41.9248 | -78.4942 | #REF! | #REF! | #REF! | #REF! | #REF!
71 | -- | #REF! | 2 | McKean | 41.6308 | -78.5754 | #REF! | #REF! | #REF! | #REF! | #REF!
72 | -- | #REF! | 2 | McKean | 41.6713 | -78.3998 | #REF! | #REF! | #REF! | #REF! | #REF!
73 | -- | #REF! | 2 | McKean | 41.9658 | -78.6771 | #REF! | #REF! | #REF! | #REF! | #REF!
74 | -- | #REF! | 2 | Mifflin | 40.6278 | -77.6746 | #REF! | #REF! | #REF! | #REF! | #REF!
75 | -- | #REF! | 2 | Mifflin | 40.6279 | -77.6742 | #REF! | #REF! | #REF! | #REF! | #REF!
76 | -- | #REF! | 2 | Mifflin | 40.6888 | -77.5584 | #REF! | #REF! | #REF! | #REF! | #REF!
77 | -- | #REF! | 2 | Mifflin | 40.7052 | -77.5347 | #REF! | #REF! | #REF! | #REF! | #REF!
78 | -- | #REF! | 2 | Mifflin | 40.5683 | -77.6762 | #REF! | #REF! | #REF! | #REF! | #REF!
79 | -- | #REF! | 2 | Potter | 41.7632 | -78.0383 | #REF! | #REF! | #REF! | #REF! | #REF!
80 | -- | #REF! | 2 | Potter | 41.625 | -77.7181 | #REF! | #REF! | #REF! | #REF! | #REF!
81 | -- | #REF! | 2 | Potter | 41.8694 | -78.002 | #REF! | #REF! | #REF! | #REF! | #REF!
82 | -- | #REF! | 2 | Potter | 41.9114 | -78.0977 | #REF! | #REF! | #REF! | #REF! | #REF!
83 | -- | #REF! | 2 | Potter | 41.9392 | -78.1428 | #REF! | #REF! | #REF! | #REF! | #REF!
84 | -- | #REF! | 2 | Potter | 41.9463 | -77.6856 | #REF! | #REF! | #REF! | #REF! | #REF!
85 | -- | #REF! | 2 | Potter | 41.9444 | -77.6732 | #REF! | #REF! | #REF! | #REF! | #REF!
86 | -- | #REF! | 2 | Potter | 41.8127 | -77.7879 | #REF! | #REF! | #REF! | #REF! | #REF!
87 | -- | #REF! | 2 | Potter | 41.7032 | -77.7375 | #REF! | #REF! | #REF! | #REF! | #REF!
88 | -- | #REF! | 2 | Potter | 41.7818 | -78.1651 | #REF! | #REF! | #REF! | #REF! | #REF!
89 | -- | #REF! | 3 | Bradford | 41.7765 | -76.7922 | #REF! | #REF! | #REF! | #REF! | #REF!
90 | Y | #REF! | 3 | Bradford | 41.7171 | -76.3591 | #REF! | #REF! | #REF! | #REF! | #REF!
91 | -- | #REF! | 3 | Bradford | 41.6218 | -76.4392 | #REF! | #REF! | #REF! | #REF! | #REF!
92 | Y | #REF! | 3 | Bradford | 41.6554 | -76.1377 | #REF! | #REF! | #REF! | #REF! | #REF!
93 | -- | #REF! | 3 | Bradford | 41.7028 | -76.5568 | #REF! | #REF! | #REF! | #REF! | #REF!
94 | Y | #REF! | 3 | Bradford | 41.8304 | -76.3501 | #REF! | #REF! | #REF! | #REF! | #REF!
95 | Y | #REF! | 3 | Bradford | 41.8231 | -76.1839 | #REF! | #REF! | #REF! | #REF! | #REF!
96 | Y | #REF! | 3 | Bradford | 41.7132 | -76.6387 | #REF! | #REF! | #REF! | #REF! | #REF!
97 | Y | #REF! | 3 | Bradford | 41.7477 | -76.2075 | #REF! | #REF! | #REF! | #REF! | #REF!
98 | Y | #REF! | 3 | Bradford | 41.7808 | -76.1399 | #REF! | #REF! | #REF! | #REF! | #REF!
99 | -- | #REF! | 3 | Bradford | 41.9375 | -76.1941 | #REF! | #REF! | #REF! | #REF! | #REF!
100 | -- | #REF! | 3 | Bradford | 41.9308 | -76.7021 | #REF! | #REF! | #REF! | #REF! | #REF!
101 | -- | #REF! | 3 | Columbia | 41.1038 | -76.6084 | #REF! | #REF! | #REF! | #REF! | #REF!
102 | Y | #REF! | 3 | Columbia | 41.1351 | -76.4583 | #REF! | #REF! | #REF! | #REF! | #REF!
103 | Y | #REF! | 3 | Columbia | 41.0524 | -76.4285 | #REF! | #REF! | #REF! | #REF! | #REF!
104 | Y | #REF! | 3 | Columbia | 41.1988 | -76.4669 | #REF! | #REF! | #REF! | #REF! | #REF!
106 | -- | #REF! | 3 | Lycoming | 41.1781 | -76.9111 | #REF! | #REF! | #REF! | #REF! | #REF!
107 | Y | #REF! | 3 | Lycoming | 41.164 | -77.2209 | #REF! | #REF! | #REF! | #REF! | #REF!
108 | -- | #REF! | 3 | Lycoming | 41.2972 | -76.906 | #REF! | #REF! | #REF! | #REF! | #REF!
109 | -- | #REF! | 3 | Lycoming | 41.2321 | -76.6095 | #REF! | #REF! | #REF! | #REF! | #REF!
110 | -- | #REF! | 3 | Lycoming | 41.3207 | -77.3864 | #REF! | #REF! | #REF! | #REF! | #REF!
111 | -- | #REF! | 3 | Lycoming | 41.36 | -77.4116 | #REF! | #REF! | #REF! | #REF! | #REF!
112 | Y | #REF! | 3 | Lycoming | 41.1189 | -77.0668 | #REF! | #REF! | #REF! | #REF! | #REF!
113 | -- | #REF! | 3 | Lycoming | 41.2445 | -76.6174 | #REF! | #REF! | #REF! | #REF! | #REF!
114 | Y | #REF! | 3 | Lycoming | 41.2428 | -76.561 | #REF! | #REF! | #REF! | #REF! | #REF!
115 | -- | #REF! | 3 | Lycoming | 41.2432 | -76.6833 | #REF! | #REF! | #REF! | #REF! | #REF!
116 | -- | #REF! | 3 | Montour | 41.0322 | -76.7506 | #REF! | #REF! | #REF! | #REF! | #REF!
117 | -- | #REF! | 3 | Montour | 41.0928 | -76.7045 | #REF! | #REF! | #REF! | #REF! | #REF!
118 | Y | #REF! | 3 | Montour | 41.0989 | -76.6614 | #REF! | #REF! | #REF! | #REF! | #REF!
119 | -- | #REF! | 3 | Northumberland | 40.9955 | -76.7899 | #REF! | #REF! | #REF! | #REF! | #REF!
120 | -- | #REF! | 3 | Northumberland | 40.8906 | -76.5581 | #REF! | #REF! | #REF! | #REF! | #REF!
121 | -- | #REF! | 3 | Northumberland | 40.7919 | -76.817 | #REF! | #REF! | #REF! | #REF! | #REF!
122 | -- | #REF! | 3 | Northumberland | 40.762 | -76.8353 | #REF! | #REF! | #REF! | #REF! | #REF!
123 | -- | #REF! | 3 | Northumberland | 40.7907 | -76.7248 | #REF! | #REF! | #REF! | #REF! | #REF!
124 | -- | #REF! | 3 | Snyder | 40.8299 | -76.8365 | #REF! | #REF! | #REF! | #REF! | #REF!
125 | -- | #REF! | 3 | Sullivan | 41.4441 | -76.7066 | #REF! | #REF! | #REF! | #REF! | #REF!
126 | Y | #REF! | 3 | Sullivan | 41.5162 | -76.4103 | #REF! | #REF! | #REF! | #REF! | #REF!
127 | -- | #REF! | 3 | Tioga | 41.466 | -76.579 | #REF! | #REF! | #REF! | #REF! | #REF!
128 | -- | #REF! | 3 | Tioga | 41.9264 | -77.5213 | #REF! | #REF! | #REF! | #REF! | #REF!
129 | Y | #REF! | 3 | Tioga | 41.9334 | -77.4793 | #REF! | #REF! | #REF! | #REF! | #REF!
130 | -- | #REF! | 3 | Tioga | 41.9301 | -76.9323 | #REF! | #REF! | #REF! | #REF! | #REF!
131 | Y | #REF! | 3 | Tioga | 41.7352 | -77.5822 | #REF! | #REF! | #REF! | #REF! | #REF!
132 | Y | #REF! | 3 | Tioga | 41.6215 | -77.3662 | #REF! | #REF! | #REF! | #REF! | #REF!
133 | Y | #REF! | 3 | Tioga | 41.9921 | -77.3798 | #REF! | #REF! | #REF! | #REF! | #REF!
134 | -- | #REF! | 3 | Tioga | 41.7979 | -77.2643 | #REF! | #REF! | #REF! | #REF! | #REF!
135 | -- | #REF! | 3 | Union | 41.0124 | -76.9825 | #REF! | #REF! | #REF! | #REF! | #REF!
136 | -- | #REF! | 3 | Union | 41.0124 | -76.9822 | #REF! | #REF! | #REF! | #REF! | #REF!
137 | Y | #REF! | 3 | Union | 40.9734 | -76.9525 | #REF! | #REF! | #REF! | #REF! | #REF!
138 | Y | #REF! | 3 | Union | 40.8831 | -77.1972 | #REF! | #REF! | #REF! | #REF! | #REF!
139 | -- | #REF! | 4 | Lackawanna | 41.4894 | -75.6804 | #REF! | #REF! | #REF! | #REF! | #REF!
140 | -- | #REF! | 4 | Luzerne | 41.1809 | -75.6994 | #REF! | #REF! | #REF! | #REF! | #REF!
141 | -- | #REF! | 4 | Luzerne | 41.0483 | -76.0083 | #REF! | #REF! | #REF! | #REF! | #REF!
142 | Y | #REF! | 4 | Pike | 41.4116 | -74.8935 | #REF! | #REF! | #REF! | #REF! | #REF!
143 | -- | #REF! | 4 | Pike | 41.2992 | -74.9598 | #REF! | #REF! | #REF! | #REF! | #REF!
144 | -- | #REF! | 4 | Susquehanna | 41.8929 | -75.73 | #REF! | #REF! | #REF! | #REF! | #REF!
145 | -- | #REF! | 4 | Susquehanna | 41.7101 | -75.6714 | #REF! | #REF! | #REF! | #REF! | #REF!
146 | Y | #REF! | 4 | Susquehanna | 41.8408 | -76.0292 | #REF! | #REF! | #REF! | #REF! | #REF!
147 | -- | #REF! | 4 | Susquehanna | 41.8429 | -76.0189 | #REF! | #REF! | #REF! | #REF! | #REF!
148 | -- | #REF! | 4 | Susquehanna | 41.6514 | -75.6917 | #REF! | #REF! | #REF! | #REF! | #REF!
149 | -- | #REF! | 4 | Susquehanna | 41.8248 | -75.9123 | #REF! | #REF! | #REF! | #REF! | #REF!
150 | -- | #REF! | 4 | Susquehanna | 41.815 | -76.1057 | #REF! | #REF! | #REF! | #REF! | #REF!
151 | Y | #REF! | 4 | Susquehanna | 41.9134 | -75.5628 | #REF! | #REF! | #REF! | #REF! | #REF!
152 | -- | #REF! | 4 | Susquehanna | 41.9045 | -75.7351 | #REF! | #REF! | #REF! | #REF! | #REF!
153 | Y | #REF! | 4 | Susquehanna | 41.6489 | -75.5995 | #REF! | #REF! | #REF! | #REF! | #REF!
154 | -- | #REF! | 4 | Susquehanna | 41.6553 | -75.6602 | #REF! | #REF! | #REF! | #REF! | #REF!
155 | -- | #REF! | 4 | Susquehanna | 41.9715 | -75.9134 | #REF! | #REF! | #REF! | #REF! | #REF!
156 | -- | #REF! | 4 | Wayne | 41.6681 | -75.2546 | #REF! | #REF! | #REF! | #REF! | #REF!
157 | -- | #REF! | 4 | Wayne | 41.5542 | -75.4081 | #REF! | #REF! | #REF! | #REF! | #REF!
158 | Y | #REF! | 4 | Wayne | 41.8244 | -75.1497 | #REF! | #REF! | #REF! | #REF! | #REF!
159 | Y | #REF! | 4 | Wayne | 41.5696 | -75.2254 | #REF! | #REF! | #REF! | #REF! | #REF!
160 | -- | #REF! | 4 | Wayne | 41.4041 | -75.3364 | #REF! | #REF! | #REF! | #REF! | #REF!
161 | Y | #REF! | 4 | Wayne | 41.9429 | -75.3848 | #REF! | #REF! | #REF! | #REF! | #REF!
162 | Y | #REF! | 4 | Wayne | 41.8907 | -75.3364 | #REF! | #REF! | #REF! | #REF! | #REF!
163 | -- | #REF! | 4 | Wayne | 41.9976 | -75.4019 | #REF! | #REF! | #REF! | #REF! | #REF!
164 | -- | #REF! | 4 | Wyoming | 41.6145 | -76.0478 | #REF! | #REF! | #REF! | #REF! | #REF!
165 | -- | #REF! | 4 | Wyoming | 41.4142 | -75.9074 | #REF! | #REF! | #REF! | #REF! | #REF!
166 | Y | #REF! | 4 | Wyoming | 41.58 | -75.9166 | #REF! | #REF! | #REF! | #REF! | #REF!
167 | Y | #REF! | 4 | Wyoming | 41.4076 | -76.0296 | #REF! | #REF! | #REF! | #REF! | #REF!
168 | -- | #REF! | 5 | Berks | 40.2902 | -75.9472 | #REF! | #REF! | #REF! | #REF! | #REF!
169 | -- | #REF! | 5 | Berks | 40.427 | -75.934 | #REF! | #REF! | #REF! | #REF! | #REF!
170 | -- | #REF! | 5 | Berks | 40.5255 | -75.875 | #REF! | #REF! | #REF! | #REF! | #REF!
171 | -- | #REF! | 5 | Berks | 40.5493 | -75.9633 | #REF! | #REF! | #REF! | #REF! | #REF!
172 | -- | #REF! | 5 | Berks | 40.5493 | -75.9633 | #REF! | #REF! | #REF! | #REF! | #REF!
173 | Y | #REF! | 5 | Carbon | 40.8514 | -75.7132 | #REF! | #REF! | #REF! | #REF! | #REF!
174 | -- | #REF! | 5 | Carbon | 40.8892 | -75.9184 | #REF! | #REF! | #REF! | #REF! | #REF!
175 | -- | #REF! | 5 | Lehigh | 40.5942 | -75.5007 | #REF! | #REF! | #REF! | #REF! | #REF!
176 | -- | #REF! | 5 | Lehigh | 40.6504 | -75.4656 | #REF! | #REF! | #REF! | #REF! | #REF!
177 | -- | #REF! | 5 | Lehigh | 40.5508 | -75.4054 | #REF! | #REF! | #REF! | #REF! | #REF!
178 | -- | #REF! | 5 | Lehigh | 40.5475 | -75.6073 | #REF! | #REF! | #REF! | #REF! | #REF!
179 | -- | #REF! | 5 | Monroe | 40.901 | -75.497 | #REF! | #REF! | #REF! | #REF! | #REF!
180 | Y | #REF! | 5 | Monroe | 40.9557 | -75.2876 | #REF! | #REF! | #REF! | #REF! | #REF!
181 | Y | #REF! | 5 | Monroe | 41.0911 | -75.288 | #REF! | #REF! | #REF! | #REF! | #REF!
182 | Y | #REF! | 5 | Monroe | 41.1684 | -75.2733 | #REF! | #REF! | #REF! | #REF! | #REF!
183 | Y | #REF! | 5 | Monroe | 41.1732 | -75.4152 | #REF! | #REF! | #REF! | #REF! | #REF!
184 | Y | #REF! | 5 | Monroe | 40.9377 | -75.3928 | #REF! | #REF! | #REF! | #REF! | #REF!
185 | Y | #REF! | 5 | Monroe | 41.0528 | -75.5539 | #REF! | #REF! | #REF! | #REF! | #REF!
186 | Y | #REF! | 5 | Monroe | 41.1118 | -75.5609 | #REF! | #REF! | #REF! | #REF! | #REF!
187 | Y | #REF! | 5 | Monroe | 41.1117 | -75.5065 | #REF! | #REF! | #REF! | #REF! | #REF!
188 | Y | #REF! | 5 | Monroe | 41.1271 | -75.308 | #REF! | #REF! | #REF! | #REF! | #REF!
189 | Y | #REF! | 5 | Monroe | 41.1018 | -75.2696 | #REF! | #REF! | #REF! | #REF! | #REF!
190 | Y | #REF! | 5 | Monroe | 40.9854 | -75.2254 | #REF! | #REF! | #REF! | #REF! | #REF!
191 | Y | #REF! | 5 | Monroe | 40.951 | -75.4473 | #REF! | #REF! | #REF! | #REF! | #REF!
192 | Y | #REF! | 5 | Monroe | 40.9634 | -75.4306 | #REF! | #REF! | #REF! | #REF! | #REF!
194 | Y | #REF! | 5 | Monroe | 41.0036 | -75.2796 | #REF! | #REF! | #REF! | #REF! | #REF!
195 | Y | #REF! | 5 | Monroe | 41.1528 | -75.5799 | #REF! | #REF! | #REF! | #REF! | #REF!
196 | Y | #REF! | 5 | Monroe | 41.0538 | -75.3403 | #REF! | #REF! | #REF! | #REF! | #REF!
197 | -- | #REF! | 5 | Northampton | 40.6828 | -75.289 | #REF! | #REF! | #REF! | #REF! | #REF!
198 | -- | #REF! | 5 | Northampton | 40.6828 | -75.289 | #REF! | #REF! | #REF! | #REF! | #REF!
201 | -- | #REF! | 5 | Northampton | 40.789 | -75.3658 | #REF! | #REF! | #REF! | #REF! | #REF!
202 | -- | #REF! | 5 | Northampton | 40.8027 | -75.126 | #REF! | #REF! | #REF! | #REF! | #REF!
203 | -- | #REF! | 5 | Northampton | 40.8248 | -75.2031 | #REF! | #REF! | #REF! | #REF! | #REF!
204 | Y | #REF! | 5 | Schuylkill | 40.9031 | -76.21 | #REF! | #REF! | #REF! | #REF! | #REF!
205 | Y | #REF! | 5 | Schuylkill | 40.9212 | -76.2264 | #REF! | #REF! | #REF! | #REF! | #REF!
206 | Y | #REF! | 5 | Schuylkill | 40.9217 | -76.2265 | #REF! | #REF! | #REF! | #REF! | #REF!
207 | Y | #REF! | 5 | Schuylkill | 40.8153 | -76.1995 | #REF! | #REF! | #REF! | #REF! | #REF!
208 | Y | #REF! | 5 | Schuylkill | 40.6616 | -76.6866 | #REF! | #REF! | #REF! | #REF! | #REF!
209 | Y | #REF! | 5 | Schuylkill | 40.8525 | -76.2805 | #REF! | #REF! | #REF! | #REF! | #REF!
210 | Y | #REF! | 5 | Schuylkill | 40.7038 | -76.4901 | #REF! | #REF! | #REF! | #REF! | #REF!
211 | -- | #REF! | 6 | Bucks | 40.1878 | -74.8468 | #REF! | #REF! | #REF! | #REF! | #REF!
212 | -- | #REF! | 6 | Chester | 39.8326 | -75.8452 | #REF! | #REF! | #REF! | #REF! | #REF!
213 | -- | #REF! | 6 | Chester | 40.0722 | -75.7863 | #REF! | #REF! | #REF! | #REF! | #REF!
214 | -- | #REF! | 6 | Delaware | 39.8979 | -75.3162 | #REF! | #REF! | #REF! | #REF! | #REF!
215 | -- | #REF! | 6 | Montgomery | 40.3734 | -75.5184 | #REF! | #REF! | #REF! | #REF! | #REF!
216 | -- | #REF! | 6 | Montgomery | 40.1219 | -75.0515 | #REF! | #REF! | #REF! | #REF! | #REF!
217 | -- | #REF! | 6 | Montgomery | 40.1232 | -75.1915 | #REF! | #REF! | #REF! | #REF! | #REF!
218 | -- | #REF! | 6 | Montgomery | 40.0033 | -75.2683 | #REF! | #REF! | #REF! | #REF! | #REF!
219 | -- | #REF! | 6 | Montgomery | 40.267 | -75.6728 | #REF! | #REF! | #REF! | #REF! | #REF!
220 | -- | #REF! | 8 | Adams | 39.8346 | -77.2199 | #REF! | #REF! | #REF! | #REF! | #REF!
221 | -- | #REF! | 8 | Adams | 39.9812 | -77.2343 | #REF! | #REF! | #REF! | #REF! | #REF!
222 | -- | #REF! | 8 | Adams | 40.0131 | -77.2029 | #REF! | #REF! | #REF! | #REF! | #REF!
223 | -- | #REF! | 8 | Adams | 39.7588 | -77.124 | #REF! | #REF! | #REF! | #REF! | #REF!
224 | -- | #REF! | 8 | Adams | 39.8002 | -77.3497 | #REF! | #REF! | #REF! | #REF! | #REF!
225 | -- | #REF! | 8 | Adams | 39.8838 | -76.9831 | #REF! | #REF! | #REF! | #REF! | #REF!
226 | -- | #REF! | 8 | Adams | 39.9462 | -77.3403 | #REF! | #REF! | #REF! | #REF! | #REF!
227 | -- | #REF! | 8 | Adams | 39.9411 | -77.2045 | #REF! | #REF! | #REF! | #REF! | #REF!
228 | -- | #REF! | 8 | Adams | 39.9154 | -77.2217 | #REF! | #REF! | #REF! | #REF! | #REF!
229 | -- | #REF! | 8 | Adams | 39.9825 | -77.1646 | #REF! | #REF! | #REF! | #REF! | #REF!
230 | -- | #REF! | 8 | Adams | 40.0031 | -77.1924 | #REF! | #REF! | #REF! | #REF! | #REF!
231 | -- | #REF! | 8 | Adams | 39.8612 | -77.136 | #REF! | #REF! | #REF! | #REF! | #REF!
232 | -- | #REF! | 8 | Adams | 39.8305 | -77.3177 | #REF! | #REF! | #REF! | #REF! | #REF!
233 | -- | #REF! | 8 | Adams | 39.9899 | -77.2529 | #REF! | #REF! | #REF! | #REF! | #REF!
234 | -- | #REF! | 8 | Adams | 39.977 | -77.2255 | #REF! | #REF! | #REF! | #REF! | #REF!
235 | -- | #REF! | 8 | Adams | 39.9014 | -77.4676 | #REF! | #REF! | #REF! | #REF! | #REF!
236 | -- | #REF! | 8 | Cumberland | 40.2338 | -77.1388 | #REF! | #REF! | #REF! | #REF! | #REF!
237 | -- | #REF! | 8 | Cumberland | 40.0794 | -77.1932 | #REF! | #REF! | #REF! | #REF! | #REF!
238 | -- | #REF! | 8 | Cumberland | 40.0338 | -77.304 | #REF! | #REF! | #REF! | #REF! | #REF!
239 | -- | #REF! | 8 | Cumberland | 40.1842 | -77.406 | #REF! | #REF! | #REF! | #REF! | #REF!
240 | -- | #REF! | 8 | Cumberland | 40.2381 | -77.4452 | #REF! | #REF! | #REF! | #REF! | #REF!
241 | -- | #REF! | 8 | Cumberland | 40.212 | -76.9065 | #REF! | #REF! | #REF! | #REF! | #REF!
242 | -- | #REF! | 8 | Cumberland | 40.1118 | -77.2847 | #REF! | #REF! | #REF! | #REF! | #REF!
243 | -- | #REF! | 8 | Cumberland | 40.0834 | -77.5432 | #REF! | #REF! | #REF! | #REF! | #REF!
244 | -- | #REF! | 8 | Cumberland | 40.2091 | -77.4366 | #REF! | #REF! | #REF! | #REF! | #REF!
245 | -- | #REF! | 8 | Dauphin | 40.628 | -76.778 | #REF! | #REF! | #REF! | #REF! | #REF!
246 | -- | #REF! | 8 | Dauphin | 40.2995 | -76.6385 | #REF! | #REF! | #REF! | #REF! | #REF!
247 | -- | #REF! | 8 | Dauphin | 40.4805 | -76.8825 | #REF! | #REF! | #REF! | #REF! | #REF!
248 | -- | #REF! | 8 | Franklin | 39.9054 | -77.4783 | #REF! | #REF! | #REF! | #REF! | #REF!
249 | -- | #REF! | 8 | Franklin | 40.2257 | -77.6928 | #REF! | #REF! | #REF! | #REF! | #REF!
250 | -- | #REF! | 8 | Franklin | 40.0916 | -77.6481 | #REF! | #REF! | #REF! | #REF! | #REF!
251 | -- | #REF! | 8 | Franklin | 39.9768 | -77.7583 | #REF! | #REF! | #REF! | #REF! | #REF!
252 | -- | #REF! | 8 | Franklin | 39.9649 | -77.7302 | #REF! | #REF! | #REF! | #REF! | #REF!
253 | -- | #REF! | 8 | Lancaster | 40.0629 | -76.5162 | #REF! | #REF! | #REF! | #REF! | #REF!
254 | -- | #REF! | 8 | Lancaster | 40.006 | -76.1108 | #REF! | #REF! | #REF! | #REF! | #REF!
255 | -- | #REF! | 8 | Lancaster | 40.2191 | -76.2577 | #REF! | #REF! | #REF! | #REF! | #REF!
256 | -- | #REF! | 8 | Lancaster | 40.0289 | -75.967 | #REF! | #REF! | #REF! | #REF! | #REF!
257 | -- | #REF! | 8 | Lancaster | 40.0249 | -75.9487 | #REF! | #REF! | #REF! | #REF! | #REF!
258 | -- | #REF! | 8 | Lancaster | 39.9533 | -75.9967 | #REF! | #REF! | #REF! | #REF! | #REF!
259 | -- | #REF! | 8 | Lancaster | 40.0379 | -76.343 | #REF! | #REF! | #REF! | #REF! | #REF!
260 | -- | #REF! | 8 | Lancaster | 40.1893 | -76.0169 | #REF! | #REF! | #REF! | #REF! | #REF!
261 | -- | #REF! | 8 | Lancaster | 40.1476 | -76.2715 | #REF! | #REF! | #REF! | #REF! | #REF!
262 | -- | #REF! | 8 | Lancaster | 40.1328 | -75.9367 | #REF! | #REF! | #REF! | #REF! | #REF!
263 | -- | #REF! | 8 | Lancaster | 40.1437 | -76.0207 | #REF! | #REF! | #REF! | #REF! | #REF!
264 | -- | #REF! | 8 | Lancaster | 40.2039 | -76.1822 | #REF! | #REF! | #REF! | #REF! | #REF!
265 | -- | #REF! | 8 | Lancaster | 40.1348 | -76.1741 | #REF! | #REF! | #REF! | #REF! | #REF!
266 | -- | #REF! | 8 | Lancaster | 40.2441 | -76.1136 | #REF! | #REF! | #REF! | #REF! | #REF!
267 | -- | #REF! | 8 | Lancaster | 40.2452 | -76.2489 | #REF! | #REF! | #REF! | #REF! | #REF!
268 | -- | #REF! | 8 | Lancaster | 40.2276 | -76.335 | #REF! | #REF! | #REF! | #REF! | #REF!
269 | -- | #REF! | 8 | Lancaster | 40.1772 | -76.2417 | #REF! | #REF! | #REF! | #REF! | #REF!
270 | -- | #REF! | 8 | Lancaster | 40.1656 | -76.0222 | #REF! | #REF! | #REF! | #REF! | #REF!
271 | -- | #REF! | 8 | Lancaster | 40.2413 | -76.1414 | #REF! | #REF! | #REF! | #REF! | #REF!
272 | -- | #REF! | 8 | Lancaster | 40.243 | -76.123 | #REF! | #REF! | #REF! | #REF! | #REF!
273 | -- | #REF! | 8 | Lancaster | 39.7552 | -76.1071 | #REF! | #REF! | #REF! | #REF! | #REF!
274 | -- | #REF! | 8 | Lancaster | 39.7625 | -76.1542 | #REF! | #REF! | #REF! | #REF! | #REF!
275 | -- | #REF! | 8 | Lancaster | 39.8481 | -76.1136 | #REF! | #REF! | #REF! | #REF! | #REF!
276 | -- | #REF! | 8 | Lancaster | 39.8517 | -76.0433 | #REF! | #REF! | #REF! | #REF! | #REF!
277 | -- | #REF! | 8 | Lancaster | 39.8806 | -76.1047 | #REF! | #REF! | #REF! | #REF! | #REF!
278 | -- | #REF! | 8 | Lancaster | 39.9171 | -76.1749 | #REF! | #REF! | #REF! | #REF! | #REF!
279 | -- | #REF! | 8 | Lancaster | 39.9172 | -76.1748 | #REF! | #REF! | #REF! | #REF! | #REF!
280 | -- | #REF! | 8 | Lancaster | 40.0549 | -76.1706 | #REF! | #REF! | #REF! | #REF! | #REF!
281 | -- | #REF! | 8 | Lancaster | 39.7943 | -76.2593 | #REF! | #REF! | #REF! | #REF! | #REF!
282 | -- | #REF! | 8 | Lancaster | 39.9843 | -76.4059 | #REF! | #REF! | #REF! | #REF! | #REF!
283 | -- | #REF! | 8 | Lancaster | 39.9922 | -76.3802 | #REF! | #REF! | #REF! | #REF! | #REF!
284 | -- | #REF! | 8 | Lebanon | 40.4373 | -76.542 | #REF! | #REF! | #REF! | #REF! | #REF!
285 | -- | #REF! | 8 | Perry | 40.3377 | -76.9276 | #REF! | #REF! | #REF! | #REF! | #REF!
286 | -- | #REF! | 8 | Perry | 40.3821 | -77.4535 | #REF! | #REF! | #REF! | #REF! | #REF!
287 | -- | #REF! | 8 | Perry | 40.5752 | -76.9961 | #REF! | #REF! | #REF! | #REF! | #REF!
288 | -- | #REF! | 8 | Perry | 40.3831 | -77.3077 | #REF! | #REF! | #REF! | #REF! | #REF!
289 | -- | #REF! | 8 | Perry | 40.371 | -77.4011 | #REF! | #REF! | #REF! | #REF! | #REF!
290 | -- | #REF! | 8 | Perry | 40.3591 | -77.381 | #REF! | #REF! | #REF! | #REF! | #REF!
291 | -- | #REF! | 8 | Perry | 40.5142 | -77.1297 | #REF! | #REF! | #REF! | #REF! | #REF!
292 | -- | #REF! | 8 | Perry | 40.2982 | -77.5129 | #REF! | #REF! | #REF! | #REF! | #REF!
293 | -- | #REF! | 8 | Perry | 40.3291 | -77.2846 | #REF! | #REF! | #REF! | #REF! | #REF!
294 | -- | #REF! | 8 | Perry | 40.5159 | -77.2365 | #REF! | #REF! | #REF! | #REF! | #REF!
295 | -- | #REF! | 8 | York | 39.9677 | -76.5979 | #REF! | #REF! | #REF! | #REF! | #REF!
296 | -- | #REF! | 8 | York | 39.9621 | -76.5144 | #REF! | #REF! | #REF! | #REF! | #REF!
297 | -- | #REF! | 8 | York | 39.9398 | -76.4871 | #REF! | #REF! | #REF! | #REF! | #REF!
298 | -- | #REF! | 8 | York | 39.8005 | -76.7392 | #REF! | #REF! | #REF! | #REF! | #REF!
299 | -- | #REF! | 8 | York | 39.8008 | -76.7417 | #REF! | #REF! | #REF! | #REF! | #REF!
300 | -- | #REF! | 8 | York | 40.0343 | -76.7871 | #REF! | #REF! | #REF! | #REF! | #REF!
301 | -- | #REF! | 8 | York | 39.7217 | -76.3374 | #REF! | #REF! | #REF! | #REF! | #REF!
302 | -- | #REF! | 8 | York | 39.9603 | -76.5536 | #REF! | #REF! | #REF! | #REF! | #REF!
303 | -- | #REF! | 8 | York | 39.8317 | -76.9275 | #REF! | #REF! | #REF! | #REF! | #REF!
304 | -- | #REF! | 8 | York | 39.8104 | -76.8732 | #REF! | #REF! | #REF! | #REF! | #REF!
305 | -- | #REF! | 8 | York | 39.731 | -76.9479 | #REF! | #REF! | #REF! | #REF! | #REF!
306 | -- | #REF! | 8 | York | 40.0106 | -76.8066 | #REF! | #REF! | #REF! | #REF! | #REF!
307 | -- | #REF! | 8 | York | 40.0176 | -76.9748 | #REF! | #REF! | #REF! | #REF! | #REF!
308 | -- | #REF! | 8 | York | 40.162 | -76.9218 | #REF! | #REF! | #REF! | #REF! | #REF!
309 | -- | #REF! | 8 | York | 39.9307 | -76.9034 | #REF! | #REF! | #REF! | #REF! | #REF!
310 | -- | #REF! | 9 | Bedford | 40.0394 | -78.6882 | #REF! | #REF! | #REF! | #REF! | #REF!
311 | -- | #REF! | 9 | Bedford | 40.0418 | -78.6799 | #REF! | #REF! | #REF! | #REF! | #REF!
312 | -- | #REF! | 9 | Bedford | 40.1906 | -78.6379 | #REF! | #REF! | #REF! | #REF! | #REF!
313 | -- | #REF! | 9 | Bedford | 39.8966 | -78.672 | #REF! | #REF! | #REF! | #REF! | #REF!
314 | -- | #REF! | 9 | Bedford | 40.2541 | -78.583 | #REF! | #REF! | #REF! | #REF! | #REF!
315 | -- | #REF! | 9 | Bedford | 40.0192 | -78.2589 | #REF! | #REF! | #REF! | #REF! | #REF!
316 | -- | #REF! | 9 | Bedford | 40.0528 | -78.3252 | #REF! | #REF! | #REF! | #REF! | #REF!
317 | -- | #REF! | 9 | Bedford | 40.0978 | -78.3167 | #REF! | #REF! | #REF! | #REF! | #REF!
318 | -- | #REF! | 9 | Bedford | 40.2599 | -78.4888 | #REF! | #REF! | #REF! | #REF! | #REF!
319 | -- | #REF! | 9 | Blair | 40.5864 | -78.2457 | #REF! | #REF! | #REF! | #REF! | #REF!
320 | -- | #REF! | 9 | Blair | 40.5912 | -78.2365 | #REF! | #REF! | #REF! | #REF! | #REF!
321 | -- | #REF! | 9 | Blair | 40.616 | -78.1704 | #REF! | #REF! | #REF! | #REF! | #REF!
322 | -- | #REF! | 9 | Blair | 40.2673 | -78.4716 | #REF! | #REF! | #REF! | #REF! | #REF!
323 | -- | #REF! | 9 | Blair | 40.6893 | -78.2362 | #REF! | #REF! | #REF! | #REF! | #REF!
324 | -- | #REF! | 9 | Cambria | 40.3312 | -78.7402 | #REF! | #REF! | #REF! | #REF! | #REF!
325 | -- | #REF! | 9 | Cambria | 40.3331 | -78.7246 | #REF! | #REF! | #REF! | #REF! | #REF!
326 | -- | #REF! | 9 | Cambria | 40.6534 | -78.4967 | #REF! | #REF! | #REF! | #REF! | #REF!
327 | -- | #REF! | 9 | Fulton | 39.743 | -78.3593 | #REF! | #REF! | #REF! | #REF! | #REF!
328 | -- | #REF! | 9 | Fulton | 39.8439 | -78.1487 | #REF! | #REF! | #REF! | #REF! | #REF!
329 | -- | #REF! | 9 | Fulton | 39.854 | -78.1398 | #REF! | #REF! | #REF! | #REF! | #REF!
330 | -- | #REF! | 9 | Fulton | 39.8549 | -78.1363 | #REF! | #REF! | #REF! | #REF! | #REF!
331 | -- | #REF! | 9 | Fulton | 39.8563 | -78.0451 | #REF! | #REF! | #REF! | #REF! | #REF!
332 | -- | #REF! | 9 | Fulton | 39.9886 | -78.0596 | #REF! | #REF! | #REF! | #REF! | #REF!
333 | -- | #REF! | 9 | Fulton | 40.0275 | -78.0282 | #REF! | #REF! | #REF! | #REF! | #REF!
334 | -- | #REF! | 9 | Fulton | 39.8596 | -78.0346 | #REF! | #REF! | #REF! | #REF! | #REF!
335 | -- | #REF! | 9 | Huntingdon | 40.4912 | -78.0388 | #REF! | #REF! | #REF! | #REF! | #REF!
336 | -- | #REF! | 9 | Huntingdon | 40.5401 | -77.9603 | #REF! | #REF! | #REF! | #REF! | #REF!
337 | -- | #REF! | 9 | Huntingdon | 40.5574 | -77.9527 | #REF! | #REF! | #REF! | #REF! | #REF!
338 | -- | #REF! | 9 | Huntingdon | 40.4508 | -77.9036 | #REF! | #REF! | #REF! | #REF! | #REF!
339 | -- | #REF! | 9 | Huntingdon | 40.1826 | -78.1152 | #REF! | #REF! | #REF! | #REF! | #REF!
340 | -- | #REF! | 9 | Huntingdon | 40.6178 | -77.9684 | #REF! | #REF! | #REF! | #REF! | #REF!
341 | -- | #REF! | 9 | Huntingdon | 40.5957 | -77.862 | #REF! | #REF! | #REF! | #REF! | #REF!
342 | -- | #REF! | 9 | Huntingdon | 40.6009 | -77.8322 | #REF! | #REF! | #REF! | #REF! | #REF!
343 | -- | #REF! | 9 | Huntingdon | 40.5824 | -78.0459 | #REF! | #REF! | #REF! | #REF! | #REF!
344 | -- | #REF! | 9 | Somerset | 40.0744 | -78.8699 | #REF! | #REF! | #REF! | #REF! | #REF!
345 | -- | #REF! | 9 | Somerset | 40.075 | -78.8667 | #REF! | #REF! | #REF! | #REF! | #REF!
346 | -- | #REF! | 9 | Somerset | 39.9649 | -78.9481 | #REF! | #REF! | #REF! | #REF! | #REF!
347 | -- | #REF! | 9 | Somerset | 39.7544 | -79.3142 | #REF! | #REF! | #REF! | #REF! | #REF!
348 | -- | #REF! | 9 | Somerset | 39.7766 | -79.3107 | #REF! | #REF! | #REF! | #REF! | #REF!
349 | -- | #REF! | 9 | Somerset | 39.7817 | -79.3174 | #REF! | #REF! | #REF! | #REF! | #REF!
350 | -- | #REF! | 9 | Somerset | 40.0153 | -78.9019 | #REF! | #REF! | #REF! | #REF! | #REF!
351 | -- | #REF! | 9 | Somerset | 39.97 | -78.9029 | #REF! | #REF! | #REF! | #REF! | #REF!
352 | -- | #REF! | 9 | Somerset | 40.0705 | -78.9142 | #REF! | #REF! | #REF! | #REF! | #REF!
353 | -- | #REF! | 9 | Somerset | 39.8089 | -79.1065 | #REF! | #REF! | #REF! | #REF! | #REF!
354 | -- | #REF! | 9 | Somerset | 39.7733 | -78.7894 | #REF! | #REF! | #REF! | #REF! | #REF!
355 | -- | #REF! | 9 | Somerset | 39.8996 | -79.0119 | #REF! | #REF! | #REF! | #REF! | #REF!
356 | -- | #REF! | 9 | Somerset | 39.8461 | -79.0011 | #REF! | #REF! | #REF! | #REF! | #REF!
357 | -- | #REF! | 9 | Somerset | 40.1007 | -78.9565 | #REF! | #REF! | #REF! | #REF! | #REF!
358 | -- | #REF! | 10 | Armstrong | 40.6124 | -79.5838 | #REF! | #REF! | #REF! | #REF! | #REF!
359 | Y | #REF! | 10 | Armstrong | 40.8639 | -79.2354 | #REF! | #REF! | #REF! | #REF! | #REF!
360 | Y | #REF! | 10 | Armstrong | 40.8317 | -79.2905 | #REF! | #REF! | #REF! | #REF! | #REF!
361 | -- | #REF! | 10 | Armstrong | 40.797 | -79.3157 | #REF! | #REF! | #REF! | #REF! | #REF!
362 | -- | #REF! | 10 | Armstrong | 40.6885 | -79.4279 | #REF! | #REF! | #REF! | #REF! | #REF!
363 | -- | #REF! | 10 | Armstrong | 40.5769 | -79.5012 | #REF! | #REF! | #REF! | #REF! | #REF!
364 | -- | #REF! | 10 | Armstrong | 40.6367 | -79.5387 | #REF! | #REF! | #REF! | #REF! | #REF!
365 | -- | #REF! | 10 | Armstrong | 40.833 | -79.6244 | #REF! | #REF! | #REF! | #REF! | #REF!
366 | Y | #REF! | 10 | Armstrong | 40.8627 | -79.676 | #REF! | #REF! | #REF! | #REF! | #REF!
367 | Y | #REF! | 10 | Armstrong | 40.7994 | -79.5668 | #REF! | #REF! | #REF! | #REF! | #REF!
368 | -- | #REF! | 10 | Armstrong | 40.8086 | -79.5483 | #REF! | #REF! | #REF! | #REF! | #REF!
369 | Y | #REF! | 10 | Butler | 40.7866 | -80.145 | #REF! | #REF! | #REF! | #REF! | #REF!
370 | -- | #REF! | 10 | Butler | 40.9514 | -79.9002 | #REF! | #REF! | #REF! | #REF! | #REF!
371 | Y | #REF! | 10 | Butler | 40.8097 | -79.8375 | #REF! | 0 | #REF! | #REF! | #REF!
372 | -- | #REF! | 10 | Butler | 40.867 | -79.8292 | #REF! | #REF! | #REF! | #REF! | #REF!
373 | Y | #REF! | 10 | Butler | 40.6743 | -79.8288 | #REF! | #REF! | #REF! | #REF! | #REF!
374 | -- | #REF! | 10 | Butler | 40.8194 | -79.9457 | #REF! | #REF! | #REF! | #REF! | #REF!
375 | -- | #REF! | 10 | Butler | 40.7786 | -80.0096 | #REF! | #REF! | #REF! | #REF! | #REF!
376 | Y | #REF! | 10 | Butler | 40.7394 | -79.9596 | #REF! | #REF! | #REF! | #REF! | #REF!
377 | -- | #REF! | 10 | Butler | 40.8102 | -80.1082 | #REF! | #REF! | #REF! | #REF! | #REF!
378 | -- | #REF! | 10 | Butler | 40.9603 | -79.9313 | #REF! | #REF! | #REF! | #REF! | #REF!
379 | -- | #REF! | 10 | Butler | 40.7734 | -80.1304 | #REF! | #REF! | #REF! | #REF! | #REF!
380 | -- | #REF! | 10 | Clarion | 41.256 | -79.4723 | #REF! | #REF! | #REF! | #REF! | #REF!
381 | -- | #REF! | 10 | Clarion | 41.0299 | -79.4817 | #REF! | #REF! | #REF! | #REF! | #REF!
382 | -- | #REF! | 10 | Clarion | 41.0233 | -79.4814 | #REF! | #REF! | #REF! | #REF! | #REF!
383 | -- | #REF! | 10 | Clarion | 40.995 | -79.4857 | #REF! | #REF! | #REF! | #REF! | #REF!
384 | -- | #REF! | 10 | Clarion | 41.1131 | -79.5653 | #REF! | #REF! | #REF! | #REF! | #REF!
385 | -- | #REF! | 10 | Clarion | 41.3144 | -79.3887 | #REF! | #REF! | #REF! | #REF! | #REF!
386 | -- | #REF! | 10 | Indiana | 40.5371 | -79.3754 | #REF! | #REF! | #REF! | #REF! | #REF!
387 | -- | #REF! | 10 | Indiana | 40.6265 | -78.8533 | #REF! | #REF! | #REF! | #REF! | #REF!
388 | -- | #REF! | 10 | Indiana | 40.7287 | -79.2014 | #REF! | #REF! | #REF! | #REF! | #REF!
389 | -- | #REF! | 10 | Indiana | 40.5283 | -79.3752 | #REF! | #REF! | #REF! | #REF! | #REF!
390 | -- | #REF! | 10 | Indiana | 40.7137 | -79.1285 | #REF! | #REF! | #REF! | #REF! | #REF!
391 | -- | #REF! | 10 | Jefferson | 40.9365 | -78.9339 | #REF! | #REF! | #REF! | #REF! | #REF!
392 | -- | #REF! | 10 | Jefferson | 40.9642 | -78.8798 | #REF! | #REF! | #REF! | #REF! | #REF!
393 | -- | #REF! | 10 | Jefferson | 41.0137 | -78.8303 | #REF! | #REF! | #REF! | #REF! | #REF!
394 | -- | #REF! | 10 | Jefferson | 41.0894 | -79.1532 | #REF! | #REF! | #REF! | #REF! | #REF!
395 | -- | #REF! | 10 | Jefferson | 41.2136 | -79.1473 | #REF! | #REF! | #REF! | #REF! | #REF!
396 | -- | #REF! | 11 | Allegheny | 40.6347 | -79.9399 | #REF! | #REF! | #REF! | #REF! | #REF!
397 | -- | #REF! | 11 | Allegheny | 40.45 | -80.2504 | #REF! | #REF! | #REF! | #REF! | #REF!
398 | -- | #REF! | 11 | Allegheny | 40.4243 | -79.8594 | #REF! | #REF! | #REF! | #REF! | #REF!
399 | -- | #REF! | 11 | Allegheny | 40.2642 | -79.8786 | #REF! | #REF! | #REF! | #REF! | #REF!
402 | -- | #REF! | 11 | Allegheny | 40.1978 | -79.8883 | #REF! | #REF! | #REF! | #REF! | #REF!
403 | -- | #REF! | 11 | Allegheny | 40.2146 | -79.8275 | #REF! | #REF! | #REF! | #REF! | #REF!
404 | -- | #REF! | 11 | Allegheny | 40.625 | -79.9265 | #REF! | #REF! | #REF! | #REF! | #REF!
405 | Y | #REF! | 11 | Allegheny | 40.6069 | -79.8913 | #REF! | #REF! | #REF! | #REF! | #REF!
406 | -- | #REF! | 11 | Allegheny | 40.347 | -80.1695 | #REF! | #REF! | #REF! | #REF! | #REF!
407 | -- | #REF! | 11 | Allegheny | 40.5314 | -79.8484 | #REF! | #REF! | #REF! | #REF! | #REF!
408 | -- | #REF! | 11 | Allegheny | 40.5816 | -79.7787 | #REF! | #REF! | #REF! | #REF! | #REF!
409 | -- | #REF! | 11 | Allegheny | 40.5864 | -79.7767 | #REF! | #REF! | #REF! | #REF! | #REF!
410 | -- | #REF! | 11 | Allegheny | 40.5495 | -79.9145 | #REF! | #REF! | #REF! | #REF! | #REF!
411 | -- | #REF! | 11 | Allegheny | 40.5355 | -79.8478 | #REF! | #REF! | #REF! | #REF! | #REF!
412 | Y | #REF! | 11 | Allegheny | 40.5377 | -79.851 | #REF! | #REF! | #REF! | #REF! | #REF!
413 | -- | #REF! | 11 | Allegheny | 40.5812 | -79.9071 | #REF! | #REF! | #REF! | #REF! | #REF!
414 | Y | #REF! | 11 | Allegheny | 40.5206 | -79.9382 | #REF! | #REF! | #REF! | #REF! | #REF!
415 | Y | #REF! | 11 | Allegheny | 40.523 | -79.936 | #REF! | #REF! | #REF! | #REF! | #REF!
416 | Y | #REF! | 11 | Allegheny | 40.5273 | -79.927 | #REF! | #REF! | #REF! | #REF! | #REF!
417 | -- | #REF! | 11 | Allegheny | 40.5917 | -79.8217 | #REF! | #REF! | #REF! | #REF! | #REF!
418 | Y | #REF! | 11 | Allegheny | 40.5745 | -79.8227 | #REF! | #REF! | #REF! | #REF! | #REF!
419 | Y | #REF! | 11 | Allegheny | 40.652 | -79.7938 | #REF! | #REF! | #REF! | #REF! | #REF!
420 | Y | #REF! | 11 | Allegheny | 40.6322 | -79.7613 | #REF! | #REF! | #REF! | #REF! | #REF!
421 | -- | #REF! | 11 | Allegheny | 40.2381 | -79.9463 | #REF! | #REF! | #REF! | #REF! | #REF!
422 | Y | #REF! | 11 | Allegheny | 40.2516 | -79.9121 | #REF! | #REF! | #REF! | #REF! | #REF!
423 | -- | #REF! | 11 | Allegheny | 40.2784 | -79.8559 | #REF! | #REF! | #REF! | #REF! | #REF!
424 | -- | #REF! | 11 | Allegheny | 40.277 | -79.869 | #REF! | #REF! | #REF! | #REF! | #REF!
425 | -- | #REF! | 11 | Allegheny | 40.2726 | -79.7982 | #REF! | #REF! | #REF! | #REF! | #REF!
426 | -- | #REF! | 11 | Allegheny | 40.275 | -79.7993 | #REF! | #REF! | #REF! | #REF! | #REF!
427 | -- | #REF! | 11 | Allegheny | 40.3083 | -79.8335 | #REF! | #REF! | #REF! | #REF! | #REF!
428 | -- | #REF! | 11 | Allegheny | 40.3309 | -79.7877 | #REF! | #REF! | #REF! | #REF! | #REF!
429 | -- | #REF! | 11 | Allegheny | 40.351 | -79.8961 | #REF! | #REF! | #REF! | #REF! | #REF!
430 | -- | #REF! | 11 | Allegheny | 40.352 | -79.9645 | #REF! | #REF! | #REF! | #REF! | #REF!
431 | Y | #REF! | 11 | Allegheny | 40.3667 | -79.9493 | #REF! | #REF! | #REF! | #REF! | #REF!
432 | -- | #REF! | 11 | Allegheny | 40.3682 | -79.9476 | #REF! | #REF! | #REF! | #REF! | #REF!
433 | Y | #REF! | 11 | Allegheny | 40.4258 | -79.808 | #REF! | #REF! | #REF! | #REF! | #REF!
434 | -- | #REF! | 11 | Allegheny | 40.4922 | -79.7436 | #REF! | #REF! | #REF! | #REF! | #REF!
435 | -- | #REF! | 11 | Allegheny | 40.5441 | -79.7605 | #REF! | #REF! | #REF! | #REF! | #REF!
436 | Y | #REF! | 11 | Allegheny | 40.3278 | -79.8165 | #REF! | #REF! | #REF! | #REF! | #REF!
437 | -- | #REF! | 11 | Allegheny | 40.3402 | -80.0791 | #REF! | #REF! | #REF! | #REF! | #REF!
438 | Y | #REF! | 11 | Allegheny | 40.2783 | -79.9773 | #REF! | #REF! | #REF! | #REF! | #REF!
439 | -- | #REF! | 11 | Allegheny | 40.2661 | -79.9305 | #REF! | #REF! | #REF! | #REF! | #REF!
440 | -- | #REF! | 11 | Allegheny | 40.2685 | -79.9259 | #REF! | #REF! | #REF! | #REF! | #REF!
441 | -- | #REF! | 11 | Allegheny | 40.4113 | -80.1556 | #REF! | #REF! | #REF! | #REF! | #REF!
442 | -- | #REF! | 11 | Allegheny | 40.3896 | -79.9556 | #REF! | #REF! | #REF! | #REF! | #REF!
443 | -- | #REF! | 11 | Allegheny | 40.3895 | -79.941 | #REF! | #REF! | #REF! | #REF! | #REF!
444 | -- | #REF! | 11 | Allegheny | 40.3953 | -80.2586 | #REF! | #REF! | #REF! | #REF! | #REF!
445 | -- | #REF! | 11 | Allegheny | 40.4014 | -80.2449 | #REF! | #REF! | #REF! | #REF! | #REF!
446 | Y | #REF! | 11 | Allegheny | 40.5209 | -79.9658 | #REF! | #REF! | #REF! | #REF! | #REF!
447 | -- | #REF! | 11 | Allegheny | 40.5816 | -80.1483 | #REF! | #REF! | #REF! | #REF! | #REF!
448 | -- | #REF! | 11 | Allegheny | 40.5953 | -80.1949 | #REF! | #REF! | #REF! | #REF! | #REF!
449 | -- | #REF! | 11 | Allegheny | 40.6087 | -80.1593 | #REF! | #REF! | #REF! | #REF! | #REF!
450 | -- | #REF! | 11 | Allegheny | 40.6105 | -80.1539 | #REF! | #REF! | #REF! | #REF! | #REF!
451 | -- | #REF! | 11 | Beaver | 40.6602 | -80.4773 | #REF! | #REF! | #REF! | #REF! | #REF!
452 | -- | #REF! | 11 | Beaver | 40.784 | -80.4542 | #REF! | #REF! | #REF! | #REF! | #REF!
453 | -- | #REF! | 11 | Beaver | 40.8218 | -80.254 | #REF! | #REF! | #REF! | #REF! | #REF!
454 | -- | #REF! | 11 | Beaver | 40.7723 | -80.2369 | #REF! | #REF! | #REF! | #REF! | #REF!
455 | -- | #REF! | 11 | Beaver | 40.6718 | -80.294 | #REF! | #REF! | #REF! | #REF! | #REF!
456 | -- | #REF! | 11 | Beaver | 40.5944 | -80.28 | #REF! | #REF! | #REF! | #REF! | #REF!
457 | -- | #REF! | 11 | Beaver | 40.5417 | -80.3008 | #REF! | #REF! | #REF! | #REF! | #REF!
458 | -- | #REF! | 11 | Beaver | 40.6116 | -80.4874 | #REF! | #REF! | #REF! | #REF! | #REF!
459 | -- | #REF! | 11 | Beaver | 40.6224 | -80.4971 | #REF! | #REF! | #REF! | #REF! | #REF!
460 | -- | #REF! | 11 | Beaver | 40.7235 | -80.367 | #REF! | #REF! | #REF! | #REF! | #REF!
461 | -- | #REF! | 11 | Beaver | 40.7245 | -80.3626 | #REF! | #REF! | #REF! | #REF! | #REF!
462 | -- | #REF! | 11 | Beaver | 40.7325 | -80.3365 | #REF! | #REF! | #REF! | #REF! | #REF!
463 | -- | #REF! | 11 | Beaver | 40.7468 | -80.3856 | #REF! | #REF! | #REF! | #REF! | #REF!
464 | -- | #REF! | 11 | Beaver | 40.6606 | -80.4837 | #REF! | #REF! | #REF! | #REF! | #REF!
465 | -- | #REF! | 11 | Lawrence | 41.1081 | -80.4759 | #REF! | #REF! | #REF! | #REF! | #REF!
466 | -- | #REF! | 11 | Lawrence | 41.1062 | -80.4504 | #REF! | #REF! | #REF! | #REF! | #REF!
467 | -- | #REF! | 11 | Lawrence | 41.1211 | -80.342 | #REF! | #REF! | #REF! | #REF! | #REF!
468 | -- | #REF! | 11 | Lawrence | 41.0081 | -80.4686 | #REF! | #REF! | #REF! | #REF! | #REF!
469 | -- | #REF! | 11 | Lawrence | 41.0251 | -80.4328 | #REF! | #REF! | #REF! | #REF! | #REF!
470 | -- | #REF! | 11 | Lawrence | 41.0894 | -80.289 | #REF! | #REF! | #REF! | #REF! | #REF!
471 | -- | #REF! | 11 | Lawrence | 41.0895 | -80.3154 | #REF! | #REF! | #REF! | #REF! | #REF!
472 | -- | #REF! | 11 | Lawrence | 41.1063 | -80.3292 | #REF! | #REF! | #REF! | #REF! | #REF!
473 | -- | #REF! | 11 | Lawrence | 41.0944 | -80.3191 | #REF! | #REF! | #REF! | #REF! | #REF!
474 | -- | #REF! | 11 | Lawrence | 41.0892 | -80.2875 | #REF! | #REF! | #REF! | #REF! | #REF!
475 | -- | #REF! | 11 | Lawrence | 40.9918 | -80.2619 | #REF! | #REF! | #REF! | #REF! | #REF!
476 | -- | #REF! | 11 | Lawrence | 40.9941 | -80.2446 | #REF! | #REF! | #REF! | #REF! | #REF!
477 | -- | #REF! | 11 | Lawrence | 40.9363 | -80.3418 | #REF! | #REF! | #REF! | #REF! | #REF!
478 | -- | #REF! | 11 | Lawrence | 40.9379 | -80.3513 | #REF! | #REF! | #REF! | #REF! | #REF!
479 | -- | #REF! | 11 | Lawrence | 40.9714 | -80.4936 | #REF! | #REF! | #REF! | #REF! | #REF!
480 | -- | #REF! | 11 | Lawrence | 40.9684 | -80.5192 | #REF! | #REF! | #REF! | #REF! | #REF!
481 | -- | #REF! | 11 | Lawrence | 40.9214 | -80.4775 | #REF! | #REF! | #REF! | #REF! | #REF!
482 | -- | #REF! | 11 | Lawrence | 40.9376 | -80.3662 | #REF! | #REF! | #REF! | #REF! | #REF!
483 | -- | #REF! | 12 | Fayette | 39.9603 | -79.8778 | #REF! | #REF! | #REF! | #REF! | #REF!
484 | -- | #REF! | 12 | Fayette | 39.7661 | -79.6245 | #REF! | #REF! | #REF! | #REF! | #REF!
485 | -- | #REF! | 12 | Fayette | 39.9514 | -79.4421 | #REF! | #REF! | #REF! | #REF! | #REF!
486 | -- | #REF! | 12 | Fayette | 39.9931 | -79.4141 | #REF! | #REF! | #REF! | #REF! | #REF!
487 | -- | #REF! | 12 | Fayette | 40.0681 | -79.3992 | #REF! | #REF! | #REF! | #REF! | #REF!
488 | -- | #REF! | 12 | Fayette | 39.9522 | -79.73 | #REF! | #REF! | #REF! | #REF! | #REF!
489 | -- | #REF! | 12 | Fayette | 40.0264 | -79.5896 | #REF! | #REF! | #REF! | #REF! | #REF!
490 | -- | #REF! | 12 | Fayette | 40.0518 | -79.6059 | #REF! | #REF! | #REF! | #REF! | #REF!
491 | -- | #REF! | 12 | Fayette | 40.0531 | -79.6047 | #REF! | #REF! | #REF! | #REF! | #REF!
492 | -- | #REF! | 12 | Fayette | 39.9512 | -79.7354 | #REF! | #REF! | #REF! | #REF! | #REF!
493 | -- | #REF! | 12 | Fayette | 40.0549 | -79.555 | #REF! | #REF! | #REF! | #REF! | #REF!
494 | -- | #REF! | 12 | Fayette | 40.0871 | -79.393 | #REF! | #REF! | #REF! | #REF! | #REF!
495 | -- | #REF! | 12 | Fayette | 40.0434 | -79.5299 | #REF! | #REF! | #REF! | #REF! | #REF!
496 | -- | #REF! | 12 | Fayette | 39.9448 | -79.5793 | #REF! | #REF! | #REF! | #REF! | #REF!
497 | -- | #REF! | 12 | Fayette | 40.0751 | -79.358 | #REF! | #REF! | #REF! | #REF! | #REF!
498 | -- | #REF! | 12 | Fayette | 40.0744 | -79.3556 | #REF! | #REF! | #REF! | #REF! | #REF!
499 | -- | #REF! | 12 | Fayette | 39.8234 | -79.5687 | #REF! | #REF! | #REF! | #REF! | #REF!
500 | -- | #REF! | 12 | Fayette | 39.8401 | -79.8968 | #REF! | #REF! | #REF! | #REF! | #REF!
501 | -- | #REF! | 12 | Fayette | 39.8992 | -79.898 | #REF! | #REF! | #REF! | #REF! | #REF!
502 | -- | #REF! | 12 | Fayette | 39.8926 | -79.914 | #REF! | #REF! | #REF! | #REF! | #REF!
503 | -- | #REF! | 12 | Fayette | 40.1092 | -79.8319 | #REF! | #REF! | #REF! | #REF! | #REF!
504 | -- | #REF! | 12 | Greene | 39.8548 | -80.3139 | #REF! | #REF! | #REF! | #REF! | #REF!
505 | -- | #REF! | 12 | Greene | 39.9689 | -80.317 | #REF! | #REF! | #REF! | #REF! | #REF!
506 | -- | #REF! | 12 | Greene | 39.9048 | -80.1507 | #REF! | #REF! | #REF! | #REF! | #REF!
507 | -- | #REF! | 12 | Greene | 39.9381 | -80.0456 | #REF! | #REF! | #REF! | #REF! | #REF!
508 | -- | #REF! | 12 | Greene | 39.9728 | -80.0461 | #REF! | #REF! | #REF! | #REF! | #REF!
509 | -- | #REF! | 12 | Greene | 39.9619 | -80.0536 | #REF! | #REF! | #REF! | #REF! | #REF!
510 | -- | #REF! | 12 | Greene | 39.8937 | -80.1789 | #REF! | #REF! | #REF! | #REF! | #REF!
511 | -- | #REF! | 12 | Greene | 39.8727 | -80.1211 | #REF! | #REF! | #REF! | #REF! | #REF!
512 | -- | #REF! | 12 | Greene | 39.8048 | -79.9493 | #REF! | #REF! | #REF! | #REF! | #REF!
513 | -- | #REF! | 12 | Greene | 39.8939 | -80.1591 | #REF! | #REF! | #REF! | #REF! | #REF!
514 | -- | #REF! | 12 | Greene | 39.8905 | -80.1222 | #REF! | #REF! | #REF! | #REF! | #REF!
515 | -- | #REF! | 12 | Greene | 39.723 | -80.3497 | #REF! | #REF! | #REF! | #REF! | #REF!
516 | -- | #REF! | 12 | Greene | 39.7715 | -80.2717 | #REF! | #REF! | #REF! | #REF! | #REF!
517 | -- | #REF! | 12 | Washington | 40.024 | -80.2053 | #REF! | #REF! | #REF! | #REF! | #REF!
518 | -- | #REF! | 12 | Washington | 40.321 | -80.2307 | #REF! | #REF! | #REF! | #REF! | #REF!
519 | -- | #REF! | 12 | Washington | 40.1324 | -79.8909 | #REF! | #REF! | #REF! | #REF! | #REF!
520 | -- | #REF! | 12 | Washington | 40.2504 | -80.0035 | #REF! | #REF! | #REF! | #REF! | #REF!
521 | -- | #REF! | 12 | Washington | 40.0344 | -80.2664 | #REF! | #REF! | #REF! | #REF! | #REF!
522 | -- | #REF! | 12 | Washington | 40.1954 | -80.4481 | #REF! | #REF! | #REF! | #REF! | #REF!
523 | -- | #REF! | 12 | Washington | 40.0596 | -79.9682 | #REF! | #REF! | #REF! | #REF! | #REF!
524 | -- | #REF! | 12 | Washington | 40.1804 | -79.9387 | #REF! | #REF! | #REF! | #REF! | #REF!
525 | -- | #REF! | 12 | Washington | 40.1717 | -80.1749 | #REF! | #REF! | #REF! | #REF! | #REF!
526 | -- | #REF! | 12 | Washington | 40.0394 | -80.2224 | #REF! | #REF! | #REF! | #REF! | #REF!
527 | -- | #REF! | 12 | Washington | 40.0808 | -80.1777 | #REF! | #REF! | #REF! | #REF! | #REF!
528 | -- | #REF! | 12 | Washington | 40.0429 | -80.0907 | #REF! | #REF! | #REF! | #REF! | #REF!
529 | -- | #REF! | 12 | Washington | 40.1273 | -79.9895 | #REF! | #REF! | #REF! | #REF! | #REF!
530 | -- | #REF! | 12 | Washington | 40.1481 | -79.9792 | #REF! | #REF! | #REF! | #REF! | #REF!
531 | -- | #REF! | 12 | Washington | 40.0634 | -79.982 | #REF! | #REF! | #REF! | #REF! | #REF!
532 | -- | #REF! | 12 | Washington | 40.0563 | -79.9628 | #REF! | #REF! | #REF! | #REF! | #REF!
533 | -- | #REF! | 12 | Washington | 40.0523 | -79.9361 | #REF! | #REF! | #REF! | #REF! | #REF!
534 | -- | #REF! | 12 | Washington | 40.1311 | -79.9255 | #REF! | #REF! | #REF! | #REF! | #REF!
535 | -- | #REF! | 12 | Washington | 40.0024 | -80.4726 | #REF! | #REF! | #REF! | #REF! | #REF!
536 | -- | #REF! | 12 | Washington | 40.4654 | -80.4784 | #REF! | #REF! | #REF! | #REF! | #REF!
537 | -- | #REF! | 12 | Washington | 40.321 | -80.4418 | #REF! | #REF! | #REF! | #REF! | #REF!
538 | -- | #REF! | 12 | Washington | 40.3099 | -80.4451 | #REF! | #REF! | #REF! | #REF! | #REF!
539 | -- | #REF! | 12 | Washington | 40.3266 | -80.2548 | #REF! | #REF! | #REF! | #REF! | #REF!
540 | -- | #REF! | 12 | Washington | 40.1984 | -80.4077 | #REF! | #REF! | #REF! | #REF! | #REF!
541 | -- | #REF! | 12 | Westmoreland | 40.143 | -79.4865 | #REF! | #REF! | #REF! | #REF! | #REF!
542 | Y | #REF! | 12 | Westmoreland | 40.5714 | -79.7495 | #REF! | #REF! | #REF! | #REF! | #REF!
543 | -- | #REF! | 12 | Westmoreland | 40.2804 | -79.6488 | #REF! | #REF! | #REF! | #REF! | #REF!
544 | Y | #REF! | 12 | Westmoreland | 40.2855 | -79.2348 | #REF! | #REF! | #REF! | #REF! | #REF!
545 | Y | #REF! | 12 | Westmoreland | 40.5188 | -79.6934 | #REF! | #REF! | #REF! | #REF! | #REF!
546 | Y | #REF! | 12 | Westmoreland | 40.1957 | -79.2407 | #REF! | #REF! | #REF! | #REF! | #REF!
547 | Y | #REF! | 12 | Westmoreland | 40.2189 | -79.2191 | #REF! | #REF! | #REF! | #REF! | #REF!
548 | -- | #REF! | 12 | Westmoreland | 40.2513 | -79.2218 | #REF! | #REF! | #REF! | #REF! | #REF!
549 | Y | #REF! | 12 | Westmoreland | 40.262 | -79.1966 | #REF! | #REF! | #REF! | #REF! | #REF!
550 | -- | #REF! | 12 | Westmoreland | 40.2522 | -79.3904 | #REF! | #REF! | #REF! | #REF! | #REF!
551 | -- | #REF! | 12 | Westmoreland | 40.3219 | -79.1307 | #REF! | #REF! | #REF! | #REF! | #REF!
552 | Y | #REF! | 12 | Westmoreland | 40.2604 | -79.2015 | #REF! | #REF! | #REF! | #REF! | #REF!
553 | -- | #REF! | 12 | Westmoreland | 40.2753 | -79.2044 | #REF! | #REF! | #REF! | #REF! | #REF!
554 | Y | #REF! | 12 | Westmoreland | 40.4404 | -79.5439 | #REF! | #REF! | #REF! | #REF! | #REF!
555 | -- | #REF! | 12 | Westmoreland | 40.2197 | -79.5095 | #REF! | #REF! | #REF! | #REF! | #REF!
556 | Y | #REF! | 12 | Westmoreland | 40.2869 | -79.5109 | #REF! | #REF! | #REF! | #REF! | #REF!
557 | -- | #REF! | 12 | Westmoreland | 40.2137 | -79.4974 | #REF! | #REF! | #REF! | #REF! | #REF!
558 | -- | #REF! | 12 | Westmoreland | 40.3302 | -79.6148 | #REF! | #REF! | #REF! | #REF! | #REF!
559 | Y | #REF! | 12 | Westmoreland | 40.4233 | -79.6367 | #REF! | #REF! | #REF! | #REF! | #REF!
560 | -- | #REF! | 12 | Westmoreland | 40.1812 | -79.8058 | #REF! | #REF! | #REF! | #REF! | #REF!
561 | -- | #REF! | 12 | Fayette | 39.9017 | -79.8937 | #REF! | #REF! | #REF! | #REF! | #REF!
562 | -- | #REF! | 12 | Fayette | 39.8982 | -79.8993 | #REF! | #REF! | #REF! | #REF! | #REF!
563 | -- | #REF! | 12 | Fayette | 39.8931 | -79.9153 | #REF! | #REF! | #REF! | #REF! | #REF!
564 | -- | #REF! | 8 | Cumberland | 40.212 | -76.9072 | #REF! | #REF! | #REF! | #REF! | #REF!

## 1st 30 Bridges Summary (hidden)
| JV # | Region | Total Facility Qty | Prior | Restrictive | Concurrent | Coordinated | Not Affected | Incorporated | Overhead | Underground | Require Stakeout Only | Require Stakeout and Clearing | Need Stakeout, Clearing, and Earthwork
1 | 1 | East | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | X
2 | 2 | East | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
3 | 3 | West | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Final
4 | 4 | West | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
5 | 5 | West | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | X |  | Not Final
6 | 6 | East | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  | Not Final
7 | 7 | Central | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 |  | X
8 | 8 | West | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | X |  | Not Final
9 | 9 | East | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | X
10 | 10 | Central | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
11 | 11 | East | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 12 | East | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | X
13 | 13 | East | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
14 | 14 | West | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | X |  | Not Final
15 | 15 | West | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | X |  | Not Final
16 | 16 | East | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  |  | Not Final
17 | 17 | Central | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | X
18 | 18 | Central | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | X
19 | 19 | East | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
20 | 20 | West | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | X |  |  | Not Final
21 | 21 | East | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
22 | 22 | Central | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
23 | 23 | Central | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | X
24 | 24 | Central | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | X
25 | 25 | Central | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | X
26 | 26 | Central | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | X
27 | 27 | East | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
28 | 28 | West | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Not Final
29 | 29 | West | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
30 | 30 | West | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 3 | 12 | 0

## Utility Issues Log (hidden)
Entry |  | Entry | [10 empty] | Entry | Entry | Entry | Entry
Column |  | Column | [10 empty] | Column | Column | Column | Column
↓ |  | ↓ | [10 empty] | ↓ | ↓ | ↓ | ↓
Issue Number (IN-JV#-Letter Des.) | Early Completion (Y/N) | JV # | Bridge Key # | MPMS # | BMS # | District | County | Location | Feature Carried | Feature Intersected | PWKP Region | RBR RFC Month (yyyy/mm/dd) | Issue Description | Issue Date (yyyy/mm/dd) | Issue Resolution | Issue Resolution Date (yyyy/mm/dd)
IN139a | -- | 139 | 20820 | 96689 | 35401900200731 | 4 | Lackawanna | S ABINGTON TP OVER I-81 | SR 4019 EDELLA RD | SR 0081 I-81 | No Entry | No Entry | Gravity SS connected to bridge. Involved process for utility owner to design/relocate. PennDOT wishes them to get started and wants us to release authorization for them to begin utility relocation design. PennDOT also notes an adjacent Turnpike Bridge is scheduled for replacement and would like to sync construction dates to minimize detour impacts to public. | 2015-01-14
| No Entry |  | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry
| No Entry |  | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry
| No Entry |  | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry
| No Entry |  | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry
| No Entry |  | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry
| No Entry |  | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry
| No Entry |  | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry
| No Entry |  | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry
| No Entry |  | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry | No Entry

## Old Sheet (hidden)
UTILITIES01 |  | Early Completion Bridges - 2015 |  |  |  | 87 |  | EACH | 8/26 - 1397 changed to REB |  | OVER ROADWAY | [30 empty] | 10 | EACH | [11 empty] | IF "UNKNOWN", RANK AS 0.25 | [99 empty] | IF "UNKNOWN", RANK AS 0.25 | [53 empty] | IF "UNKNOWN", RANK AS 0.25
|  | Remaining Bridges - 2016 through 2018 |  |  |  | 471 |  | EACH | 9/16 - 505 changed to REB |  | OVER RAILROAD REQUIRING FLAGMEN | [30 empty] | 4 | EACH | [11 empty] | IF "POSSIBLE", RANK AS 0.50 | [99 empty] | IF "POSSIBLE", RANK AS 0.50 | [53 empty] | IF "POSSIBLE", RANK AS 0.50
[6 empty] | ~~~~~~~~ |  |  |  |  | OVER ABANDONED RAILROAD | [30 empty] | 1 | EACH | [11 empty] | IF "PROBABLE", RANK AS 0.75 | [99 empty] | IF "PROBABLE", RANK AS 0.75 | [53 empty] | IF "PROBABLE", RANK AS 0.75
[6 empty] | 558 |  | EACH |  |  | OVER WATERWAYS | [30 empty] | 544 | EACH
~~~~~~~
[11 empty] | TOTAL BRIDGES AS OF 06/18/14 | [30 empty] | 559 | EACH
|  |  |  | PHASED - 2015 ECB's |  | 39 |  | EACH | 45094001400882 |  | R = REMOVED FROM PROPOSAL BY PADOT | [30 empty] | -5 | EACH
|  |  |  | PHASED - REMAINING BRIDGES |  | 159 |  | EACH |  |  | A - ADDED TO PROPOSAL BY PADOT | [30 empty] | 4 | EACH | [198 empty] | Consent
[6 empty] | ~~~~~~~~~ | [235 empty] | to Enter
|  |  |  | PHASED - TOTAL |  | 198 |  | EACH |  |  | ADJACENT RAILROAD REQUIRING FLAGMEN | [30 empty] | 6 | EACH | [7 empty] | RAILROAD |  |  |  | PennDOT | JV | JV |  | JV | [17 empty] | ROW |  |  | PennDOT | JV | JV |  | JV | [17 empty] | ROW |  |  | PennDOT | JV | JV |  | JV | [17 empty] | ROW |  |  | PennDOT | JV | JV |  | JV | [17 empty] | ROW |  |  | PennDOT | JV | JV |  | JV |  |  |  | ROW |  |  | PennDOT | JV | JV |  | JV |  |  |  | ROW |  |  | PennDOT | JV | JV |  | JV | [17 empty] | ROW | [34 empty] | ROW |  |  | Conflict Criteria |  | Conflict Totals |  |  | Agreement
[56 empty] | field | field |  | field | [17 empty] | Nearest |  |  |  | field | field |  | field | [17 empty] | Nearest |  |  |  | field | field |  | field | [17 empty] | Nearest |  |  |  | field | field |  | field | [17 empty] | Nearest |  |  |  | field | field |  | field |  |  |  | Nearest |  |  |  | field | field |  | field |  |  |  | Nearest |  |  |  | field | field |  | field | [17 empty] | Nearest | [6 empty] | No. of | [32 empty] | For Sorting |  |  | required
|  |  |  | TBD AS OF 06/03/14 |  | 32 |  | EACH | [34 empty] | PennDOT | JV | JV | PennDOT | PennDOT | JV | JV | [6 empty] | inspection | inspection |  | inspection | [17 empty] | Bridge |  |  |  | inspection | inspection |  | inspection | [17 empty] | Bridge |  |  |  | inspection | inspection |  | inspection | [17 empty] | Bridge |  |  |  | inspection | inspection |  | inspection | [17 empty] | Bridge |  |  |  | inspection | inspection |  | inspection |  |  |  | Bridge |  |  |  | inspection | inspection |  | inspection |  |  |  | Bridge |  |  |  | inspection | inspection |  | inspection | [17 empty] | Bridge |  |  | Structure | Structure | Structure | Structure | Possible | No. of | Total | No. of |  |  | Total |  |  | No. of |  | Total |  |  | No. of |  | Total |  |  | No. of |  | Total | [5 empty] | Centerline | Nearest |  |  | Nearest |  |  |  |  | for
[77 empty] | Extremity to | [24 empty] | Extremity to | [24 empty] | Extremity to | [24 empty] | Extremity to | [10 empty] | Extremity to | [10 empty] | Extremity to | [24 empty] | Extremity to |  |  | Attached | Attached | Attached | Attached | De-energize | Relocate | Relocate | Relocate |  | Company | Relocate |  |  | Relocate | Company | Relocate |  |  | Relocate | Company | Relocate |  |  | Relocate | Company | Relocate |  |  | Total |  |  | of Bridge | Bridge |  |  | Bridge | End of Abutment |  |  |  | Temporary
|  | 2 WEEK SCHEDULE |  |  | STRUCTURE ATTACHED UTILITY | [44 empty] | Effected |  | Duration |  | Due | No. of | No. of |  | Company |  | Total |  |  | 2" | 3" | 4" | 5" | 6" | 8" | 10" | 12" | 14" | 16" | 18" | 20" | 24" | Unknown | Pole/Line | In or Out | In or Out | No. of | No. of |  | Company |  | Total |  |  | 2" | 3" | 4" | 5" | 6" | 8" | 10" | 12" | 14" | 16" | 18" | 20" | 24" | Unknown | Pole/Line | In or Out | In or Out | No. of | No. of |  | Company |  | Total |  |  | 2" | 3" | 4" | 5" | 6" | 8" | 10" | 12" | 14" | 16" | 18" | 20" | 24" | Unknown | Pole/Line | In or Out | In or Out | No. of | No. of |  | Company |  | Total |  |  | 2" | 3" | 4" | 5" | 6" | 8" | 10" | 12" | 14" | 16" | 18" | 20" | 24" | Unknown | Pole/Line | In or Out | In or Out | No. of | No. of |  | Company |  | Total |  |  | Pole/Line | In or Out | In or Out | No. of | No. of |  | Company |  | Total |  |  | Pole/Line | In or Out | In or Out | No. of | No. of |  | Company |  | Total |  |  | 2" | 3" | 4" | 5" | 6" | 8" | 10" | 12" | 14" | 16" | 18" | 20" | 24" | Unknown | Pole/Line | In or Out | In or Out |  | Temporary |  |  | in lieu |  |  |  |  | Owner | Permanent |  |  | Permanent | Owner | Permanent |  |  | Permanent | Owner | Permanent |  |  | Permanent | Owner | Permanent |  |  | No. of |  |  | to | Extremity to |  |  | Extremity to | to | Bridge Total | Bridge Total | Underground & Poles | Relocation | Grand Total Cost |  |  | Grand Total Cost
[43 empty] | Existing | assumed additional | New Proposed | Existing | Proposed | assumed additional | New Proposed | Land |  | of | Total | Diligence | Relocate | Relocate | Diameter | Owner |  | Relocate | [15 empty] | Dia. | offset | of ROW Calc | of ROW | Relocate | Relocate | Diameter | Owner |  | Relocate | [15 empty] | Dia. | offset | of ROW Calc | of ROW | Relocate | Relocate | Diameter | Owner |  | Relocate | [15 empty] | Dia. | offset | of ROW Calc | of ROW | Relocate | Relocate | Diameter | Owner |  | Relocate | [15 empty] | Dia. | offset | of ROW Calc | of ROW | Relocate | Relocate | Diameter | Owner |  | Relocate |  |  | offset | of ROW Calc | of ROW | Relocate | Relocate | Diameter | Owner |  | Relocate |  |  | offset | of ROW Calc | of ROW | Relocate | Relocate | Diameter | Owner | Underground | Relocate | [15 empty] | Dia. | offset | of ROW Calc | of ROW |  | Support | Temporary |  | of | Aerial | Aerial | Aerial | Aerial | Aerial | Aerial |  |  | Aerial | Aerial | Aerial |  |  | Aerial | Aerial | Aerial |  |  | Aerial | Aerial | Aerial |  |  | Relocate |  |  | ROW | Pole/Line | IN OR OUT | IN OR OUT | Pole/Line | Pole/Line | Underground | Aerial Pole | Grand Total | Aerial | Underground | Approx. Crew Cost | Underground | Aerial | Approx. Crew Cost | Aerial
| Early | [41 empty] | Bridge | lengthing | Bridge | Bridge | Bridge Width | width for parapet | Bridge Width | Area | No. of | Railroad | Railroad | Test | Underground | Underground | Underground | Underground | Underground | Underground | Avg. Unit Price | Total Cost | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Avg. Unit Cost | Total Cost | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground |  |  | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground |  |  | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground |  |  | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground |  |  | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground |  |  | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Relocate | across | Support | Relocate | Aerial |  |  | Electric | Electric | Electric | Electric | Avg. Unit Cost | Total Cost | Telephone | Telephone | Telephone | Avg. Unit Cost | Total Cost | TV | TV | TV | Avg. Unit Cost | Total Cost | Fiber Optic | Fiber Optic | Fiber Optic | Avg. Unit Cost | Total Cost | Aerial | Avg. Unit Cost | Total Cost | offset | offset | OF ROW CALC | OF ROW | offset | Distance | Conflicts | Conflicts | Conflicts |  | Conflicts | Per Day | # Schedule Days | Conflicts | Per Day | # Schedule Days | HDR Notes | Notes by Walsh
Count | Completion | JV # | MPMS # | Bridge | BMS # | District | PWKP Region | County | Location |  | Feature Intersected |  | Br Length | New | Width-JV | New | Type | Location | ROW Plan Submitted | Util Clearance Report | Conditional D-419 Date | Final D-419 Date | As-Builts | Permit Obtained | I/S or O/S ROW | Util = Prop Interest? | Reimbursable? | Size | OH-UG | Type Mat'l | Conflict Y-N-I-PIP | Utility Owner | Owner Number | Req'd Reloc Date | Relocation Length | Unit Cost | Poles-MH's-Valves | Unit Cost | Factor | Total Cost | Remarks |  | Length | of Bridge | Length | Width | Curb to Curb | & buffer | Curb to Curb | Length | Railroad | flagmen | flagmen | Pits | Water | Water | Water | Water | Water | Water |  |  | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary |  |  | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Gas | Gas | Gas | Gas | Gas | Gas | Avg. Unit Cost | Total Cost | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Oil | Oil | Oil | Oil | Oil | Oil | Avg. Unit Cost | Total Cost | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Fiber Optic | Fiber Optic | Fiber Optic | Fiber Optic | Fiber Optic | Fiber Optic | Avg. Unit Cost | Total Cost | Fiber Optic | Fiber Optic | Fiber Optic | Electric | Electric | Electric | Electric | Electric | Electric | Avg. Unit Cost | Total Cost | Electric | Electric | Electric | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Avg. Unit Cost | Total Cost | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Utility | waterway |  | Utility | Relocation |  |  |  | Voltage | [19 empty] | Pole | [8 empty] | (Includes | [10 empty] | As of 5/29/14
Count | (Y / N) | JV # |  | Key | BMS # | District |  | County | Location | Road Carried | Feature Intersected | Pa One Call Serial No. | Exist | New | Exist | New |  |  | Y/N | Y/N |  |  | Y/N | Y/N | Y/N | Y/N | Y/N | [14 empty] | Functional Class | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | flagmen | (SHFT) | (HOURS) | (EACH) | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (FEET) | (FEET) |  | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (FEET) | (FEET) |  | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (FEET) | (FEET) |  | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (FEET) | (FEET) |  | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (FEET) | (FEET) |  | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (FEET) | (FEET) |  | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (FEET) | (FEET) |  | (Type - i.e. waterline) | (Y = 1, N = 0) | Required | (LF) | (EACH) | (Y = 1, N = 0) | (LF) | (EACH) | (KW) | Name | (LF) |  |  | (EACH) | Name | (LF) |  |  | (EACH) | Name | (LF) |  |  | (EACH) | Name | (LF) |  |  | (EACH) |  |  | (FEET) | (FEET) | (FEET) |  | (FEET) | (FEET) | Attachments) |  |  | (Y = 1, N = 0)
1 | Y | 405 | 63324 | 1339 | 02091003000000 | 11 |  | Allegheny | 250' SOUTH OF SR 1020 |  | DEER CREEK |  | 52 | 72 | 33 | 54 | Gas |  |  |  | 2014-06-25 | 2014-10-17 | [5 empty] | Unk | UG |  | I |  |  |  | 72 | [6 empty] | Urban Major Arterial | 52 | 20 | 72 | 33.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 40 | 120.88 | 4835.2 | [13 empty] | 40 |  |  |  |  | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | Gas | 1 | Yes | 72 |  | 1 | 3600 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 4835.2 | 7500 | 1 | 17608.5 | 10000 | 2 |  |  |  | 97120 | 12879
1 | Y | 405 | 63324 | 1339 | 02091003000000 | 11 |  | Allegheny | 250' SOUTH OF SR 1020 |  | DEER CREEK |  | 52 | 72 | 33 | 54 | Elect |  |  |  | 2014-06-25 | 2014-10-17 | [6 empty] | OH |  | Y | Duquesne |  |  | 600 | [6 empty] | Urban Major Arterial | 52 | 20 | 72 | 33.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 40 | 120.88 | 4835.2 | [13 empty] | 40 |  |  |  |  | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | Gas | 1 | Yes | 72 |  | 1 | 3600 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 4835.2 | 7500 | 1 | 17608.5 | 10000 | 2 |  |  |  | 90155 | 12902
1 | Y | 405 | 63324 | 1339 | 02091003000000 | 11 |  | Allegheny | 250' SOUTH OF SR 1020 |  | DEER CREEK |  | 52 | 72 | 33 | 54 | Elect |  |  |  | 2014-06-25 | 2014-10-17 | [6 empty] | OH |  | Y |  |  |  | 600 | [6 empty] | Urban Major Arterial | 52 | 20 | 72 | 33.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 40 | 120.88 | 4835.2 | [13 empty] | 40 |  |  |  |  | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | Gas | 1 | Yes | 72 |  | 1 | 3600 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 4835.2 | 7500 | 1 | 17608.5 | 10000 | 2 |  |  |  | 97121 | 13084
1 | Y | 405 | 63324 | 1339 | 02091003000000 | 11 |  | Allegheny | 250' SOUTH OF SR 1020 |  | DEER CREEK |  | 52 | 72 | 33 | 54 | Comm |  |  |  | 2014-06-25 | 2014-10-17 | [6 empty] | OH | Tele | y | Consolidated |  |  | 600 | [6 empty] | Urban Major Arterial | 52 | 20 | 72 | 33.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 40 | 120.88 | 4835.2 | [13 empty] | 40 |  |  |  |  | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | Gas | 1 | Yes | 72 |  | 1 | 3600 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 4835.2 | 7500 | 1 | 17608.5 | 10000 | 2 |  |  |  | 97117 | 13122
1 | Y | 405 | 63324 | 1339 | 02091003000000 | 11 |  | Allegheny | 250' SOUTH OF SR 1020 |  | DEER CREEK |  | 52 | 72 | 33 | 54 | Comm |  |  |  | 2014-06-25 | 2014-10-17 | [6 empty] | OH | Tele | y |  |  |  | 600 | [6 empty] | Urban Major Arterial | 52 | 20 | 72 | 33.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 40 | 120.88 | 4835.2 | [13 empty] | 40 |  |  |  |  | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | Gas | 1 | Yes | 72 |  | 1 | 3600 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 4835.2 | 7500 | 1 | 17608.5 | 10000 | 2 |  |  |  | 97118 | 13128
1 | Y | 405 | 63324 | 1339 | 02091003000000 | 11 |  | Allegheny | 250' SOUTH OF SR 1020 |  | DEER CREEK |  | 52 | 72 | 33 | 54 | Comm |  |  |  | 2014-06-25 | 2014-10-17 | [6 empty] | OH | TV | y | Comcast |  |  | 600 | [6 empty] | Urban Major Arterial | 52 | 20 | 72 | 33.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 40 | 120.88 | 4835.2 | [13 empty] | 40 |  |  |  |  | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | Gas | 1 | Yes | 72 |  | 1 | 3600 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 4835.2 | 7500 | 1 | 17608.5 | 10000 | 2 |  |  |  | 89176 | 13027
1 | Y | 405 | 63324 | 1339 | 02091003000000 | 11 |  | Allegheny | 250' SOUTH OF SR 1020 |  | DEER CREEK |  | 52 | 72 | 33 | 54 | Wtr |  |  |  | 2014-06-25 | 2014-10-17 | [6 empty] | UG |  | y | Oakmont Muni Auth |  |  | 600 | [6 empty] | Urban Major Arterial | 52 | 20 | 72 | 33.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 40 | 120.88 | 4835.2 | [13 empty] | 40 |  |  |  |  | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | Gas | 1 | Yes | 72 |  | 1 | 3600 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 4835.2 | 7500 | 1 | 17608.5 | 10000 | 2 |  |  |  | 97124 | 13367
[21 empty] | #N/A | [230 empty] | 1140 | 16373
[21 empty] | #N/A | [230 empty] | 74663 | 17195
2 | Y | 412 | 63342 | 1400 | 02101100102295 | 11 |  | Allegheny | 1/2 MI.N.OF SR 0028 |  | GUYS RUN |  | 21 | 41 | 25.8 | 54 | SS | [10 empty] | Unk | UG |  | Y | Harmar TWP |  |  | 700 | [6 empty] | Urban Minor Collector | 21 | 20 | 41 | 25.8 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1 | 1 |  |  |  | 82 | 477.3 | 39138.6 | [13 empty] | 82 |  |  |  | 1 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2000 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [9 empty] | 39138.6 | 7500 | 6 | 13240.5 | 10000 | 2 |  |  |  | 1370 | 17207
2 | Y | 412 | 63342 | 1400 | 02101100102295 | 11 |  | Allegheny | 1/2 MI.N.OF SR 0028 |  | GUYS RUN |  | 21 | 41 | 25.8 | 54 | Gas | [10 empty] | Unk | UG |  | ? | Peoples Gas |  |  | ? | [5 empty] | Summer | Urban Minor Collector | 21 | 20 | 41 | 25.8 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1 | 1 |  |  |  | 82 | 477.3 | 39138.6 | [13 empty] | 82 |  |  |  | 1 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2000 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [9 empty] | 39138.6 | 7500 | 6 | 13240.5 | 10000 | 2 |  |  |  | 93595 | 17208
2 | Y | 412 | 63342 | 1400 | 02101100102295 | 11 |  | Allegheny | 1/2 MI.N.OF SR 0028 |  | GUYS RUN |  | 21 | 41 | 25.8 | 54 | Elect | [11 empty] | OH |  | N | West Penn PWr |  |  | 400 | [6 empty] | Urban Minor Collector | 21 | 20 | 41 | 25.8 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1 | 1 |  |  |  | 82 | 477.3 | 39138.6 | [13 empty] | 82 |  |  |  | 1 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2000 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [9 empty] | 39138.6 | 7500 | 6 | 13240.5 | 10000 | 2 |  |  |  | 1398 | 17209
2 | Y | 412 | 63342 | 1400 | 02101100102295 | 11 |  | Allegheny | 1/2 MI.N.OF SR 0028 |  | GUYS RUN |  | 21 | 41 | 25.8 | 54 | Tel | [11 empty] | OH |  | N | Verizon |  |  | 400 | [6 empty] | Urban Minor Collector | 21 | 20 | 41 | 25.8 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1 | 1 |  |  |  | 82 | 477.3 | 39138.6 | [13 empty] | 82 |  |  |  | 1 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2000 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [9 empty] | 39138.6 | 7500 | 6 | 13240.5 | 10000 | 2 |  |  |  | 97328 | 25833
2 | Y | 412 | 63342 | 1400 | 02101100102295 | 11 |  | Allegheny | 1/2 MI.N.OF SR 0028 |  | GUYS RUN |  | 21 | 41 | 25.8 | 54 | Wtr | [11 empty] | UG |  | Y | Harmar TWP |  |  | 700 | [6 empty] | Urban Minor Collector | 21 | 20 | 41 | 25.8 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1 | 1 |  |  |  | 82 | 477.3 | 39138.6 | [13 empty] | 82 |  |  |  | 1 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2000 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [9 empty] | 39138.6 | 7500 | 6 | 13240.5 | 10000 | 2 |  |  |  | 1686 | 25858
1 | Y | 412 | 63342 | 1400 | 02101100102295 | 11 |  | Allegheny | 1/2 MI.N.OF SR 0028 |  | GUYS RUN |  | 21 | 41 | 25.8 | 54 | TV | [11 empty] | OH |  | Y | Comcast |  |  | 700 | [6 empty] | Urban Minor Collector | 21 | 20 | 41 | 25.8 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1 | 1 |  |  |  | 82 | 477.3 | 39138.6 | [13 empty] | 82 |  |  |  | 1 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2000 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [9 empty] | 39138.6 | 7500 | 6 | 13240.5 | 10000 | 2 |  |  |  | 58092 | 26008
1 | Y | 412 | 63342 | 1400 | 02101100102295 | 11 |  | Allegheny | 1/2 MI.N.OF SR 0028 |  | GUYS RUN |  | 21 | 41 | 25.8 | 54 | TV | [11 empty] | OH |  | Y |  |  |  | 400 | [6 empty] | Urban Minor Collector | 21 | 20 | 41 | 25.8 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1 | 1 |  |  |  | 82 | 477.3 | 39138.6 | [13 empty] | 82 |  |  |  | 1 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2000 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [9 empty] | 39138.6 | 7500 | 6 | 13240.5 | 10000 | 2 |  |  |  | 93160 | 33765
[252 empty] | 2251 | 33788
[252 empty] | 97457 | 33956
[252 empty] | 2438 | 33957
3 | Y | 414 | 63343 | 1405 | 02101300202226 | 11 |  | Allegheny | 4283' N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 38 | 58 | 28.0 | 54 | Wtr | Rt |  |  | 2014-06-27 | 2014-11-21 | [5 empty] | 6 | UG |  | I | Hampton-Shaler |  |  | 50 | [5 empty] | Case thru WW - inst new on Str | Urban Minor Arterial | 38 | 20 | 58 | 28.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  |  |  | 50 | 249.45 | 12472.5 |  |  |  |  | 50 | [12 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | PEOPLES |  | 50 | 120.88 | 6044 |  |  | 50 | [14 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 6" Water, 4" Gas | 1 | Yes | 116 |  | 1 | 2000 | 1 |  | DUQUESNE LIGHT | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 18516.5 | 7500 | 3 | 13240.5 | 10000 | 2 |  |  |  | 2546 | 33982
3 | Y | 414 | 63343 | 1405 | 02101300202226 | 11 |  | Allegheny | 4283' N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 38 | 58 | 28.0 | 54 | Gas | Rt |  |  | 2014-06-27 | 2014-11-21 | [5 empty] | 4 | UG |  | y | Peoples |  |  | 50 | [5 empty] | Summer | Urban Minor Arterial | 38 | 20 | 58 | 28.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  |  |  | 50 | 249.45 | 12472.5 |  |  |  |  | 50 | [12 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | PEOPLES |  | 50 | 120.88 | 6044 |  |  | 50 | [14 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 6" Water, 4" Gas | 1 | Yes | 116 |  | 1 | 2000 | 1 |  | DUQUESNE LIGHT | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 18516.5 | 7500 | 3 | 13240.5 | 10000 | 2 |  |  |  | 2580 | 34001
3 | Y | 414 | 63343 | 1405 | 02101300202226 | 11 |  | Allegheny | 4283' N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 38 | 58 | 28.0 | 54 | Elect | Rt |  |  | 2014-06-27 | 2014-11-21 | [6 empty] | OH |  | Y | DUQUESNE LIGHT |  |  | 400 | [6 empty] | Urban Minor Arterial | 38 | 20 | 58 | 28.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  |  |  | 50 | 249.45 | 12472.5 |  |  |  |  | 50 | [12 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | PEOPLES |  | 50 | 120.88 | 6044 |  |  | 50 | [14 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 6" Water, 4" Gas | 1 | Yes | 116 |  | 1 | 2000 | 1 |  | DUQUESNE LIGHT | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 18516.5 | 7500 | 3 | 13240.5 | 10000 | 2 |  |  |  | 2548 | 34056
3 | Y | 414 | 63343 | 1405 | 02101300202226 | 11 |  | Allegheny | 4283' N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 38 | 58 | 28.0 | 54 | Elect |  |  |  | 2014-06-27 | 2014-11-21 | [6 empty] | OH |  | Y | DUQUESNE LIGHT |  |  | 400 | [6 empty] | Urban Minor Arterial | 38 | 20 | 58 | 28.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  |  |  | 50 | 249.45 | 12472.5 |  |  |  |  | 50 | [12 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | PEOPLES |  | 50 | 120.88 | 6044 |  |  | 50 | [14 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 6" Water, 4" Gas | 1 | Yes | 116 |  | 1 | 2000 | 1 |  | DUQUESNE LIGHT | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 18516.5 | 7500 | 3 | 13240.5 | 10000 | 2 |  |  |  | 84954 | 34077
3 | Y | 414 | 63343 | 1405 | 02101300202226 | 11 |  | Allegheny | 4283' N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 38 | 58 | 28.0 | 54 | Comm |  |  |  | 2014-06-27 | 2014-11-21 | [5 empty] | TV | OH |  | Y | Comcast |  |  | 400 | [6 empty] | Urban Minor Arterial | 38 | 20 | 58 | 28.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  |  |  | 50 | 249.45 | 12472.5 |  |  |  |  | 50 | [12 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | PEOPLES |  | 50 | 120.88 | 6044 |  |  | 50 | [14 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 6" Water, 4" Gas | 1 | Yes | 116 |  | 1 | 2000 | 1 |  | DUQUESNE LIGHT | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 18516.5 | 7500 | 3 | 13240.5 | 10000 | 2 |  |  |  | 97452 | 34169
2 | Y | 414 | 63343 | 1405 | 02101300202226 | 11 |  | Allegheny | 4283' N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 38 | 58 | 28.0 | 54 | Comm |  |  |  | 2014-06-27 | 2014-11-21 | [5 empty] | Tele | OH |  | Y | Verizon |  |  | 400 | [6 empty] | Urban Minor Arterial | 38 | 20 | 58 | 28.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  |  |  | 50 | 249.45 | 12472.5 |  |  |  |  | 50 | [12 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | PEOPLES |  | 50 | 120.88 | 6044 |  |  | 50 | [14 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 6" Water, 4" Gas | 1 | Yes | 116 |  | 1 | 2000 | 1 |  | DUQUESNE LIGHT | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 18516.5 | 7500 | 3 | 13240.5 | 10000 | 2 |  |  |  | 85095 | 8831
|  | 414 | 63343 | 1405 | 02101300202226 | 11 |  | Allegheny | 4283' N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 38 | 58 | 28.0 | 54 | SS |  |  |  | 2014-06-27 | 2014-11-21 | [5 empty] | 8 | UG |  | N | Shaler TWP |  |  | 400 | [5 empty] | inc pump station | [210 empty] | 88201 | 9265
4 | Y | 415 | 63344 | 1406 | 02101300300428 | 11 |  | Allegheny | 1 MI. N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 29 | 49 | 28.0 | 54 | Wtr |  |  |  | 2014-06-30 | 2014-11-04 | [5 empty] | 4 | UG |  | N | Hampton-Shaler |  |  | 50 | [6 empty] | Urban Minor Arterial | 29 | 20 | 49 | 28.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  |  |  | 50 | 249.45 | 12472.5 |  |  | 50 | [14 empty] | 1 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 1 |  |  |  | 50 | 120.88 | 6044 | [5 empty] | 50 | [11 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 4" Water, 8" Gas (asbestos wrapped) | 1 | Yes | 98 |  | 1 | 1600 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | [9 empty] | 18516.5 | 7500 | 3 | 12148.5 | 10000 | 2 | Existing gas line (asbestos wrapped) is 8' off existing bridge |  |  | 88155 | 9360
4 | Y | 415 | 63344 | 1406 | 02101300300428 | 11 |  | Allegheny | 1 MI. N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 29 | 49 | 28.0 | 54 | SS |  |  |  | 2014-06-30 | 2014-11-04 | [5 empty] | ? | UG |  | ? |  |  |  | ? | [216 empty] | 85135 | 9576
4 | Y | 415 | 63344 | 1406 | 02101300300428 | 11 |  | Allegheny | 1 MI. N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 29 | 49 | 28.0 | 54 | Gas |  |  |  | 2014-06-30 | 2014-11-04 | [5 empty] | 8 | UG |  | Y | Peoples Gas |  |  | 50 | [216 empty] | 81359 | 9577
4 | Y | 415 | 63344 | 1406 | 02101300300428 | 11 |  | Allegheny | 1 MI. N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 29 | 49 | 28.0 | 54 | Elect |  |  |  | 2014-06-30 | 2014-11-04 | [6 empty] | OH |  | N | Duquesne |  |  | 400 | [216 empty] | 2893 | 9679
4 | Y | 415 | 63344 | 1406 | 02101300300428 | 11 |  | Allegheny | 1 MI. N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 29 | 49 | 28.0 | 54 | Elect |  |  |  | 2014-06-30 | 2014-11-04 | [6 empty] | OH |  | Y |  |  |  | 400 | [216 empty] | 85125 | 9431
3 | Y | 415 | 63344 | 1406 | 02101300300428 | 11 |  | Allegheny | 1 MI. N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 29 | 49 | 28.0 | 54 | Comm |  |  |  | 2014-06-30 | 2014-11-04 | [5 empty] | Tele | OH |  | N | Verizon |  |  | 400 | [216 empty] | 85128 | 9434
1 | Y | 415 | 63344 | 1406 | 02101300300428 | 11 |  | Allegheny | 1 MI. N.E. OF SR 0008 |  | LITTLE PINE CREEK |  | 29 | 49 | 28.0 | 54 | Comm |  |  |  | 2014-06-30 | 2014-11-04 | [5 empty] | TV | OH |  | N | Comcast |  |  | 400 | [216 empty] | 88199 | 9451
[252 empty] | 91413 | 9778
5 | Y | 416 | 78223 | 42177 | 02101300400000 | 11 |  | Allegheny | 2 MILES WEST OF SR 1006 |  | BRANCH LITTLE PINE CREEK |  | 11 | 31 | 34.5 | 54 | Gas |  |  |  | 2014-06-30 | 2014-11-13 | [5 empty] | 8 | UG |  | Y | Peoples |  |  | 50 | [6 empty] | Urban Minor Arterial | 11 | 20 | 31 | 34.5 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 1 |  |  |  | 50 | 120.88 | 6044 | [5 empty] | 50 | [11 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 8" Gas (asbestos wrapped) | 1 | Yes | 31 |  | 1 | 1600 | 2 |  |  | 800 | 2.73 | 2184 | 1 | BELL TELEPHONE | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [9 empty] | 6044 | 7500 | 1 | 12148.5 | 10000 | 2 | Existing gas line (asbestos wrapped) is 8' off existing bridge |  |  | 3195 | 9790
5 | Y | 416 | 78223 | 42177 | 02101300400000 | 11 |  | Allegheny | 2 MILES WEST OF SR 1006 |  | BRANCH LITTLE PINE CREEK |  | 11 | 31 | 34.5 | 54 | Elect |  |  |  | 2014-06-30 | 2014-11-13 | [6 empty] | OH |  | Y | Duquesne |  |  | 400 | [216 empty] | 69443 | 11245
5 | Y | 416 | 78223 | 42177 | 02101300400000 | 11 |  | Allegheny | 2 MILES WEST OF SR 1006 |  | BRANCH LITTLE PINE CREEK |  | 11 | 31 | 34.5 | 54 | Wtr |  |  |  | 2014-06-30 | 2014-11-13 | [6 empty] | UG |  | Y | Hampton-Shaler |  |  | 400 | [216 empty] | 91508 | 11390
5 | Y | 416 | 78223 | 42177 | 02101300400000 | 11 |  | Allegheny | 2 MILES WEST OF SR 1006 |  | BRANCH LITTLE PINE CREEK |  | 11 | 31 | 34.5 | 54 | Comm |  |  |  | 2014-06-30 | 2014-11-13 | [5 empty] | tele | OH |  | Y | Verizon |  |  | 400 | [216 empty] | 85076 | 11399
5 | Y | 416 | 78223 | 42177 | 02101300400000 | 11 |  | Allegheny | 2 MILES WEST OF SR 1006 |  | BRANCH LITTLE PINE CREEK |  | 11 | 31 | 34.5 | 54 | Comm |  |  |  | 2014-06-30 | 2014-11-13 | [5 empty] | TV | OH |  | Y | Comcast |  |  | 400 | [216 empty] | 85079 | 11403
4 | Y | 416 | 78223 | 42177 | 02101300400000 | 11 |  | Allegheny | 2 MILES WEST OF SR 1006 |  | BRANCH LITTLE PINE CREEK |  | 11 | 31 | 34.5 | 54 |  |  |  |  | 2014-06-30 | 2014-11-13 | [229 empty] | 93323 | 11404
[252 empty] | 93372 | 11454
6 | Y | 418 | 27287 | 1435 | 02101600801980 | 11 |  | Allegheny | 70' WEST OF SR 1015 |  | LITTLE DEER CREEK |  | 37 | 57 | 26.5 | 50 | Gas |  |  |  | 2014-06-27 | 2014-12-23 | [9 empty] | Dominion | [9 empty] | Urban Local | 37 | 20 | 57 | 26.5 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0.5 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0.5 | 0 |  | DOMINION |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0.5 | 1200 | 1 |  | DUQUESNE LIGHT | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [9 empty] | 5.778e-29 | 7500 | 1 | 11056.5 | 10000 | 2 |  |  |  | 88626 | 11461
6 | Y | 418 | 27287 | 1435 | 02101600801980 | 11 |  | Allegheny | 70' WEST OF SR 1015 |  | LITTLE DEER CREEK |  | 37 | 57 | 26.5 | 50 | Elect |  |  |  | 2014-06-27 | 2014-12-23 | [6 empty] | OH |  | Y | DUQUESNE LIGHT |  |  | 400 | [216 empty] | 89978 | 11658
6 | Y | 418 | 27287 | 1435 | 02101600801980 | 11 |  | Allegheny | 70' WEST OF SR 1015 |  | LITTLE DEER CREEK |  | 37 | 57 | 26.5 | 50 | Comm |  |  |  | 2014-06-27 | 2014-12-23 | [5 empty] | Tele | OH |  | Y |  |  |  | 400 | [216 empty] | 3571 | 11698
6 | Y | 418 | 27287 | 1435 | 02101600801980 | 11 |  | Allegheny | 70' WEST OF SR 1015 |  | LITTLE DEER CREEK |  | 37 | 57 | 26.5 | 50 | Comm |  |  |  | 2014-06-27 | 2014-12-23 | [5 empty] | TV | OH |  | Y |  |  |  | 400 | [216 empty] | 85119 | 11807
[252 empty] | 91510 | 12163
7 | Y | 419 | 63356 | 1455 | 02102801801751 | 11 |  | Allegheny | 200' WEST OF SR 1031 |  | LARDINTOWN RUN |  | 34 | 54 | 35.0 | 54 | Unk |  |  |  | 2014-06-26 | 2014-10-07 | [6 empty] | UG |  | Y | [10 empty] | Rural Minor Arterial | 34 | 20 | 54 | 35.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0.5 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 5.778e-29 | 7500 | 1 | 11056.5 | 10000 | 2 |  |  |  | 69040 | 12239
7 | Y | 419 | 63356 | 1455 | 02102801801751 | 11 |  | Allegheny | 200' WEST OF SR 1031 |  | LARDINTOWN RUN |  | 34 | 54 | 35.0 | 54 | Elect |  |  |  | 2014-06-26 | 2014-10-07 | [6 empty] | OH |  | Y |  |  |  | 400 | [216 empty] | 85152 | 15531
7 | Y | 419 | 63356 | 1455 | 02102801801751 | 11 |  | Allegheny | 200' WEST OF SR 1031 |  | LARDINTOWN RUN |  | 34 | 54 | 35.0 | 54 | Comm |  |  |  | 2014-06-26 | 2014-10-07 | [5 empty] | Tele | OH |  | Y | Bell Tele |  |  | 400 | [216 empty] | 69088 | 15535
7 | Y | 419 | 63356 | 1455 | 02102801801751 | 11 |  | Allegheny | 200' WEST OF SR 1031 |  | LARDINTOWN RUN |  | 34 | 54 | 35.0 | 54 | Comm |  |  |  | 2014-06-26 | 2014-10-07 | [5 empty] | TV | OH |  | Y |  |  |  | 400 | [216 empty] | 88185 | 15560
[252 empty] | 88195 | 19992
8 | Y | 420 | 63513 | 1471 | 02103400501321 | 11 |  | Allegheny | 4200' S.E. OF SR 1033 |  | BULL CREEK |  | 74 | 94 | 34.5 | 52 |  |  |  |  | 2014-06-26 | 2014-11-14 | [19 empty] | Rural Minor Arterial | 74 | 20 | 94 | 34.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 2 |  |  | 800 | 2.73 | 2184 | 2 | BELL TELEPHONE | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [10 empty] | 5.778e-29 | 7500 | 1 | 18222.75 | 10000 | 2 |  |  |  | 4194 | 20021
8 | Y | 420 | 63513 | 1471 | 02103400501321 | 11 |  | Allegheny | 4200' S.E. OF SR 1033 |  | BULL CREEK |  | 74 | 94 | 34.5 | 52 |  |  |  |  | 2014-06-26 | 2014-11-14 | [229 empty] | 4214 | 20106
8 | Y | 420 | 63513 | 1471 | 02103400501321 | 11 |  | Allegheny | 4200' S.E. OF SR 1033 |  | BULL CREEK |  | 74 | 94 | 34.5 | 52 |  |  |  |  | 2014-06-26 | 2014-11-14 | [229 empty] | 4218 | 20118
8 | Y | 420 | 63513 | 1471 | 02103400501321 | 11 |  | Allegheny | 4200' S.E. OF SR 1033 |  | BULL CREEK |  | 74 | 94 | 34.5 | 52 |  |  |  |  | 2014-06-26 | 2014-11-14 | [229 empty] | 81508 | 20137
1 | Y | 420 | 63513 | 1471 | 02103400501321 | 11 |  | Allegheny | 4200' S.E. OF SR 1033 |  | BULL CREEK |  | 74 | 94 | 34.5 | 52 |  |  |  |  | 2014-06-26 | 2014-11-14 | [229 empty] | 91518 | 20147
[252 empty] | 78606 | 25213
9 | Y | 422 | 62174 | 1481 | 02200101300130 | 11 |  | Allegheny | AT PANGBURN RD |  | PERRY MILL RUN (ADJACENT CSX) |  | 79 | 99 | 29.0 | 52 | [25 empty] | Urban Minor Collector | 79 | 20 | 99 | 29.0 | 28 | 24 | 52 |  | 1 | 45 | 450 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2000 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 13240.5 | 10000 | 2 |  |  |  | 78605 | 25216
10 | Y | 431 | 63547 | 1567 | 02204600800256 | 11 |  | Allegheny | 50'EAST/SCHUTE RD. |  | STREETS RUN (ADJACENT UNION) |  | 48 | 68 | 39.4 | 56 |  |  |  |  | 2014-06-24 | 2014-12-03 | [19 empty] | Urban Minor Arterial | 48 | 20 | 68 | 39.4 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  | EQUITABLE |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 4344 | 25243
11 | Y | 433 | 27419 | 1600 | 02206500402452 | 11 |  | Allegheny | 2656' N.E. OF SR 2053 |  | THOMPSON RUN |  | 65 | 85 | 29.0 | 56 |  |  |  |  | 2014-06-27 | 2014-12-19 | [19 empty] | Urban Minor Collector | 65 | 20 | 85 | 29.0 | 32 | 24 | 56 |  | 1 | 20 | 200 | 2 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1 | 1 |  |  |  | 50 | 477.3 | 23865 | [13 empty] | 50 |  |  |  | 0 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | [9 empty] | 23865 | 7500 | 4 | 11056.5 | 10000 | 2 |  |  |  | 88664 | 25281
12 | Y | 436 | 63557 | 1671 | 02211800203544 | 11 |  | Allegheny | 500' SOUTHEAST OF SR 0048 |  | LONG RUN |  | 52 | 72 | 32.0 | 56 | [25 empty] | Urban Minor Arterial | 52 | 20 | 72 | 32.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1 | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 8" Gas (asbestos wrapped ?) | 1 | Yes | 72 |  | 1 | 2000 | 2 |  |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 13240.5 | 10000 | 2 |  |  |  | 88183 | 25297
13 | Y | 438 | 28446 | 1715 | 02301400302259 | 11 |  | Allegheny | 3/4 MI.N.W.OF SR 3015 |  | PINEY FORK CREEK |  | 47 | 67 | 22.0 | 48 |  |  |  |  | 2014-06-27 | 2014-12-17 | [19 empty] | Urban Local | 47 | 20 | 67 | 22.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1 | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 9964.5 | 10000 | 1 |  |  |  | 85215 | 25308
14 | Y | 446 | 74338 | 1950 | 02401700500880 | 11 |  | Allegheny | NEAR TWP GARAGE |  | LITTLE PINE CREEK |  | 41 | 61 | 25.5 | 50 |  |  |  |  | 2014-06-30 | 2014-11-24 | [19 empty] | Urban Local | 41 | 20 | 61 | 25.5 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 1 | 1 |  |  |  | 61 | 249.45 | 15216.45 | [13 empty] | 61 |  |  |  | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | PNG |  | 61 | 120.88 | 7373.68 | 61 | [16 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 2 |  |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 22590.13 | 7500 | 4 | 14332.5 | 10000 | 2 |  |  |  | 4341 | 25313
15 | Y | 359 | 24085 | 3097 | 03083901001927 | 10 |  | Armstrong | SOUTH OF DAYTON NO. 2 |  | GLADE RUN |  | 47 | 67 | 40.0 | 58 | [25 empty] | Rural Major Collector | 47 | 20 | 67 | 40.0 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 11056.5 | 10000 | 2 |  |  |  | 85259 | 25314
16 | Y | 360 | 79606 | 3160 | 03103900600000 | 10 |  | Armstrong | BRYAN |  | TRIB S FRK PINE CR |  | 31 | 51 | 25.0 | 62 |  |  |  |  | 2014-06-24 | 2014-12-19 | [19 empty] | Rural Minor Collector | 31 | 20 | 51 | 25.0 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 85234 | 25418
17 | Y | 366 | 24153 | 3282 | 03301300602401 | 10 |  | Armstrong | NICHOLA NO.1 |  | BUFFALO CREEK |  | 74 | 94 | 26.6 | 48 |  |  |  |  | 2014-06-25 | 2014-12-02 | [19 empty] | Rural Minor Collector | 74 | 20 | 94 | 26.6 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 9964.5 | 10000 | 1 |  |  |  | 4336 | 25420
18 | Y | 367 | 83284 | 3293 | 03301702501033 | 10 |  | Armstrong | CENTER HILL NO. 6 |  | GLADE RUN |  | 83 | 103 | 26.3 | 56 | [25 empty] | Rural Minor Collector | 83 | 20 | 103 | 26.3 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 4 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 50 | 120.88 | 6044 |  |  | 50 | [15 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 4" Gas | 1 | Yes | 103 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 6044 | 7500 | 1 | 11056.5 | 10000 | 2 |  |  |  | 85237 | 25459
19 | Y | 90 | 99281 | 6104 | 08018704000000 | 3 |  | Bradford | 1 MILE SOUTH OF DURELL |  | DURELL CREEK |  | 33 | 53 | 25.5 | 54 | [5 empty] | 2014-06-23 | [19 empty] | Rural Major Collector | 33 | 20 | 53 | 25.5 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25.00, 30.00 | [9 empty] | 0 | 7500 | 0 | 9964.5 | 10000 | 1 |  |  |  | 4340 | 25461
20 | Y | 92 | 5093 | 6164 | 08036700101794 | 3 |  | Bradford | 3.5 MI.SOUTH OF SILVARA |  | FARGO CREEK |  | 33 | 53 | 25.7 | 52 | [5 empty] | 2014-06-24 | [19 empty] | Rural Minor Collector | 33 | 20 | 53 | 25.7 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | [9 empty] | 0 | 7500 | 0 | 11056.5 | 10000 | 2 |  |  |  | 88630 | 25462
21 | Y | 94 | 76863 | 6193 | 08046700100052 | 3 |  | Bradford | 2 MILE SOUTH OF ROME BORO |  | WYSOX CREEK |  | 86 | 106 | 33.5 | 76 | [5 empty] | 2014-04-09 | [19 empty] | Rural Major Collector | 86 | 20 | 106 | 33.5 | 52 | 24 | 76 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 68965 | 25489
22 | Y | 95 | 5210 | 6203 | 8046702700000 | 3 |  | Bradford | PIKE TWP .4M S SR 1013 |  | OVER ROCKWELL CREEK |  | 25 | 45 | 26.6 | 56 | [5 empty] | 2014-06-19 | [19 empty] | Rural Major Collector | 25 | 20 | 45 | 26.6 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 1 |  |  |  | 45 | 32.1 | 1444.5 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 1444.5 | 7500 | 1 | 0 | 10000 | 0 |  |  |  | 4486 | 25495
23 | Y | 96 | 5039 | 6216 | 8051402000863 | 3 |  | Bradford | 2.5 MI.N.OF W.FRANKLIN |  | N BR TOWANDA CREEK |  | 98 | 118 | 24.4 | 52 | [5 empty] | 2014-02-20 | [19 empty] | Rural Major Collector | 98 | 20 | 118 | 24.4 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 25 | [9 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 78611 | 25500
24 | Y | 97 | 5208 | 6224 | 08070601701340 | 3 |  | Bradford | 2 MI. NE. OF CAMPTOWN |  | COLD CREEK |  | 67 | 87 | 26.0 | 56 | [5 empty] | 2014-05-23 | [19 empty] | Rural Minor Arterial | 67 | 20 | 87 | 26.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 25 | [9 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 93322 | 25535
25 | Y | 98 | 5215 | 6227 | 08070602601160 | 3 |  | Bradford | STEVENS TWP .1M E LR08034 |  | OVER ROSS CREEK |  | 43 | 63 | 26.2 | 56 | [5 empty] | 2014-05-01 | [19 empty] | Rural Minor Arterial | 43 | 20 | 63 | 26.2 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 25.00, 35.00 | [9 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 4642 | 26468
26 | Y | 369 | 24806 | 7834 | 10006800200616 | 10 |  | Butler | ZELIENOPLE BORO NO. 2 |  | GLADE RUN |  | 37 | 57 | 41.0 | 48 | [25 empty] | Urban Minor Arterial | 37 | 20 | 57 | 41.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 3 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1600 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 12148.5 | 10000 | 2 |  |  |  | 85297 | 26469
27 | Y | 371 | 24667 | 7935 | 10035603000333 | 10 |  | Butler | CALDWELL DRIVE |  | TRIB TO THORN CREEK |  | 24 | 44 | 34.0 | 48 |  |  |  |  | 2014-06-30 | 2014-09-25 | [19 empty] | Rural Minor Arterial | 24 | 20 | 44 | 34.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  | PEOPLES |  | 50 | 120.88 | 6044 | [13 empty] | 50 |  |  |  |  | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1600 | 2 |  | CENTRAL ELECTRIC | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 6044 | 7500 | 1 | 12148.5 | 10000 | 2 |  |  |  | 4676 | 26472
28 | Y | 373 | 78002 | 8025 | 10200700101196 | 10 |  | Butler | SAXONBURG BLVD NO.1 |  | BULL CREEK |  | 33 | 53 | 34.0 | 48 | [25 empty] | Rural Major Collector | 33 | 20 | 53 | 34.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 11056.5 | 10000 | 2 |  |  |  | 4677 | 26477
29 | Y | 376 | 83335 | 8073 | 10301200500000 | 10 |  | Butler | CRUIKSHANK ROAD |  | TRIB TO GLADE RUN |  | 30 | 50 | 20.8 | 50 | [5 empty] | 2014-06-23 | [19 empty] | Rural Minor Collector | 30 | 20 | 50 | 20.8 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 85275 | 26595
30 | Y | 173 | 85764 | 8994 | 13020902602676 | 5 |  | Carbon | PACKERTON HOLLOW |  | BEAVER RUN |  | 21 | 41 | 43.7 | 64 | [25 empty] | Urban Principal Arterial | 21 | 20 | 41 | 43.7 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 4 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 50 | 120.88 | 6044 |  |  |  |  | 50 | [13 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 6" Gas | 1 | Yes | 41 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 6044 | 7500 | 1 | 0 | 10000 | 0 |  |  |  | 88640 | 30090
31 | Y | 102 | 98939 | 12555 | 19025402500486 | 3 |  | Columbia | 3.5 MI E OF MILLVILLE |  | TRIB TO MUD RUN |  | 20 | 40 | 33.0 | 56 |  |  |  |  | 2014-06-23 | 2014-09-25 | [19 empty] | Rural Major Collector | 20 | 20 | 40 | 33.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3600 | 3 |  | PPL | 1200 | 2.73 | 3276 | 3 |  | 1200 | 2.73 | 3276 | 3 |  | 1200 | 2.73 | 3276 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | [9 empty] | 0 | 7500 | 0 | 17608.5 | 10000 | 2 |  |  |  | 69501 | 30144
32 | Y | 103 | 5578 | 12592 | 19048703700177 | 3 |  | Columbia | 1 MILE N OF LIGHTSTREET |  | STONY BROOK CREEK |  | 33 | 53 | 25.8 | 58 | [5 empty] | 2014-04-23 | [19 empty] | Rural Minor Arterial | 33 | 20 | 53 | 25.8 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 20 | [9 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 93375 | 30156
33 | Y | 104 | 78822 | 12738 | 19403101120000 | 3 |  | Columbia | 3 MI W OF WALLER |  | OVER LITTLE FISHING CR. |  | 43 | 63 | 17.9 | 48 |  |  |  |  | 2014-06-20 | 2014-09-17 | [19 empty] | Rural Local | 43 | 20 | 63 | 17.9 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 1 |  | PPL | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [9 empty] | 0 | 7500 | 0 | 9964.5 | 10000 | 1 |  |  |  | 85309 | 30162
34 | Y | 107 | 6049 | 24566 | 41004403440880 | 3 |  | Lycoming | 4.5 MI S OF JERSEY SHORE |  | OVER ANTES CREEK |  | 88 | 108 | 24.5 | 56 | [5 empty] | 2014-06-25 | [19 empty] | Rural Minor Arterial | 88 | 20 | 108 | 24.5 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 3 |  | PPL | 1200 | 2.73 | 3276 |  |  | 0 | 2.73 | 0 | 3 |  | 1200 | 2.73 | 3276 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 40 |  |  |  |  | 13 |  |  |  |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | COMPLETE, pole offset in site visit notes/sketches | PRELIMINARY ASSUMPTIONS: LENGTHENING BRIDGE 10' WIDENING 8'; NO QTY'S INPUTED , OVERHEAD LINES EVIDENT IN PICTURES, QTY'S NEED ENTERED BASED ON ASSUMPTIONS |  | 4805 | 30166
35 | Y | 112 | 6057 | 24850 | 41200200320000 | 3 |  | Lycoming | 3 MI W OF ELIMSPORT |  | OVER WHITE DEER HOLE CR |  | 41 | 61 | 18.0 | 48 |  |  |  |  | 2014-06-20 | 2014-09-17 | [19 empty] | Rural Local | 41 | 20 | 61 | 18.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 22 |  |  |  |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offset in site visit notes/sketches |  |  | 4897 | 30190
36 | Y | 114 | 74022 | 24928 | 41205000120000 | 3 |  | Lycoming | 2.5 MI E OF LAIRDSVILLE |  | OVER LITTLE MUNCY CREEK |  | 56 | 76 | 16.4 | 48 | [5 empty] | 2014-06-04 | [19 empty] | Rural Local | 56 | 20 | 76 | 16.4 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 16.5 | [9 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 4898 | 30191
37 | Y | 180 | 91680 | 26795 | 45020903110000 | 5 |  | Monroe | AT JUNCT. WITH PA33 SB |  | APPENZELL CREEK |  | 124 | 144 | 54.0 | 76 | [5 empty] | 2014-05-08 | [19 empty] | Urban Principal Arterial | 124 | 20 | 144 | 54.0 | 52 | 24 | 76 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 4899 | 30233
38 | Y | 181 | 79157 | 26811 | 45031401101750 | 5 |  | Monroe | 2.5 M. S.OF SWIFTWATER |  | SWIFTWATER CREEK |  | 57 | 77 | 33.9 | 54 | [5 empty] | 2014-04-11 | [19 empty] | Rural Major Collector | 57 | 20 | 77 | 33.9 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 93373 | 30348
39 | Y | 182 | 79158 | 26832 | 45039000300932 | 5 |  | Monroe | MOUNTAIN HOME |  | MILL CREEK |  | 53 | 73 | 40.0 | 64 | [25 empty] | Rural Minor Arterial | 53 | 20 | 73 | 40.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  |  | 50 | 249.45 | 12472.5 | [13 empty] | 50 |  |  |  |  | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 12472.5 | 7500 | 2 | 11056.5 | 10000 | 2 |  |  |  | 85402 | 30435
40 | Y | 183 | 11649 | 26887 | 45061105100000 | 5 |  | Monroe | TOBYHANNA |  | TOBYHANNA CREEK |  | 70 | 90 | 71.7 | 92 | [5 empty] | 2014-06-06 | [19 empty] | Urban Minor Arterial | 70 | 20 | 90 | 71.7 | 68 | 24 | 92 |  | 1e-17 | 1e-28 | 1e-30 | 4 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 60 | 120.88 | 7252.8 | [13 empty] | 60 |  |  |  |  | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 7252.8 | 7500 | 1 | 0 | 10000 | 0 |  |  |  | 83457 | 6074
41 | Y | 184 | 11730 | 26888 | 45071500201751 | 5 |  | Monroe | 1 M. N.OF BRODHEADSVILLE |  | MCMICHAELS CREEK |  | 70 | 90 | 24.8 | 56 | [25 empty] | Rural Major Collector | 70 | 20 | 90 | 24.8 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 11056.5 | 10000 | 2 |  |  |  | 99281 | 6104
42 | Y | 185 | 96445 | 26901 | 45090300200000 | 5 |  | Monroe | 0.33 MI.W.OF PA 115 |  | TRIB.TO TUNKHANNOCK CK. |  | 21 | 41 | 31.0 | 56 | [25 empty] | Rural Major Collector | 21 | 20 | 41 | 31.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2800 | 3 |  |  | 1200 | 2.73 | 3276 | 3 |  | 1200 | 2.73 | 3276 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 15424.5 | 10000 | 2 |  |  |  | 5038 | 6136
43 | Y | 186 | 85879 | 26904 | 45094000701313 | 5 |  | Monroe | 2 MI.E.OF BLAKESLEE |  | DAVEY RUN |  | 27 | 47 | 59.3 | 64 | [25 empty] | Rural Minor Arterial | 27 | 20 | 47 | 59.3 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 60 | 120.88 | 7252.8 | [13 empty] | 60 |  |  |  |  | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 7252.8 | 7500 | 1 | 0 | 10000 | 0 |  |  |  | 5093 | 6164
44 | Y | 187 | 89628 | 26907 | 45094001400882 | 5 |  | Monroe | 5 MI.E.OF BLAKESLEE |  | TOBYHANNA CK.(POCONO LKE |  | 62 | 82 | 43.3 | 64 | [25 empty] | Rural Minor Arterial | 62 | 20 | 82 | 43.3 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None - 4" conduit in parapet for lighting | 0 | None | 0 |  | 1 | 2800 | 1 |  |  | 400 | 2.73 | 1092 | 3 |  | 1200 | 2.73 | 3276 | 3 |  | 1200 | 2.73 | 3276 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 15424.5 | 10000 | 2 |  |  |  | 79247 | 6191
45 | Y | 188 | 79204 | 26914 | 45094003900000 | 5 |  | Monroe | 2 MI.E. OF MT.POCONO |  | PARADISE CREEK |  | 53 | 73 | 42.0 | 64 | [25 empty] | Rural Minor Arterial | 53 | 20 | 73 | 42.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 11056.5 | 10000 | 2 |  |  |  | 76863 | 6193
46 | Y | 189 | 79170 | 26924 | 45100400300941 | 5 |  | Monroe | 1.2 M. E. OF PA 314 |  | PARADISE CREEK |  | 63 | 83 | 30.5 | 52 | [5 empty] | 2014-04-24 | [19 empty] | Rural Local | 63 | 20 | 83 | 30.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 9964.5 | 10000 | 1 |  |  |  | 5210 | 6203
47 | Y | 190 | 76368 | 26962 | 45200900101729 | 5 |  | Monroe | BRIDGE ST. |  | POCONO CREEK |  | 119 | 139 | 33.7 | 56 | [25 empty] | Urban Major Collector | 119 | 20 | 139 | 33.7 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 11056.5 | 10000 | 2 |  |  |  | 5039 | 6216
48 | Y | 191 | 96447 | 27011 | 45300900220000 | 5 |  | Monroe | T-939 S.OF MERWINSBURG |  | POHOPOCO CREEK |  | 42 | 62 | 26.1 | 52 | [5 empty] | 2014-06-19 | [19 empty] | Rural Minor Collector | 42 | 20 | 62 | 26.1 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 5208 | 6224
49 | Y | 192 | 11758 | 27017 | 45301100300000 | 5 |  | Monroe | SUGAR HOLLOW ROAD |  | SUGAR HOLLOW CREEK |  | 30 | 50 | 25.8 | 50 | [25 empty] | Rural Minor Arterial | 30 | 20 | 50 | 25.8 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 600 | 1 |  |  | 200 | 2.73 | 546 | 1 |  | 200 | 2.73 | 546 | 1 |  | 200 | 2.73 | 546 |  |  |  | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [10 empty] | 0 | 7500 | 0 | 5528.25 | 10000 | 1 |  |  |  | 5215 | 6227
50 | Y | 194 | 79185 | 27042 | 45302301202040 | 5 |  | Monroe | RIM ROCK DRIVE |  | POCONO CREEK |  | 139 | 159 | 43.0 | 64 | [25 empty] | Urban Major Collector | 139 | 20 | 159 | 43.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2000 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 13240.5 | 10000 | 2 |  |  |  | 98535 | 6348
51 | Y | 195 | 85849 | 27055 | 45400300702976 | 5 |  | Monroe | LOCUST RIDGE ROAD |  | TROUT CREEK |  | 53 | 73 | 26.8 | 54 | [25 empty] | Rural Local | 53 | 20 | 73 | 26.8 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  | PPL | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 11056.5 | 10000 | 2 |  |  |  | 5218 | 6476
52 | Y | 196 | 79187 | 27059 | 45400600200000 | 5 |  | Monroe | .7 M. W.OF LR 45024 |  | POCONO CREEK |  | 77 | 97 | 30.3 | 56 | [25 empty] | Rural Local | 77 | 20 | 97 | 30.3 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 0 | 7500 | 0 | 3276 | 10000 | 1 |  |  |  | 5589 | 12486
53 | Y | 118 | 74037 | 28389 | 47100600500000 | 3 |  | Montour | 7MI NE OF WASHINGTOVILLE |  | BR OF CHILLISQUAQUE CR. |  | 41 | 61 | 26.2 | 48 | [5 empty] | 2014-06-05 | [19 empty] | Rural Local | 41 | 20 | 61 | 26.2 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 25 |  |  |  |  | 50 |  |  |  |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offset in site visit notes/sketches |  |  | 98939 | 12555
54 | Y | 142 | 96726 | 29947 | 51100700301853 | 4 |  | Pike | SHOHOLA TWP 1.4M N SR1005 |  | TWIN LAKES CREEK |  | 38 | 58 | 29.8 | 52 |  |  |  |  | 2014-06-26 | 2014-12-15 | [19 empty] | Rural Local | 38 | 20 | 58 | 29.8 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  |  | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 4 | 3890.25 | 15561 | 25 | 10 | 0.1 | IN ROW | [6 empty] | 5.778e-29 | 7500 | 1 | 17745 | 10000 | 2 |  |  |  | 5578 | 12592
55 | Y | 204 | 12717 | 30678 | 53033902000276 | 5 |  | Schuylkill | VILLAGE OF ZIONS GROVE |  | CATAWISSA CREEK |  | 100 | 120 | 24.0 | 48 | [25 empty] | Rural Major Collector | 100 | 20 | 120 | 24.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [10 empty] | 0 | 7500 | 0 | 7166.25 | 10000 | 1 |  |  |  | 78822 | 12738
56 | Y | 205 | 12710 | 30679 | 53033902400902 | 5 |  | Schuylkill | CATAWISSA CREEK ROAD |  | CATAWISSA CREEK |  | 88 | 108 | 25.0 | 48 | [25 empty] | Rural Major Collector | 88 | 20 | 108 | 25.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 11056.5 | 10000 | 2 |  |  |  | 91436 | 24511
57 | Y | 206 | 12710 | 30680 | 53033902401098 | 5 |  | Schuylkill | CATAWISSA CREEK ROAD |  | TRIB.TO CATAWISSA CREEK |  | 15 | 35 | 34.8 | 56 | [25 empty] | Rural Major Collector | 15 | 20 | 35 | 34.8 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 11056.5 | 10000 | 2 |  |  |  | 6049 | 24566
58 | Y | 207 | 85810 | 30730 | 53092400702725 | 5 |  | Schuylkill | SOUTH SHENANDOAH |  | REMOVED RR & KEHLY RUN |  | 213 | 233 | 69.7 | 94 | [25 empty] | Rural Principal Arterial | 213 | 20 | 233 | 69.7 | 70 | 24 | 94 |  | 1e-17 | 1e-28 | 1e-30 | 4 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 1 |  |  |  | 233 | 477.3 | 111210.9 | [13 empty] | 233 |  |  |  |  | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1800 | 1 |  |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 111210.9 | 7500 | 15 | 12694.5 | 10000 | 2 |  |  |  | 6023 | 24591
59 | Y | 208 | 85724 | 30832 | 53401600100000 | 5 |  | Schuylkill | VILLAGE OF KLINGERSTOWN |  | MAHANTANGO CREEK |  | 76 | 96 | 26.0 | 52 |  |  |  |  | 2014-06-25 | 2014-11-05 | [19 empty] | Rural Minor Collector | 76 | 20 | 96 | 26.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 9964.5 | 10000 | 1 |  |  |  | 6145 | 24603
60 | Y | 209 | 47695 | 30856 | 53403600300000 | 5 |  | Schuylkill | 0.75 MI.E.OF COLUMBIA CO. |  | TREXLER RUN |  | 24 | 44 | 20.7 | 46 | [25 empty] | Rural Local | 24 | 20 | 44 | 20.7 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 400 |  |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 8872.5 | 10000 | 1 |  |  |  | 6045 | 24748
61 | Y | 210 | 12522 | 30862 | 53403900200000 | 5 |  | Schuylkill | VILLAGE OF HAAS |  | MAHANTANGO CREEK |  | 28 | 48 | 18.2 | 46 | [25 empty] | Rural Minor Collector | 28 | 20 | 48 | 18.2 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 1 |  | PPL | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 9964.5 | 10000 | 1 |  |  |  | 6054 | 24751
62 | Y | 126 | 7021 | 31966 | 56008705202440 | 3 |  | Sullivan | 0.25 MI W OF DUSHORE |  | OVER LITTLE LOYALSOCK CR |  | 68 | 88 | 33.0 | 56 | [5 empty] | 2014-06-24 | [19 empty] | Rural Minor Arterial | 68 | 20 | 88 | 33.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 4 | 3890.25 | 15561 | 40 | [9 empty] | 0 | 7500 | 0 | 17745 | 10000 | 2 |  |  |  | 6057 | 24850
63 | Y | 146 | 9719 | 32307 | 57026703200000 | 4 |  | Susquehanna | FORST LKE TP .8M N SR4012 |  | STONE STREET CREEK |  | 22 | 42 | 25.4 | 54 | [5 empty] | 2014-06-19 | [19 empty] | Rural Minor Arterial | 22 | 20 | 42 | 25.4 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  |  | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 5.778e-29 | 7500 | 1 | 11056.5 | 10000 | 2 |  | PRELIMINARY ASSUMPTIONS: SAME LENGTH, WIDENING 7', BOX CULVERT DESIGN |  | 6052 | 24881
64 | Y | 151 | 85782 | 32401 | 57100700500000 | 4 |  | Susquehanna | THMPSN TWP 1.7M N SR 1004 |  | SOUTH BR CANAWACTA CREEK |  | 45 | 65 | 28.0 | 48 | [5 empty] | 2014-06-19 | [19 empty] | Rural Local | 45 | 20 | 65 | 28.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  |  | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 5.778e-29 | 7500 | 1 | 0 | 10000 | 0 |  |  |  | 74022 | 24928
65 | Y | 153 | 96727 | 32478 | 57200800203639 | 4 |  | Susquehanna | CLIFFORD TWP 200'W TR 106 |  | DUNDAFF CREEK |  | 48 | 68 | 31.0 | 54 |  |  |  |  | 2014-06-24 | 2014-12-15 | [19 empty] | Rural Local | 48 | 20 | 68 | 31.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  |  | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 5.778e-29 | 7500 | 1 | 9964.5 | 10000 | 1 |  |  |  | 6144 | 24938
66 | Y | 129 | 7251 | 32843 | 58024903220000 | 3 |  | Tioga | 3.5 MI E OF WESTFIELD |  | OVER JEMISON CREEK |  | 51 | 71 | 26.1 | 57 | [5 empty] | 2014-01-08 | [19 empty] | Rural Major Collector | 51 | 20 | 71 | 26.1 | 33 | 24 | 57 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  | Noted in site visit, orientation/offset unknown | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 40 | [9 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offset not given in site visit, poles appear closer than 15' in photos |  |  | 6387 | 28361
67 | Y | 131 | 79055 | 33080 | 58300103901413 | 3 |  | Tioga | 1 MI S OF WATROUS |  | OVER ELK RUN |  | 58 | 78 | 24.5 | 54 | [5 empty] | 2014-05-20 | [19 empty] | Rural Local | 58 | 20 | 78 | 24.5 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 1 | 1 | 800 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | 5 | 7.75 | IN ROW |  | 2 |  |  |  |  | 0 | 7500 | 0 | 9964.5 | 10000 | 1 | COMPLETE, pole offset in site visit notes | PRELIMINARY ASSUMPTIONS: SPREAD FOOTING, POSSIBLE DEENERGIZE |  | 6381 | 28387
68 | Y | 132 | 7136 | 33083 | 58300500400000 | 3 |  | Tioga | VILLAGE OF DRAPER |  | OVER STONY FORK CREEK |  | 48 | 68 | 23.6 | 48 | [5 empty] | 2014-05-28 | [19 empty] | Rural Local | 48 | 20 | 68 | 23.6 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [9 empty] | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  |  | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 25 | [9 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, site visit information not available, PennDOT photos show no utilities |  |  | 74037 | 28389
69 | Y | 133 | 7347 | 33180 | 58401702800000 | 3 |  | Tioga | 2 MI NW OF OSCEOLA |  | HOLDEN CREEK |  | 43 | 63 | 26.3 | 52 | [5 empty] | 2014-06-24 | [19 empty] | Rural Minor Collector | 43 | 20 | 63 | 26.3 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  | Noted in site visit, orientation/offset unknown | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 3 | 3890.25 | 11670.75 | 25 |  |  |  |  | 3 |  |  |  |  | 0 | 7500 | 0 | 14946.75 | 10000 | 2 | COMPLETE, pole offset in site visit notes |  |  | 97586 | 29174
70 | Y | 137 | 83478 | 33478 | 59100300200000 | 3 |  | Union | 2 MI NE BUFFALO CROSS RDS |  | OVER BUFFALO CREEK |  | 80 | 100 | 20.2 | 52 | [5 empty] | 2014-04-07 | [19 empty] | Rural Local | 80 | 20 | 100 | 20.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 20 | [9 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 6669 | 29178
71 | Y | 138 | 74043 | 33543 | 59300202000501 | 3 |  | Union | VILLAGE OF LAURELTON |  | OVER LAUREL RUN |  | 56 | 76 | 22.1 | 54 | [5 empty] | 2014-06-04 | [19 empty] | Rural Minor Collector | 56 | 20 | 76 | 22.1 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1600 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [9 empty] | 0 | 7500 | 0 | 12148.5 | 10000 | 2 | COMPLETE, no pole offsets given in site visit notes, from photos it appears power not in conflict, communication lines in conflict |  |  | 79230 | 29303
72 | Y | 158 | 68917 | 35624 | 63101801602046 | 4 |  | Wayne | MANCHSTR TP 3.7M E TR 191 |  | BR LITTLE EQUINUNK CREEK |  | 24 | 44 | 18.3 | 46 | [5 empty] | 2014-06-19 | [19 empty] | Rural Local | 24 | 20 | 44 | 18.3 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  |  | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 25 | [9 empty] | 5.778e-29 | 7500 | 1 | 0 | 10000 | 0 |  |  |  | 6603 | 29306
73 | Y | 159 | 68927 | 35654 | 63200700301844 | 4 |  | Wayne | BERLIN TWP @ JCT SR 2009 |  | HOLBERT CREEK |  | 40 | 60 | 24.5 | 48 |  |  |  |  | 2014-06-24 | 2014-12-15 | [19 empty] | Rural Local | 40 | 20 | 60 | 24.5 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  |  | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 5.778e-29 | 7500 | 1 | 0 | 10000 | 0 |  | PRELIMINARY ASSUMPTIONS: LENGTHENING 10', WIDENING 2' |  | 88047 | 29311
74 | Y | 161 | 67584 | 35765 | 63300601600000 | 4 |  | Wayne | SCOTT TWP .5 M E SR 4037 |  | BALLS CREEK |  | 40 | 60 | 24.0 | 46 | [25 empty] | Rural Minor Collector | 40 | 20 | 60 | 24.0 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 25 | [9 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 88799 | 31169
75 | Y | 162 | 79580 | 35802 | 63403302600090 | 4 |  | Wayne | BUCKINGHAM TWP 90'N TR370 |  | SHEHAWKEN CREEK |  | 32 | 52 | 33.0 | 54 |  |  |  |  | 2014-06-25 | 2014-12-15 | [19 empty] | Rural Local | 32 | 20 | 52 | 33.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 11056.5 | 10000 | 2 |  |  |  | 89977 | 31948
76 | Y | 542 | 76089 | 36002 | 64005600501506 | 12 |  | Westmoreland | CITY OF NEW KENSINGTON |  | LITTLE PUCKETA CREEK |  | 47 | 67 | 26.8 | 104 | [5 empty] | 2014-06-03 | [19 empty] | Urban Principal Arterial | 47 | 20 | 67 | 26.8 | 80 | 24 | 104 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 7021 | 31966
77 | Y | 544 | 31601 | 36168 | 64025900700000 | 12 |  | Westmoreland | LIGONIER TOWNSHIP |  | COALPIT RUN |  | 33 | 53 | 25.0 | 48 | [5 empty] | 2014-05-29 | [19 empty] | Rural Minor Collector | 33 | 20 | 53 | 25.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 7009 | 31981
78 | Y | 545 | 74418 | 36207 | 64036601720000 | 12 |  | Westmoreland | MUNICIPAL. OF MURRYSVILLE |  | PUCKETA CREEK |  | 50 | 70 | 43.0 | 62 | [5 empty] | 2014-06-03 | [19 empty] | Rural Principal Arterial | 50 | 20 | 70 | 43.0 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2000 | 1 |  |  | 400 | 2.73 | 1092 | 2 | BELL TELEPHONE | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 13240.5 | 10000 | 2 |  |  |  | 7326 | 32822
79 | Y | 546 | 31826 | 36228 | 64038102400504 | 12 |  | Westmoreland | LIGONIER TOWNSHIP |  | LINN RUN |  | 37 | 57 | 20.2 | 50 | [5 empty] | 2014-06-09 | [19 empty] | Rural Minor Collector | 37 | 20 | 57 | 20.2 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 11056.5 | 10000 | 2 |  |  |  | 7251 | 32843
80 | Y | 547 | 31614 | 36230 | 64038103000000 | 12 |  | Westmoreland | LIGONIER TOWNSHIP |  | LAUGHLINTOWN RUN |  | 30 | 50 | 20.7 | 48 | [5 empty] | 2014-06-09 | [19 empty] | Rural Minor Collector | 30 | 20 | 50 | 20.7 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 50 | 120.88 | 6044 | [5 empty] | 50 | [12 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 8" Gas | 1 | Yes | 50 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 6044 | 7500 | 1 | 11056.5 | 10000 | 2 |  |  |  | 87929 | 32931
81 | Y | 549 | 76122 | 36251 | 64071103000565 | 12 |  | Westmoreland | LIGONIER TOWNSHIP |  | MILL CREEK |  | 68 | 88 | 34.0 | 58 | [5 empty] | 2014-06-16 | [19 empty] | Rural Minor Arterial | 68 | 20 | 88 | 34.0 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1600 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 0 | 7500 | 0 | 12148.5 | 10000 | 2 |  |  |  | 79055 | 33080
82 | Y | 552 | 31611 | 36387 | 64101700400238 | 12 |  | Westmoreland | LIGONIER TOWNSHIP |  | MILL CREEK |  | 56 | 76 | 31.5 | 48 | [5 empty] | 2014-06-16 | [19 empty] | Rural Major Collector | 56 | 20 | 76 | 31.5 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 1 |  |  |  | 76 | 249.45 | 18958.2 | [13 empty] | 76 |  |  |  |  | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1600 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 4 | 3890.25 | 15561 | 25 | [9 empty] | 18958.2 | 7500 | 3 | 19929 | 10000 | 2 |  |  |  | 7136 | 33083
83 | Y | 554 | 31304 | 36431 | 64103400500000 | 12 |  | Westmoreland | SALEM TOWNSHIP |  | BEAVER RUN |  | 44 | 64 | 24.2 | 48 | [5 empty] | 2014-05-29 | [19 empty] | Rural Local | 44 | 20 | 64 | 24.2 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | [10 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 7347 | 33180
84 | Y | 556 | 79418 | 36482 | 64201300201727 | 12 |  | Westmoreland | HEMPFIELD TOWNSHIP |  | SLATE CREEK |  | 30 | 50 | 26.7 | 54 | [5 empty] | 2014-07-08 | [19 empty] | Urban Collector | 30 | 20 | 50 | 26.7 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 1 |  |  | 3" | 50 | 25.68 | 1284 |  |  |  |  | 1 |  |  |  | 50 | 56.12 | 2806 |  |  |  |  | 50 | [12 empty] | 3" Conduit, 6" Unknown | 1 | Yes | 100 |  | 1 | 1600 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 4090 | 7500 | 1 | 12148.5 | 10000 | 2 |  |  |  | 83470 | 33209
85 | Y | 559 | 91189 | 36750 | 64405300120000 | 12 |  | Westmoreland | MUNICIPAL. OF MURRYSVILLE |  | TURTLE CREEK |  | 33 | 53 | 32.0 | 54 | [5 empty] | 2014-06-09 | [19 empty] | Rural Local | 33 | 20 | 53 | 32.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 50 | 120.88 | 6044 | [5 empty] | 50 | [12 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 8" Gas | 1 | Yes | 53 |  | 1 | 1600 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 6044 | 7500 | 1 | 12148.5 | 10000 | 2 |  |  |  | 7542 | 33469
86 | Y | 166 | 68786 | 37192 | 65100100500000 | 4 |  | Wyoming | TUNKHANNOCK TP JCT SR1002 |  | OUTLET LAKE CAREY |  | 36 | 56 | 29.0 | 50 | [5 empty] | 2014-06-19 | [19 empty] | Rural Local | 36 | 20 | 56 | 29.0 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 25 | [9 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 7542 | 33470
87 | Y | 167 | 68806 | 37222 | 65200100500596 | 4 |  | Wyoming | MONROE TWP .2 M S SR 2002 |  | SOUTH RUN CREEK |  | 30 | 50 | 27.6 | 48 | [5 empty] | 2014-06-19 | [19 empty] | Rural Local | 30 | 20 | 50 | 27.6 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 |  |  |  | 0 | 2.73 | 0 |  |  | 0 | 2.73 | 0 |  |  |  | 2.73 | 0 |  |  |  | 2.73 | 0 | 0 | 3890.25 | 0 | 25 | [9 empty] | 0 | 7500 | 0 | 0 | 10000 | 0 |  |  |  | 83478 | 33478
1 | -- | 411 | 89100 | 1397 | 02101100101018 | 11 |  | Allegheny | 1028'N.OF FREEPORT RD. |  | GUYS RUN |  | 36 | 56 | 28.0 | 54 | [25 empty] | Urban Minor Collector | 36 | 20 | 56 | 28.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | EQT |  | 50 | 120.88 | 6044 | [5 empty] | 50 | [11 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 8" EQT Gas | 1 | Yes | 56 |  | 1 | 3200 | 2 |  |  | 800 | 2.73 | 2184 | 3 |  | 1200 | 2.73 | 3276 | 3 |  | 1200 | 2.73 | 3276 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 6044 | 7500 | 1 | 16516.5 | 10000 | 2 |  |  |  | 74043 | 33543
2 | -- | 396 | 62523 | 505 | 02000804101108 | 11 |  | Allegheny | @ INTERSECTION W/SR 0910 |  | WEST BRANCH DEER CREEK |  | 24 | 44 | 70.0 | 82 | [25 empty] | Urban Principal Arterial | 24 | 20 | 44 | 70.0 | 58 | 24 | 82 |  | 1e-17 | 1e-28 | 1e-30 | 4 |  | 0 |  |  |  | 0 | 249.45 | 0 | [18 empty] | 1 |  |  |  | 80 | 477.3 | 38184 | [13 empty] | 80 |  |  |  |  | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3600 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 |  |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [10 empty] | 38184 | 7500 | 6 | 17608.5 | 10000 | 2 |  |  |  | 96689 | 20820
3 | -- | 12 | 1398 | 17209 | 27066601100240 | 1 |  | Forest | HICKORY TOWNSHIP |  | OVER BEAVER RUN |  | 37 | 57 | 27.5 | 48 | [25 empty] | Rural Major Collector | 37 | 20 | 57 | 27.5 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets not given in site visit notes |  |  | 67364 | 23795
4 | -- | 13 | 97328 | 25833 | 43017304703518 | 1 |  | Mercer | NEW LEBANON BOROUGH |  | OVER MILL CREEK |  | 28 | 48 | 40.8 | 62 | [25 empty] | Rural Major Collector | 28 | 20 | 48 | 40.8 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 0 |  |  | Marker in notes, parallel to road, distance unknown | 0 | 120.88 | 0 | [13 empty] | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets not given in site visit notes |  |  | 97506 | 24493
5 | -- | 3 | 97121 | 13084 | 20028501000629 | 1 |  | Crawford | NORTH SHENANGO TOWNSHIP |  | OVER BENNETT RUN |  | 38 | 58 | 43.0 | 64 | [25 empty] | Rural Minor Arterial | 38 | 20 | 58 | 43.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 | 1 |  |  | Noted in site visit, orientation/offset unknown | 58 | 32.1 | 1861.8 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3600 | 6 |  |  | 3600 | 2.73 | 9828 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | 8 | -4.5 | OUT OF ROW |  | 2 | 1 | 2 | 3 |  | 1861.8 | 7500 | 1 | 17608.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 96726 | 29947
6 | -- | 4 | 97117 | 13122 | 20040801800428 | 1 |  | Crawford | RICHMOND TOWNSHIP |  | OVER TEMPLE RUN | 20143580160 | 65 | 85 | 26.0 | 52 | [25 empty] | Rural Major Collector | 65 | 20 | 85 | 26.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0.25 | 1 | 4 |  | Noted in site visit, parallel to road, 20' offset | 85 | 120.88 | 10274.8 |  |  | 85 | [14 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 10 | 1 | 1 | 2 |  | 10274.8 | 7500 | 2 | 4982.25 | 10000 | 1 | COMPLETE , gas line size estimated from site visit photo of above ground valve |  |  | 67514 | 29982
7 | -- | 25 | 85095 | 8831 | 12012000400000 | 2 |  | Cameron | TRUMAN |  | BIG RUN |  | 21 | 41 | 41.6 | 66 | [25 empty] | Rural Minor Arterial | 21 | 20 | 41 | 41.6 | 42 | 24 | 66 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 30 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes |  |  | 96737 | 32153
8 | -- | 6 | 89176 | 13027 | 20088601600750 | 1 |  | Crawford | WOODCOCK BOROUGH |  | OVER GRAVEL RUN |  | 72 | 92 | 43.0 | 52 | [25 empty] | Rural Major Collector | 72 | 20 | 92 | 43.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 | 1 |  |  | Pedestal adj to GR, line parallel to road | 92 | 32.1 | 2953.2 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3000 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 12 | 1 | 2 | 3 |  | 2953.2 | 7500 | 1 | 15970.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 89023 | 32244
9 | -- | 29 | 81359 | 9577 | 14100200801726 | 2 |  | Centre | YARNELL |  | BRANCH LITTLE MARSH CR |  | 29 | 49 | 26.5 | 52 | [25 empty] | Rural Minor Collector | 29 | 20 | 49 | 26.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 25 |  |  |  |  | 100 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes |  |  | 9719 | 32307
10 | -- | 57 | 78606 | 25213 | 42000605100562 | 2 |  | McKean | HAZELHURST |  | MARVIN CREEK |  | 34 | 54 | 43.0 | 64 | [25 empty] | Rural Principal Arterial - Other | 34 | 20 | 54 | 43.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets not given in site visit notes | PRELIMINARY ASSUMPTIONS: BRIDGE IS LENGTHENED 5 FT/SIDE; NO AERIAL ELECTRIC POLE/WIRE RELOCATIONS NECESSARY BASED ON PICTURES |  | 79572 | 32308
11 | -- | 9 | 74663 | 17195 | 27006201302194 | 1 |  | Forest | TIONESTA BOROUGH |  | OVER TUBBS RUN |  | 25 | 45 | 35.1 | 64 | [25 empty] | Rural Principal Arterial | 25 | 20 | 45 | 35.1 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1 | 1 | 24 |  | Noted in site visit, crosses road and runs parallel to road | 109 | 477.3 | 52025.7 | [12 empty] | 109 |  |  |  |  | 0.5 | 1 | 3 |  | Noted in site visit, parallel to road, 25' offset, valves above ground | 45 | 120.88 | 5439.6 |  | 45 | [15 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 24" transverse (adjacent ) unknown ? | 0 | None | 0 | 0 | 1 | 8400 | 9 |  |  | 5400 | 2.73 | 14742 | 4 |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 57465.3 | 7500 | 8 | 30712.5 | 10000 | 4 | COMPLETE, pole offsets not given in site visit notes, poles appear closer than 15' in photos, gas line size estimated from PennDOT photos of above ground valve assembly | 24" san sewer crosses transversely over bridge abutment. This was classified as underground not attached. |  | 9656 | 32327
12 | -- | 61 | 88183 | 25297 | 42015500200000 | 2 |  | McKean | LIBERTY |  | PORTAGE CREEK |  | 73 | 93 | 41.1 | 62 | [25 empty] | Rural Major Collector | 73 | 20 | 93 | 41.1 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 25 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes |  |  | 96729 | 32365
13 | -- | 101 | 5589 | 12486 | 19004402401397 | 3 |  | Columbia | 1.9 MI NW OF JERSEYTOWN |  | TRIB E BR CHILLISQUAQUE |  | 22 | 42 | 33.3 | 56 | [25 empty] | Rural Major Collector | 22 | 20 | 42 | 33.3 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  | PPL | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 18 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offset in site visit notes/sketches | POLE OFFSET IS 18' IN SITE VISIT, CORRECT ALL EARIAL TO NO RELOCATIONS |  | 100550 | 32378
14 | -- | 115 | 6144 | 24938 | 41206101702204 | 3 |  | Lycoming | 3MI.E OF HUGHESVILLE |  | OVER SUGAR RUN |  | 46 | 66 | 26.0 | 50 | [25 empty] | Rural Local | 46 | 20 | 66 | 26.0 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 18 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offset in site visit notes/sketches |  |  | 85782 | 32401
15 | -- | 127 | 7009 | 31981 | 56015401501564 | 3 |  | Tioga | 4 MI SE OF FORKSVILLE |  | OVER DOUBLE RUN |  | 26 | 46 | 25.8 | 54 | [25 empty] | Rural Major Collector | 26 | 20 | 46 | 25.8 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 40 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 96734 | 32437
16 | -- | 141 | 97506 | 24493 | 40800500201030 | 4 |  | Luzerne | BUTLER TWP OVER I-80 WB |  | SR 0080 I-80 WB |  | 77 | 97 | 35.5 | 64 | [25 empty] | Rural Freeways/Expressways/Interstates | 77 | 20 | 97 | 35.5 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, no utilities visible in PennDOT photos |  |  | 96727 | 32478
17 | -- | 163 | 9978 | 35810 | 63403703303161 | 4 |  | Wayne | SCOTT TWP .2 M S SR 4043 |  | OQUAGA CREEK |  | 33 | 53 | 21.0 | 51 | [25 empty] | Rural Minor Collector | 33 | 20 | 53 | 21.0 | 27 | 24 | 51 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 25 |  |  |  |  | 20 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offset given in site visit notes |  |  | 9679 | 32507
18 | -- | 16 | 93160 | 33765 | 60042702200000 | 1 |  | Venango | PLUM TOWNSHIP |  | OVER SUGAR CREEK TRIB |  | 39 | 59 | 26.0 | 52 | [25 empty] | Rural Major Collector | 39 | 20 | 59 | 26.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 1 |  |  | Pedestal in photo, line parallel to road, 25' offset | 59 | 32.1 | 1893.9 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1e-17 | 3890.25 | 3.8903e-14 | [6 empty] | 1 | 1e-17 | 1 |  | 1893.9 | 7500 | 1 | 3.8903e-14 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, no sketch |  |  | 96736 | 32647
19 | -- | 165 | 10243 | 37172 | 65029201500354 | 4 |  | Wyoming | N MORELND TP .1M W SR2009 |  | BR WHITELOCK CREEK |  | 23 | 43 | 27.5 | 50 | [25 empty] | Rural Minor Collector | 23 | 20 | 43 | 27.5 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 25 |  |  |  |  | 15 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offset given in site visit notes |  |  | 68876 | 35471
20 | -- | 197 | 99555 | 28493 | 48003300200000 | 5 |  | Northampton | US22/PA33 INTERCHANGE |  | SR 22(LR772) |  | 216 | 236 | 56.5 | 80 | [25 empty] | Urban Freeways/Expressways/Interstates | 216 | 20 | 236 | 56.5 | 56 | 24 | 80 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 0 |  |  | Attached to bridge, services lights on bridge | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None - conduit in parapet for lighting | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets not given in site visit |  |  | 9969 | 35508
21 | -- | 198 | 99555 | 28494 | 48003300210000 | 5 |  | Northampton | US22/PA33 INTERCHANGE |  | SR 22(LR772) |  | 216 | 236 | 56.5 | 80 | [25 empty] | Urban Freeways/Expressways/Interstates | 216 | 20 | 236 | 56.5 | 56 | 24 | 80 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 0 |  |  | Attached to bridge, services lights on bridge | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None - conduit in parapet for lighting | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets not given in site visit |  |  | 68917 | 35624
22 | -- | 201 | 85947 | 28606 | 48051202101582 | 5 |  | Northampton | W.MOORESTOWN RD.@ HEYER |  | BUSHKILL CR. |  | 80 | 100 | 26.2 | 56 | [25 empty] | Urban Minor Arterial | 80 | 20 | 100 | 26.2 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 10 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes | Assuming Integral Abutment no relocation necessary |  | 68927 | 35654
23 | -- | 213 | 86306 | 10599 | 15400800402407 | 6 |  | Chester | BRANDYWINE MANOR 19E02 (3360E09) |  | INDIAN RUN |  | 22 | 42 | 24.0 | 46 | [25 empty] | Rural Local | 22 | 20 | 42 | 24.0 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 5" Unknown | 1 | Yes | 42 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | UNKNOWN | [5 empty] | 1 | 0 | 1 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, no overhead utilities seen in site visit photos, unknown pipe attached to outside of bridge, pipe not noted in notes, no utility sketch, pipe size estimated from photos |  |  | 67584 | 35675
24 | -- | 22 | 2548 | 34056 | 61012700902381 | 1 |  | Warren | TRIUMPH TOWNSHIP |  | OVER GORDON RUN |  | 29 | 49 | 37.0 | 57 | [25 empty] | Rural Major Collector | 29 | 20 | 49 | 37.0 | 33 | 24 | 57 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0.25 | 1 |  |  | Noted in PennDOT notes, orientation/distance unknown | 49 | 477.3 | 23387.7 | [13 empty] | 49 |  |  |  | 0.25 | 0 |  |  | Marker/vent pipe visible, parallel to road, 20' offset | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 3" Unknown | 1 | Yes | 49 | 0 | 1 | 4800 | 4 |  |  | 3200 | 2.73 | 8736 | 1 |  | 800 | 2.73 | 2184 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [5 empty] | 7 | 2 | 3 | 5 |  | 23387.7 | 7500 | 4 | 24774.75 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes, unknown attached pipe size estimated from site visit photos |  |  | 56752 | 35765
25 | -- | 23 | 84954 | 34077 | 61095701700981 | 1 |  | Warren | FREEHOLD TOWNSHIP |  | OVER LITTLE BROKENSTRAW |  | 72 | 92 | 39.3 | 52 | [25 empty] | Rural Minor Arterial | 72 | 20 | 92 | 39.3 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 | 1 |  |  | Marker/vent pipe visible, perpendicular, far approach | 92 | 120.88 | 11120.96 | [13 empty] | 92 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 | 1 |  |  | Possible crossing, perpendicular, far approach | 52 | 32.1 | 1669.2 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 2 | 1 | 3 |  | 12790.16 | 7500 | 2 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, poles appear closer than 15' |  |  | 79580 | 35802
26 | -- | 24 | 97452 | 34169 | 61301000600428 | 1 |  | Warren | SPRING CREEK TOWNSHIP |  | OVER WHITNEY RUN | 20143571624 | 51 | 71 | 33.0 | 50 | [25 empty] | Rural Major Collector | 51 | 20 | 71 | 33.0 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 | 1 |  |  | Pedestal in photo, parallel to road, distance unknown | 71 | 32.1 | 2279.1 |  |  |  | 1e-17 | 1 |  |  | Pedestal noted in site visit, orientation/offset unknown | 71 | 25.68 | 1823.28 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1e-17 | 3890.25 | 3.8903e-14 | [6 empty] | 2 | 1e-17 | 2 |  | 4102.38 | 7500 | 1 | 3.8903e-14 | 10000 | 1 | COMPLETE |  |  | 9978 | 35810
27 | -- | 224 | 18051 | 98 | 01011601100000 | 8 |  | Adams | 1 MI N E OF FAIRFIELD |  | MUDDY RUN |  | 36 | 56 | 26.2 | 64 | [25 empty] | Rural Minor Arterial | 36 | 20 | 56 | 26.2 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 20 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes, 20' Left and 20' Right |  |  | 10230 | 37163
28 | -- | 231 | 74951 | 229 | 01200600400591 | 8 |  | Adams | 2 MI. S.E. HUNTERSTOWN |  | CSX; WESTERN MARYLAND RR | 20143580152 | 75 | 95 | 27.6 | 52 | [25 empty] | Rural Minor Collector | 75 | 20 | 95 | 27.6 | 28 | 24 | 52 |  | 1 | 45 | 450 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  | Attached to bridge | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 10" Gas | 1 | Yes | 95 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 18 | 1 | 0 | 1 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes, 30' Left and 18' Right, size of attached gas line estimated from site visit photo |  |  | 10243 | 37172
29 | -- | 27 | 88155 | 9360 | 14014403400099 | 2 |  | Centre | BELLEFONTE |  | YOCUM RUN |  | 32 | 52 | 44.0 | 68 | [25 empty] | Urban Other Principal Arterial | 32 | 20 | 52 | 44.0 | 44 | 24 | 68 |  | 1e-17 | 1e-28 | 1e-30 | 8 | 1 | 1 |  |  | Noted in site visit photo, parallel to road, offset 15' | 52 | 249.45 | 12971.4 | [13 empty] | 52 |  |  |  | 1e-17 | 1 |  |  | Noted in site visit notes, crosses at far approach | 68 | 477.3 | 32456.4 | [13 empty] | 68 |  |  |  | 1 | 1 |  |  | Noted in site visit, parallel to road, 10' offset | 52 | 120.88 | 6285.76 | [13 empty] | 52 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 | 1 |  |  | Noted in site visit, 3 lines painted, parallel to road, distance unknown | 156 | 32.1 | 5007.6 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4800 | 2 |  |  | 1200 | 2.73 | 3276 | 4 |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 2 | 3890.25 | 7780.5 | [5 empty] | 5 | 4 | 2 | 6 |  | 56721.16 | 7500 | 8 | 20884.5 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes |  |  | 68786 | 37192
30 | -- | 232 | 87675 | 319 | 01301301000061 | 8 |  | Adams | KNOXLYN |  | MARSH CREEK |  | 30 | 50 | 13.8 | 52 | [25 empty] | Rural Minor Collector | 30 | 20 | 50 | 13.8 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 15 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes, 30' Left and 15' Right |  |  | 68806 | 37222
31 | -- | 247 | 87457 | 14578 | 22400400202505 | 8 |  | Dauphin | 2 MI. W. ENDERS |  | ARMSTRONG CREEK |  | 68 | 88 | 26.9 | 52 | [25 empty] | Rural Local | 68 | 20 | 88 | 26.9 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 18 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes |  |  | 79078 | 4900
32 | -- | 248 | 87686 | 17407 | 28023302000092 | 8 |  | Franklin | AT CALEDONIA STATE PARK |  | CARBAUGH RUN |  | 47 | 67 | 37.4 | 56 | [25 empty] | Rural Major Collector | 47 | 20 | 67 | 37.4 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  | Noted in site visit, crosses at far side near SR 30 | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  | Noted in site visit, crosses at far side near SR 30 | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 30 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes |  |  | 78877 | 4946
33 | -- | 31 | 85125 | 9431 | 14304001301062 | 2 |  | Centre | PORT MATILDA |  | LAUREL RUN |  | 39 | 59 | 50.0 | 74 | [25 empty] | Rural Principal Arterial - Other | 39 | 20 | 59 | 50.0 | 50 | 24 | 74 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  |  | Water blow off noted in site visit notes, orientation/distance unknown | 59 | 249.45 | 14717.55 | [13 empty] | 59 |  |  |  | 1 | 1 |  |  | Sewer manhole in photo, orientation unknown, 15' offset | 59 | 477.3 | 28160.7 | [13 empty] | 59 |  |  |  | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 10200 | 8 |  |  | 4800 | 2.73 | 13104 | 3 |  | 1800 | 2.73 | 4914 | 5 |  | 3000 | 2.73 | 8190 | 1 |  | 600 | 2.73 | 1638 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 42878.25 | 7500 | 6 | 35626.5 | 10000 | 4 | COMPLETE, pole offsets not given in site visit notes, poles appear closer than 15' |  |  | 78889 | 4953
34 | -- | 249 | 63173 | 17408 | 28027400200000 | 8 |  | Franklin | 1 ML. N. OF DOYLESBURG |  | BR. TUSCARORA CREEK | 20143580224 | 38 | 58 | 26.0 | 52 | [25 empty] | Rural Minor Arterial | 38 | 20 | 58 | 26.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 30 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes |  |  | 85635 | 4957
35 | -- | 262 | 91266 | 21403 | 36101900500000 | 8 |  | Lancaster | 1.5 MI. S.E. CHURCHTOWN |  | Conestoga River | 20143571514 | 39 | 59 | 17.8 | 52 | [25 empty] | Rural Local | 39 | 20 | 59 | 17.8 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 79081 | 5147
36 | -- | 34 | 91413 | 9778 | 14400200702338 | 2 |  | Centre | CLARENCE |  | LITTLE SANDY RUN |  | 46 | 66 | 25.0 | 52 | [25 empty] | Rural Minor Collector | 46 | 20 | 66 | 25.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 1 | 1 |  |  | Noted in site visit notes, parallel to road, 18' offset | 66 | 249.45 | 16463.7 | [13 empty] | 66 |  |  |  | 1 | 1 |  |  | Noted in site visit notes, crosses road, mh 10' behind near abutment | 52 | 477.3 | 24819.6 | [13 empty] | 52 |  |  |  | 1e-17 | 1 |  |  | Noted in site visit, crosses road, 50' behind near abutment | 52 | 120.88 | 6285.76 | [13 empty] | 52 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3200 | 3 |  |  | 1200 | 2.73 | 3276 | 4 |  | 1600 | 2.73 | 4368 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 8 | 3 | 1 | 4 |  | 47569.06 | 7500 | 7 | 12626.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 85764 | 8994
37 | -- | 271 | 87515 | 21482 | 36105300200000 | 8 |  | Lancaster | 0.5 MI. W. DENVER BORO |  | COCALICO CREEK |  | 41 | 61 | 19.0 | 52 | [25 empty] | Urban Local | 41 | 20 | 61 | 19.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  | Noted in site visit, orientation/offset unknown | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE | UNDERGROUND GAS NOTED IN SITE VISIT NOT FIBER OPTIC, GAS LINE APPEARS TO NOT CONFLICT WITH BRIDGE |  | 85762 | 9104
38 | -- | 275 | 20123 | 21533 | 36201000560000 | 8 |  | Lancaster | PUSEYVILLE |  | W BR OCTORARO |  | 55 | 75 | 24.0 | 52 | [25 empty] | Rural Local | 55 | 20 | 75 | 24.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 85693 | 23144
39 | -- | 281 | 19812 | 21601 | 36300400200000 | 8 |  | Lancaster | DRUMORE |  | FISHING CREEK |  | 35 | 55 | 25.0 | 52 | [25 empty] | Rural Minor Collector | 35 | 20 | 55 | 25.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 89633 | 23228
40 | -- | 38 | 85076 | 11399 | 17021904201459 | 2 |  | Clearfield | CURRY RUN |  | CURRY RUN |  | 50 | 70 | 41.7 | 62 | [25 empty] | Rural Principal Arterial - Other | 50 | 20 | 70 | 41.7 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 |  |  |  | Noted in PennDOT notes, orientation/distance unknown | 70 | 120.88 | 8461.6 | [13 empty] | 70 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 | 1 |  |  | Shown in site visit, orientation/distance unknown | 70 | 32.1 | 2247 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 800 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 40 | 2 | 17.15 | IN ROW | 2 |  | 1 | 1 | 2 |  | 10708.6 | 7500 | 2 | 6074.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 85683 | 23330
41 | -- | 283 | 20151 | 21662 | 36303201100000 | 8 |  | Lancaster | Letort Road over Little Conestoga Creek |  | LITTLE CONESTOGA CREEK |  | 85 | 105 | 28.0 | 56 | [25 empty] | Urban Minor Collector | 85 | 20 | 105 | 28.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 25 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes, no sketch |  |  | 89639 | 23136
42 | -- | 40 | 93323 | 11404 | 17021904700185 | 2 |  | Clearfield | BELLS LANDING |  | BELL RUN |  | 73 | 93 | 41.7 | 66 | [25 empty] | Rural Principal Arterial - Other | 73 | 20 | 93 | 41.7 | 42 | 24 | 66 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 | 1 |  |  | Shown in site visit, parallel to roadway, 13' offset | 93 | 32.1 | 2985.3 | 13 | 6.15 | IN ROW | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1e-17 | 3890.25 | 3.8903e-14 | 40 |  |  |  |  | 25 | 1 | 1e-17 | 1 |  | 2985.3 | 7500 | 1 | 3.8903e-14 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 85811 | 26785
43 | -- | 284 | 91352 | 22812 | 38402000800000 | 8 |  | Lebanon | INDIANTOWN GAP |  | AIRE RUN | 20143571525 | 25 | 45 | 66.2 | 90 | [25 empty] | Rural Major Collector | 25 | 20 | 45 | 66.2 | 66 | 24 | 90 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 | 0 |  |  | Noted in site visit, assume crossing road, valves 50' back from near abutment | 0 | 249.45 | 0 | [13 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 20 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes | ACESS BOX AND WATER CAPS NOTED, APPEAR TO BE AWAY FROM BRIDGE AND WON'T INTERFERE WITH CONSTRUCTION |  | 91680 | 26795
44 | -- | 42 | 88626 | 11461 | 17025503200000 | 2 |  | Clearfield | HOLLYWOOD |  | MINE CAVE IN |  | 53 | 73 | 36.0 | 56 | [25 empty] | Rural Minor Arterial | 53 | 20 | 73 | 36.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  |  | Noted in site visit, parallel to road, bridge buried | 73 | 249.45 | 18209.85 | [13 empty] | 73 |  |  |  | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 |  |  |  | Noted in PennDOT notes, parallel to road, bridge buried | 73 | 120.88 | 8824.24 | [13 empty] | 73 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 6600 | 6 |  |  | 3600 | 2.73 | 9828 | 4 |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 27034.09 | 7500 | 4 | 25798.5 | 10000 | 3 | COMPLETE, pole offsets not given in site visit notes, poles appear closer than 15' |  |  | 79157 | 26811
45 | -- | 287 | 79054 | 29468 | 50001707600000 | 8 |  | Perry | LIVERPOOL BORO |  | TRIB TO SUSQUEHANNA |  | 30 | 50 | 33.3 | 58 | [25 empty] | Rural Major Collector | 30 | 20 | 50 | 33.3 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 79158 | 26832
46 | -- | 44 | 3571 | 11698 | 17200703101047 | 2 |  | Clearfield | WEST DECATUR |  | LAUREL RUN | 20143580324 | 27 | 47 | 25.9 | 52 | [25 empty] | Rural Local | 27 | 20 | 47 | 25.9 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 1 | 1 |  |  | Noted in site visit, parallel to road, offset unknown | 47 | 249.45 | 11724.15 | [13 empty] | 47 |  |  |  | 1 | 1 |  |  | Noted in site visit, parallel to road, offset unknown | 47 | 477.3 | 22433.1 | [13 empty] | 47 |  |  |  | 1 | 1 |  |  | Noted in site visit, parallel to road, 15' offset | 47 | 120.88 | 5681.36 | [13 empty] | 47 | 15 | 2.05 | IN ROW | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 7200 | 6 |  |  | 4800 | 2.73 | 13104 | 1 |  | 800 | 2.73 | 2184 | 2 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | 30 | 8 | 9.05 | IN ROW |  | 8 | 3 | 3 | 6 |  | 39838.61 | 7500 | 6 | 31326.75 | 10000 | 4 | COMPLETE, pole offsets given in site visit notes | PRELIMINARY ASSUMPTIONS: NO BRIDGE LENGTHENING; NO SAN SEWER RELOCATE NECESSARY, CHECK POLE/LINE RELOCATION QTY'S |  | 11649 | 26887
47 | -- | 45 | 85119 | 11807 | 17300902501042 | 2 |  | Clearfield | 2 MI SE TROUTVILLE |  | E BR MAHONING CREEK |  | 52 | 72 | 24.0 | 52 | [25 empty] | Rural Minor Collector | 52 | 20 | 72 | 24.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 | 1 |  |  | Noted in site visit, crosses road, distance from approach unknown | 52 | 25.68 | 1335.36 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 1 |  |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 25 | 8 | 5 | IN ROW |  | 8 | 1 | 1 | 2 |  | 1335.36 | 7500 | 1 | 4982.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 11730 | 26888
48 | -- | 289 | 87465 | 29565 | 50085002201839 | 8 |  | Perry | 1MI NO OF FORT ROBINSON |  | BIXLERS RUN |  | 88 | 108 | 26.4 | 52 | [25 empty] | Rural Major Collector | 88 | 20 | 108 | 26.4 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  | Stand pipe and mh noted in site visit, assume parallel to road, offset unknown | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 75 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes | Walsh corrected to no sanitary sewer conflict. |  | 96445 | 26901
49 | -- | 47 | 69040 | 12239 | 18047700300000 | 2 |  | Clinton | SALONA |  | LONG RUN | 20143580327 | 43 | 63 | 25.0 | 56 | [25 empty] | Urban Collector | 43 | 20 | 63 | 25.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 1 |  |  |  | Noted in PennDOT notes, orientation/offset unknown | 63 | 249.45 | 15715.35 | [13 empty] | 63 |  |  |  | 1 |  |  |  | Noted in PennDOT notes, orientation/offset unknown | 63 | 477.3 | 30069.9 | [13 empty] | 63 |  |  |  | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1 | 1 |  |  | Noted in PennDOT notes, orientation/offset unknown | 63 | 25.68 | 1617.84 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4800 | 5 |  |  | 2000 | 2.73 | 5460 | 4 |  | 1600 | 2.73 | 4368 | 3 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | UNKNOW |  |  |  | 6 |  | 1 | 1 | 2 |  | 47403.09 | 7500 | 7 | 16994.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes | PENNDOT STATES SEVERAL UNDERGROUND UTILITIES, SITE VISIT PICTURES & CHECKLIST SHOW NOTHING NEEDS FURTHER INVESTIGAGED |  | 85879 | 26904
50 | -- | 48 | 85152 | 15531 | 24012002801546 | 2 |  | Elk | CITY OF ST MARYS |  | BRANCH ELK CREEK |  | 23 | 43 | 44.0 | 66 | [25 empty] | Urban Minor Arterial | 23 | 20 | 43 | 44.0 | 42 | 24 | 66 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 1 | 1 |  |  | Noted in site visit, crosses road, 25' north of bridge approach | 66 | 249.45 | 16463.7 | [13 empty] | 66 |  |  |  | 1 | 1 |  |  | Noted in site visit, crosses road, 27' north of bridge | 66 | 477.3 | 31501.8 | [13 empty] | 66 |  |  |  | 1 | 1 |  |  | Noted in site visit, crosses road, 23' south of bridge approach | 43 | 120.88 | 5197.84 | [13 empty] | 43 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 7800 | 5 |  |  | 3000 | 2.73 | 8190 | 5 |  | 3000 | 2.73 | 8190 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 0 | 3 | 2 | 5 |  | 53163.34 | 7500 | 8 | 29074.5 | 10000 | 3 | COMPLETE, line crosses over bridge |  |  | 89628 | 26907
51 | -- | 303 | 91367 | 37878 | 66304500800853 | 8 |  | York | JACOBS MILLS |  | OIL CREEK |  | 43 | 63 | 25.6 | 56 | [25 empty] | Rural Local | 43 | 20 | 63 | 25.6 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 15 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes |  |  | 79204 | 26914
52 | -- | 50 | 88185 | 15560 | 24021904900000 | 2 |  | Elk | JOHNSONBURG |  | POWERS RUN |  | 63 | 83 | 52.3 | 64 | [25 empty] | Rural Principal Arterial - Other | 63 | 20 | 83 | 52.3 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 8 | 1 |  |  |  | Moved to attached to structure column | 0 | 249.45 | 0 | [17 empty] | 1 | 0 |  |  | Moved to attached to structure column | 0 | 477.3 | 0 | [17 empty] | 1 | 2 |  |  | 2 gas lines noted in site visit, parallel to road, offset unknown | 332 | 120.88 | 40132.16 | [13 empty] | 332 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 6" Water, 10" Sewer | 1 | Yes | 166 | 0 | 1 | 2400 | 3 |  |  | 1200 | 2.73 | 3276 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 | 3890.25 | 3890.25 | [5 empty] | 10 | 3 | 1 | 4 |  | 40132.16 | 7500 | 6 | 10442.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, water and sewer line pipe sizes estimated from site visit photos |  |  | 79170 | 26924
53 | -- | 51 | 88195 | 19992 | 34003507200000 | 2 |  | Juniata | MCALISTERVILLE |  | TRIB LOST CREEK |  | 34 | 54 | 34.0 | 58 | [25 empty] | Rural Minor Arterial | 34 | 20 | 54 | 34.0 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1 | 1 |  |  | Noted in site visit, orientation unknown, mh 27' left from edge of road | 54 | 477.3 | 25774.2 | [13 empty] | 54 |  |  |  | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 0 |  |  | 0 | 2.73 | 0 | 3 |  | 1800 | 2.73 | 4914 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 30 | 3 | 10 | IN ROW |  |  | 1 | 2 | 3 |  | 25774.2 | 7500 | 4 | 14332.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes | CHECK POLE/LINE & UNDERGROUND RELOCATION QTY'S, SAN SEWER RELOCATION? PENNDOT NOTES STORM SEWER RELOCATION |  | 76368 | 26962
54 | -- | 304 | 87596 | 37890 | 66305100200000 | 8 |  | York | 1 MI.W. OF JEFFERSON |  | CODORUS CREEK |  | 34 | 54 | 20.0 | 48 | [25 empty] | Rural Local | 34 | 20 | 54 | 20.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, no utilities in conflict, site visit notes may be referencing a different bridge, confirmed no conflict with Google Street View |  |  | 96447 | 27011
55 | -- | 307 | 83428 | 37976 | 66401200602478 | 8 |  | York | 0.5 MI.E. OF KRALLTOWN |  | DOE RUN |  | 60 | 80 | 24.6 | 52 | [25 empty] | Rural Minor Collector | 60 | 20 | 80 | 24.6 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 11758 | 27017
56 | -- | 54 | 4218 | 20118 | 34100400300549 | 2 |  | Juniata | MCALISTERVILLE |  | LITTLE LOST CREEK |  | 22 | 42 | 27.4 | 52 | [25 empty] | Rural Local | 22 | 20 | 42 | 27.4 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1e-17 | 1 |  |  | Noted in site visit, orientation/offset unknown | 42 | 249.45 | 10476.9 | [13 empty] | 42 |  |  |  | 1e-17 | 1 |  |  | Noted in site visit, orientation/offset unknown | 42 | 477.3 | 20046.6 | [13 empty] | 42 |  |  |  | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1 | 0 |  |  | Site visit indicates water and sewer | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 5400 | 4 | 100 |  | 2400 | 2.73 | 6552 | 3 |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 4 | 2 | 2 | 4 |  | 30523.5 | 7500 | 5 | 22522.5 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes |  |  | 79185 | 27042
57 | -- | 312 | 21563 | 4010 | 05005600901305 | 9 |  | Bedford | 1.68 MILE WEST FROM PA 96 |  | BAREFOOT RUN | 20143561437 | 47 | 67 | 39.8 | 64 | [25 empty] | Rural Principal Arterial | 47 | 20 | 67 | 39.8 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 30 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH lines 30'+ from bridge. No relocations. |  |  | 85849 | 27055
58 | -- | 316 | 21552 | 4177 | 05101200400000 | 9 |  | Bedford | 1.73 MILE EAST FROM SR 1009 |  | RAYSTOWN BR JUNIATA RIV. |  | 230 | 250 | 19.6 | 50 | [25 empty] | Rural Local | 230 | 20 | 250 | 19.6 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 30 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH poles offset 24' from bridge per site visit info. No relocations. |  |  | 79187 | 27059
59 | -- | 317 | 21600 | 4196 | 05102000500880 | 9 |  | Bedford | 0.16 MILE EAST FROM SR 1009 |  | PIPERS RUN | 20143580298 | 38 | 58 | 28.3 | 52 | [25 empty] | Rural Minor Collector | 38 | 20 | 58 | 28.3 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 20 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified near the bridge. UG Telephone crosses the road 20'+ from the bridge abutment. |  |  | 99555 | 28493
60 | -- | 58 | 78605 | 25216 | 42000605800309 | 2 |  | McKean | MARVINDALE |  | WARNER BROOK |  | 45 | 65 | 42.5 | 64 | [25 empty] | Rural Principal Arterial - Other | 45 | 20 | 65 | 42.5 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 | 1 |  |  | Noted in site visit, parallel to road, offset unknown | 65 | 120.88 | 7857.2 | [13 empty] | 65 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 13200 | 7 |  |  | 8400 | 2.73 | 22932 | 2 |  | 2400 | 2.73 | 6552 | 1 |  | 1200 | 2.73 | 3276 | 1 |  | 1200 | 2.73 | 3276 | 5 | 3890.25 | 19451.25 | [5 empty] | 8 | 1 | 5 | 6 |  | 7857.2 | 7500 | 2 | 55487.25 | 10000 | 6 | COMPLETE, pole offsets given in site visit notes |  |  | 99555 | 28494
61 | -- | 59 | 4344 | 25243 | 42004600600000 | 2 |  | McKean | 3 MI SE BETULA |  | HAVENS BROOK |  | 30 | 50 | 26.8 | 56 | [25 empty] | Rural Minor Arterial | 30 | 20 | 50 | 26.8 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 | 1 |  |  | Noted in site visit, orientation/offset unknown | 50 | 120.88 | 6044 | [13 empty] | 50 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1e-17 | 3890.25 | 3.8903e-14 | [6 empty] | 1 | 1e-17 | 1 |  | 6044 | 7500 | 1 | 3.8903e-14 | 10000 | 1 | COMPLETE |  |  | 85947 | 28606
62 | -- | 318 | 74424 | 4386 | 05403101601407 | 9 |  | Bedford | VILLAGE OF QUEEN |  | BEAVERDAM CREEK |  | 61 | 81 | 25.0 | 54 | [25 empty] | Rural Minor Collector | 61 | 20 | 81 | 25.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 30 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH poles 12'+ from bridge. No OH relocation anticipated. No other utilities identified in site visit. |  |  | 67256 | 28660
63 | -- | 333 | 88142 | 17853 | 29065504501203 | 9 |  | Fulton | 1.4 MI. SOUTH OF TURNPIKE |  | FORTUNE TELLER CREEK |  | 23 | 43 | 24.5 | 52 | [25 empty] | Rural Major Collector | 23 | 20 | 43 | 24.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 30 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No OH utilities within 20' of the bridge. No other utilities identified in site visit or by PennDOT. |  |  | 12098 | 28672
64 | -- | 62 | 85215 | 25308 | 42015501900182 | 2 |  | McKean | 1 MI N PORT ALLEGHENY |  | TWO MILE CREEK |  | 45 | 65 | 41.6 | 64 | [25 empty] | Rural Major Collector | 45 | 20 | 65 | 41.6 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 | 8 |  | Noted in site visit, crosses 60' far approach | 64 | 120.88 | 7736.32 | [5 empty] | 64 | [11 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 7736.32 | 7500 | 2 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, poles appear closer than 15' in photos, gas line size estimated from site visit photos |  |  | 12717 | 30678
65 | -- | 63 | 4341 | 25313 | 42015502701162 | 2 |  | McKean | 3 MI SE LARABEE |  | ROCK RUN |  | 33 | 53 | 36.0 | 64 | [25 empty] | Rural Major Collector | 33 | 20 | 53 | 36.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 | 1 |  |  | Noted in site visit, orientation/offset unknown | 53 | 120.88 | 6406.64 | [13 empty] | 53 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 11000 | 7 |  |  | 7000 | 2.73 | 19110 | 2 |  | 2000 | 2.73 | 5460 | 1 |  | 1000 | 2.73 | 2730 | 1 |  | 1000 | 2.73 | 2730 | 4 | 3890.25 | 15561 | [5 empty] | 0 | 1 | 4 | 5 |  | 6406.64 | 7500 | 1 | 45591 | 10000 | 5 | COMPLETE, line crosses over bridge |  |  | 12710 | 30679
66 | -- | 335 | 74433 | 18576 | 31002202300000 | 9 |  | Huntingdon | OVER TR 26 |  | PA 0026 |  | 62 | 82 | 65.0 | 86 | [25 empty] | Urban Principal Arterial | 62 | 20 | 82 | 65.0 | 62 | 24 | 86 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 60 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH 15' to 20' offset from bridge. Gas line runs parallel to bridge 25'+ offset from bridge. No anticipated relocations. |  |  | 12710 | 30680
67 | -- | 65 | 85234 | 25418 | 42034604101617 | 2 |  | McKean | 3 MI E BRADFORD |  | FOSTER BROOK |  | 51 | 71 | 37.0 | 64 | [25 empty] | Urban Collector | 51 | 20 | 71 | 37.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 1e-17 | 1 |  |  | Noted in site visit, orientation/offset unknown | 71 | 249.45 | 17710.95 | [13 empty] | 71 |  |  |  | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  |  | Noted in site visit, orientation/offset unknown | 71 | 120.88 | 8582.48 | [13 empty] | 71 |  |  |  | 1 | 1 |  |  | Noted in PennDOT notes, orientation/offset unknown | 71 | 191.55 | 13600.05 | [13 empty] | 71 |  |  |  | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 8000 | 4 |  |  | 3200 | 2.73 | 8736 | 1 |  | 800 | 2.73 | 2184 | 2 |  | 1600 | 2.73 | 4368 | 3 |  | 2400 | 2.73 | 6552 | 3 | 3890.25 | 11670.75 | [6 empty] | 3 | 3 | 6 |  | 39893.48 | 7500 | 6 | 33510.75 | 10000 | 4 | COMPLETE, pole offsets not given in site visit, poles appear closer than 15' in photos |  |  | 85810 | 30730
68 | -- | 66 | 4336 | 25420 | 42034604201811 | 2 |  | McKean | DERRICK CITY |  | FOSTER BROOK |  | 51 | 71 | 36.5 | 64 | [25 empty] | Rural Major Collector | 51 | 20 | 71 | 36.5 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 | 1 |  |  | Noted in site visit, orientation unknown, mh 30' off shoulder | 71 | 477.3 | 33888.3 | [13 empty] | 71 |  |  |  | 1e-17 | 1 |  |  | Noted in site visit, crosses road, 30' near approach | 64 | 120.88 | 7736.32 | [13 empty] | 64 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 8000 | 4 |  |  | 3200 | 2.73 | 8736 | 2 |  | 1600 | 2.73 | 4368 | 4 |  | 3200 | 2.73 | 8736 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [5 empty] | 10 | 2 | 3 | 5 |  | 41624.62 | 7500 | 6 | 33510.75 | 10000 | 4 | COMPLETE, pole offsets given in site visit notes |  |  | 85724 | 30832
69 | -- | 67 | 85237 | 25459 | 42064602900000 | 2 |  | McKean | 1 MI N GILMORE |  | PENNBROOK RUN |  | 32 | 52 | 33.3 | 56 | [25 empty] | Rural Major Collector | 32 | 20 | 52 | 33.3 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1e-17 | 1 |  |  | Noted in site visit, orientation/offset unknown | 52 | 249.45 | 12971.4 | [13 empty] | 52 |  |  |  | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  |  | Noted in site visit, orientation/offset unknown | 52 | 120.88 | 6285.76 | [13 empty] | 52 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3200 | 6 |  |  | 2400 | 2.73 | 6552 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 2 | 1 | 3 |  | 19257.16 | 7500 | 3 | 12626.25 | 10000 | 2 | COMPLETE, pole offsets not given in site visit, poles appear closer than 15' in photos |  |  | 47695 | 30856
70 | -- | 68 | 4340 | 25461 | 42077001300784 | 2 |  | McKean | CUSTER CITY |  | SHEPPARD RUN |  | 32 | 52 | 25.8 | 56 | [25 empty] | Rural Major Collector | 32 | 20 | 52 | 25.8 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 1 | 1 |  |  | Noted in PennDOT notes, orientation/offset unknown | 52 | 249.45 | 12971.4 | [13 empty] | 52 |  |  |  | 1 | 1 |  |  | Noted in PennDOT notes, orientation/offset unknown | 52 | 477.3 | 24819.6 | [13 empty] | 52 |  |  |  | 1e-17 | 1 |  |  | Noted in site visit, parallel to road, 5' offset | 52 | 120.88 | 6285.76 | [13 empty] | 52 | 5 | 7.1 | IN ROW | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2800 | 4 |  |  | 1600 | 2.73 | 4368 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 25 | 15 | -2.9 | OUT OF ROW |  | 15 | 3 | 1 | 4 |  | 44076.76 | 7500 | 6 | 11534.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes | BRIDGE IS PHASED; 5" GAS LINE IS TECHNICALLY NOT ATTACHED TO BRIDGE THEREFORE IT'S QUANTIFIED AS UNDERGROUND, TEMPORARY RELOCATE OR BORE UNDER CREEK |  | 12522 | 30862
71 | -- | 69 | 88630 | 25462 | 42077001400000 | 2 |  | McKean | CUSTER CITY |  | SHEPPARD RUN | 20143580408 | 34 | 54 | 26.0 | 56 | [25 empty] | Urban Collector | 34 | 20 | 54 | 26.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 1e-17 | 1 |  |  | Noted in site visit, orientation/offset unknown | 54 | 249.45 | 13470.3 | [13 empty] | 54 |  |  |  | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  |  | Noted in site visit, orientation/offset unknown, cut and capped | 54 | 120.88 | 6527.52 | [13 empty] | 54 |  |  |  | 1 |  |  |  | Noted in PennDOT notes, orientation/offset unknown | 54 | 191.55 | 10343.7 | [13 empty] | 54 |  |  |  | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  | Electric lines overhead | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 1 | Light service only |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 40 | 2 | 1 | 3 |  | 30341.52 | 7500 | 5 | 4982.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes, street light service line only overhead conflict |  |  | 56830 | 7262
72 | -- | 70 | 68965 | 25489 | 42101500100472 | 2 |  | McKean | WRIGHTS CORNERS |  | NORTH BRANCH COLE CREEK |  | 33 | 53 | 31.0 | 56 | [25 empty] | Rural Local | 33 | 20 | 53 | 31.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  |  | Noted in site visit, crosses road, within near approach | 56 | 120.88 | 6769.28 | [13 empty] | 56 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 40 | 1 | 0 | 1 |  | 6769.28 | 7500 | 1 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes |  |  | 81284 | 10497
73 | -- | 71 | 4486 | 25495 | 42200100100806 | 2 |  | McKean | 6 MI SW CLERMONT |  | SEVEN MILE RUN | 20143580345 | 33 | 53 | 26.2 | 50 | [25 empty] | Rural Major Collector | 33 | 20 | 53 | 26.2 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0.25 | 1 |  |  | Noted in site visit, crosses road, under bridge | 50 | 120.88 | 6044 | [13 empty] | 50 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 | 1 |  |  | Noted in site visit, crosses road, under bridge | 50 | 32.1 | 1605 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1e-17 | 3890.25 | 3.8903e-14 | [6 empty] | 2 | 1e-17 | 2 |  | 7649 | 7500 | 2 | 3.8903e-14 | 10000 | 1 | COMPLETE |  |  | 86306 | 10599
74 | -- | 340 | 23058 | 18773 | 31100800400000 | 9 |  | Huntingdon | 1 MI.E.OF COTTAGE |  | SHAVERS CREEK |  | 69 | 89 | 20.1 | 48 | [25 empty] | Rural Local | 69 | 20 | 89 | 20.1 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 30 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH lines 25'+ offset from the bridge. No other utilities identified in site visit or by PennDOT. |  |  | 15232 | 15002
75 | -- | 73 | 93322 | 25535 | 42401100102339 | 2 |  | McKean | BRADFORD |  | BENNETT BROOK |  | 23 | 43 | 24.0 | 48 | [25 empty] | Urban Collector | 23 | 20 | 43 | 24.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  |  | Noted in site visit, parallel to road, 15' offset | 43 | 120.88 | 5197.84 | [13 empty] | 43 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4400 | 8 |  |  | 3200 | 2.73 | 8736 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 6 | 1 | 1 | 2 |  | 5197.84 | 7500 | 1 | 15902.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 102315 | 27513
76 | -- | 342 | 74449 | 18785 | 31101900600000 | 9 |  | Huntingdon | 1.75 MILE NORTH FROM PA 26 |  | E BR STANDING STONE CRK |  | 57 | 77 | 27.0 | 48 | [25 empty] | Rural Local | 57 | 20 | 77 | 27.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 30 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH lines 15'+ offset from the bridge based on site visit pics. No exact offsets given. |  |  | 102218 | 27605
77 | -- | 351 | 23571 | 31528 | 55100700300000 | 9 |  | Somerset | 0.99 MILE NORTH FROM PA 160 |  | TRIB STONYCREEK RIVER |  | 47 | 67 | 23.7 | 52 | [25 empty] | Rural Local | 47 | 20 | 67 | 23.7 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 30 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH lines outside construction area. UG T line approximately 25' from the abutment - no relocation anticipated. |  |  | 86343 | 27643
78 | -- | 76 | 4676 | 26472 | 44100200800896 | 2 |  | Mifflin | 3 MI NE REEDSVILLE |  | HONEY CREEK |  | 97 | 117 | 18.2 | 52 | [25 empty] | Rural Minor Collector | 97 | 20 | 117 | 18.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 1 | 1 |  |  | Noted in site visit, orientation/offset unknown | 117 | 249.45 | 29185.65 | [13 empty] | 117 |  |  |  | 1 | 1 |  |  | Noted in site visit, orientation/offset unknown | 117 | 477.3 | 55844.1 | [13 empty] | 117 |  |  |  | 1e-17 | 1 |  |  | Noted in site visit, orientation/offset unknown | 117 | 120.88 | 14142.96 | [13 empty] | 117 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3200 | 1 |  |  | 800 | 2.73 | 2184 | 2 |  | 1600 | 2.73 | 4368 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 3 | 3 | 6 |  | 99172.71 | 7500 | 14 | 20406.75 | 10000 | 3 | COMPLETE, pole offsets not given in site visit, poles appear closer than 15' in photos |  |  | 67373 | 27757
79 | -- | 77 | 4677 | 26477 | 44100201200618 | 2 |  | Mifflin | LOCKE MILLS |  | HONEY CREEK |  | 66 | 86 | 18.2 | 52 | [25 empty] | Rural Minor Collector | 66 | 20 | 86 | 18.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1 | 1 |  |  | Dry hydrant, location unknown | 86 | 56.12 | 4826.32 | [13 empty] | 86 |  |  |  | None | 0 | None | 0 | 0 | 1 | 4800 | 0 |  |  | 0 | 2.73 | 0 | 3 |  | 2400 | 2.73 | 6552 | 3 |  | 2400 | 2.73 | 6552 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 1 | 3 | 4 |  | 4826.32 | 7500 | 1 | 24774.75 | 10000 | 3 | COMPLETE, pole offsets not given in site visit, poles appear closer than 15' in photos |  |  | 81290 | 27868
80 | -- | 356 | 23454 | 31651 | 55202600300000 | 9 |  | Somerset | 2 MI.NE.OF MEYERSDALE |  | BLUE LICK CREEK |  | 28 | 48 | 18.7 | 48 | [25 empty] | Rural Local | 28 | 20 | 48 | 18.7 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 30 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities located near the bridge in the site visit or by PennDOT. |  |  | 87428 | 47
81 | -- | 79 | 88640 | 30090 | 52000602300000 | 2 |  | Potter | COUDERSPORT BORO |  | DINGMANS RUN |  | 28 | 48 | 45.0 | 68 | [25 empty] | Rural Minor Arterial | 28 | 20 | 48 | 45.0 | 44 | 24 | 68 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 1 | 1 |  | Coudersport Boro | Noted in site visit, orientation/offset unknown | 48 | 249.45 | 11973.6 | [13 empty] | 48 |  |  |  | 1e-17 | 1 |  | Coudersport Boro | Noted in site visit, orientation/offset unknown | 48 | 477.3 | 22910.4 | [13 empty] | 48 |  |  |  | 1 | 1 |  | UGI | Noted in site visit, orientation/offset unknown | 48 | 120.88 | 5802.24 | [13 empty] | 48 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3600 | 5 |  |  | 2000 | 2.73 | 5460 | 3 |  | 1200 | 2.73 | 3276 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 3 | 1 | 4 |  | 40686.24 | 7500 | 6 | 13718.25 | 10000 | 2 | COMPLETE, pole offsets not given in site visit, poles appear closer than 15' in photos |  |  | 87427 | 71
82 | -- | 80 | 69501 | 30144 | 52004402700000 | 2 |  | Potter | CARTER CAMP |  | LITTLE KETTLE CREEK |  | 36 | 56 | 26.0 | 54 | [25 empty] | Rural Minor Arterial | 36 | 20 | 56 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 1e-17 | 1 |  |  | Noted in site visit, orientation/offset unknown | 56 | 249.45 | 13969.2 | [13 empty] | 56 |  |  |  | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  |  | Noted in site visit, orientation/offset unknown | 56 | 120.88 | 6769.28 | [13 empty] | 56 |  |  |  | 1 | 1 |  |  | Noted in site visit, orientation/offset unknown | 56 | 191.55 | 10726.8 | [13 empty] | 56 |  |  |  | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2000 | 4 |  |  | 1600 | 2.73 | 4368 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 3 | 1 | 4 |  | 31465.28 | 7500 | 5 | 9350.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit, poles appear closer than 15' in photos |  |  | 87417 | 75
83 | -- | 81 | 93375 | 30156 | 52004408101925 | 2 |  | Potter | 1 MI SE HEBRON CENTRE |  | SOUTH BRANCH OSWAYO CR |  | 22 | 42 | 32.9 | 58 | [25 empty] | Rural Minor Arterial | 22 | 20 | 42 | 32.9 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  |  | Noted in site visit, orientation/offset unknown | 42 | 120.88 | 5076.96 | [13 empty] | 42 |  |  |  | 1e-17 | 1 |  |  | Noted in site visit, orientation/offset unknown | 42 | 191.55 | 8045.1 | [13 empty] | 42 |  |  |  | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 2 | 1 | 3 |  | 13122.06 | 7500 | 2 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit, poles appear closer than 15' in photos |  |  | 87673 | 87
84 | -- | 368 | 98070 | 3294 | 03301702801869 | 10 |  | Armstrong | BRIAR HILL |  | SR0422 EB/WB & RAMPS F&G |  | 369 | 389 | 48.0 | 54 | [25 empty] | Rural Minor Collector | 369 | 20 | 389 | 48.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified during site visit or by PennDOT |  |  | 18051 | 98
85 | -- | 83 | 4805 | 30166 | 52004410100000 | 2 |  | Potter | SHARON CENTER |  | SHARON CREEK |  | 22 | 42 | 34.0 | 58 | [25 empty] | Rural Minor Arterial | 22 | 20 | 42 | 34.0 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 | 1 |  | UGI | Noted in site visit, orientation/offset unknown | 42 | 120.88 | 5076.96 | [13 empty] | 42 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 6 | 1 | 2 | 3 |  | 5076.96 | 7500 | 1 | 19246.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 99774 | 128
86 | -- | 84 | 4897 | 30190 | 52004904300530 | 2 |  | Potter | MILLS |  | MARSH CREEK | 20143580428 | 26 | 46 | 30.5 | 58 | [25 empty] | Rural Minor Arterial | 26 | 20 | 46 | 30.5 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 | 1 |  |  | Noted in site visit, orientation/offset unknown | 46 | 477.3 | 21955.8 | [13 empty] | 46 |  |  |  | 1e-17 | 1 |  | UGI | Noted in site visit, orientation/offset unknown | 46 | 120.88 | 5560.48 | [13 empty] | 46 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4800 | 4 |  |  | 2400 | 2.73 | 6552 | 3 |  | 1800 | 2.73 | 4914 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 8 | 2 | 2 | 4 |  | 27516.28 | 7500 | 4 | 20884.5 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes |  |  | 87436 | 135
87 | -- | 372 | 24779 | 8016 | 10102500100211 | 10 |  | Butler | RINGNECK |  | BONNIE BROOK |  | 65 | 85 | 33.0 | 52 | [25 empty] | Rural Major Collector | 65 | 20 | 85 | 33.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified in site visit or by PennDOT |  |  | 87434 | 148
88 | -- | 374 | 83332 | 8061 | 10300400300433 | 10 |  | Butler | MCCALMONT NO.1 |  | CONNOQUENESSING CR |  | 83 | 103 | 19.0 | 52 | [25 empty] | Rural Minor Collector | 83 | 20 | 103 | 19.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified in site visit or by PennDOT |  |  | 18146 | 160
89 | -- | 377 | 77989 | 8104 | 10302700500194 | 10 |  | Butler | SENACA SCHOOL |  | LIT CONNOQUENESSING CR |  | 72 | 92 | 35.6 | 68 | [25 empty] | Rural Major Collector | 72 | 20 | 92 | 35.6 | 44 | 24 | 68 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | Only utility identified in site visit is power to school flashing light. This should not be affected by construction. |  |  | 87676 | 185
90 | -- | 378 | 89967 | 8113 | 10400201302768 | 10 |  | Butler | SOUTH OF QUEEN JCT. |  | B & LE RR | 20143580231 | 140 | 160 | 31.0 | 54 | [25 empty] | Rural Major Collector | 140 | 20 | 160 | 31.0 | 30 | 24 | 54 |  | 1 | 60 | 600 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH identified in site visit, but 50' from bridge structure. No relocations. |  |  | 87671 | 198
91 | -- | 89 | 83457 | 6074 | 08001403400602 | 3 |  | Bradford | TROY BORO |  | FALL BROOK |  | 32 | 52 | 43.0 | 58 | [25 empty] | Rural Minor Arterial | 32 | 20 | 52 | 43.0 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 0 | 1 |  |  | Noted in site visit, orientation/offset unknown | 52 | 249.45 | 12971.4 | [13 empty] | 52 |  |  |  | 1 | 1 |  |  | Noted in site visit, orientation/offset unknown | 52 | 477.3 | 24819.6 | [13 empty] | 52 |  |  |  | 1 | 1 |  |  | Noted in site visit, orientation/offset unknown | 52 | 120.88 | 6285.76 | [13 empty] | 52 |  |  |  | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 11400 | 13 |  |  | 7800 | 2.73 | 21294 | 4 |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 |  |  |  |  | 1 | 3 | 2 | 5 |  | 44076.76 | 7500 | 6 | 38902.5 | 10000 | 4 | COMPLETE, pole offsets given in site visit notes |  |  | 74951 | 229
92 | -- | 379 | 24710 | 8334 | 10800505000898 | 10 |  | Butler | ROCK LAKE SB RAMP NO.2 |  | SR0019 NB |  | 145 | 165 | 35.3 | 56 | [25 empty] | Urban Freeways/Expressways/Interstates | 145 | 20 | 165 | 35.3 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified in site visit or by PennDOT |  |  | 87675 | 319
93 | -- | 383 | 25221 | 11042 | 16200900100000 | 10 |  | Clarion | LAWSONHAM NO.1 |  | REDBANK CREEK |  | 202 | 222 | 24.5 | 50 | [25 empty] | Rural Major Collector | 202 | 20 | 222 | 24.5 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified in site visit. One call noted that National Fuel does not have active lines within 15' of the bridge, but could have abandoned lines in the area. |  |  | 87437 | 362
94 | -- | 385 | 83256 | 11088 | 16401500301431 | 10 |  | Clarion | HUEFNER NO.3 |  | LICKING CREEK |  | 45 | 65 | 36.4 | 54 | [25 empty] | Rural Minor Collector | 45 | 20 | 65 | 36.4 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified in site visit or by PennDOT. One call noted that National Fuel does not have active lines within 15' of the bridge, but could have abandoned lines in the area. |  |  | 87438 | 364
95 | -- | 387 | 95851 | 19183 | 32055302000620 | 10 |  | Indiana | ALVERDA NO.2 |  | DUTCH RUN |  | 40 | 60 | 33.5 | 54 | [25 empty] | Rural Major Collector | 40 | 20 | 60 | 33.5 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 |  |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified in site visit or by PennDOT |  |  | 90784 | 381
96 | -- | 388 | 25780 | 19200 | 32095403700000 | 10 |  | Indiana | WILLET |  | SOUTH BRANCH PLUM CREEK | 20143580238 | 42 | 62 | 26.6 | 48 | [25 empty] | Rural Major Collector | 42 | 20 | 62 | 26.6 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 0 |  |  | Gas line 80' LT of bridge | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities near the bridge. Gas line identified 80' LT of bridge. |  |  | 90694 | 13564
97 | -- | 390 | 78120 | 19392 | 32401000100530 | 10 |  | Indiana | KIMMEL RD NO.1 |  | CROOKED CREEK |  | 119 | 139 | 33.5 | 52 | [25 empty] | Rural Local | 119 | 20 | 139 | 33.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  | 1 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities near bridge. Gas line crosses roadway 100' from the end of the bridge. |  |  | 87424 | 13616
98 | -- | 409 | 28128 | 1373 | 02100103601567 | 11 |  | Allegheny | NEAR BAILEY RUN ROAD |  | BAILEYS RUN |  | 44 | 64 | 50.0 | 64 | [25 empty] | Urban Major Arterial | 44 | 20 | 64 | 50.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  |  |  | 60 | 249.45 | 14967 | [7 empty] | 60 | [9 empty] | 1 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 1 |  |  |  | 60 | 120.88 | 7252.8 | [7 empty] | 60 | [9 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 12" Water, 12" Gas | 1 | Yes | 128 |  | 1 | 8400 | 6 |  |  | 3600 | 2.73 | 9828 | 4 |  | 2400 | 2.73 | 6552 | 4 |  | 2400 | 2.73 | 6552 | 0 |  |  | 2.73 | 0 | 4 | 3890.25 | 15561 | 23.5 | [5 empty] | 3 | 4 | 7 |  | 22219.8 | 7500 | 3 | 38493 | 10000 | 4 |  |  |  | 90695 | 13735
99 | -- | 423 | 26417 | 1496 | 02200800100053 | 11 |  | Allegheny | @ INTER. WITH SR 2010 |  | WYLIE RUN |  | 28 | 48 | 23.0 | 52 | [25 empty] | Urban Local | 28 | 20 | 48 | 23.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | Should be able to avoid waterline - 12.5' RT of bridge deck |  |  | 89274 | 13741
100 | -- | 429 | 63529 | 1559 | 02204500300840 | 11 |  | Allegheny | DRAVOSBURG OVER UNION RR |  | UNION RAILROAD | 20143571433 | 123 | 143 | 62.6 | 76 | [25 empty] | Urban Principal Arterial | 123 | 20 | 143 | 62.6 | 52 | 24 | 76 |  | 1 | 120 | 1200 | 2 |  | 1 |  | PA AMERICAN WATER |  | 50 | 249.45 | 12472.5 | [5 empty] | 50 | [12 empty] | 0 |  |  |  | 0 | 477.3 | 0 | [18 empty] | 0 |  |  |  | 0 | 120.88 | 0 | [18 empty] | 0 |  |  |  | 0 | 191.55 | 0 | [18 empty] | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  |  | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  |  | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 8" Waterline (asbestos wrapped ?) | 1 | Yes | 143 |  | 1 | 1600 | 1 |  |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  |  | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 12472.5 | 7500 | 2 | 12148.5 | 10000 | 2 |  |  |  | 74054 | 13824
101 | -- | 435 | 27275 | 1626 | 02207501900000 | 11 |  | Allegheny | 200'N.OF ENTRANCE DRIVE |  | AVR RAILROAD |  | 32 | 52 | 26.0 | 58 | [25 empty] | Urban Minor Arterial | 32 | 20 | 52 | 26.0 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [17 empty] | 1 |  |  | Peoples Gas |  | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 6" Gas | 1 | Yes | 52 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 1 | 0 | 1 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No site visit info as of 5-27-2014 |  |  | 90739 | 13896
102 | -- | 447 | 78413 | 1974 | 02403200902202 | 11 |  | Allegheny | 419' W OF LR 02090 |  | BR LITTLE SEWICKLEY CRK |  | 13 | 33 | 28.0 | 52 | [25 empty] | Urban Minor Collector | 13 | 20 | 33 | 28.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No site visit info as of 5-27-2014 |  |  | 102789 | 13897
103 | -- | 448 | 78414 | 1976 | 02403600701676 | 11 |  | Allegheny | @ INTER.TURKEY FOOT ROAD |  | BR.BIG SEWICKLEY CREEK |  | 19 | 39 | 32.6 | 56 | [25 empty] | Urban Minor Arterial | 19 | 20 | 39 | 32.6 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No site visit info as of 5-27-2014 |  |  | 74055 | 13946
104 | -- | 449 | 78416 | 1980 | 02403601303135 | 11 |  | Allegheny | @ CAMP MEETING RD. EXT. |  | BR.BIG SEWICKLEY CREEK |  | 17 | 37 | 35.0 | 56 | [25 empty] | Urban Minor Arterial | 17 | 20 | 37 | 35.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [17 empty] | 1 |  |  | Columbia Gas |  | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No site visit info as of 5-27-2014 |  |  | 90769 | 13948
105 | -- | 450 | 78417 | 1982 | 02403601400961 | 11 |  | Allegheny | @ INTER.WITH APPL.4846 |  | BR.BIG SEWICKLEY CREEK |  | 18 | 38 | 32.0 | 56 | [25 empty] | Urban Minor Arterial | 18 | 20 | 38 | 32.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No site visit info as of 5-27-2014 |  |  | 90770 | 13961
106 | -- | 452 | 28944 | 3602 | 04016805001748 | 11 |  | Beaver | .4 MI.SW OF TWP.RD.603 |  | PAINTERS RUN |  | 23 | 43 | 22.0 | 54 | [25 empty] | Rural Major Collector | 23 | 20 | 43 | 22.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | All site visit pics are rotated. No utilities within 50' of bridge - OH 50' offset |  |  | 100078 | 14441
107 | -- | 455 | 69069 | 3693 | 04300500800933 | 11 |  | Beaver | @ INTER.W/TWP.RD.491 |  | MOON RUN |  | 19 | 39 | 28.0 | 62 | [25 empty] | Urban Minor Collector | 19 | 20 | 39 | 28.0 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 0 |  |  | Waterline offset 15'+ - elevated across channel | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | All site visit pics are rotated. OH lines and water line offset 15'+ from the bridge |  |  | 47519 | 14481
108 | -- | 119 | 97586 | 29174 | 49102700400616 | 3 |  | Northumberland | VILLAGE OF POTTSGROVE |  | OVER ROSS RUN |  | 27 | 47 | 32.9 | 48 | [25 empty] | Rural Minor Collector | 27 | 20 | 47 | 32.9 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, orientation/offset unknown | 47 | 477.3 | 22433.1 | [13 empty] | 47 |  |  |  | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3000 | 2 |  | PPL | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 |  |  |  |  | 8 | 1 | 2 | 3 |  | 22433.1 | 7500 | 3 | 15970.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 87457 | 14578
109 | -- | 457 | 70805 | 3717 | 04302500701409 | 11 |  | Beaver | @ INTER. WITH TWP.RD.544 |  | RAREDON RUN | 20143580299 | 44 | 64 | 26.5 | 54 | [25 empty] | Rural Minor Collector | 44 | 20 | 64 | 26.5 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No site visit info as of 5-27-2014 |  |  | 87686 | 17407
110 | -- | 460 | 99793 | 3747 | 04401201000519 | 11 |  | Beaver | 200'EAST&UNDER SR 0060 |  | SOUTH BRANCH BRADY RUN |  | 52 | 72 | 26.0 | 54 | [25 empty] | Urban Local | 52 | 20 | 72 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | All site visit pics are rotated. OH lines offset 15'+ from the bridge deck. |  |  | 63173 | 17408
111 | -- | 462 | 78310 | 3750 | 04401201500926 | 11 |  | Beaver | 100 FT WEST OF SR 0051 |  | BRADYS RUN |  | 60 | 80 | 36.7 | 56 | [25 empty] | Urban Minor Collector | 60 | 20 | 80 | 36.7 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | All site visit pics are rotated. OH lines offset 15'+ from the bridge deck. |  |  | 87683 | 17471
112 | -- | 466 | 78362 | 22265 | 37020801000000 | 11 |  | Lawrence | 3000' WEST OF SR 0551 |  | BRANCH DEER CREEK |  | 12 | 32 | 31.0 | 52 | [25 empty] | Rural Minor Arterial | 12 | 20 | 32 | 31.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  | Penn Power | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH lines 16' offset from bridge - no relocations |  |  | 78710 | 17592
113 | -- | 124 | 88799 | 31169 | 54102300401962 | 3 |  | Snyder | VILLAGE OF HUMMELS WHARF |  | TRIB TO SUSQUEHANNA RVR |  | 24 | 44 | 39.5 | 62 | [25 empty] | Urban Major Collector | 24 | 20 | 44 | 39.5 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 12 | 0 | 1 |  |  | Noted in site visit, parallel to road, 13' right of bridge | 44 | 249.45 | 10975.8 | [13 empty] | 44 |  |  |  | 0 |  |  |  | Attached to bridge | 0 | 477.3 | 0 | [17 empty] | 1 |  |  |  | Noted in PennDOT notes, orientation/offset unknown | 44 | 120.88 | 5318.72 | [13 empty] | 44 |  |  |  | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, serving cell tower | 62 | 32.1 | 1990.2 |  |  |  | 0 | 1 |  |  | Noted in site visit, serving cell tower | 62 | 25.68 | 1592.16 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 10" Sewer, 14" Sewer (both force main) | 1 | Yes | 88 | 0 | 1 | 8000 | 6 |  |  | 4800 | 2.73 | 13104 | 3 |  | 2400 | 2.73 | 6552 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | 25 |  |  |  |  | 0 | 4 | 3 | 7 |  | 19876.88 | 7500 | 3 | 33510.75 | 10000 | 4 | COMPLETE, pole offset from site visit sketch, attached pipe sizes from site visit sketch |  |  | 78708 | 17593
114 | -- | 470 | 78370 | 22358 | 37095601200542 | 11 |  | Lawrence | 2 MI.EAST OF SR 0018 |  | NESHANNOCK CREEK |  | 130 | 150 | 38.5 | 52 | [25 empty] | Rural Minor Collector | 130 | 20 | 150 | 38.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH lines 20' offset from bridge. No other utilities identified. |  |  | 19965 | 20976
115 | -- | 474 | 78378 | 22374 | 37100900603315 | 11 |  | Lawrence | 100' SOUTH OF SR 0956 |  | BRANCH NESHANNOCK CREEK |  | 65 | 85 | 18.2 | 46 | [25 empty] | Rural Local | 65 | 20 | 85 | 18.2 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH lines 20' LT of the bridge. No other utilities identified by site visits or PennDOT |  |  | 87315 | 21043
116 | -- | 475 | 99796 | 22378 | 37101200700000 | 11 |  | Lawrence | 300'WEST OF TWP.RD.478 |  | BIG RUN |  | 67 | 87 | 27.5 | 48 | [25 empty] | Rural Local | 67 | 20 | 87 | 27.5 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified during site visit or by PennDOT |  |  | 87316 | 21196
117 | -- | 478 | 99798 | 22416 | 37201200103494 | 11 |  | Lawrence | 100' WEST OF TWP.RD.434 |  | BRANCH OF MCKEE RUN |  | 10 | 30 | 24.0 | 52 | [25 empty] | Rural Major Collector | 10 | 20 | 30 | 24.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  |  |  |  | Water line flagged 15' from bridge - no relocation | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No OH utilities identified in site visit. Water line flagged in field visit pics - 15 from the bridge - no relocation necessary |  |  | 87536 | 21237
118 | -- | 480 | 99797 | 22439 | 37300300800000 | 11 |  | Lawrence | 1/4 MI. SOUTH OF SR 0317 |  | HICKORY CREEK |  | 25 | 45 | 25.0 | 46 | [25 empty] | Rural Local | 25 | 20 | 45 | 25.0 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities located during site visit or by PennDOT |  |  | 87554 | 21238
119 | -- | 482 | 80677 | 22455 | 37301500201288 | 11 |  | Lawrence | 1/4 MI W OF SR 2012 |  | MCKEE RUN | 20143571138 | 28 | 48 | 27.0 | 54 | [25 empty] | Urban Minor Collector | 28 | 20 | 48 | 27.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities located during site visit or by PennDOT |  |  | 19915 | 21251
120 | -- | 485 | 74174 | 16713 | 26100100200639 | 12 |  | Fayette | SPRINGFIELD TOWNSHIP |  | MILL RUN |  | 39 | 59 | 15.7 | 46 | [25 empty] | Rural Local | 39 | 20 | 59 | 15.7 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH lines in the area, but should not affect bridge construction. No other utilities identified in the area. |  |  | 87505 | 21277
121 | -- | 490 | 74345 | 16757 | 26103100601336 | 12 |  | Fayette | UPPER TYRONE TOWNSHIP |  | GALLEY RUN |  | 38 | 58 | 25.7 | 48 | [25 empty] | Rural Major Collector | 38 | 20 | 58 | 25.7 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified in site visit or by PennDOT. |  |  | 91194 | 21292
122 | -- | 491 | 76009 | 16758 | 26103100700299 | 12 |  | Fayette | CONNELLSVILLE & U. TYRONE |  | BRANCH OF GALLEY RUN |  | 35 | 55 | 22.3 | 48 | [25 empty] | Rural Major Collector | 35 | 20 | 55 | 22.3 | 24 | 24 | 48 |  | 1 | 45 | 450 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified in site visit or by PennDOT. |  |  | 78868 | 21326
123 | -- | 503 | 79337 | 17052 | 26404400201593 | 12 |  | Fayette | WASHINGTON TOWNSHIP |  | DOWNERS RUN |  | 46 | 66 | 26.8 | 50 | [25 empty] | Urban Local | 46 | 20 | 66 | 26.8 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | WW does not cross road or bridge per the sit visit sketch of lines coming to/from MH. |  |  | 91266 | 21403
124 | -- | 515 | 88079 | 18351 | 30300600100674 | 12 |  | Greene | GILMORE TOWNSHIP |  | PA. FORK DUNKARD CREEK | 20143571385 | 45 | 65 | 14.0 | 46 | [25 empty] | Rural Minor Collector | 45 | 20 | 65 | 14.0 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities near the bridge. 20" gas line crosses the roadway approx. 60' from the abutment. |  |  | 87521 | 21409
125 | -- | 526 | 98374 | 34879 | 62200700200048 | 12 |  | Washington | AMWELL TOWNSHIP |  | HORNE RUN |  | 26 | 46 | 24.0 | 48 | [25 empty] | Rural Minor Collector | 26 | 20 | 46 | 24.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities anticipated to be affected by construction. |  |  | 74958 | 21415
126 | -- | 531 | 51507 | 34977 | 62203400500000 | 12 |  | Washington | WEST PIKE RUN TOWNSHIP |  | BRANCH OF PIKE RUN |  | 25 | 45 | 22.3 | 46 | [25 empty] | Rural Minor Collector | 25 | 20 | 45 | 22.3 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities found near the bridge in the site visit or by PennDOT. |  |  | 19927 | 21417
127 | -- | 534 | 30715 | 34996 | 62203700403160 | 12 |  | Washington | FALLOWFIELD TOWNSHIP |  | MAPLE CREEK |  | 22 | 42 | 25.0 | 48 | [25 empty] | Urban Collector | 22 | 20 | 42 | 25.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH lines outside construction area. Water line identified crossing the road 20'+ from the abutment - no relocation anticipated. |  |  | 100523 | 21439
128 | -- | 540 | 30635 | 35227 | 62406100401960 | 12 |  | Washington | HOPEWELL AND BLAINE TWP. |  | BRUSH RUN |  | 40 | 60 | 15.0 | 46 | [25 empty] | Rural Local | 40 | 20 | 60 | 15.0 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified in the site visit or by PennDOT. |  |  | 63230 | 21446
129 | -- | 548 | 76121 | 36248 | 64071102601107 | 12 |  | Westmoreland | LIGONIER TOWNSHIP |  | MILL CREEK |  | 88 | 108 | 36.0 | 58 | [25 empty] | Rural Minor Arterial | 88 | 20 | 108 | 36.0 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 12" Unknown | 1 | Yes | 108 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 30 |  | 12 | IN ROW |  |  | 1 | 0 | 1 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | Unknown 8" to 12" line attached to the bridge. Gas markers in the area. |  |  | 20124 | 21454
130 | -- | 551 | 31972 | 36365 | 64100400200165 | 12 |  | Westmoreland | FAIRFIELD TOWNSHIP |  | HENDRICKS CREEK |  | 31 | 51 | 15.1 | 46 | [25 empty] | Rural Local | 31 | 20 | 51 | 15.1 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No utilities identified near the bridge during the site visit or by PennDOT. |  |  | 87706 | 21459
131 | -- | 561 | 81636 | 16920 | 26301301601348 | 12 |  | Fayette | GERMAN TOWNSHIP |  | MIDDLE RUN |  | 31 | 51 | 24.0 | [27 empty] | 31 | 20 | 51 | 24.0 |  |  |  |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No site visit info as of 5-27-2014 |  |  | 91323 | 21474
132 | -- | 562 | 79326 | 16923 | 26301301701416 | 12 |  | Fayette | GERMAN TOWNSHIP |  | MIDDLE RUN |  | 45 | 65 | 26.3 | [27 empty] | 45 | 20 | 65 | 26.3 |  |  |  |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 3" Gas | 1 | Yes | 65 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 1 | 0 | 1 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No site visit info as of 5-27-2014 |  |  | 87515 | 21482
133 | -- | 563 | 74190 | 16930 | 26301301901171 | 12 |  | Fayette | GERMAN TOWNSHIP |  | MIDDLE RUN |  | 52 | 72 | 16.8 | [27 empty] | 52 | 20 | 72 | 16.8 |  |  |  |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | No site visit info as of 5-27-2014 |  |  | 87566 | 21487
134 | -- | 311 | 21558 | 3955 | 05003001100000 | 9 |  | Bedford | 2.3 MI.W.OF SHELLSBURG |  | SHAWNEE CREEK |  | 50 | 70 | 43.1 | 64 | [25 empty] | Rural Principal Arterial | 50 | 20 | 70 | 43.1 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 50.00, 40.00 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | OH lines 16' offset from the bridge. No relocations. |  |  | 91324 | 21514
135 | -- | 407 | 27185 | 1365 | 02100102101194 | 11 |  | Allegheny | BARGE BASIN O/ABNDONED RR |  | ABANDONED RR TRACK | 20143580503 | 40 | 60 | 48.0 | 60 | [25 empty] | Urban Principal Arterial | 40 | 20 | 60 | 48.0 | 36 | 24 | 60 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [13 empty] | 0 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 400 | 1 |  | West Penn Power | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 4982.25 | 10000 | 1 | No site visit info as of 5-27-2014 |  |  | 87516 | 21518
136 | -- | 8 | 1140 | 16373 | 25401100800860 | 1 |  | Erie | MILL CREEK TOWNSHIP |  | OVER WALNUT CREEK |  | 63 | 83 | 33.0 | 58 | [25 empty] | Rural Major Collector | 63 | 20 | 83 | 33.0 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  | Permit for attached gas in file | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 20123 | 21533
137 | -- | 10 | 1370 | 17207 | 27066600700000 | 1 |  | Forest | HICKORY TOWNSHIP |  | OVER BEAVER RUN |  | 65 | 85 | 27.0 | 48 | [25 empty] | Rural Major Collector | 65 | 20 | 85 | 27.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 87562 | 21536
138 | -- | 164 | 10230 | 37163 | 65026700100659 | 4 |  | Wyoming | MESHOPPEN BOR .1 M N TR 6 |  | LITTLE MESHOPPEN CREEK |  | 23 | 43 | 31.0 | 50 | [25 empty] | Rural Major Collector | 23 | 20 | 43 | 31.0 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 | 1 |  |  | Noted in site visit sketch, orientation/offset unknown | 43 | 249.45 | 10726.35 | [13 empty] | 43 |  |  |  | 0 | 1 |  |  | Noted in site visit photos, orientation/offset unknown | 43 | 477.3 | 20523.9 | [13 empty] | 43 |  |  |  | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4800 | 4 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 2 | 3890.25 | 7780.5 | 25 |  |  |  |  | 6 | 2 | 2 | 4 |  | 31250.25 | 7500 | 5 | 20884.5 | 10000 | 3 | COMPLETE, pole offset given in site visit notes |  |  | 91108 | 21545
139 | -- | 15 | 58092 | 26008 | 43302001700000 | 1 |  | Mercer | JEFFERSON TOWNSHIP |  | OVER LACKAWANNOCK CREEK |  | 23 | 43 | 16.5 | 48 | [25 empty] | Rural Local | 23 | 20 | 43 | 16.5 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 25 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes |  |  | 19964 | 21558
140 | -- | 168 | 79078 | 4900 | 06062501301318 | 5 |  | Berks | NEW HOLLAND ROAD |  | ANGELICA CREEK |  | 38 | 58 | 25.0 | 54 | [25 empty] | Urban Minor Arterial | 38 | 20 | 58 | 25.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit notes/sketch, parallel to road, offset unknown | 58 | 477.3 | 27683.4 | [13 empty] | 58 |  |  |  | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 6 | 1 | 1 | 2 |  | 27683.4 | 7500 | 4 | 7166.25 | 10000 | 1 | COMPLETE, pole offset given in site visit notes |  |  | 87518 | 21559
141 | -- | 19 | 2438 | 33957 | 61000603900000 | 1 |  | Warren | BROKENSTRAW TOWNSHIP |  | OVER MEAD RUN |  | 32 | 52 | 39.5 | 64 | [25 empty] | Rural Principal Arterial | 32 | 20 | 52 | 39.5 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 87501 | 21595
142 | -- | 30 | 2893 | 9679 | 14201300100000 | 2 |  | Centre | 2 MI NE COBURN |  | PINE CREEK | 20143580136 | 59 | 79 | 14.1 | 52 | [25 empty] | Rural Local | 59 | 20 | 79 | 14.1 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, site visit photos available but no notes, no relocations indicated |  |  | 19812 | 21601
143 | -- | 35 | 3195 | 9790 | 14400600100000 | 2 |  | Centre | CASANOVA |  | MOSHANNON CREEK |  | 160 | 180 | 28.0 | 52 | [25 empty] | Rural Minor Collector | 160 | 20 | 180 | 28.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  | Moved to attached to structure column | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 5" Water | 1 | Yes | 180 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1e-17 | 3890.25 | 3.8903e-14 | 25 |  |  |  |  | 15 | 1 | 1e-17 | 1 |  | 0 | 7500 | 0 | 3.8903e-14 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes, water line size estimated from site visit photos |  |  | 63229 | 21637
144 | -- | 172 | 79081 | 5147 | 06300900701675 | 5 |  | Berks | W.WYOMISSING AVE. |  | WYOMISSING CREEK |  | 37 | 57 | 26.0 | 54 | [25 empty] | Urban Minor Arterial | 37 | 20 | 57 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 | 1 |  |  | Noted in site visit notes/photos, orientation/offset unknown | 57 | 249.45 | 14218.65 | [13 empty] | 57 |  |  |  | 0 | 1 |  |  | Noted in site visit notes, orientation/offset unknown, not shown in sketch | 57 | 477.3 | 27206.1 | [13 empty] | 57 |  |  |  | 0 | 1 |  |  | Noted in site visit notes/sketch, parallel to road, 5' offset (under wingwall) | 57 | 120.88 | 6890.16 | [13 empty] | 57 |  |  |  | 0 | 1 |  |  | Noted in site visit, orientation/offset unknown, not shown in sketch | 57 | 191.55 | 10918.35 | [13 empty] | 57 |  |  |  | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 6 | 4 | 1 | 5 |  | 59233.26 | 7500 | 8 | 4982.25 | 10000 | 1 | COMPLETE, pole offset given in site visit notes, only telephone in conflict |  |  | 20151 | 21662
145 | -- | 36 | 69443 | 11245 | 17005306400000 | 2 |  | Clearfield | MORRISDALE |  | EMIGH RUN | 20143580396 | 24 | 44 | 42.7 | 68 | [25 empty] | Rural Minor Arterial | 24 | 20 | 44 | 42.7 | 44 | 24 | 68 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  | Noted in PennDOT notes, orientation/distance unknown | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 40 |  |  |  |  | 100 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes | PER CURT B NO UTILITIES WERE LAYED OUT IN THE AREA AND BORINGS WERE DONE. WALSH IS ELIMINATING THE SAN SEWER CONFLICT FROM SPREADSHEET |  | 91352 | 22812
146 | -- | 175 | 85693 | 23144 | 39022202103224 | 5 |  | Lehigh | HAMILTON ST. |  | CEDAR CREEK |  | 85 | 105 | 63.0 | 78 | [25 empty] | Urban Principal Arterial | 85 | 20 | 105 | 63.0 | 54 | 24 | 78 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 1 |  |  | Noted in site visit sketch, crosses and parallel, offset unknown | 183 | 249.45 | 45649.35 | [13 empty] | 183 |  |  |  | 0 | 0 |  |  | Noted in site visit, parallel to road, offset 25' from abutment | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 1 |  |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 45649.35 | 7500 | 7 | 4982.25 | 10000 | 1 | COMPLETE, guy wire and street lighting service wire are only conflicts |  |  | 87462 | 29426
147 | -- | 176 | 89633 | 23228 | 39100400202044 | 5 |  | Lehigh | 1600'E.OF RACE ST.BRIDGE |  | CATASAUQUA CREEK |  | 44 | 64 | 41.4 | 56 | [25 empty] | Urban Minor Arterial | 44 | 20 | 64 | 41.4 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 0 | 0 |  |  | Assumed attached to bridge per site visit notes, not verified | 0 | 249.45 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, orientation unknown, mh 30' from abutment | 56 | 477.3 | 26728.8 | [13 empty] | 56 |  |  |  | 0 | 0 |  |  | Attached to bridge, verified by photos | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 8" Gas, 8" Water | 1 | Yes | 128 | 0 | 1 | 16000 | 8 |  |  | 8000 | 2.73 | 21840 | 4 |  | 4000 | 2.73 | 10920 | 1 |  | 1000 | 2.73 | 2730 | 3 |  | 3000 | 2.73 | 8190 | 4 | 3890.25 | 15561 | [5 empty] | 3 | 2 | 4 | 6 |  | 26728.8 | 7500 | 4 | 59241 | 10000 | 6 | COMPLETE, pole offsets given in site visit notes, estimated attached gas line from site visit photos |  |  | 93582 | 29451
148 | -- | 177 | 85683 | 23330 | 39204900302189 | 5 |  | Lehigh | CAMP MEETING ROAD |  | SAUCON CREEK | 20143580203 | 93 | 113 | 25.8 | 56 | [25 empty] | Urban Local | 93 | 20 | 113 | 25.8 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 0 | 1 |  |  | 2 water lines noted in site visit, parallel to road, one adj & the other 15' offset | 226 | 249.45 | 56375.7 | [13 empty] | 226 |  |  |  | 0 | 1 |  |  | Noted in site visit, crosses road, 20' from near abutment | 56 | 477.3 | 26728.8 | [13 empty] | 56 |  |  |  | 0 | 0 |  |  | Attached to bridge per site visit notes, hidden from view in photos | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 8" Gas | 1 | Yes | 113 | 0 | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 15 | 3 | 0 | 3 |  | 83104.5 | 7500 | 12 | 0 | 10000 | 0 | COMPLETE, pole offset given in site visit notes |  |  | 79054 | 29468
149 | -- | 178 | 89639 | 23136 | 39622200303519 | 5 |  | Lehigh | TREXLERTOWN NEAR RT.100 |  | IRON RUN |  | 71 | 91 | 45.0 | 65 | [25 empty] | Urban Principal Arterial | 71 | 20 | 91 | 45.0 | 41 | 24 | 65 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, crosses road, distance from abutment unknown | 65 | 477.3 | 31024.5 | [13 empty] | 65 |  |  |  | 0 | 0 |  |  | Attached to bridge per site visit notes, verified by photos | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 12" Gas | 1 | Yes | 91 | 0 | 1 | 5600 | 4 |  |  | 3200 | 2.73 | 8736 | 2 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 1 |  | 800 | 2.73 | 2184 | 3 | 3890.25 | 11670.75 | [5 empty] | 10 | 2 | 3 | 5 |  | 31024.5 | 7500 | 5 | 26958.75 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes, gas line size estimated from site visit photos |  |  | 73961 | 29518
150 | -- | 39 | 85079 | 11403 | 17021904602606 | 2 |  | Clearfield | BELLS LANDING |  | POPLAR RUN |  | 32 | 52 | 41.1 | 66 | [25 empty] | Rural Principal Arterial - Other | 32 | 20 | 52 | 41.1 | 42 | 24 | 66 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 40 |  |  |  |  | 75 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes |  |  | 87465 | 29565
151 | -- | 41 | 93372 | 11454 | 17025502200000 | 2 |  | Clearfield | 2 MI SW PENFIELD |  | BENNETT BRANCH |  | 45 | 65 | 33.2 | 56 | [25 empty] | Rural Minor Arterial | 45 | 20 | 65 | 33.2 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 90716 | 29566
152 | -- | 60 | 88664 | 25281 | 42005904500000 | 2 |  | McKean | 1 MI W ORMSBY |  | TRIB KINZUA CREEK |  | 22 | 42 | 39.3 | 64 | [25 empty] | Rural Minor Arterial | 22 | 20 | 42 | 39.3 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 87491 | 29605
153 | -- | 64 | 85259 | 25314 | 42015502900238 | 2 |  | McKean | 2 MI SE LARABEE |  | NEWELL CREEK |  | 50 | 70 | 35.7 | 64 | [25 empty] | Rural Major Collector | 50 | 20 | 70 | 35.7 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 | 0 |  |  | Noted in site visit, parallel to road, >30' offset | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [5 empty] | 50 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offsets given in site visit notes |  |  | 101098 | 29651
154 | -- | 72 | 78611 | 25500 | 42200200320000 | 2 |  | McKean | BETULA |  | WEST BRANCH POTATO CREEK |  | 51 | 71 | 35.8 | 48 | [25 empty] | Rural Local | 51 | 20 | 71 | 35.8 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 | 0 |  |  | Underground phone on left, out of the way | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 79042 | 29673
155 | -- | 116 | 6387 | 28361 | 47025400200000 | 3 |  | Montour | 4.5 M W OF LIMESTONEVILLE |  | OVER LIMESTONE RUN | 20143571637 | 66 | 86 | 27.5 | 60 | [25 empty] | Rural Major Collector | 66 | 20 | 86 | 27.5 | 36 | 24 | 60 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 40 |  |  |  |  | 140 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offset in site visit notes/sketches |  |  | 79047 | 29693
156 | -- | 123 | 88047 | 29311 | 49402600100165 | 3 |  | Northumberland | 2 MI S OF AUGUSTAVILLE |  | OVER LITTLE SHAMOKIN CR. |  | 37 | 57 | 20.4 | 52 | [25 empty] | Rural Minor Collector | 37 | 20 | 57 | 20.4 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 16.5 |  |  |  |  | 48 | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE, pole offset in site visit notes/sketches |  |  | 91353 | 37488
157 | -- | 130 | 87929 | 32931 | 58054902602539 | 3 |  | Tioga | 0.5 MI S OF JOBS CORNERS |  | OVER SEELY CREEK |  | 25 | 45 | 26.4 | 54 | [25 empty] | Rural Major Collector | 25 | 20 | 45 | 26.4 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1e-17 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | 25 | [5 empty] | 0 | 0 | 0 |  | 0 | 7500 | 0 | 0 | 10000 | 0 | COMPLETE |  |  | 87693 | 37491
158 | -- | 99 | 98535 | 6348 | 8105900700582 | 3 |  | Bradford | 1 MI. W. OF WARREN CENTER |  | OVER WAPPASENING CREEK |  | 43 | 63 | 16.4 | 48 | [25 empty] | Rural Local | 43 | 20 | 63 | 16.4 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 25 |  |  |  |  | 0 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 4982.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, no sketch, per notes telephone line over bridge, not shown in photos |  |  | 91191 | 37590
159 | -- | 125 | 89977 | 31948 | 56008701100148 | 3 |  | Sullivan | VILLAGE OF HILLSGROVE |  | OVER MILL CREEK |  | 59 | 79 | 25.8 | 56 | [25 empty] | Rural Minor Arterial | 59 | 20 | 79 | 25.8 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 1 |  |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 40 |  |  |  |  | 0 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 4982.25 | 10000 | 1 | COMPLETE, pole offsets from site visit sketch, service line only requires relocation, main overhead utilities offset 18' |  |  | 78860 | 37607
160 | -- | 93 | 79247 | 6191 | 08041403800000 | 3 |  | Bradford | VILLAGE OF FRANKLINDALE |  | TRIB.TO TOWANDA CREEK |  | 22 | 42 | 35.1 | 56 | [25 empty] | Rural Minor Arterial | 22 | 20 | 42 | 35.1 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 30 | [5 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 3890.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, no sketch, per photos guy wire conflict only |  |  | 87551 | 37608
161 | -- | 216 | 102218 | 27605 | 46201300320000 | 6 |  | Montgomery | 1.5MI.WEST PHILA. 33C07 |  | VALLEY CR. 3372B1 |  | 38 | 58 | 48.5 | 60 | [25 empty] | Urban Principal Arterial | 38 | 20 | 58 | 48.5 | 36 | 24 | 60 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 1 |  |  | Noted in site visit, parallel to road, 8' inside parapet per site visit notes | 0 | 249.45 | 0 | [13 empty] | 0 |  |  |  | 0 | 0 |  |  | Noted in site visit, parallel to road, offset 20' from bridge | 0 | 477.3 | 0 | [17 empty] | 0 | 1 | 4 |  | Noted in site visit notes, parallel to road, 7' from bridge, size from paint marks | 58 | 120.88 | 7011.04 |  |  | 58 | [14 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 12800 | 8 |  |  | 6400 | 2.73 | 17472 | 4 |  | 3200 | 2.73 | 8736 | 1 |  | 800 | 2.73 | 2184 | 3 |  | 2400 | 2.73 | 6552 | 3 | 3890.25 | 11670.75 | [5 empty] | 5 | 2 | 3 | 5 |  | 7011.04 | 7500 | 1 | 46614.75 | 10000 | 5 | COMPLETE, pole offsets given in site visit notes |  |  | 78878 | 37641
162 | -- | 217 | 86343 | 27643 | 46202700500209 | 6 |  | Montgomery | SPRINGFIELD TWP. 31B07 |  | SANDY RUN |  | 46 | 66 | 26.0 | 56 | [25 empty] | Urban Minor Arterial | 46 | 20 | 66 | 26.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, parallel to road, offset 8' from bridge | 66 | 477.3 | 31501.8 | [13 empty] | 66 |  |  |  | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 6400 | 4 |  |  | 3200 | 2.73 | 8736 | 2 |  | 1600 | 2.73 | 4368 | 1 |  | 800 | 2.73 | 2184 | 1 |  | 800 | 2.73 | 2184 | 3 | 3890.25 | 11670.75 | [6 empty] | 1 | 3 | 4 |  | 31501.8 | 7500 | 5 | 29142.75 | 10000 | 3 | COMPLETE, no pole offsets given in site visit notes, poles appear closer than 15' in photos |  |  | 78896 | 37725
163 | -- | 218 | 67373 | 27757 | 46304400500389 | 6 |  | Montgomery | WYNNEWOOD;WOODSIDE 3478H10 |  | BRANCH INDIAN CREEK |  | 20 | 40 | 34.6 | 50 | [25 empty] | Urban Major Collector | 20 | 20 | 40 | 34.6 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 | 1 |  |  | Noted in site visit, parallel to bridge, offset unknown | 40 | 249.45 | 9978 | [13 empty] | 40 |  |  |  | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 1 |  |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 9978 | 7500 | 2 | 4982.25 | 10000 | 1 | COMPLETE, no pole offsets given in site visit notes, pole appears closer than 15' in Google Maps Streetview, other underground utilities not noted but may be encountered |  |  | 87695 | 37726
164 | -- | 17 | 2251 | 33788 | 60201301000000 | 1 |  | Venango | CRANBERRY TOWNSHIP |  | OVER EAST SANDY CREEK |  | 132 | 152 | 26.7 | 54 | [25 empty] | Rural Major Collector | 132 | 20 | 152 | 26.7 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1600 | 4 |  |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 8258.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, poles appear closer than 15' |  |  | 91367 | 37878
165 | -- | 220 | 87428 | 47 | 01003003000000 | 8 |  | Adams | GETTYSBURG |  | ROCK CREEK |  | 98 | 118 | 46.8 | 72 | [25 empty] | Urban Principal Arterial | 98 | 20 | 118 | 46.8 | 48 | 24 | 72 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, parallel to road, 10' right of wing wall | 118 | 120.88 | 14263.84 | [13 empty] | 118 |  |  |  | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 9600 | 8 |  |  | 6400 | 2.73 | 17472 | 2 |  | 1600 | 2.73 | 4368 | 1 |  | 800 | 2.73 | 2184 | 1 |  | 800 | 2.73 | 2184 | 3 | 3890.25 | 11670.75 | [5 empty] | 1 | 1 | 3 | 4 |  | 14263.84 | 7500 | 2 | 37878.75 | 10000 | 4 | COMPLETE, pole offsets given in site visit notes |  |  | 87596 | 37890
166 | -- | 221 | 87427 | 71 | 01003402200745 | 8 |  | Adams | N. OF BIGLERVILLE |  | OPOSSUM CREEK |  | 50 | 70 | 26.0 | 64 | [25 empty] | Rural Minor Arterial | 50 | 20 | 70 | 26.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, orientation/offset unknown | 70 | 477.3 | 33411 | [13 empty] | 70 |  |  |  | 0 | 1 |  |  | Noted in site visit, parallel to road, per photo appears to be 5' left of bridge | 70 | 120.88 | 8461.6 | [13 empty] | 70 |  |  |  | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 13600 | 12 |  |  | 9600 | 2.73 | 26208 | 1 |  | 800 | 2.73 | 2184 | 2 |  | 1600 | 2.73 | 4368 | 2 |  | 1600 | 2.73 | 4368 | 3 | 3890.25 | 11670.75 | [5 empty] | 4 | 2 | 3 | 5 |  | 41872.6 | 7500 | 6 | 48798.75 | 10000 | 5 | COMPLETE, pole offsets given in site visit notes, 6' Left and 4' Right |  |  | 87595 | 37921
167 | -- | 21 | 2580 | 34001 | 61002705203359 | 1 |  | Warren | BROKENSTRAW TOWNSHIP |  | OVER HAZELTINE HOLLOW RU |  | 31 | 51 | 26.0 | 56 | [25 empty] | Rural Minor Arterial | 31 | 20 | 51 | 26.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 | 0 |  |  | Marker visible, parallel to road, >30' offset | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 1 | 1 | 3200 | 8 |  |  | 3200 | 2.73 | 8736 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 6 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 12626.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, power lines in conflict, communication lines not |  |  | 74944 | 37946
168 | -- | 223 | 87673 | 87 | 01009701000240 | 8 |  | Adams | 1 MI. N. OF LITTLESTOWN |  | ALLOWAY CREEK |  | 50 | 70 | 41.3 | 64 | [25 empty] | Rural Minor Arterial | 50 | 20 | 70 | 41.3 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, parallel to road, per notes 8' right of wing walls | 70 | 120.88 | 8461.6 | [13 empty] | 70 |  |  |  | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 7200 | 8 |  |  | 4800 | 2.73 | 13104 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 2 | 3890.25 | 7780.5 | [5 empty] | 4 | 1 | 2 | 3 |  | 8461.6 | 7500 | 2 | 27436.5 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes, 4' Left and 4' Right |  |  | 83428 | 37976
169 | -- | 55 | 81508 | 20137 | 34200601501696 | 2 |  | Juniata | VAN WERT |  | DOE RUN |  | 26 | 46 | 26.1 | 52 | [25 empty] | Rural Minor Collector | 26 | 20 | 46 | 26.1 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 0 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 4982.25 | 10000 | 1 | COMPLETE, line crosses over bridge |  |  | 90222 | 38007
170 | -- | 225 | 99774 | 128 | 01019402401689 | 8 |  | Adams | ABBOTTSTOWN |  | BRANCH OF BEAVER CREEK |  | 29 | 49 | 28.4 | 64 | [25 empty] | Urban Minor Arterial | 29 | 20 | 49 | 28.4 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 0 | 1 |  |  | Noted in site visit, parallel to road, 10' right of bridge | 49 | 249.45 | 12223.05 | [13 empty] | 49 |  |  |  | 0 | 1 |  |  | Noted in site visit, crosses road at far abutment | 64 | 477.3 | 30547.2 | [13 empty] | 64 |  |  |  | 0 | 0 |  |  | Noted in site visit, parallel to road, per notes 25' right of bridge | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 8 | 2 | 2 | 4 |  | 42770.25 | 7500 | 6 | 19246.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 91192 | 38023
171 | -- | 117 | 6381 | 28387 | 47100600100570 | 3 |  | Montour | 3 MI.N.WASHINGTONVILLE |  | MCKEE CREEK |  | 40 | 60 | 19.1 | 48 | [25 empty] | Rural Local | 40 | 20 | 60 | 19.1 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 800 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 25 |  |  |  |  | 15 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 6074.25 | 10000 | 1 | COMPLETE, pole offset in site visit notes/sketches |  |  | 88114 | 3954
172 | -- | 120 | 6669 | 29178 | 49200100200000 | 3 |  | Northumberland | 3 MI N OF ELYSBURG BORO |  | LITTLE ROARING CREEK |  | 23 | 43 | 26.3 | 48 | [25 empty] | Rural Minor Collector | 23 | 20 | 43 | 26.3 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 25 | [5 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 4982.25 | 10000 | 1 | COMPLETE, pole offset not given in site visit, poles appear closer than 15' in PennDOT photos |  |  | 21558 | 3955
173 | -- | 128 | 7326 | 32822 | 58004901400434 | 3 |  | Tioga | 0.5 MI E OF WESTFIELD |  | OVER CALIFORNIA BROOK |  | 42 | 62 | 47.5 | 62 | [25 empty] | Rural Minor Arterial | 42 | 20 | 62 | 47.5 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 1 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 |  |  |  | Noted in PennDOT notes, orientation/offset unknown | 62 | 120.88 | 7494.56 | [13 empty] | 62 |  |  |  | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 25 | [5 empty] | 0 | 1 | 1 |  | 7494.56 | 7500 | 1 | 4982.25 | 10000 | 1 | COMPLETE, pole offset not given in site visit, poles appear closer than 15' in photos |  |  | 21563 | 4010
174 | -- | 134 | 83470 | 33209 | 58403501300426 | 3 |  | Tioga | 3.5 MI NE OF WELLSBORO |  | OVER CATLIN HOLLOW CREEK |  | 64 | 84 | 27.3 | 56 | [25 empty] | Rural Minor Collector | 64 | 20 | 84 | 27.3 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1600 | 0 |  |  | 0 | 2.73 | 0 | 4 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 30 |  |  |  |  | 15 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 8258.25 | 10000 | 1 | COMPLETE, pole offset in site visit notes |  |  | 21455 | 4044
175 | -- | 148 | 9656 | 32327 | 57037400502476 | 4 |  | Susquehanna | LENOX TWP .5 M E SR 2016 |  | EAST BR TUNKHANNOCK CRK |  | 110 | 130 | 28.0 | 54 | [25 empty] | Rural Major Collector | 110 | 20 | 130 | 28.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 3 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes/sketch, 1 pole appears to be closer than 15' in photos | PRELIMINARY ASSUMPTIONS: LENGTHENING BRIDGE 48', WIDENING BRIDGE 5'; WIRES VISIBLE NEEDS VERIFIED |  | 88121 | 4122
176 | -- | 150 | 100550 | 32378 | 57085800500000 | 4 |  | Susquehanna | RUSH TWP 2 M N TR 706 |  | GAYLORD CREEK |  | 52 | 72 | 37.5 | 56 | [25 empty] | Rural Minor Collector | 52 | 20 | 72 | 37.5 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 6 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 4982.25 | 10000 | 1 | COMPLETE, pole offset given in site visit notes |  |  | 21596 | 4174
177 | -- | 155 | 96736 | 32647 | 57400201300000 | 4 |  | Susquehanna | SILVER LK T 1.2M E SR4001 |  | RHINEY CREEK |  | 30 | 50 | 30.3 | 52 | [25 empty] | Rural Major Collector | 30 | 20 | 50 | 30.3 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 800 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 6 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 6074.25 | 10000 | 1 | COMPLETE, pole offset given in site visit notes, communication poles in conflict, power poles are not in conflict |  |  | 21552 | 4177
178 | -- | 202 | 67256 | 28660 | 48100400601655 | 5 |  | Northampton | 3 MI.W.OF RIVERTON |  | OUGHOUGHTON CREEK |  | 46 | 66 | 26.0 | 52 | [25 empty] | Rural Major Collector | 46 | 20 | 66 | 26.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 3 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 10 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 21600 | 4196
179 | -- | 234 | 87438 | 364 | 01400601202897 | 8 |  | Adams | ASPERS |  | OPOSSUM CREEK |  | 66 | 86 | 26.0 | 52 | [25 empty] | Rural Minor Collector | 66 | 20 | 86 | 26.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, parallel to road, per notes 8' left of bridge | 86 | 120.88 | 10395.68 | [13 empty] | 86 |  |  |  | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 3 |  |  | 1800 | 2.73 | 4914 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 2 | 1 | 2 | 3 |  | 10395.68 | 7500 | 2 | 14332.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 74424 | 4386
180 | -- | 235 | 90784 | 381 | 01401100101013 | 8 |  | Adams | NEAR ADAMS & FRANK.LINE |  | CARBAUGH RUN |  | 43 | 63 | 27.2 | 52 | [25 empty] | Rural Local | 43 | 20 | 63 | 27.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, crosses 25' from near abutment, along road under right wingwalls | 115 | 120.88 | 13901.2 | [13 empty] | 115 |  |  |  | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 10 | 1 | 2 | 3 |  | 13901.2 | 7500 | 2 | 14332.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 22107 | 5699
181 | -- | 236 | 90694 | 13564 | 21001105202844 | 8 |  | Cumberland | 1 MI EAST OF MIDDLESEX |  | LETORT SPRING CREEK |  | 46 | 66 | 75.5 | 98 | [25 empty] | Urban Principal Arterial | 46 | 20 | 66 | 75.5 | 74 | 24 | 98 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 | 0 |  |  | Noted in site visit, parallel to road, per notes 50' left of bridge | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  | Noted in site visit, parallel to road, per notes 60' left of bridge | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  | Presumed gas line attached to bridge | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 1 |  |  | Noted in site visit, services street light at far right abutment | 66 | 25.68 | 1694.88 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 16" Gas (insulated) | 1 | Yes | 66 | 0 | 1 | 7200 | 6 |  |  | 3600 | 2.73 | 9828 | 4 |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 2 | 3890.25 | 7780.5 | [5 empty] | 3 | 2 | 2 | 4 |  | 1694.88 | 7500 | 1 | 27436.5 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes, 7' Left and 3' Right, size of attached gas line estimated from photos |  |  | 74376 | 5702
182 | -- | 230 | 87671 | 198 | 01101601101587 | 8 |  | Adams | GARDNERS |  | UPPER BERMUDIAN CREEK |  | 79 | 99 | 26.0 | 52 | [25 empty] | Rural Local | 79 | 20 | 99 | 26.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1600 | 4 |  |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 10 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 8258.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 21957 | 5709
183 | -- | 244 | 90770 | 13961 | 21400800302148 | 8 |  | Cumberland | WASHINGTON |  | BACK CREEK |  | 27 | 47 | 24.3 | 52 | [25 empty] | Rural Local | 27 | 20 | 47 | 24.3 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 400 | 1 |  |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 8 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 4982.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes, 8' Left and 20' Right, line crosses over bridge |  |  | 21961 | 5763
184 | -- | 267 | 63230 | 21446 | 36103501500846 | 8 |  | Lancaster | 0.75 MILE N. OF NEWTOWN |  | MIDDLE CREEK |  | 27 | 47 | 18.1 | 52 | [25 empty] | Rural Minor Collector | 27 | 20 | 47 | 18.1 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 800 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | UNKNOWN | [5 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 6074.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 21967 | 5883
185 | -- | 273 | 91324 | 21514 | 36200200602329 | 8 |  | Lancaster | KIRKS MILL |  | REYNOLDS RUN |  | 34 | 54 | 27.3 | 52 | [25 empty] | Rural Local | 34 | 20 | 54 | 27.3 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 3 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 22626 | 8424
186 | -- | 346 | 23517 | 31343 | 55003104200000 | 9 |  | Somerset | 0.5 MILE EAST OF SR 1005 |  | SANDY HOLLOW CREEK |  | 50 | 70 | 40.0 | 64 | [25 empty] | Rural Minor Arterial | 50 | 20 | 70 | 40.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 3 |  |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 28.00, 32.00 | [5 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | OH E located directly behind guardrail. No other utilities identified. |  |  | 22627 | 8425
187 | -- | 370 | 24757 | 7925 | 10030800801195 | 10 |  | Butler | RIDER CHURCH |  | TRIB TO STONY RUN |  | 34 | 54 | 33.4 | 54 | [25 empty] | Rural Major Collector | 34 | 20 | 54 | 33.4 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 6074.25 | 10000 | 1 | UG telephone identified during site visit. Based on flags, UG T should not be impacted by construction. |  |  | 22444 | 8580
188 | -- | 395 | 83343 | 19807 | 33400100700000 | 10 |  | Jefferson | NORTH OF ROSEVILLE |  | MILL CREEK |  | 64 | 84 | 25.1 | 48 | [25 empty] | Rural Minor Collector | 64 | 20 | 84 | 25.1 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 2 |  |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 6074.25 | 10000 | 1 | OH E crosses the bridge at an angle. OH T and Cable lines are 15'+ from the bridge. |  |  | 22797 | 17813
189 | -- | 501 | 79325 | 16922 | 26301301700955 | 12 |  | Fayette | GERMAN TOWNSHIP |  | MIDDLE RUN |  | 43 | 63 | 26.3 | 48 | [25 empty] | Rural Minor Collector | 43 | 20 | 63 | 26.3 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 400 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 4982.25 | 10000 | 1 | OH telephone lines cross over the edge of the bridge. No other utilities identified in the site visit. |  |  | 22798 | 17826
190 | -- | 528 | 98377 | 34907 | 62201500200805 | 12 |  | Washington | WEST BETHLEHEM TOWNSHIP |  | DANIELS RUN |  | 52 | 72 | 20.8 | 50 | [25 empty] | Rural Minor Collector | 52 | 20 | 72 | 20.8 | 26 | 24 | 50 |  | 1 | 20 | 200 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 400 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 4982.25 | 10000 | 1 | OH Telephone line crosses over the bridge at an angle. No other utilities identified near the bridge. |  |  | 22825 | 17827
191 | -- | 536 | 31146 | 35103 | 62400300701841 | 12 |  | Washington | HANOVER TOWNSHIP |  | KINGS CREEK |  | 37 | 57 | 15.5 | 46 | [25 empty] | Rural Local | 37 | 20 | 57 | 15.5 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 6074.25 | 10000 | 1 | OH lines offset 5' from the edge of bridge. No other utilities identified near the bridge. |  |  | 22826 | 17828
192 | -- | 537 | 30552 | 35171 | 62402300200000 | 12 |  | Washington | CROSS CREEK TOWNSHIP |  | NORTH FORK CROSS CREEK |  | 28 | 48 | 13.5 | 48 | [25 empty] | Rural Local | 28 | 20 | 48 | 13.5 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 400 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 4982.25 | 10000 | 1 | OH telephone line crosses over the channel at the edge of the bridge. |  |  | 22827 | 17832
193 | -- | 539 | 81846 | 35201 | 62403900701840 | 12 |  | Washington | MOUNT PLEASANT TOWNSHIP |  | MILLERS RUN |  | 34 | 54 | 18.7 | 48 | [25 empty] | Rural Minor Collector | 34 | 20 | 54 | 18.7 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 400 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 4982.25 | 10000 | 1 | OH line offset 12' from the edge of the one lane bridge. |  |  | 22832 | 17850
194 | -- | 14 | 1686 | 25858 | 43031801500622 | 1 |  | Mercer | LACKAWANNOCK TOWNSHIP |  | OVER LT NESHANNOCK CK BR |  | 59 | 79 | 35.0 | 56 | [25 empty] | Rural Minor Collector | 59 | 20 | 79 | 35.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1600 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 13 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 8258.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 88142 | 17853
195 | -- | 91 | 5038 | 6136 | 08022001301099 | 3 |  | Bradford | VILLAGE OF STEVENSON |  | SOUTH BRANCH TOWANDA CR | 20143580167 | 72 | 92 | 26.0 | 64 | [25 empty] | Rural Minor Arterial | 72 | 20 | 92 | 26.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 25 | [5 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 22837 | 17873
196 | -- | 110 | 6045 | 24748 | 41041400100417 | 3 |  | Lycoming | 2 MI N OF WATERVILLE |  | OVER UPPER PINE BOT.R. |  | 36 | 56 | 26.2 | 52 | [25 empty] | Rural Major Collector | 36 | 20 | 56 | 26.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 800 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 25 |  |  |  |  | 12 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 6074.25 | 10000 | 1 | COMPLETE, pole offset in site visit notes/sketches |  |  | 74433 | 18576
197 | -- | 251 | 78710 | 17592 | 28400801900060 | 8 |  | Franklin | 2 MI. NE OF EDENVILLE |  | DENNIS RUN |  | 64 | 84 | 27.4 | 52 | [25 empty] | Rural Local | 64 | 20 | 84 | 27.4 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, orientation/offset unknown | 84 | 32.1 | 2696.4 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 600 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 6 | 1 | 2 | 3 |  | 2696.4 | 7500 | 1 | 9418.5 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes, 10' Left and 6' Right, line crosses over bridge |  |  | 23030 | 18601
198 | -- | 121 | 79230 | 29303 | 49402000301775 | 3 |  | Northumberland | 2.5 MI NW OF FISHERS FERRY |  | HOLLOWING RUN |  | 55 | 75 | 26.7 | 48 | [25 empty] | Rural Minor Collector | 55 | 20 | 75 | 26.7 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 2 |  | PPL | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 16.5 |  |  |  |  | 7 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | COMPLETE, pole offset in site visit notes/sketches |  |  | 22980 | 18603
199 | -- | 122 | 6603 | 29306 | 49402200101591 | 3 |  | Northumberland | .25 MI E OF FISHERS FERRY |  | OVER BOILE RUN |  | 23 | 43 | 26.4 | 48 | [25 empty] | Rural Local | 23 | 20 | 43 | 26.4 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1600 | 3 |  | PPL | 1200 | 2.73 | 3276 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 10 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 8258.25 | 10000 | 1 | COMPLETE, pole offset in site visit notes/sketches |  |  | 23039 | 18703
200 | -- | 152 | 96734 | 32437 | 57101801302350 | 4 |  | Susquehanna | NEW MILFORD .6 M W TR 11 |  | BEAVER CREEK | 20143580483 | 40 | 60 | 26.2 | 48 | [25 empty] | Rural Minor Collector | 40 | 20 | 60 | 26.2 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3200 | 4 |  |  | 1600 | 2.73 | 4368 | 4 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 6 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 12626.25 | 10000 | 2 | COMPLETE, pole offset given in site visit notes | PRELIMINARY ASSUMPTIONS: LENGTHENING BRIDGE 10', SAME WIDTH; |  | 23038 | 18742
201 | -- | 156 | 68876 | 35471 | 63019106701296 | 4 |  | Wayne | OREGON TWP 1.5M N SR 4019 |  | BIG BROOK CREEK | 20143580183 | 28 | 48 | 26.0 | 54 | [25 empty] | Rural Minor Arterial | 28 | 20 | 48 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 4 |  |  | 1600 | 2.73 | 4368 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 25 |  |  |  |  | 6 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 10442.25 | 10000 | 2 | COMPLETE, pole offset given in site visit notes |  |  | 23058 | 18773
202 | -- | 171 | 85635 | 4957 | 06100800300000 | 5 |  | Berks | .5 MI.SOUTH OF HAMBURG |  | WINDSOR CREEK |  | 27 | 47 | 27.5 | 52 | [25 empty] | Rural Minor Collector | 27 | 20 | 47 | 27.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3600 | 4 |  |  | 1600 | 2.73 | 4368 | 5 |  | 2000 | 2.73 | 5460 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 0 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 13718.25 | 10000 | 2 | COMPLETE, all lines cross over edge of bridge |  |  | 23114 | 18784
203 | -- | 203 | 12098 | 28672 | 48101500801677 | 5 |  | Northampton | @ INT. WITH T-604 |  | WALTZ CREEK |  | 46 | 66 | 30.5 | 56 | [25 empty] | Rural Major Collector | 46 | 20 | 66 | 30.5 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 2 |  |  | 800 | 2.73 | 2184 | 4 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 6 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 10442.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 74449 | 18785
204 | -- | 258 | 19915 | 21251 | 36037204240000 | 8 |  | Lancaster | Christiana Borough |  | Williams Run |  | 87 | 107 | 36.0 | 48 | [25 empty] | Urban Minor Arterial | 87 | 20 | 107 | 36.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, assume parallel to road, no sketch or detailed notes | 107 | 477.3 | 51071.1 | [13 empty] | 107 |  |  |  | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3000 | 2 |  |  | 1200 | 2.73 | 3276 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 51071.1 | 7500 | 7 | 15970.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 23116 | 18881
205 | -- | 259 | 87505 | 21277 | 36046202200000 | 8 |  | Lancaster | Columbia Ave over Little Conestoga Creek |  | LITTLE CONESTOGA CREEK |  | 44 | 64 | 52.3 | 76 | [25 empty] | Urban Minor Arterial | 44 | 20 | 64 | 52.3 | 52 | 24 | 76 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 0 | 1 |  |  | Noted in site visit, orientation/offset unknown | 64 | 249.45 | 15964.8 | [13 empty] | 64 |  |  |  | 0 | 1 |  |  | Noted in site visit, orientation/offset unknown | 64 | 477.3 | 30547.2 | [13 empty] | 64 |  |  |  | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 1 |  |  | Noted in site visit, orientation/offset unknown | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 8" Water, 12" Fiber Optic, 16" Sewer | 1 | Yes | 192 | 0 | 1 | 7200 | 3 |  |  | 2400 | 2.73 | 6552 | 3 |  | 2400 | 2.73 | 6552 | 2 |  | 1600 | 2.73 | 4368 | 1 |  | 800 | 2.73 | 2184 | 3 | 3890.25 | 11670.75 | [5 empty] | 5 | 4 | 3 | 7 |  | 46512 | 7500 | 7 | 31326.75 | 10000 | 4 | COMPLETE, pole offsets given in site visit notes |  |  | 88158 | 45123
206 | -- | 229 | 87676 | 185 | 01101400501701 | 8 |  | Adams | VILLAGE OF LIMEROCK MILL |  | BERMUDIAN CREEK |  | 43 | 63 | 25.7 | 52 | [25 empty] | Rural Minor Collector | 43 | 20 | 63 | 25.7 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 4 |  |  | 1600 | 2.73 | 4368 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 8 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 10442.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 92698 | 41517
207 | -- | 238 | 90695 | 13735 | 21023300900266 | 8 |  | Cumberland | PINE GROVE FURNACE |  | TOMS RUN |  | 21 | 41 | 25.6 | 54 | [25 empty] | Rural Major Collector | 21 | 20 | 41 | 25.6 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 16.5 |  |  |  |  | 3 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 23517 | 31343
208 | -- | 242 | 74055 | 13946 | 21301900100000 | 8 |  | Cumberland | MONTSERA |  | YELLOW BREECHES CREEK |  | 50 | 70 | 18.0 | 52 | [25 empty] | Rural Local | 50 | 20 | 70 | 18.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 0 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 23586 | 31469
209 | -- | 246 | 47519 | 14481 | 22201200100356 | 8 |  | Dauphin | .5 MI. N. OF HERSHEY |  | NS RAILROAD (PENN EAST) |  | 96 | 116 | 29.7 | 56 | [25 empty] | Urban Local | 96 | 20 | 116 | 29.7 | 32 | 24 | 56 |  | 1 | 45 | 450 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  | Noted in site visit, assume crossing road, 200' far left | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  | Noted in site visit, within railroad ROW, should avoid | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3600 | 4 |  |  | 1600 | 2.73 | 4368 | 5 |  | 2000 | 2.73 | 5460 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 13718.25 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, one pole appears to be closer than 15', guy wires cross over bridge |  |  | 23410 | 31470
210 | -- | 250 | 87683 | 17471 | 28099706500000 | 8 |  | Franklin | TOWNSHIP LINE LURG.& LETT |  | CONODOGUINET CREEK |  | 67 | 87 | 32.6 | 62 | [25 empty] | Rural Minor Arterial | 67 | 20 | 87 | 32.6 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2000 | 3 |  |  | 1200 | 2.73 | 3276 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 35 | 10 | 8.7 | IN ROW |  | 10 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 9350.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 74446 | 31471
211 | -- | 252 | 78708 | 17593 | 28400802301142 | 8 |  | Franklin | 3 MI E OF EDENVILLE |  | ROCKY SPRING CREEK |  | 74 | 94 | 30.2 | 52 | [25 empty] | Rural Local | 74 | 20 | 94 | 30.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 8 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 23516 | 31521
212 | -- | 266 | 100523 | 21439 | 36103400200000 | 8 |  | Lancaster | 1MI NE DENVER |  | SWAMP CREEK |  | 32 | 52 | 27.2 | 52 | [25 empty] | Rural Local | 32 | 20 | 52 | 27.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1600 | 3 |  |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 8258.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, no sketch, power poles only appear closer than 15' in photos |  |  | 23571 | 31528
213 | -- | 274 | 87516 | 21518 | 36200500300000 | 8 |  | Lancaster | 1MI NOF NEW TEXAS |  | LITTLE CONOWINGO CRK |  | 37 | 57 | 26.2 | 52 | [25 empty] | Rural Local | 37 | 20 | 57 | 26.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 23588 | 31532
214 | -- | 278 | 19964 | 21558 | 36202000100000 | 8 |  | Lancaster | CAMARGO |  | BEAVER CREEK | 20143571656 | 36 | 56 | 23.0 | 52 | [25 empty] | Rural Local | 36 | 20 | 56 | 23.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 800 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 6074.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 74467 | 31588
215 | -- | 286 | 93582 | 29451 | 50001701101051 | 8 |  | Perry | 2 MILES WEST OF KISTLER |  | BIXLERS RUN |  | 42 | 62 | 27.1 | 52 | [25 empty] | Rural Major Collector | 42 | 20 | 62 | 27.1 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1600 | 2 |  |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 9 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 8258.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 23428 | 31608
216 | -- | 291 | 87491 | 29605 | 50101502002360 | 8 |  | Perry | 2 MI.S. OF MILLERSTOWN |  | WILD CAT RUN |  | 49 | 69 | 44.3 | 56 | [25 empty] | Rural Minor Collector | 49 | 20 | 69 | 44.3 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2000 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 800 | 2.73 | 2184 | 3 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 1 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 9350.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 23549 | 31630
217 | -- | 305 | 87595 | 37921 | 66307100100000 | 8 |  | York | 1 MILE S.W. OF PA 94 |  | SOUTH BR CONEWAGO CREEK |  | 33 | 53 | 26.3 | 52 | [25 empty] | Rural Local | 33 | 20 | 53 | 26.3 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  | Noted in site visit, assume in intersecting roadways, 50' back from near abut | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 12 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 23454 | 31651
218 | -- | 341 | 23114 | 18784 | 31101900100185 | 9 |  | Huntingdon | 0.03 MILE NORTH FROM PA 26 |  | STANDING STONE CREEK |  | 114 | 134 | 25.0 | 48 | [25 empty] | Rural Local | 114 | 20 | 134 | 25.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 800 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 30 | [5 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 6074.25 | 10000 | 1 | OH pole offset unknown from bridge or wing. Assume relocation of the pole. No other utilities identified in site visit or by PennDOT. |  |  | 23601 | 31758
219 | -- | 500 | 74189 | 16910 | 26301100900000 | 12 |  | Fayette | NICHOLSON & GERMAN TWPS. |  | CATS CREEK |  | 28 | 48 | 26.0 | 48 | [25 empty] | Rural Minor Collector | 28 | 20 | 48 | 26.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 6074.25 | 10000 | 1 | OH telephone and cable identified near the bridge on one side. No other utilities identified in the site visit. |  |  | 83197 | 2992
220 | -- | 509 | 74203 | 18222 | 30101400803315 | 12 |  | Greene | MORGAN TOWNSHIP |  | CASTILE RUN |  | 68 | 88 | 16.0 | 46 | [25 empty] | Rural Local | 68 | 20 | 88 | 16.0 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | OH lines cross over the bridge and wings. No other utilities identified in site visit or by PennDOT. |  |  | 24085 | 3097
221 | -- | 535 | 30881 | 35090 | 62303700801515 | 12 |  | Washington | WEST FINLEY TOWNSHIP |  | ROBINSON RUN |  | 39 | 59 | 17.0 | 46 | [25 empty] | Rural Minor Collector | 39 | 20 | 59 | 17.0 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 6074.25 | 10000 | 1 | OH lines cross over near one of the wings of the bridge. No other utilities identified near the bridge. |  |  | 79606 | 3160
222 | -- | 18 | 97457 | 33956 | 61000603502233 | 1 |  | Warren | BROKENSTRAW TOWNSHIP |  | OVER WINTROTH RUN |  | 21 | 41 | 39.0 | 64 | [25 empty] | Rural Principal Arterial | 21 | 20 | 41 | 39.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  | Marker visible, parallel to road, >30' offset | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 1 | 1 | 4400 | 8 |  |  | 3200 | 2.73 | 8736 | 1 |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 8 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 15902.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 24000 | 3169
223 | -- | 20 | 2546 | 33982 | 61000608200000 | 1 |  | Warren | SHEFFIELD TOWNSHIP |  | OVER FOUR MILE RUN |  | 44 | 64 | 42.0 | 64 | [25 empty] | Rural Principal Arterial | 44 | 20 | 64 | 42.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 12" Gas | 1 | Yes | 64 | 0 | 1 | 4000 | 4 |  |  | 1600 | 2.73 | 4368 | 2 |  | 800 | 2.73 | 2184 | 4 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 8 | 1 | 1 | 2 |  | 0 | 7500 | 0 | 14810.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, gas line size estimated from site visit photos |  |  | 83252 | 3176
224 | -- | 74 | 4642 | 26468 | 44065502201820 | 2 |  | Mifflin | KISHACOQUILLAS |  | FROG HOLLOW RUN |  | 22 | 42 | 42.0 | 64 | [25 empty] | Rural Minor Arterial | 22 | 20 | 42 | 42.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  | Noted in site visit, parallel to road, offset 39' | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2800 | 4 |  |  | 1600 | 2.73 | 4368 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 3.25 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 11534.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 74202 | 3232
225 | -- | 85 | 4898 | 30191 | 52004904400406 | 2 |  | Potter | MILLS |  | BRANCH COWANESQUE CR |  | 20 | 40 | 32.3 | 58 | [25 empty] | Rural Minor Arterial | 20 | 20 | 40 | 32.3 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3200 | 4 |  |  | 1600 | 2.73 | 4368 | 3 |  | 1200 | 2.73 | 3276 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 3 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 12626.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 24023 | 3245
226 | -- | 86 | 4899 | 30233 | 52044900501401 | 2 |  | Potter | 2 MI N WALTON |  | BUCKSELLER RUN |  | 20 | 40 | 26.3 | 58 | [25 empty] | Rural Minor Arterial | 20 | 20 | 40 | 26.3 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3600 | 4 |  |  | 1600 | 2.73 | 4368 | 3 |  | 1200 | 2.73 | 3276 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 10 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 13718.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 24018 | 3278
227 | -- | 87 | 93373 | 30348 | 52200201302331 | 2 |  | Potter | 2 MI SW GERMANIA STATION |  | LYMAN RUN |  | 100 | 120 | 27.0 | 48 | [25 empty] | Rural Major Collector | 100 | 20 | 120 | 27.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2800 | 4 |  |  | 1600 | 2.73 | 4368 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 4 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 11534.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 24153 | 3282
228 | -- | 144 | 96737 | 32153 | 57001104601461 | 4 |  | Susquehanna | N MILFRD TP .2M S SR 1018 |  | SALT LICK CREEK |  | 54 | 74 | 49.0 | 70 | [25 empty] | Rural Major Collector | 54 | 20 | 74 | 49.0 | 46 | 24 | 70 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3600 | 4 |  |  | 1600 | 2.73 | 4368 | 2 |  | 800 | 2.73 | 2184 | 3 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 25 | 5 | -4.5 | OUT OF ROW |  | 6 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 13718.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 83284 | 3293
229 | -- | 260 | 91194 | 21292 | 36062501302573 | 8 |  | Lancaster | 1 MI. S. OF BOWMANSVILLE |  | MUDDY CREEK |  | 54 | 74 | 34.5 | 54 | [25 empty] | Rural Major Collector | 54 | 20 | 74 | 34.5 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2800 | 4 |  |  | 1600 | 2.73 | 4368 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 11534.25 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 98070 | 3294
230 | -- | 282 | 63229 | 21637 | 36301702401388 | 8 |  | Lancaster | 0.5 MI.NORTH OF LETORT |  | W.BR.CONESTOGA CREEK |  | 39 | 59 | 26.0 | 56 | [25 empty] | Urban Minor Collector | 39 | 20 | 59 | 26.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2800 | 4 |  |  | 1600 | 2.73 | 4368 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 5 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 11534.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, no sketch |  |  | 24806 | 7834
231 | -- | 285 | 87462 | 29426 | 50001100300893 | 8 |  | Perry | MARYSVILLE BORO |  | FISHING CREEK |  | 30 | 50 | 42 | 76 | [25 empty] | Urban Principle Arterial | 30 | 20 | 50 | 42 | 52 | 24 | 76 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 1 |  |  | mh's noted in site visit, crosses under bridge under stream bed | 76 | 477.3 | 36274.8 | [13 empty] | 76 |  |  |  | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4800 | 3 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1600 | 2.73 | 4368 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [5 empty] | 8 | 1 | 3 | 4 |  | 36274.8 | 7500 | 5 | 24774.75 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes, guy wire crosses directly over bridge |  |  | 24757 | 7925
232 | -- | 322 | 21961 | 5763 | 07300500100050 | 9 |  | Blair | .5 MI.W.OF SPROUL |  | BEAVERDAM CREEK |  | 62 | 82 | 25.8 | 50 | [25 empty] | Rural Local | 62 | 20 | 82 | 25.8 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2800 | 3 |  |  | 1200 | 2.73 | 3276 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 30 | [5 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 11534.25 | 10000 | 2 | OH lines run along the edge of the bridge. No other utilities identified. |  |  | 24667 | 7935
233 | -- | 349 | 74446 | 31471 | 55052300801065 | 9 |  | Somerset | DUMAS |  | TRIB TO WHITES CREEK | 20143580320 | 11 | 31 | 25.0 | 52 | [25 empty] | Rural Minor Arterial | 11 | 20 | 31 | 25.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4800 | 4 |  |  | 1600 | 2.73 | 4368 | 4 |  | 1600 | 2.73 | 4368 | 4 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 30 | [5 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 16994.25 | 10000 | 2 | OH lines cross over the channel 8' from the bridge. Two pink flags found near the bridge opening - unknown. |  |  | 24779 | 8016
234 | -- | 492 | 76012 | 16782 | 26104300200093 | 12 |  | Fayette | N. UNION & FRANKLIN TWPS. |  | REDSTONE CREEK | 20143580347/20143580348 | 82 | 102 | 25.0 | 50 | [25 empty] | Rural Minor Collector | 82 | 20 | 102 | 25.0 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 4 - 4" Conduit | 1 | Yes | 408 |  | 1 | 2000 | 3 |  |  | 1200 | 2.73 | 3276 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 0 | 7500 | 0 | 9350.25 | 10000 | 1 | Unknown utility attached to the bridge - 4-4" conduit. One OH pole located close to the bridge - relocate. |  |  | 78002 | 8025
235 | -- | 499 | 74184 | 16868 | 26201500300000 | 12 |  | Fayette | WHARTON TOWNSHIP |  | MEADOW RUN |  | 30 | 50 | 25.0 | 48 | [25 empty] | Rural Local | 30 | 20 | 50 | 25.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 7166.25 | 10000 | 1 | OH line identified near the bridge on one side. No other utilities identified in the site visit or by PennDOT. |  |  | 83332 | 8061
236 | -- | 533 | 81841 | 34985 | 62203600500000 | 12 |  | Washington | WEST PIKE RUN TOWNSHIP |  | PIKE RUN |  | 50 | 70 | 23.0 | 48 | [25 empty] | Rural Major Collector | 50 | 20 | 70 | 23.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 2 |  |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | 40 | [5 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 10442.25 | 10000 | 2 | OH lines cross the channel near the bridge. Water line identified during site visit 20'+ from the bridge - no relocation anticipated. |  |  | 24703 | 8071
237 | -- | 28 | 85135 | 9576 | 14100200501555 | 2 |  | Centre | YARNELL |  | LITTLE MARSH CREEK |  | 29 | 49 | 23.4 | 48 | [25 empty] | Rural Minor Collector | 29 | 20 | 49 | 23.4 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2000 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 | 3890.25 | 3890.25 | 25 | 5 | 8.3 | IN ROW |  | 5 | 0 | 1 | 1 |  | 0 | 7500 | 0 | 9350.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 83335 | 8073
238 | -- | 256 | 87536 | 21237 | 36034003700000 | 8 |  | Lancaster | 1 MI. W. OF CAIN |  | PEQUEA CREEK |  | 91 | 111 | 32.8 | 58 | [25 empty] | Rural Major Collector | 91 | 20 | 111 | 32.8 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2000 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 | 3890.25 | 3890.25 | [6 empty] | 0 | 1 | 1 |  | 0 | 7500 | 0 | 9350.25 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 77989 | 8104
239 | -- | 293 | 79042 | 29673 | 50301700100000 | 8 |  | Perry | AT BRIDGEPORT |  | TRIB SHERMANS CREEK |  | 30 | 50 | 24.4 | 48 | [25 empty] | Rural Local | 30 | 20 | 50 | 24.4 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 1 |  |  | UG telephone noted in site visit, markers at far left abutment, offset unknown | 50 | 32.1 | 1605 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 3 |  |  | 1200 | 2.73 | 3276 | 3 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 20 | 1 | 1 | 2 |  | 1605 | 7500 | 1 | 10442.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, all lines go directly over bridge |  |  | 89967 | 8113
240 | -- | 2 | 90155 | 12902 | 20000608400273 | 1 |  | Crawford | CAMBRIDGE TOWNSHIP |  | OVER FRENCH CREEK TRIB #3 |  | 11 | 31 | 30 | 56 | [25 empty] | Rural Minor Arterial | 11 | 20 | 31 | 30 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 35 | 12 | 8 | IN ROW |  | 12 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 24710 | 8334
241 | -- | 295 | 91353 | 37488 | 66012401400000 | 8 |  | York | 1.5 W OF DELROY |  | KREUTZ CREEK |  | 43 | 63 | 25.8 | 64 | [25 empty] | Urban Minor Collector | 43 | 20 | 63 | 25.8 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 | 1 |  |  | Noted in site visit, orientation/offset unknown, no sketch | 0 | 249.45 | 0 | [13 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 6" Water | 1 | Yes | 63 | 0 | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 83229 | 10975
242 | -- | 37 | 91508 | 11390 | 17021902800000 | 2 |  | Clearfield | MCGEES MILLS |  | WHISKEY RUN |  | 34 | 54 | 43.0 | 68 | [25 empty] | Rural Principal Arterial - Other | 34 | 20 | 54 | 43.0 | 44 | 24 | 68 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 4 |  |  | 2400 | 2.73 | 6552 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 40 | 12 | 6.5 | IN ROW |  | 12 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, power in conflict, communications lines are not |  |  | 83232 | 10997
243 | -- | 43 |  | 11658 |  | 2 |  | Clearfield | HAWK RUN |  | HAWK RUN |  | 26 | 46 | 24.9 | 52 | [25 empty] | Rural Major Collector | 26 | 20 | 46 | 24.9 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 600 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 |  |  |  |  | 0 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 9418.5 | 10000 | 1 | COMPLETE, lines cross over bridge |  |  | 83234 | 10996
244 | -- | 53 | 4214 | 20106 | 34100200200000 | 2 |  | Juniata | 0.5 MI E CUBA MILLS |  | LOST CREEK |  | 106 | 126 | 24.2 | 52 | [25 empty] | Rural Minor Collector | 106 | 20 | 126 | 24.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 600 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 20 | 7.5 | 0.4 | IN ROW |  | 0 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 9418.5 | 10000 | 1 | COMPLETE, overhead line crosses over bridge |  |  | 25221 | 11042
245 | -- | 109 | 6145 | 24603 | 41011801700622 | 3 |  | Lycoming | VILLAGE OF LAIRDSVILLE |  | OVER BIG RUN |  | 33 | 53 | 34 | 61 | [25 empty] | Rural Minor Arterial | 33 | 20 | 53 | 34 | 37 | 24 | 61 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 600 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 0 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 9418.5 | 10000 | 1 | COMPLETE, pole offset in site visit notes, telephone line crosses directly over bridge |  |  | 83241 | 11049
246 | -- | 300 | 78878 | 37641 | 66092100900000 | 8 |  | York | 3 MI.E. OF DOVER |  | TRIB TO LITTLE CONEWAGO |  | 29 | 49 | 27.5 | 64 | [25 empty] | Urban Minor Collector | 29 | 20 | 49 | 27.5 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 8 | 0 | 1 |  |  | Noted in site visit, parallel to road, offset unknown | 49 | 249.45 | 12223.05 | [13 empty] | 49 |  |  |  | 0 | 1 |  |  | mh noted in site visit, orientation/offset of line unknown | 49 | 477.3 | 23387.7 | [13 empty] | 49 |  |  |  | 0 | 1 |  |  | Noted in site visit, orientation/offset unknown | 49 | 120.88 | 5923.12 | [13 empty] | 49 |  |  |  | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 1 |  |  | UG telephone noted in site visit, markers at near right abutment, offset unknown | 49 | 32.1 | 1572.9 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2800 | 4 |  |  | 1600 | 2.73 | 4368 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 7 | 4 | 1 | 5 |  | 43106.77 | 7500 | 6 | 11534.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, no sketch |  |  | 83256 | 11088
247 | -- | 301 | 78896 | 37725 | 66202800800249 | 8 |  | York | DELTA BORO |  | SCOTT'S RUN |  | 34 | 54 | 42.6 | 50 | [25 empty] | Rural Local | 34 | 20 | 54 | 42.6 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 | 1 |  |  | Noted is site visit, assume crossing road, location unknown | 50 | 249.45 | 12472.5 | [13 empty] | 50 |  |  |  | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4000 | 4 |  |  | 1600 | 2.73 | 4368 | 4 |  | 1600 | 2.73 | 4368 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 | 3890.25 | 3890.25 | [5 empty] | 10 | 1 | 1 | 2 |  | 12472.5 | 7500 | 2 | 14810.25 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, no sketch |  |  | 83293 | 19087
248 | -- | 145 | 89023 | 32244 | 57010601220638 | 4 |  | Susquehanna | LENOX TWP .1 M E TR 92 |  | TUNKHANNOCK CREEK | 20143561422 | 114 | 134 | 29.0 | 64 | [25 empty] | Rural Minor Arterial | 114 | 20 | 134 | 29.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 600 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 9418.5 | 10000 | 1 | COMPLETE, pole offsets not given in site visit notes/sketch, poles appear closer than 15' in photos | PRELIMINARY ASSUMPTIONS: LENGTHENING BRIDGE 30', WIDENING BRIDGE 12'; 6 WIRES VISIBLE NEEDS VERIFIED |  | 95851 | 19183
249 | -- | 219 | 81290 | 27868 | 46404200341011 | 6 |  | Montgomery | NW POTTSTOWN 11B6/3026C8 |  | MANATAWNY CREEK | 20143571505 | 131 | 151 | 31.5 | 52 | [25 empty] | Urban Major Collector | 131 | 20 | 151 | 31.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 3 |  |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 6 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 25780 | 19200
250 | -- | 228 | 18146 | 160 | 01039400600526 | 8 |  | Adams | VILLAGE OF TABLE ROCK |  | CONEWAGO CREEK |  | 154 | 174 | 25.2 | 64 | [25 empty] | Rural Minor Collector | 154 | 20 | 174 | 25.2 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 0 |  |  | 0 | 2.73 | 0 | 4 |  | 2400 | 2.73 | 6552 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 6 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 25584 | 19320
251 | -- | 263 | 87521 | 21409 | 36102100420000 | 8 |  | Lancaster | S.OF UNION GROVE |  | CONESTOGA RIVER |  | 137 | 157 | 22.9 | 52 | [25 empty] | Rural Local | 137 | 20 | 157 | 22.9 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 2 |  |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos, power only, communication lines are OK |  |  | 78120 | 19392
252 | -- | 306 | 74944 | 37946 | 66400102102301 | 8 |  | York | 2 MILES E. OF DOVER |  | FOX RUN |  | 98 | 118 | 26.0 | 64 | [25 empty] | Urban Minor Arterial | 98 | 20 | 118 | 26.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 1 |  |  | mh noted in site visit, crosses beneath first span of bridge | 64 | 477.3 | 30547.2 | [13 empty] | 64 |  |  |  | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [5 empty] | 1 | 1 | 1 | 2 |  | 30547.2 | 7500 | 5 | 7166.25 | 10000 | 1 | COMPLETE, pole offsets given in site visit notes |  |  | 83282 | 19550
253 | -- | 270 | 91323 | 21474 | 36104800500000 | 8 |  | Lancaster | 1.25 MI.E. OF TERRE HILL |  | BLACK CREEK |  | 38 | 58 | 26.2 | 48 | [25 empty] | Rural Local | 38 | 20 | 58 | 26.2 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 83312 | 19699
254 | -- | 277 | 91108 | 21545 | 36201500400000 | 8 |  | Lancaster | 2 MI E OF COLLINS |  | WEST BRANCH OCTORARO CR |  | 96 | 116 | 24.6 | 52 | [25 empty] | Rural Minor Collector | 96 | 20 | 116 | 24.6 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 26151 | 19708
255 | -- | 297 | 91191 | 37590 | 66042504600314 | 8 |  | York | 1.2 MI.S.E. OF CRALEY |  | FISHING CREEK |  | 48 | 68 | 25.7 | 54 | [25 empty] | Rural Major Collector | 48 | 20 | 68 | 25.7 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 30 | 6 | 11.15 | IN ROW |  | 4 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 26069 | 19737
256 | -- | 298 | 78860 | 37607 | 66061601000255 | 8 |  | York | .5 MI. N.W. OF GLEN ROCK |  | TRIB TO S BR CODORUS CR |  | 58 | 78 | 26.1 | 56 | [25 empty] | Rural Major Collector | 58 | 20 | 78 | 26.1 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | 2 | 9.95 | IN ROW |  | 2 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit note, 2' Left and 20' Right |  |  | 83343 | 19807
257 | -- | 308 | 90222 | 38007 | 66403300403136 | 8 |  | York | 1.0 MI.N.E. ANDERSONTOWN |  | YELLOW BREECHES CREEK |  | 122 | 142 | 19.5 | 52 | [25 empty] | Rural Local | 122 | 20 | 142 | 19.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 0 |  |  | 0 | 2.73 | 0 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 5 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, 5' Left and 15' Right, communication lines only in conflict |  |  | 62523 | 505
258 | -- | 327 | 22797 | 17813 | 29048400101102 | 9 |  | Fulton | 0.2 MILE EAST OF TR 26 |  | SIDELING HILL CREEK |  | 118 | 138 | 25.9 | 48 | [25 empty] | Rural Major Collector | 118 | 20 | 138 | 25.9 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 600 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 24.00, 34.00 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 9418.5 | 10000 | 1 | OH E offset 20'+ from the bridge. OH T offset less than 5' from bridge. |  |  | 27272 | 659
259 | -- | 332 | 22832 | 17850 | 29065503900454 | 9 |  | Fulton | .1 M N TR30,HARRISONVILLE |  | SINDELDECKER BRANCH |  | 31 | 51 | 24.4 | 52 | [25 empty] | Rural Major Collector | 31 | 20 | 51 | 24.4 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 600 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 20 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 9418.5 | 10000 | 1 | OH telephone within 8' of the edge of bridge. No other utilities identified near the bridge. |  |  | 28154 | 664
260 | -- | 334 | 22837 | 17873 | 29100100100266 | 9 |  | Fulton | WEBSTER MILLS |  | SPRING RUN |  | 37 | 57 | 28.0 | 52 | [25 empty] | Rural Local | 37 | 20 | 57 | 28.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 600 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 9418.5 | 10000 | 1 | OH telephone 3' offset from bridge. No other utilities identified near the bridge in site visit or by PennDOT. |  |  | 73522 | 709
261 | -- | 354 | 23428 | 31608 | 55201301000000 | 9 |  | Somerset | 0.46 MILE SOUTH FROM SR 3002 |  | POWDER RUN | 20143580119 | 39 | 59 | 14.0 | 48 | [25 empty] | Rural Minor Collector | 39 | 20 | 59 | 14.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 600 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 9418.5 | 10000 | 1 | OH lines 10' offset from one-lane bridge. No other utilities identified in the site visit. |  |  | 37590 | 954
262 | -- | 444 | 89079 | 1881 | 02310800100174 | 11 |  | Allegheny | 200' S.W. OF SR 3049 |  | NORTH BRANCH ROBINSON RN |  | 16 | 36 | 26.1 | 54 | [25 empty] | Rural Major Collector | 16 | 20 | 36 | 26.1 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 2 |  | West Penn Power | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | OH electric is the only utility identified in site visit |  |  | 28597 | 961
263 | -- | 484 | 51484 | 16673 | 26038100801000 | 12 |  | Fayette | WHARTON TOWNSHIP |  | STONY RUN | 20143580452 | 37 | 57 | 25.0 | 50 | [25 empty] | Rural Major Collector | 37 | 20 | 57 | 25.0 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 600 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 9418.5 | 10000 | 1 | OH telephone crosses bridge at an angle. No other utilities identified in the area. |  |  | 63321 | 1334
264 | -- | 1 | 97120 | 12879 | 20000604100000 | 1 |  | Crawford | VERNON TOWNSHIP |  | OVER TR CONNEAUT LK OUT |  | 23 | 43 | 69.5 | 95 | [25 empty] | Rural Principal Arterial | 23 | 20 | 43 | 69.5 | 71 | 24 | 95 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3000 | 0 |  |  | 0 | 2.73 | 0 | 3 |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 50 | 12 | 3.25 | IN ROW |  | 12 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 15970.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 63324 | 1339
265 | -- | 7 | 97124 | 13367 | 20401100200000 | 1 |  | Crawford | HAYFIELD TOWNSHIP |  | OVER WOLF RUN TRIB |  | 26 | 46 | 24.5 | 50 | [25 empty] | Rural Major Collector | 26 | 20 | 46 | 24.5 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0.5 |  |  |  | Noted in PennDOT notes and photos, orientation/offset unknown | 46 | 477.3 | 21955.8 | [13 empty] | 46 |  |  |  | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 0 |  |  | 0 | 2.73 | 0 | 3 |  | 1800 | 2.73 | 4914 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 8 | 0 | 2 | 2 |  | 21955.8 | 7500 | 3 | 14332.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 78185 | 1346
266 | -- | 11 | 93595 | 17208 | 27066600900000 | 1 |  | Forest | HICKORY TOWNSHIP |  | OVER BEAVER RUN |  | 30 | 50 | 25.5 | 48 | [25 empty] | Rural Major Collector | 30 | 20 | 50 | 25.5 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 1 | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | COMPLETE, No distances given in site visit notes, poles appear closer than 15' |  |  | 27185 | 1365
267 | -- | 32 | 85128 | 9434 | 14304001500701 | 2 |  | Centre | 1 MI E PORT MATILDA |  | SUNNYSIDE HOLLOW RUN |  | 45 | 65 | 45.0 | 64 | [25 empty] | Rural Principal Arterial - Other | 45 | 20 | 65 | 45.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 7200 | 4 |  |  | 2400 | 2.73 | 6552 | 8 |  | 4800 | 2.73 | 13104 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 27436.5 | 10000 | 3 | COMPLETE, pole offsets not given in site visit notes, poles appear closer than 15' |  |  | 27188 | 1372
268 | -- | 154 | 9679 | 32507 | 57202100501583 | 4 |  | Susquehanna | LENOX TWP OVER SR 0081 |  | SR 0081 I-81 |  | 210 | 230 | 33.5 | 52 | [25 empty] | Rural Local | 210 | 20 | 230 | 33.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 |  | 8.25 | IN ROW |  |  | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offset not given in site visit notes, poles appear closer than 15' in site visit photos | LONG BRIDGE OVER ROUTE 81 |  | 28128 | 1373
269 | -- | 323 | 21967 | 5883 | 07403100301171 | 9 |  | Blair | TYRONE BOROUGH |  | DECKER RUN |  | 21 | 41 | 30.0 | 54 | [25 empty] | Urban Minor Collector | 21 | 20 | 41 | 30.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 7 | 1 | 1 |  |  | Water line marker, FH, and meters located in line with end of bridge | 41 | 249.45 | 10227.45 | [13 empty] | 41 |  |  |  | 1 | 1 |  |  | WW MH located in roadway | 41 | 477.3 | 19569.3 | [13 empty] | 41 |  |  |  | 1 | 1 |  |  | Direction of gas line not specified in site visit | 41 | 120.88 | 4956.08 | [13 empty] | 41 |  |  |  | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0.5 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | [5 empty] | 3 | 2 | 5 |  | 34752.83 | 7500 | 5 | 19246.5 | 10000 | 2 | OH Lines 5' offset from bridge. Water line identified by markers, FH, and meters in site visit. Gas line identified in pavement, but no direction of line given. |  |  | 78220 | 1390
270 | -- | 160 | 56752 | 35675 | 63401401300733 | 4 |  | Wayne | SALEM TWP .6 M N SR 3008 |  | ARIEL CREEK |  | 49 | 69 | 24.3 | 48 | [5 empty] | 2014-06-19 | [19 empty] | Rural Local | 49 | 20 | 69 | 24.3 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 |  |  |  |  | 10 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | COMPLETE, pole offset given in site visit notes |  |  | 89100 | 1397
271 | -- | 169 | 78877 | 4946 | 06100400100619 | 5 |  | Berks | WILLOW CREEK BRIDGE |  | WILLOW CREEK |  | 56 | 76 | 23.2 | 54 | [25 empty] | Urban Minor Collector | 56 | 20 | 76 | 23.2 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 6 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | COMPLETE, pole offset given in site visit notes | POLE RELOCATION QTY CHANGED FROM 1 TO 2 TOTAL |  | 63342 | 1400
272 | -- | 174 | 85762 | 9104 | 13401000501489 | 5 |  | Carbon | GERHARDS, QUAKAKE RD. |  | QUAKAKE CREEK |  | 34 | 54 | 26.2 | 54 | [25 empty] | Rural Major Collector | 34 | 20 | 54 | 26.2 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 2 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | COMPLETE, pole offset given in site visit notes |  |  | 28603 | 1404
273 | -- | 214 | 15232 | 15002 | 23042000701072 | 6 |  | Delaware | FOLSOM, NR MACDADE 35D09/3697K07 |  | STONY CREEK / 3697-K6 |  | 30 | 50 | 30.2 | 56 | [25 empty] | Urban Principal Arterial | 30 | 20 | 50 | 30.2 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 0 | 0 |  |  | Attached to bridge per PennDOT photo | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  | Attached to bridge per site visit photo and notes | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 6" Water, 8" Sewer | 1 | Yes | 100 | 0 | 1 | 3000 | 4 |  |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 0 | 7500 | 0 | 15970.5 | 10000 | 2 | COMPLETE, no pole offsets given in site visit notes, no utility sketch, poles appear closer than 15', water line not noted in site visit, pipe types and sizes estimated from PennDOT photo |  |  | 63343 | 1405
274 | -- | 226 | 87436 | 135 | 01023401202343 | 8 |  | Adams | CULPS CORNERS |  | CONEWAGO CREEK |  | 50 | 70 | 26.0 | 52 | [25 empty] | Rural Minor Collector | 50 | 20 | 70 | 26.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3600 | 4 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 3 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 17608.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, 3' Left and 4' Right |  |  | 63344 | 1406
275 | -- | 240 | 74054 | 13824 | 21099702601555 | 8 |  | Cumberland | MCCREA |  | DOUBLING GAP CREEK |  | 67 | 87 | 25.9 | 52 | [25 empty] | Rural Minor Collector | 67 | 20 | 87 | 25.9 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 7800 | 9 |  |  | 5400 | 2.73 | 14742 | 4 |  | 2400 | 2.73 | 6552 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 8 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 29074.5 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes |  |  | 78223 | 42177
276 | -- | 245 | 100078 | 14441 | 22101800101692 | 8 |  | Dauphin | 3 MI. N W GRATZ |  | DEEP CREEK |  | 26 | 46 | 20.0 | 48 | [25 empty] | Rural Local | 26 | 20 | 46 | 20.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 5 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 99687 | 1424
277 | -- | 261 | 78868 | 21326 | 36077204500174 | 8 |  | Lancaster | 1.5 MI. S.E. OF LITITZ |  | LITITZ RUN | 20143580443 | 37 | 57 | 30.5 | 64 | [25 empty] | Urban Minor Arterial | 37 | 20 | 57 | 30.5 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  | Force main noted in site visit notes, parallel to road, 20' left of bridge | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 27287 | 1435
278 | -- | 265 | 19927 | 21417 | 36102500801639 | 8 |  | Lancaster | 0.75 mi NW of Farmersville |  | Conestoga River |  | 68 | 88 | 20.2 | 52 | [25 empty] | Rural Minor Collector | 68 | 20 | 88 | 20.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3000 | 4 |  |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 15970.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, per photos power lines cross over bridge |  |  | 63356 | 1455
279 | -- | 268 | 20124 | 21454 | 36103702100000 | 8 |  | Lancaster | Speedwell Forge Rd/Hammer Creek |  | HAMMER CREEK |  | 35 | 55 | 23.0 | 52 | [25 empty] | Rural Minor Collector | 35 | 20 | 55 | 23.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | 6 | -1 | OUT OF ROW |  |  | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, lines cross directly over bridge |  |  | 63513 | 1471
280 | -- | 269 | 87706 | 21459 | 36103900500000 | 8 |  | Lancaster | 1.5 MI.N. OF MILLWAY |  | MIDDLE CREEK |  | 30 | 50 | 21.7 | 52 | [25 empty] | Rural Minor Collector | 30 | 20 | 50 | 21.7 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | 5 | 0.65 | IN ROW |  |  | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos | ROW ASSUMED |  | 28607 | 1479
281 | -- | 272 | 87566 | 21487 | 36105500202673 | 8 |  | Lancaster | Reinholds Rd over Swamp Ck (N of i76) |  | SWAMP CREEK | 20143561430 | 35 | 55 | 26.0 | 56 | [25 empty] | Rural Local | 35 | 20 | 55 | 26.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3600 | 4 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 17608.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 62174 | 1481
282 | -- | 279 | 87518 | 21559 | 36202000200000 | 8 |  | Lancaster | 1 MI.N. CAMARGO |  | BOWEY RUN |  | 32 | 52 | 18.5 | 52 | [25 empty] | Rural Local | 32 | 20 | 52 | 18.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 26417 | 1496
283 | -- | 280 | 87501 | 21595 | 36204500700000 | 8 |  | Lancaster | North of Bird In Hand |  | Mill Creek | 20143571667/20143571668 | 62 | 82 | 20.2 | 54 | [25 empty] | Rural Minor Collector | 62 | 20 | 82 | 20.2 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 73045 | 1498
284 | -- | 288 | 73961 | 29518 | 50007401900530 | 8 |  | Perry | GREEN PARK |  | MONTOUR CREEK |  | 28 | 48 | 27.7 | 56 | [25 empty] | Rural Major Collector | 28 | 20 | 48 | 27.7 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3000 | 3 |  |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 4 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 15970.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 27451 | 1519
285 | -- | 290 | 90716 | 29566 | 50085002501777 | 8 |  | Perry | FORT ROBINSON |  | BIXLERS RUN |  | 52 | 72 | 23.0 | 52 | [25 empty] | Rural Major Collector | 52 | 20 | 72 | 23.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  | UG telephone noted in site visit notes, far right abutment going away | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 4 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, 12' Left and 4' Right, power lines go directly over bridge |  |  | 99665 | 1520
286 | -- | 292 | 101098 | 29651 | 50300600100014 | 8 |  | Perry | 4 MI SW OF BLAIN |  | SHAEFFER'S RUN |  | 35 | 55 | 15.0 | 52 | [25 empty] | Rural Local | 35 | 20 | 55 | 15.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 15 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, 20' Left and 15' Right, all lines go directly over bridge |  |  | 78224 | 1523
287 | -- | 294 | 79047 | 29693 | 50400701001472 | 8 |  | Perry | DONNALLY'S MILLS |  | RACCOON CREEK |  | 45 | 65 | 27.7 | 52 | [25 empty] | Rural Minor Collector | 45 | 20 | 65 | 27.7 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 6 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, 30' Left and 6' Right, communications lines only in conflict |  |  | 99670 | 1527
288 | -- | 296 | 87693 | 37491 | 66012402502532 | 8 |  | York | 1 MILE N OF CRALEY |  | CABIN CREEK | 20143571677 | 84 | 104 | 26.0 | 54 | [25 empty] | Rural Major Collector | 84 | 20 | 104 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 40 | 8 | 19 | IN ROW |  |  | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 63529 | 1559
289 | -- | 302 | 87695 | 37726 | 66202900902536 | 8 |  | York | 5 MILE NE OF RED LION |  | CABIN CREEK |  | 34 | 54 | 27.5 | 52 | [25 empty] | Urban Collector | 34 | 20 | 54 | 27.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 78271 | 1562
290 | -- | 309 | 91192 | 38023 | 66405100300581 | 8 |  | York | 1 MI. N.E. FARMERS |  | PARADISE CREEK |  | 43 | 63 | 25.3 | 52 | [25 empty] | Rural Local | 43 | 20 | 63 | 25.3 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 15 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, 15' Left and 25' Right, lines cross directly over the bridge |  |  | 63547 | 1567
291 | -- | 319 | 22107 | 5699 | 07101302400000 | 9 |  | Blair | .75 MI.NE.OF CULP |  | SINKING RUN |  | 36 | 56 | 33.0 | 54 | [25 empty] | Rural Major Collector | 36 | 20 | 56 | 33.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 30 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | OH Telephone and cable along side of bridge. No other utilities identified in site visit or by PennDOT. |  |  | 74324 | 1568
292 | -- | 320 | 74376 | 5702 | 07101302500908 | 9 |  | Blair | 1.5 MI.NE.OF CULP |  | SINKING RUN | 20143580307 | 52 | 72 | 32.9 | 54 | [25 empty] | Rural Major Collector | 52 | 20 | 72 | 32.9 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 30 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | OH Telephone and cable along side of bridge. No other utilities identified in site visit or by PennDOT. |  |  | 27419 | 1600
293 | -- | 325 | 22627 | 8425 | 11016002200000 | 9 |  | Cambria | 1.0 MILE NORTH OF TR 869E |  | LAUREL RUN | 20143561462 | 37 | 57 | 28.1 | 56 | [25 empty] | Rural Major Collector | 37 | 20 | 57 | 28.1 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 30 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | OH lines on one side of road right behind guardrail. No other utilities identified. |  |  | 89124 | 1620
294 | -- | 328 | 22798 | 17826 | 29052201401573 | 9 |  | Fulton | NEEDMORE |  | BARNETT RUN |  | 50 | 70 | 33.3 | 54 | [25 empty] | Rural Minor Arterial | 50 | 20 | 70 | 33.3 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 45.00, 40.00 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | OH telephone and cable offset 8' from the bridge per site visit info. |  |  | 27275 | 1626
295 | -- | 329 | 22825 | 17827 | 29052201600330 | 9 |  | Fulton | 3/4 MILE N. OF NEEDMORE |  | PALMER RUN | 20143561474 | 30 | 50 | 26.0 | 54 | [25 empty] | Rural Minor Arterial | 30 | 20 | 50 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 35.00, 40.00 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | OH telephone and cable offset 8' from the bridge per site visit info. OH E offset 25'+ from bridge. |  |  | 63557 | 1671
296 | -- | 330 | 22826 | 17828 | 29052201601370 | 9 |  | Fulton | 1 MILE NORTH OF NEEDMORE |  | LITTLE TONOLOWAY CREEK | 20143571735 | 79 | 99 | 26.1 | 54 | [25 empty] | Rural Minor Arterial | 79 | 20 | 99 | 26.1 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1800 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 40 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | OH Telephone and cable offset 6' from bridge per site visit. OH E offset 20'+ from bridge. |  |  | 27436 | 1704
297 | -- | 336 | 23030 | 18601 | 31002604900654 | 9 |  | Huntingdon | .1 MI N SR1011,CNTR UNION |  | MURRAY RUN | 20143571761 | 67 | 87 | 33.0 | 56 | [25 empty] | Rural Minor Arterial | 67 | 20 | 87 | 33.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 40.00, 30.00 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | OH telephone and cable lines cross over wings. Electric substation in the area not conflicted by bridge construction. No other utilities identified in the area. |  |  | 28446 | 1715
298 | -- | 352 | 23588 | 31532 | 55100701800000 | 9 |  | Somerset | LAMBERTSVILLE |  | LAMBERT RUN |  | 23 | 43 | 20.0 | 52 | [25 empty] | Rural Major Collector | 23 | 20 | 43 | 20.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  |  | 1 |  | Unknown utility | One Call stakes found behind guardrail | 43 | 56.12 | 2413.16 | [13 empty] | 43 |  |  |  | None | 0 | None | 0 |  | 1 | 4800 | 4 |  |  | 3200 | 2.73 | 8736 | 1 |  | 800 | 2.73 | 2184 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | 16.5 | [5 empty] | 1 | 3 | 4 |  | 2413.16 | 7500 | 1 | 24774.75 | 10000 | 3 | OH lines cross over the bridge at an angle and over the wings. One Call stakes located directly behind guardrail on each side of the channel - unknown utility? |  |  | 27386 | 1727
299 | -- | 338 | 23039 | 18703 | 31065505400533 | 9 |  | Huntingdon | .7 MI.N.SR 1005,FOUSETOWN |  | SADDLERS RUN | 20143580408 | 67 | 87 | 32.9 | 56 | [25 empty] | Rural Minor Arterial | 67 | 20 | 87 | 32.9 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1800 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | OH lines about 10' offset from the bridge. No offset distance specified in site visit info. Water line offset 20'+ from the bridge. |  |  | 28136 | 1733
300 | -- | 357 | 23601 | 31758 | 55401900700000 | 9 |  | Somerset | OVER US 30 |  | US 30 |  | 55 | 75 | 31.5 | 54 | [25 empty] | Rural Local | 55 | 20 | 75 | 31.5 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 3 |  |  | 1800 | 2.73 | 4914 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 20 | 24 | -19.75 | OUT OF ROW |  |  | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | OH lines located near the end of the wings on one side of bridge - approx. 15' from the bridge. Waterline crosses the road 20'+ from the abutment. |  |  | 27454 | 1776
301 | -- | 382 | 83234 | 10996 | 16086100620656 | 10 |  | Clarion | DIAMOND NO.1 |  | WILDCAT RUN |  | 50 | 70 | 37.8 | 62 | [25 empty] | Rural Minor Arterial | 50 | 20 | 70 | 37.8 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | OH telephone and cable lines appear to cross over wings. OH E is set back farther from bridge and will not be impacted. |  |  | 27430 | 1859
302 | -- | 394 | 26069 | 19737 | 33300302500000 | 10 |  | Jefferson | NEAR OHL NO. 1 |  | BEAVER RUN |  | 48 | 68 | 22.0 | 48 | [25 empty] | Rural Minor Collector | 48 | 20 | 68 | 22.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | OH lines cross the bring at an angle. No other utilities identified near the bridge. |  |  | 27429 | 1860
303 | -- | 463 | 99794 | 3755 | 04401900500000 | 11 |  | Beaver | 1/2 MI. WEST OF SR 4021 |  | N.BR.BRADYS RUN |  | 30 | 50 | 20.5 | 50 | [25 empty] | Rural Local | 30 | 20 | 50 | 20.5 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | All site visit pics are rotated. OH lines cross over wings |  |  | 89079 | 1881
304 | -- | 358 | 83197 | 2992 | 03006600600000 | 10 |  | Armstrong | CARNAHAN RUN NO.1 |  | CARNAHAN RUN |  | 51 | 71 | 37.6 | 50 | [25 empty] | Rural Minor Arterial | 51 | 20 | 71 | 37.6 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  | Water line marked with flags - look to impact wing | 71 | 249.45 | 17710.95 | [13 empty] | 71 |  |  |  |  | 1 |  |  | MH with concrete pad located near creek bottom | 71 | 477.3 | 33888.3 | [13 empty] | 71 | [8 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 5400 | 4 |  | West Penn Power | 2400 | 2.73 | 6552 | 3 |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 51599.25 | 7500 | 7 | 22522.5 | 10000 | 3 | No OH offset given in the site visit info. Water line located in site visit photos and looks to be in line with wing. No offset given for WW MH |  |  | 78407 | 1882
305 | -- | 496 | 29823 | 16827 | 26105501401377 | 12 |  | Fayette | DUNBAR TOWNSHIP |  | TUCKER RUN |  | 23 | 43 | 29.5 | 50 | [25 empty] | Rural Major Collector | 23 | 20 | 43 | 29.5 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 11056.5 | 10000 | 2 | OH lines cross over the wings of the bridge. No other utilities identified in the site visit or by PennDOT. |  |  | 74338 | 1950
306 | -- | 362 | 83252 | 3176 | 03200500500000 | 10 |  | Armstrong | BURRELL TWP-E OF BRICK CH |  | TRIB TO CHERRY RUN |  | 44 | 64 | 24.0 | 64 | [25 empty] | Rural Minor Collector | 44 | 20 | 64 | 24.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [17 empty] | 0.5 | 1 |  |  | Runs along road and under bridge - per site visit info | 64 | 120.88 | 7736.32 | [13 empty] | 64 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1800 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | [5 empty] | 1 | 2 | 3 |  | 7736.32 | 7500 | 2 | 12694.5 | 10000 | 2 | OH line on one side of bridge cross wings near rail. Gas line identified during site visit along road and under bridge. |  |  | 78413 | 1974
307 | -- | 363 | 74202 | 3232 | 03204701200000 | 10 |  | Armstrong | ROARING RUN |  | ROARING RUN |  | 34 | 54 | 19.7 | 62 | [25 empty] | Rural Major Collector | 34 | 20 | 54 | 19.7 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  | Water line located with markers and flags during site visit | 54 | 249.45 | 13470.3 | [13 empty] | 54 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 1 | 0 | 1 |  | 13470.3 | 7500 | 2 | 0 | 10000 | 0 | No OH identified. Site visit pics show water line markers and flags. Line appears to cross channel and maybe cross the road. |  |  | 78414 | 1976
308 | -- | 364 | 24023 | 3245 | 03205700100245 | 10 |  | Armstrong | LAUREL POINT |  | CARNAHAN RUN | 20143580317 | 47 | 67 | 23.7 | 56 | [25 empty] | Rural Minor Collector | 47 | 20 | 67 | 23.7 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  | Water line located with markers, FH, and meters 3' offset from bridge | 67 | 249.45 | 16713.15 | [13 empty] | 67 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3000 | 2 |  | West Penn Power | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 16713.15 | 7500 | 3 | 15970.5 | 10000 | 2 | OH lines within 10' of the bridge. Water line markers, flags, and FH identified within 3' of the bridge. |  |  | 78416 | 1980
309 | -- | 365 | 24018 | 3278 | 03300900800000 | 10 |  | Armstrong | CLAYPOOLE ROAD NO.3 |  | TRIB TO BUFFALO CREEK | 20143580322 | 40 | 60 | 28.0 | 64 | [25 empty] | Rural Local | 40 | 20 | 60 | 28.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  | Waterline flagged near roadway - no clear direction of line | 60 | 249.45 | 14967 | [13 empty] | 60 |  |  |  |  | 1 |  |  | MH's and flags identified in site visit - crosses road near abutment | 64 | 477.3 | 30547.2 | [13 empty] | 64 |  |  |  |  | 1 |  | Peoples | Run across the road and across the channel | 60 | 120.88 | 7252.8 | [13 empty] | 60 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3600 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 3 | 2 | 5 |  | 52767 | 7500 | 8 | 17608.5 | 10000 | 2 | Water line flagged along edge of road. WW MH's and flags identified in site visit - crosses near abutment. OH lines on both sides of the roadway. Gas cross road and channel. |  |  | 78417 | 1982
310 | -- | 532 | 31157 | 34980 | 62203600101601 | 12 |  | Washington | WEST PIKE RUN TOWNSHIP |  | PIKE RUN |  | 58 | 78 | 24.0 | 48 | [25 empty] | Rural Major Collector | 58 | 20 | 78 | 24.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 2" Equitable Gas | 1 | Yes | 78 |  | 1 | 2400 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | 2" gas line attached to the wings and the side of the bridge. |  |  | 70804 | 3599
311 | -- | 538 | 30702 | 35178 | 62402700100687 | 12 |  | Washington | CROSS CREEK TOWNSHIP |  | NORTH FORK CROSS CREEK |  | 29 | 49 | 21.5 | 48 | [25 empty] | Rural Minor Collector | 29 | 20 | 49 | 21.5 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1800 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | OH lines offset 10' from the edge of the bridge. No other utilities identified in the site visit. |  |  | 28944 | 3602
312 | -- | 46 | 91510 | 12163 | 18015000701624 | 2 |  | Clinton | 3 MILE EAST BEECH CREEK |  | MASDEN RUN |  | 30 | 50 | 34.0 | 58 | [25 empty] | Rural Minor Arterial | 30 | 20 | 50 | 34.0 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 4 |  | 2400 | 2.73 | 6552 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | 10 | -2 | OUT OF ROW |  | 10 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes | CHECK POLE/LINE RELOCATION QTY'S |  | 93613 | 3647
313 | -- | 56 | 91518 | 20147 | 34200701400000 | 2 |  | Juniata | OAKLAND MILLS |  | LOST CREEK |  | 27 | 47 | 26.3 | 52 | [25 empty] | Rural Minor Collector | 27 | 20 | 47 | 26.3 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3600 | 3 |  |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 17608.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes |  |  | 80062 | 3654
314 | -- | 75 | 85297 | 26469 | 44065502300022 | 2 |  | Mifflin | KISHACOQUILLAS |  | ALEXANDER RUN |  | 10 | 30 | 44.7 | 64 | [25 empty] | Rural Minor Arterial | 10 | 20 | 30 | 44.7 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  | Noted in site visit, parallel to road, offset 30' | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit, poles appear closer than 15' in photos |  |  | 69069 | 3693
315 | -- | 82 | 85309 | 30162 | 52004409500000 | 2 |  | Potter | CLARA |  | CLARA CREEK |  | 36 | 56 | 34.0 | 58 | [25 empty] | Rural Minor Arterial | 36 | 20 | 56 | 34.0 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 3 |  |  | 1800 | 2.73 | 4914 | 3 |  | 1800 | 2.73 | 4914 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit, poles appear closer than 15' in photos |  |  | 67378 | 3695
316 | -- | 100 | 5218 | 6476 | 08401302501496 | 3 |  | Bradford | 0.25 MI N.OF MIDDLETOWN |  | MILLER RUN |  | 25 | 45 | 25.5 | 56 | [25 empty] | Rural Major Collector | 25 | 20 | 45 | 25.5 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4800 | 6 |  |  | 3600 | 2.73 | 9828 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 |  |  |  |  | 15 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 20884.5 | 10000 | 3 | COMPLETE, pole offset in site visit notes/sketches |  |  | 70805 | 3717
317 | -- | 113 | 6052 | 24881 | 41201501720000 | 3 |  | Lycoming | 1 MI NORTH OF LAIRDSVILLE |  | OVER BIG RUN |  | 32 | 52 | 20.0 | 48 | [25 empty] | Rural Local | 32 | 20 | 52 | 20.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 1800 | 1 |  |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 |  |  |  |  | 7 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 12694.5 | 10000 | 2 | COMPLETE, pole offset in site visit notes/sketches |  |  | 70807 | 3722
318 | -- | 380 | 83229 | 10975 | 16032201801102 | 10 |  | Clarion | SHIPPENVILLE STATION |  | DEER CREEK |  | 50 | 70 | 41.6 | 62 | [25 empty] | Rural Principal Arterial | 50 | 20 | 70 | 41.6 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [18 empty] | 1 |  |  | Directly behind guardrail | 70 | 32.1 | 2247 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 1 | 0 | 1 |  | 2247 | 7500 | 1 | 0 | 10000 | 0 | No OH utilities identified in site visit. UG FO line marked just behind the guardrail on both ends of the bridge. |  |  | 89058 | 3723
319 | -- | 149 | 96729 | 32365 | 57070602700000 | 4 |  | Susquehanna | BRIDGWTR TP 2 M W TR 167 |  | PETTIS CREEK | 20143580198 | 32 | 52 | 37.5 | 60 | [25 empty] | Rural Minor Arterial | 32 | 20 | 52 | 37.5 | 36 | 24 | 60 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3600 | 4 |  |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 10 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 17608.5 | 10000 | 2 | COMPLETE, pole offset given in site visit notes |  |  | 99793 | 3747
320 | -- | 157 | 9969 | 35508 | 63029601800000 | 4 |  | Wayne | CANAAN TWP 1 M S SR 3028 |  | BRANCH OF MIDDLE CREEK |  | 22 | 42 | 26.0 | 57 | [25 empty] | Rural Major Collector | 22 | 20 | 42 | 26.0 | 33 | 24 | 57 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | COMPLETE, pole offset not given in site visit, poles appear closer than 15' in photos | BOX CULVERT, WIDENING 12' |  | 29062 | 3749
321 | -- | 211 | 56830 | 7262 | 09203701900000 | 6 |  | Bucks | BILLBOARD 38C08 (3151E10) |  | EAST BR.QUEEN ANNE CREEK | 20143580217 | 21 | 41 | 62.5 | 88 | [25 empty] | Urban Principal Arterial | 21 | 20 | 41 | 62.5 | 64 | 24 | 88 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  | Attached to bridge | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 4" Sewer | 1 | Yes | 41 | 0 | 1 | 6600 | 7 |  |  | 4200 | 2.73 | 11466 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 5 | 1 | 2 | 3 |  | 0 | 7500 | 0 | 25798.5 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes, gas line size estimated from site visit photos | Preliminary Assumptions: Box Culvert Bridge |  | 78310 | 3750
322 | -- | 237 | 87424 | 13616 | 21003400700827 | 8 |  | Cumberland | HUNTER'S RUN |  | HUNTERS RUN |  | 40 | 60 | 28.0 | 64 | [25 empty] | Rural Minor Arterial | 40 | 20 | 60 | 28.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4800 | 4 |  |  | 2400 | 2.73 | 6552 | 3 |  | 1800 | 2.73 | 4914 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [5 empty] | 8 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 20884.5 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes, 8' Left and 12' Right |  |  | 99794 | 3755
323 | -- | 239 | 89274 | 13741 | 21023303801454 | 8 |  | Cumberland | NORTH OF NEWVILLE |  | CONODOQUINET CREEK |  | 223 | 243 | 24.4 | 64 | [25 empty] | Rural Minor Arterial | 223 | 20 | 243 | 24.4 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 2 | 3890.25 | 7780.5 | [5 empty] | 8 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 78313 | 3769
324 | -- | 253 | 19965 | 20976 | 36002300301231 | 8 |  | Lancaster | 1.5 MI.E. of Marietta |  | Chickies Creek | 20143580433/20143580434 | 107 | 127 | 26.8 | 64 | [25 empty] | Rural Minor Arterial | 107 | 20 | 127 | 26.8 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 29374 | 22262
325 | -- | 257 | 87554 | 21238 | 36034003801674 | 8 |  | Lancaster | CAINS |  | MILLER'S RUN |  | 29 | 49 | 32.6 | 60 | [25 empty] | Rural Major Collector | 29 | 20 | 49 | 32.6 | 36 | 24 | 60 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3000 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 15970.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 78362 | 22265
326 | -- | 264 | 74958 | 21415 | 36102402100000 | 8 |  | Lancaster | WEST OF SPRINGVILLE |  | INDIAN RUN |  | 42 | 62 | 22.7 | 52 | [25 empty] | Rural Minor Collector | 42 | 20 | 62 | 22.7 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 5 |  |  | 3000 | 2.73 | 8190 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 29534 | 22269
327 | -- | 389 | 25584 | 19320 | 32300701200000 | 10 |  | Indiana | MARSHALL RUN NO.2 |  | MARSHALL RUN |  | 37 | 57 | 26.0 | 48 | [25 empty] | Rural Local | 37 | 20 | 57 | 26.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 3 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [17 empty] | 3 | 1 |  |  | Gas line appears to cross road near abutment | 48 | 120.88 | 5802.24 | [13 empty] | 48 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3600 | 4 |  |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 5802.24 | 7500 | 1 | 17608.5 | 10000 | 2 | OH utilities cross over wings. Gas line appears to cross road near abutment based on flags and markers. Gas line crosses channel 20'+ from edge of bridge. |  |  | 78318 | 22277
328 | -- | 276 | 87562 | 21536 | 36201200320000 | 8 |  | Lancaster | 1 MI.N. OF UNION |  | TRIB W.BR.OCTORARO |  | 27 | 47 | 25.7 | 52 | [25 empty] | Rural Local | 27 | 20 | 47 | 25.7 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 2400 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos |  |  | 89094 | 22281
329 | -- | 299 | 87551 | 37608 | 66061601001014 | 8 |  | York | 1.0 MI. NW GLEN ROCK |  | CENTERVILLE CREEK |  | 39 | 59 | 26.5 | 56 | [25 empty] | Rural Major Collector | 39 | 20 | 59 | 26.5 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3000 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 30 | 4 | 12.75 | IN ROW |  | 4 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 15970.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes, 4' Left and 4' Right |  |  | 78370 | 22358
330 | -- | 310 | 88114 | 3954 | 05003001000907 | 9 |  | Bedford | 2.8 MI.W. OF SHELLSBURG |  | BURNS CREEK |  | 16 | 36 | 32.4 | 64 | [25 empty] | Rural Principal Arterial | 16 | 20 | 36 | 32.4 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 1e-17 |  |  | 6e-15 | 2.73 | 1.638e-14 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | OH lines cross wings. No other utilities near bridge. |  |  | 69103 | 22359
331 | -- | 314 | 88121 | 4122 | 05086901201328 | 9 |  | Bedford | 3.16 MILE WEST FROM PA 96 |  | BOBS CREEK | 20143561454 | 76 | 96 | 24.1 | 52 | [25 empty] | Rural Major Collector | 76 | 20 | 96 | 24.1 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 30 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | OH lines cross wings. No other utilities identified in site visit or by PennDOT |  |  | 78374 | 22362
332 | -- | 315 | 21596 | 4174 | 05101100400000 | 9 |  | Bedford | 2 MI.N.OF BREEZEWOOD |  | TUB MILL RUN |  | 35 | 55 | 18.2 | 48 | [25 empty] | Rural Local | 35 | 20 | 55 | 18.2 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3600 | 3 |  |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 30 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 17608.5 | 10000 | 2 | OH lines cross over bridge at an angle. No other utilities identified. |  |  | 69231 | 22369
333 | -- | 326 | 22444 | 8580 | 11102601101804 | 9 |  | Cambria | 0.18 MILE WEST FROM PA 53 |  | CLEARFIELD CREEK |  | 71 | 91 | 26.0 | 54 | [25 empty] | Rural Major Collector | 71 | 20 | 91 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3000 | 3 |  |  | 1800 | 2.73 | 4914 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 30 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 15970.5 | 10000 | 2 | OH lines within 5' of bridge. No other utilities identified in site visit or by PennDOT. |  |  | 78378 | 22374
334 | -- | 397 | 27272 | 659 | 02003001202263 | 11 |  | Allegheny | 400 FEET SE OF SR 3070 |  | SOUTH FORK MONTOUR RUN |  | 38 | 58 | 42.0 | 54 | [25 empty] | Urban Minor Arterial | 38 | 20 | 58 | 42.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  | FH located approx. 10' from edge of road/bridge | 58 | 249.45 | 14468.1 | [13 empty] | 58 | [8 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | Peoples Gas |  | 58 | 120.88 | 7011.04 | [13 empty] | 58 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 2 | 0 | 2 |  | 21479.14 | 7500 | 3 | 0 | 10000 | 0 | FH identified 10' from the edge of road/bridge during the site visit. No OH utilities identified in the area. |  |  | 99796 | 22378
335 | -- | 398 | 28154 | 664 | 02003001901870 | 11 |  | Allegheny | @ INTER W/ BRADDOCK ROAD |  | FALLS RUN |  | 22 | 42 | 75.0 | 90 | [25 empty] | Urban Principal Arterial | 22 | 20 | 42 | 75.0 | 66 | 24 | 90 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1 | 1 |  | Wilkensburg Penn Joint Water |  | 42 | 249.45 | 10476.9 | [13 empty] | 42 |  |  |  |  | 1 |  |  |  | 42 | 477.3 | 20046.6 | [13 empty] | 42 |  |  |  | 1 | 1 |  | Peoples Gas | Multiple lines in the area | 42 | 120.88 | 5076.96 | [13 empty] | 42 | [8 empty] | 0 | 191.55 | 0 | [18 empty] | 1 |  |  |  | 42 | 32.1 | 1348.2 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 9600 | 6 |  |  | 4800 | 2.73 | 13104 | 2 |  | 1600 | 2.73 | 4368 | 2 |  | 1600 | 2.73 | 4368 | 2 |  | 1600 | 2.73 | 4368 | 3 | 3890.25 | 11670.75 | [6 empty] | 4 | 3 | 7 |  | 36948.66 | 7500 | 5 | 37878.75 | 10000 | 4 | Constructability needs to be looked at in regards to utilities. Many OH facilities at a major intersection with a diagonal drainage structure. |  |  | 29321 | 22379
336 | -- | 399 | 73522 | 709 | 02005100802710 | 11 |  | Allegheny | @ INTER.W/WEIGEL HILL RD. |  | FALLEN TIMBER RUN |  | 33 | 53 | 73.0 | 100 | [25 empty] | Urban Principal Arterial | 33 | 20 | 53 | 73.0 | 76 | 24 | 100 |  | 1e-17 | 1e-28 | 1e-30 | 4 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | Peoples Gas |  | 53 | 120.88 | 6406.64 | [13 empty] | 53 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 2" Conduit | 1 | Yes | 53 |  | 1 | 1200 | 1 |  | West Penn Power | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 2 | 1 | 3 |  | 6406.64 | 7500 | 1 | 7166.25 | 10000 | 1 | New development on the upstream side of the road. May impact utility relocations. |  |  | 29387 | 22396
337 | -- | 402 | 37590 | 954 | 02013600500000 | 11 |  | Allegheny | 2 MI EAST OF MON CITY BR |  | MON RIVER TRIBUTARY | 20143580439 | 11 | 31 | 40.0 | 54 | [25 empty] | Urban Minor Arterial | 11 | 20 | 31 | 40.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 1 | 4" | Equitable Gas | Sitting on outfall wings | 31 | 120.88 | 3747.28 | [13 empty] | 31 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2800 | 3 |  | West Penn Power | 1200 | 2.73 | 3276 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 3747.28 | 7500 | 1 | 11534.25 | 10000 | 2 | Gas line attached/sitting on top of wings along rail. Drainage structure continues under a home/building on upstream side. Multiple OH lines crossing bridge. |  |  | 99798 | 22416
338 | -- | 403 | 28597 | 961 | 02013601202172 | 11 |  | Allegheny | 100'W.OF INTER W/SR 2017 |  | BRANCH OF GILLESPIE RUN | 20143580328 | 14 | 34 | 26.0 | 54 | [25 empty] | Rural Minor Arterial | 14 | 20 | 34 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0.75 | 1 |  |  | Near wing, no crossing | 54 | 249.45 | 13470.3 | [13 empty] | 54 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 5600 | 2 |  |  | 1600 | 2.73 | 4368 | 3 |  | 2400 | 2.73 | 6552 | 2 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 1 | 3 | 4 |  | 13470.3 | 7500 | 2 | 26958.75 | 10000 | 3 | Flags indicate the water line doesn't cross the channel, but turns near wings and abutment. OH lines on both sides of the bridge. |  |  | 29525 | 22433
339 | -- | 404 | 63321 | 1334 | 02091002400485 | 11 |  | Allegheny | 1 MILE EAST OF RT 8 INT |  | WEST BRANCH OF DEER CREEK |  | 35 | 55 | 26.8 | 54 | [25 empty] | Urban Minor Arterial | 35 | 20 | 55 | 26.8 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [13 empty] | 0 | [8 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | Peoples Gas |  | 55 | 120.88 | 6648.4 | [13 empty] | 55 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  | 1 |  |  | Richland Twp. Municipal Auth. |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 13000 | 6 |  | West Penn Power | 6000 | 2.73 | 16380 | 4 |  | 4000 | 2.73 | 10920 | 2 |  | 2000 | 2.73 | 5460 | 1 |  | 1000 | 2.73 | 2730 | 4 | 3890.25 | 15561 | [6 empty] | 1 | 4 | 5 |  | 6648.4 | 7500 | 1 | 51051 | 10000 | 6 | OH lines on both sides of the bridge. No other utilities identified in the site visit. |  |  | 99797 | 22439
340 | -- | 406 | 78185 | 1346 | 02097800300000 | 11 |  | Allegheny | 2000'N. OF SR 3001 |  | FISHING RUN | 20143580332 | 18 | 38 | 31.5 | 52 | [25 empty] | Urban Minor Arterial | 18 | 20 | 38 | 31.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  | Pennsylvania American Water |  | 38 | 249.45 | 9479.1 | [13 empty] | 38 | [8 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | Columbia Gas |  | 38 | 120.88 | 4593.44 | [13 empty] | 38 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  | 1 |  |  | South Fayette Twp. Municipal Auth. |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 6000 | 5 |  | West Penn Power | 3000 | 2.73 | 8190 | 2 |  | 1200 | 2.73 | 3276 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 14072.54 | 7500 | 2 | 24160.5 | 10000 | 3 | OH lines on both sides of the bridge. Water line markers and meters identified within 5' of the bridge. Gas line marker in channel near bridge. |  |  | 29549 | 22441
341 | -- | 337 | 22980 | 18603 | 31002605100972 | 9 |  | Huntingdon | 0.2 MILE NORTH OF SR 1009 |  | HORN RUN |  | 30 | 50 | 33.8 | 56 | [25 empty] | Rural Minor Arterial | 30 | 20 | 50 | 33.8 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 30 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | OH lines 5' offset from bridge on one side. No other utilities identified in the site visit or by PennDOT. |  |  | 80677 | 22455
342 | -- | 408 | 27188 | 1372 | 02100103502537 | 11 |  | Allegheny | @ J.F.K.ELEM.SCHOOL |  | CRAWFORD RUN |  | 18 | 38 | 48.0 | 60 | [25 empty] | Urban Minor Arterial | 18 | 20 | 38 | 48.0 | 36 | 24 | 60 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 | 12 |  | Back of sidewalk near wings | 38 | 249.45 | 9479.1 | [7 empty] | 38 | [14 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 12" Unknown | 1 | Yes | 38 |  | 1 | 16000 | 6 |  | West Penn Power | 6000 | 2.73 | 16380 | 6 |  | 6000 | 2.73 | 16380 | 4 |  | 4000 | 2.73 | 10920 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | [6 empty] | 2 | 4 | 6 |  | 9479.1 | 7500 | 2 | 59241 | 10000 | 6 | 10" pipe identified in site visit - attached to bridge, painted green, assume WW? Urban area with OH lines on both sides of the road. |  |  | 51503 | 16651
343 | -- | 410 | 78220 | 1390 | 02100600402405 | 11 |  | Allegheny | @ INTERSECT WITH SR 1013 |  | BR LITTLE PINE CREEK |  | 14 | 34 | 45.0 | 54 | [25 empty] | Urban Minor Arterial | 14 | 20 | 34 | 45.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [13 empty] | 0 | [8 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | Peoples Gas |  | 34 | 120.88 | 4109.92 | [13 empty] | 34 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 10800 | 6 |  |  | 3600 | 2.73 | 9828 | 6 |  | 3600 | 2.73 | 9828 | 6 |  | 3600 | 2.73 | 9828 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 4109.92 | 7500 | 1 | 37264.5 | 10000 | 4 | Major signalized intersection with numerous OH lines. Constructability needs to be reviewed for utility relocations. |  |  | 51484 | 16673
344 | -- | 413 | 28603 | 1404 | 02101200602013 | 11 |  | Allegheny | 70'E.INTER.W/TWP.RD.613 |  | SHAFERS RUN |  | 13 | 33 | 21.0 | 48 | [25 empty] | Urban Minor Collector | 13 | 20 | 33 | 21.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [13 empty] | 0 | [8 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | Peoples Gas |  | 33 | 120.88 | 3989.04 | [13 empty] | 33 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4800 | 3 |  | Duquesne Light Co. | 1800 | 2.73 | 4914 | 3 |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 3989.04 | 7500 | 1 | 20884.5 | 10000 | 3 | OH lines on one side of bridge. Unknown steel pipe with cap sticking out of the ground near wing. |  |  | 74174 | 16713
345 | -- | 417 | 99687 | 1424 | 02101500702617 | 11 |  | Allegheny | NORTH/RURAL RIDGE |  | BR.LITTLE DEER CREEK |  | 15 | 35 | 22.5 | 52 | [25 empty] | Urban Minor Arterial | 15 | 20 | 35 | 22.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 6 | [5 empty] | 0 | 249.45 | 0 | [13 empty] | 0 | [8 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | Peoples Twp. / TW Phillips |  | 35 | 120.88 | 4230.8 | [13 empty] | 35 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  | 1 |  |  | Oakmont Borough Municipal Auth. |  | 0 | 56.12 | 0 | [17 empty] | 2" Conduit, 4" Gas, 8" Sewer | 1 | Yes | 105 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 2 | 0 | 2 |  | 4230.8 | 7500 | 1 | 0 | 10000 | 0 | No site visit info as of 5-27-2014 |  |  | 74176 | 16720
346 | -- | 421 | 28607 | 1479 | 02200100800335 | 11 |  | Allegheny | AT BAPTIST CHURCH |  | TRIBUT. TO MONOGAHELA R. | 20143580442 | 19 | 39 | 26.7 | 52 | [25 empty] | Urban Minor Collector | 19 | 20 | 39 | 26.7 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 6 |  | 1 |  |  | Water line located on both sides of bridge with road crossing | 91 | 249.45 | 22699.95 | [13 empty] | 91 | [8 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 39 | 120.88 | 4714.32 | [13 empty] | 39 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  | 1 |  |  | Westmoreland Co. Municipal Auth. |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4800 | 3 |  | West Penn Power | 1800 | 2.73 | 4914 | 3 |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 27414.27 | 7500 | 4 | 20884.5 | 10000 | 3 | Water line markers/flags identified on both sides of bridge and across roadway. OH line on one side of the road. Gas line crosses channel near the bridge on one side. |  |  | 81961 | 16725
347 | -- | 339 | 23038 | 18742 | 31091301901896 | 9 |  | Huntingdon | 0.4 MILE EAST FROM SR 3019, ROBERTSDALE |  | GREAT TROUGH CREEK | 20143580425 | 33 | 53 | 29.4 | 56 | [25 empty] | Rural Minor Arterial | 33 | 20 | 53 | 29.4 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 7200 | 7 |  |  | 4200 | 2.73 | 11466 | 3 |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 27436.5 | 10000 | 3 | OH lines cross the bring at an angle and cross road to Post Office. No other utilities identified near the bridge. |  |  | 29781 | 16736
348 | -- | 424 | 73045 | 1498 | 02201000102238 | 11 |  | Allegheny | 500'N.E.OF ROSS STREET |  | BRANCH OF WYLIE RUN | 20143580340 | 18 | 38 | 29.6 | 52 | [25 empty] | Urban Minor Arterial | 18 | 20 | 38 | 29.6 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 4 |  | 2 | 6" & 16" |  | Longitudinal under paving | 76 | 249.45 | 18958.2 |  |  |  |  | 38 |  |  |  |  | 38 | [8 empty] | 1 |  |  | Not seen in site visit pictures - assume relocation | 38 | 477.3 | 18137.4 | [13 empty] | 38 |  |  |  | 2 |  |  | Columbia Gas, Peoples Gas |  | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4800 | 2 |  | Allegheny Power | 1200 | 2.73 | 3276 | 3 |  | 1800 | 2.73 | 4914 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 3 | 2 | 5 |  | 37095.6 | 7500 | 5 | 20884.5 | 10000 | 3 | Site visit info shows 6" & 16" water lines under the pavement, site visit pics don't show WW line - assume relocation at 8' from bridge |  |  | 69229 | 16752
349 | -- | 425 | 27451 | 1519 | 02201701301248 | 11 |  | Allegheny | @ SR 2014 |  | BOYDS HOLLOW RUN |  | 21 | 41 | 33.0 | 52 | [25 empty] | Urban Minor Collector | 21 | 20 | 41 | 33.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | Peoples Gas | 8" to 12" Daylighted across channel | 41 | 120.88 | 4956.08 | [13 empty] | 41 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 8000 | 3 |  | West Penn Power | 2400 | 2.73 | 6552 | 4 |  | 3200 | 2.73 | 8736 | 3 |  | 2400 | 2.73 | 6552 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 1 | 3 | 4 |  | 4956.08 | 7500 | 1 | 33510.75 | 10000 | 4 | Site visit pics show 8" to 12" gas line daylighted across channel |  |  | 74345 | 16757
350 | -- | 426 | 99665 | 1520 | 02201701400112 | 11 |  | Allegheny | AT ROCK RUN RD |  | WILDCAT RUN |  | 30 | 50 | 38.0 | 52 | [25 empty] | Urban Minor Collector | 30 | 20 | 50 | 38.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 4 | [5 empty] | 0 | 249.45 | 0 | [18 empty] | 1 |  |  |  | 52 | 477.3 | 24819.6 | [13 empty] | 52 |  |  |  | 1 | 1 |  | Peoples Gas | 10' LT of bridge | 50 | 120.88 | 6044 | [13 empty] | 50 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 12" Water | 1 | Yes | 50 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 3 | 0 | 3 |  | 30863.6 | 7500 | 5 | 0 | 10000 | 0 | Site visit shows 12"+ water line attached to the bottom of bridge |  |  | 76009 | 16758
351 | -- | 427 | 78224 | 1523 | 02201800400721 | 11 |  | Allegheny | 2082 FEET SW OF SR 48 |  | CREEK |  | 21 | 41 | 28.0 | 52 | [25 empty] | Urban Minor Collector | 21 | 20 | 41 | 28.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 4 |  | 1 |  |  | Water and sewer on same side of road | 41 | 249.45 | 10227.45 | [13 empty] | 41 |  |  |  |  | 1 |  |  | WW & water on same side of road | 41 | 477.3 | 19569.3 | [13 empty] | 41 |  |  |  | 1 |  |  | Peoples Gas | Attached to structure | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 4" Gas | 1 | Yes | 41 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 3 | 0 | 3 |  | 29796.75 | 7500 | 4 | 0 | 10000 | 0 | Water, WW, and Gas all on the same side of the road, OH does not appear to be in conflict, Gas looks to be 4" |  |  | 76012 | 16782
352 | -- | 428 | 99670 | 1527 | 02202200102622 | 11 |  | Allegheny | 2644'N.E.OF LR02310 |  | BR. LONG RUN |  | 21 | 41 | 28.0 | 52 | [25 empty] | Urban Minor Collector | 21 | 20 | 41 | 28.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 4 |  | 1 |  |  |  | 41 | 249.45 | 10227.45 | [13 empty] | 41 | [8 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 1 | 4" - 6" | Peoples Gas | Thru wings on LT side | 41 | 120.88 | 4956.08 |  |  |  |  | 41 | [17 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  | 1 |  |  | Westmoreland Co. Municipal Auth. |  | 0 | 56.12 | 0 | [17 empty] | 12" Gas | 1 | Yes | 41 |  | 1 | 1600 | 3 |  |  | 1200 | 2.73 | 3276 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 3 | 1 | 4 |  | 15183.53 | 7500 | 3 | 8258.25 | 10000 | 1 | Site visit pics show 4" to 6" gas line elevated over channel thru wings (next to bridge rail) |  |  | 29820 | 16789
353 | -- | 430 | 78271 | 1562 | 02204600401678 | 11 |  | Allegheny | AT INTER./ SR 3046 |  | STREETS RUN |  | 22 | 42 | 39.0 | 56 | [25 empty] | Urban Minor Arterial | 22 | 20 | 42 | 39.0 | 32 | 24 | 56 |  | 1 | 20 | 200 | 4 | 1 | 1 |  | Pennsylvania American Water | Water line not identified in site visit or PennDOT pics | 42 | 249.45 | 10476.9 | [13 empty] | 42 | [8 empty] | 0 | 477.3 | 0 | [17 empty] | 1 |  |  | Columbia Gas |  | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 6400 | 2 |  |  | 1600 | 2.73 | 4368 | 3 |  | 2400 | 2.73 | 6552 | 3 |  | 2400 | 2.73 | 6552 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 1 | 3 | 4 |  | 10476.9 | 7500 | 2 | 29142.75 | 10000 | 3 | Limited pics from the site visit and PennDOT |  |  | 90965 | 16794
354 | -- | 432 | 74324 | 1568 | 02204600801088 | 11 |  | Allegheny | AT LUTZ HOLLOW ROAD |  | STREETS RUN |  | 19 | 39 | 40.0 | 54 | [25 empty] | Urban Minor Arterial | 19 | 20 | 39 | 40.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1 | 1 |  | Pennsylvania American Water | Water line not identified in site visit or PennDOT pics | 39 | 249.45 | 9728.55 | [13 empty] | 39 | [8 empty] | 0 | 477.3 | 0 | [18 empty] | 1 | 8" - 12" | Equitable Gas | On top of wings | 39 | 120.88 | 4714.32 | [7 empty] | 39 | [14 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 12" Gas | 1 | Yes | 39 |  | 1 | 2000 | 3 |  |  | 1200 | 2.73 | 3276 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 3 | 1 | 4 |  | 14442.87 | 7500 | 2 | 9350.25 | 10000 | 1 | Site visit pics show 8" to 12" gas line sitting on wings across water, no pics of water line identified by PennDOT |  |  | 89075 | 16806
355 | -- | 434 | 89124 | 1620 | 02207500900000 | 11 |  | Allegheny | OVER BR. LITTLE PLUM CR. |  | BR. LITTLE PLUM CREEK |  | 11 | 31 | 34.6 | 54 | [25 empty] | Urban Minor Arterial | 11 | 20 | 31 | 34.6 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  | Waterline runs parallel to road | 31 | 249.45 | 7732.95 | [13 empty] | 31 |  |  |  |  | 1 |  |  | MH identified in the roadway | 31 | 477.3 | 14796.3 | [13 empty] | 31 |  |  |  | 1 | 1 | 3" - 6" | Peoples Gas | Thru wings | 31 | 120.88 | 3747.28 |  |  |  |  | 31 | [17 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 8" Gas | 1 | Yes | 31 |  | 1 | 5400 | 3 |  |  | 1800 | 2.73 | 4914 | 3 |  | 1800 | 2.73 | 4914 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 4 | 2 | 6 |  | 26276.53 | 7500 | 4 | 22522.5 | 10000 | 3 | 3" to 6" gas line thru wings elevated over the water, no paint identifying direction of WW in roadway |  |  | 29823 | 16827
356 | -- | 343 | 23116 | 18881 | 31400900200000 | 9 |  | Huntingdon | 0.24 MILE NORTH FROM PA 305 |  | SHAVERS CREEK |  | 107 | 127 | 25.0 | 48 | [25 empty] | Rural Minor Collector | 107 | 20 | 127 | 25.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4200 | 3 |  |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | OH lines cross the bridge twice. |  |  | 29926 | 16840
357 | -- | 437 | 27436 | 1704 | 02300800420000 | 11 |  | Allegheny | 200'W.OF INTER.W/SR 3004 |  | MCLAUGHLIN RUN |  | 31 | 51 | 27.8 | 52 | [25 empty] | Urban Local | 31 | 20 | 51 | 27.8 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  | Pennsylvania American Water | Water line not identified in site visit or PennDOT pics | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [17 empty] | 2 | 2 |  | Columbia Gas, Peoples Gas | Gas line not identified in site visit or PennDOT pics | 102 | 120.88 | 12329.76 | [13 empty] | 102 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 3 | 1 | 4 |  | 12329.76 | 7500 | 2 | 7166.25 | 10000 | 1 | Water line and gas lines not identified in the site visit or PennDOT pics |  |  | 29893 | 16841
358 | -- | 439 | 27386 | 1727 | 02301800260000 | 11 |  | Allegheny | 820' S.W. OF SR 3021 |  | LOBBS RUN |  | 25 | 45 | 26.0 | 48 | [25 empty] | Urban Local | 25 | 20 | 45 | 26.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  | FH & markers along roadway | 45 | 249.45 | 11225.25 | [13 empty] | 45 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3000 | 2 |  | West Penn Power | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | [5 empty] | 1 | 2 | 3 |  | 11225.25 | 7500 | 2 | 15970.5 | 10000 | 2 | Site visit pics and info identify water line with FH and markers on edge of road |  |  | 74184 | 16868
359 | -- | 440 | 28136 | 1733 | 02302100300941 | 11 |  | Allegheny | 100' SOUTHEAST OF SR 3018 |  | LOBBS RUN |  | 27 | 47 | 26.0 | 50 | [25 empty] | Urban Local | 27 | 20 | 47 | 26.0 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  | FH along roadway | 47 | 249.45 | 11724.15 | [13 empty] | 47 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3000 | 3 |  | West Penn Power | 1800 | 2.73 | 4914 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 11724.15 | 7500 | 2 | 15970.5 | 10000 | 2 | Site visit identified gas line 20' from bridge deck and 11' form wing, WW MH 30' from bridge |  |  | 74189 | 16910
360 | -- | 441 | 27454 | 1776 | 02304801200000 | 11 |  | Allegheny | 1 MI.W.OF SR3041 |  | BR.ROBINSON RUN |  | 16 | 36 | 26.6 | 50 | [25 empty] | Urban Minor Arterial | 16 | 20 | 36 | 26.6 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  | Pennsylvania American Water | Direction of water line not identified in site visit or PennDOT pics | 36 | 249.45 | 8980.2 | [13 empty] | 36 |  |  |  |  | 1 |  | Collier Township | Direction of WW line not identified in site visit or PennDOT pics | 36 | 477.3 | 17182.8 | [13 empty] | 36 |  |  |  | 1 |  |  | Columbia Gas | Attached to structure | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 |  |  |  |  | 1 |  |  | Service to house | 36 | 25.68 | 924.48 |  |  |  | 1 |  |  | Collier Twp. Municipal Auth. |  | 0 | 56.12 | 0 | [17 empty] | 2" Gas | 1 | Yes | 36 |  | 1 | 1800 | 1 |  |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 4 | 2 | 6 |  | 27087.48 | 7500 | 4 | 12694.5 | 10000 | 2 | 2" gas line attached under bridge laterally, water and WW lined directions not clear in site visit or PennDOT pics |  |  | 81636 | 16920
361 | -- | 442 | 27430 | 1859 | 02309800500762 | 11 |  | Allegheny | 1 1/2 MI FROM GLNWOOD INT |  | GLASS RUN |  | 25 | 45 | 29.0 | 54 | [25 empty] | Urban Minor Arterial | 25 | 20 | 45 | 29.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1 | 1 |  | Pennsylvania American Water | Limited information in site visit and PennDOT info - FH on edge of roadway | 45 | 249.45 | 11225.25 | [13 empty] | 45 |  |  |  |  | 1 |  |  | Limited information in site visit and PennDOT info - MH in creek | 45 | 477.3 | 21478.5 | [13 empty] | 45 | [8 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 3 |  |  | 1800 | 2.73 | 4914 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 32703.75 | 7500 | 5 | 14332.5 | 10000 | 2 | Limited utility information in site visits and PennDOT info |  |  | 79325 | 16922
362 | -- | 443 | 27429 | 1860 | 02309800601125 | 11 |  | Allegheny | NEAR SR 3100 |  | GLASS RUN CREEK |  | 27 | 47 | 27.5 | 54 | [25 empty] | Urban Minor Arterial | 27 | 20 | 47 | 27.5 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 1 |  | Pennsylvania American Water | Waterline not identified in pics | 47 | 249.45 | 11724.15 | [13 empty] | 47 | [8 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  | Gas line not identified in pics, but noted in site visit info | 47 | 120.88 | 5681.36 | [13 empty] | 47 |  |  |  | 1 |  |  | Sunoco Pipeline LP |  | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 3 |  |  | 1800 | 2.73 | 4914 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 17405.51 | 7500 | 3 | 14332.5 | 10000 | 2 | Limited utility information in site visits and PennDOT info, gas line noted in site visit info |  |  | 79326 | 16923
363 | -- | 345 | 92698 | 41517 | 55003003702626 | 9 |  | Somerset | 1.74 MILE WEST FROM PA 160 |  | CALENDAR RUN |  | 11 | 31 | 26.0 | 64 | [25 empty] | Rural Principal Arterial | 11 | 20 | 31 | 26.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3600 | 4 |  |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 25 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 17608.5 | 10000 | 2 | OH lines within 3' of edge of structure. No other utilities identified. |  |  | 79328 | 16928
364 | -- | 445 | 78407 | 1882 | 02310800301395 | 11 |  | Allegheny | 100' N.E. OF SR 3053 |  | BR. NORTH BR.ROBINSON RN |  | 18 | 38 | 26.0 | 54 | [25 empty] | Rural Major Collector | 18 | 20 | 38 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  |  |  |  | Waterline outside bridge construction area | 0 | 249.45 | 0 | [21 empty] | WW line crosses roadway 20'+ from the abutment | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | Peoples Gas | Gas line within 9' of bridge deck | 38 | 120.88 | 4593.44 | [13 empty] | 38 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 6000 | 6 |  | Allegheny Power | 3600 | 2.73 | 9828 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 4593.44 | 7500 | 1 | 24160.5 | 10000 | 3 | Water and WW will not be affected as depicted in site visit info |  |  | 74190 | 16930
365 | -- | 347 | 23586 | 31469 | 55052300301840 | 9 |  | Somerset | LISTONBURG |  | WHITES CREEK | 20143580432 | 42 | 62 | 34.0 | 52 | [25 empty] | Rural Minor Arterial | 42 | 20 | 62 | 34.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 7800 | 5 |  |  | 3000 | 2.73 | 8190 | 5 |  | 3000 | 2.73 | 8190 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 30 | 10 | 3 | IN ROW |  |  | 0 | 2 | 2 |  | 0 | 7500 | 0 | 29074.5 | 10000 | 3 | OH lines located over edge of bridge and wings. OH crossing past abutment as well. No other utilities identified in site visit info. |  |  | 79337 | 17052
366 | -- | 350 | 23516 | 31521 | 55100400101850 | 9 |  | Somerset | SHANKSVILLE BORO. |  | RHOADS CREEK |  | 63 | 83 | 40.0 | 56 | [25 empty] | Rural Major Collector | 63 | 20 | 83 | 40.0 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 29 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | OH lines cross over the wing walls. WW MH's located in site visit 20'+ from the bridge - no relocation anticipated. |  |  | 79340 | 18013
367 | -- | 353 | 74467 | 31588 | 55200500300000 | 9 |  | Somerset | 1.95 MILE SO.FROM SR 2004 @ SUMMIT MILLS |  | ELK LICK CREEK |  | 27 | 47 | 24.1 | 48 | [25 empty] | Rural Local | 27 | 20 | 47 | 24.1 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4200 | 5 |  |  | 3000 | 2.73 | 8190 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 16.5 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | OH lines cross over the end of wings. No other utilities identified in the site visit or by PennDOT. |  |  | 79342 | 18044
368 | -- | 355 | 23549 | 31630 | 55201800600000 | 9 |  | Somerset | BEECHDALE |  | BUFFALO CREEK | 20143580311 | 61 | 81 | 24.2 | 48 | [25 empty] | Rural Local | 61 | 20 | 81 | 24.2 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3600 | 4 |  |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | 18.25, 25.00 | [5 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 17608.5 | 10000 | 2 | OH lines within 5' of the edge of bridge. No other utilities identified in the site visit. |  |  | 30291 | 18154
369 | -- | 451 | 70804 | 3599 | 04016803300983 | 11 |  | Beaver | 100'N.OF SR 4034 |  | UPPER DRY RUN |  | 28 | 48 | 43.0 | 58 | [25 empty] | Rural Major Collector | 28 | 20 | 48 | 43.0 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 0 |  | 1 |  |  | Waterline marked with paint along edge of road | 48 | 249.45 | 11973.6 | [13 empty] | 48 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 6000 | 3 |  |  | 3000 | 2.73 | 8190 | 2 |  | 2000 | 2.73 | 5460 | 1 |  | 1000 | 2.73 | 2730 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | [6 empty] | 1 | 4 | 5 |  | 11973.6 | 7500 | 2 | 31941 | 10000 | 4 | All site visit pics are rotated. Water line runs along roadway |  |  | 76037 | 18164
370 | -- | 375 | 24703 | 8071 | 10301000600000 | 10 |  | Butler | BROWNSDALE ROAD |  | GLADE RUN | 20143571422 | 84 | 104 | 24.0 | 48 | [25 empty] | Rural Minor Collector | 84 | 20 | 104 | 24.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4200 | 2 |  |  | 1200 | 2.73 | 3276 | 3 |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | OH lines 8' offset from the bridge. One pole is located directly behind a wing. |  |  | 89031 | 18214
371 | -- | 453 | 93613 | 3647 | 04100500202450 | 11 |  | Beaver | 1/4 MI. NORTH OF SR 1012 |  | BR. CONNOQUENESSING CR. |  | 10 | 30 | 27.5 | 56 | [25 empty] | Urban Minor Collector | 10 | 20 | 30 | 27.5 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | Waterline markers and paint along roadway | 30 | 249.45 | 7483.5 | [13 empty] | 30 | [8 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  | Gas line markers and paint along roadway | 30 | 120.88 | 3626.4 | [13 empty] | 30 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3600 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 11109.9 | 7500 | 2 | 17608.5 | 10000 | 2 | Water and gas line are marked along the roadway |  |  | 74203 | 18222
372 | -- | 454 | 80062 | 3654 | 04101400700193 | 11 |  | Beaver | 100'NORTHEAST OF PIKE |  | BRUSH CREEK |  | 171 | 191 | 40.0 | 54 | [25 empty] | Rural Local | 171 | 20 | 191 | 40.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | Offset from bridge and wing not given - no pics | 191 | 249.45 | 47644.95 | [13 empty] | 191 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 47644.95 | 7500 | 7 | 14332.5 | 10000 | 2 | OH crosses bridge at a skew. Water line offsets not given in the site visit info |  |  | 30335 | 18261
373 | -- | 381 | 83232 | 10997 | 16086100421587 | 10 |  | Clarion | WILDCAT NO.2 |  | WILDCAT RUN |  | 27 | 47 | 41.8 | 62 | [25 empty] | Rural Minor Arterial | 27 | 20 | 47 | 41.8 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [18 empty] | 0 |  |  | Abandoned gas line identified in site visit info | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3600 | 4 |  |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 17608.5 | 10000 | 2 | OH lines cross over wings on one side of bridge. Abandoned Gas line identified in site visit info - no pics |  |  | 79353 | 18279
374 | -- | 456 | 67378 | 3695 | 04300900600000 | 11 |  | Beaver | 0.5 MI.SOUTH OF SR 3007 |  | TRAMP MILL RUN |  | 26 | 46 | 29.5 | 56 | [25 empty] | Urban Minor Collector | 26 | 20 | 46 | 29.5 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 1 | 6"-8" | Columbia Gas | Gas line is elevated across channel and turns toward wing - partially covered | 46 | 120.88 | 5560.48 | [5 empty] | 46 | [16 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3600 | 4 |  |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 5560.48 | 7500 | 1 | 17608.5 | 10000 | 2 | OH lines cross wings and are near guardrail. Gas line is elevated across the channel and turns toward wing where it is partially covered |  |  | 30289 | 18287
375 | -- | 386 | 83293 | 19087 | 32028601500520 | 10 |  | Indiana | CLARKSBURG NO.3 |  | BLACKLEGS CREEK |  | 69 | 89 | 43.0 | 64 | [25 empty] | Rural Minor Arterial | 69 | 20 | 89 | 43.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3600 | 4 |  |  | 2400 | 2.73 | 6552 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 17608.5 | 10000 | 2 | OH lines within 10' of the edge of bridge. Water line identified in the site visit - not impacted by bridge construction. |  |  | 79356 | 18315
376 | -- | 392 | 83312 | 19699 | 33200300700000 | 10 |  | Jefferson | FOXBURG |  | MAHONING CREEK |  | 127 | 147 | 33.2 | 56 | [25 empty] | Rural Minor Collector | 127 | 20 | 147 | 33.2 | 32 | 24 | 56 |  | 1 | 20 | 200 | 4 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 6" Unknown | 1 | Yes | 147 |  | 1 | 3000 | 2 |  |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 0 | 7500 | 0 | 15970.5 | 10000 | 2 | OH within 10' of the bridge. Unknown 3" conduit attached to underside of bridge. 1" conduit attached to rail and into USGS box. |  |  | 79357 | 18317
377 | -- | 393 | 26151 | 19708 | 33200802100200 | 10 |  | Jefferson | STUMP CREEK NO.2 |  | STUMP CREEK (CROSSING @ LOW) |  | 74 | 94 | 29.5 | 54 | [25 empty] | Rural Major Collector | 74 | 20 | 94 | 29.5 | 30 | 24 | 54 |  | 1 | 20 | 200 | 0 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 6000 | 6 |  |  | 3600 | 2.73 | 9828 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 24160.5 | 10000 | 3 | OH lines within 10' of the bridge. No other utilities identified near the bridge. |  |  | 88079 | 18351
378 | -- | 459 | 89058 | 3723 | 04302700460000 | 11 |  | Beaver | GREENE TWP.-MILL CREEK |  | MILL CREEK |  | 39 | 59 | 32.0 | 54 | [25 empty] | Rural Minor Collector | 39 | 20 | 59 | 32.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4800 | 6 |  |  | 3600 | 2.73 | 9828 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 20884.5 | 10000 | 3 | All site visit pics are rotated. OH lines cross over guardrail and wings |  |  | 30231 | 18403
379 | -- | 461 | 29062 | 3749 | 04401201100256 | 11 |  | Beaver | .2 MI. N.E. OF SR 4018 |  | SOUTH BRANCH BRADY'S RUN |  | 64 | 84 | 36.7 | 54 | [25 empty] | Urban Minor Collector | 64 | 20 | 84 | 36.7 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3000 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 15970.5 | 10000 | 2 | All site visit pics are rotated. OH lines cross over guardrail and wings |  |  | 30975 | 34335
380 | -- | 469 | 89094 | 22281 | 37022401100412 | 11 |  | Lawrence | @ INTER. WITH SR 4006 |  | BRANCH OF MAHONING RIVER |  | 11 | 31 | 42.0 | 62 | [25 empty] | Rural Principal Arterial | 11 | 20 | 31 | 42.0 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 5400 | 4 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 22522.5 | 10000 | 3 | OH lines cross over the middle of the culvert and the middle of the road - construction clearance height will determine conflict |  |  | 30639 | 34417
381 | -- | 471 | 69103 | 22359 | 37095601501187 | 11 |  | Lawrence | 1/2 MI. S.E. OF SR 1005 |  | LITTLE NESHANNOCK CREEK |  | 92 | 112 | 26.0 | 52 | [25 empty] | Rural Minor Collector | 92 | 20 | 112 | 26.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | OH lines over wings near rail. No other utilities identified. |  |  | 30997 | 34609
382 | -- | 464 | 78313 | 3769 | 04403400200000 | 11 |  | Beaver | 500' WEST OF SR 0068 |  | UPPER DRY RUN |  | 22 | 42 | 14.0 | 46 | [25 empty] | Rural Local | 22 | 20 | 42 | 14.0 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  | 1 | 1 |  | Industry Borough Municipal Auth. | Not identified in site visit | 42 | 56.12 | 2357.04 | [13 empty] | 42 |  |  |  | None | 0 | None | 0 |  | 1 | 1600 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 2357.04 | 7500 | 1 | 8258.25 | 10000 | 1 | All site visit pics are rotated. OH lines slightly skewed with road so only 1 pole needs to be relocated. |  |  | 73058 | 34623
383 | -- | 465 | 29374 | 22262 | 37020800700000 | 11 |  | Lawrence | 1.5 MI. FROM ST.LINE |  | OVER DEER CREEK |  | 32 | 52 | 37.5 | 52 | [25 empty] | Rural Minor Arterial | 32 | 20 | 52 | 37.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [18 empty] | 1 |  |  | WW MH in line with end of wing - identified in site visit pics | 52 | 477.3 | 24819.6 | [13 empty] | 52 | [8 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 |  |  |  |  | 1 |  |  | Drop down to house? | 52 | 25.68 | 1335.36 |  |  |  | 1 |  |  | Verizon | Verizon Cable | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  | Penn Power | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 26154.96 | 7500 | 4 | 11056.5 | 10000 | 2 | WW MH is in line with end of wing walls - identified in site visit pics |  |  | 89048 | 34650
384 | -- | 476 | 29321 | 22379 | 37101200900000 | 11 |  | Lawrence | .5 MI.W.TWP.RD.488 |  | BIG RUN |  | 31 | 51 | 27.5 | 48 | [25 empty] | Rural Local | 31 | 20 | 51 | 27.5 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | OH utilities cross over wings of bridge. No other utilities identified during site visit or by PennDOT |  |  | 88078 | 34673
385 | -- | 467 | 29534 | 22269 | 37020802201379 | 11 |  | Lawrence | 1/2 MI.WEST / SR0158 |  | MCCLURES RUN |  | 18 | 38 | 42.0 | 58 | [25 empty] | Rural Minor Arterial | 18 | 20 | 38 | 42.0 | 34 | 24 | 58 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0.25 |  |  | Aqua America |  | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [9 empty] | 35 | [7 empty] | 1 | 1 |  | Peoples Gas | Gas line markers along roadway | 38 | 120.88 | 4593.44 | [13 empty] | 38 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4800 | 3 |  | Penn Power | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 4593.44 | 7500 | 1 | 20884.5 | 10000 | 3 | OH lines within 12' of the bridge. Gas line markers identified along the roadway |  |  | 76062 | 34692
386 | -- | 468 | 78318 | 22277 | 37022400601429 | 11 |  | Lawrence | NEAR SR 3016 |  | SWAMP |  | 15 | 35 | 43.6 | 64 | [25 empty] | Rural Principal Arterial | 15 | 20 | 35 | 43.6 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [18 empty] | 2 | 16"+ |  | 2 large lines elevated over the channel - 1 line on each side of road | 35 | 477.3 | 16705.5 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 16705.5 | 7500 | 3 | 14332.5 | 10000 | 2 | 2 WW lines of 16'+ - 1 line on each side of the roadway |  |  | 30813 | 34702
387 | -- | 487 | 81961 | 16725 | 26100700300000 | 12 |  | Fayette | SALTLICK TOWNSHIP |  | CHAMPION CREEK |  | 41 | 61 | 35.0 | 52 | [25 empty] | Rural Major Collector | 41 | 20 | 61 | 35.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 6000 | 4 |  |  | 2400 | 2.73 | 6552 | 3 |  | 1800 | 2.73 | 4914 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 24160.5 | 10000 | 3 | OH lines cross over wings on the RT side of bridge. No other utilities identified in site visit or by PennDOT. |  |  | 31155 | 34847
388 | -- | 488 | 29781 | 16736 | 26101800100206 | 12 |  | Fayette | N. UNION & FRANKLIN TWPS. |  | BUTE RUN |  | 33 | 53 | 24.0 | 50 | [25 empty] | Rural Minor Collector | 33 | 20 | 53 | 24.0 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3600 | 3 |  |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 17608.5 | 10000 | 2 | OH lines located 8' to the RT of bridge. No other utilities identified in site visit. |  |  | 98374 | 34879
389 | -- | 489 | 69229 | 16752 | 26103100100053 | 12 |  | Fayette | CONNELLSVILLE CITY & TWP. |  | MOUNTS CREEK |  | 65 | 85 | 28.3 | 54 | [25 empty] | Urban Minor Arterial | 65 | 20 | 85 | 28.3 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 14332.5 | 10000 | 2 | Unknown utility attached to the bridge 4" - 6". OH lines cross the bridge at an angle. OH poles located close to bridge abutments. |  |  | 76072 | 34901
390 | -- | 472 | 78374 | 22362 | 37095601900000 | 11 |  | Lawrence | 1 MI.NORTH TWP.RD.601 |  | BR.LITTLE NESHANNOCK CR. |  | 11 | 31 | 24.2 | 52 | [25 empty] | Rural Minor Collector | 11 | 20 | 31 | 24.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  |  | 1 | 4" |  | Unknown PVC line crosses under bridge | 52 | 56.12 | 2918.24 |  |  | 52 | [14 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 1 | 0 | 1 |  | 2918.24 | 7500 | 1 | 0 | 10000 | 0 | OH lines are offset 15' from the bridge on one side. Unknown 4" PVC pipe crosses under bridge - property owner installed?? |  |  | 98377 | 34907
391 | -- | 473 | 69231 | 22369 | 37100501501309 | 11 |  | Lawrence | 1/4 MI. N.E. OF SR 0956 |  | LITTLE NESHANNOCK CREEK |  | 132 | 152 | 26.5 | 50 | [25 empty] | Rural Minor Collector | 132 | 20 | 152 | 26.5 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [17 empty] | 1 | 1 |  | Laurel Mountain Midstream LLC | Gas line markers and flags located during site visit - at end of wings | 152 | 120.88 | 18373.76 | [13 empty] | 152 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3200 | 1 |  |  | 800 | 2.73 | 2184 | 2 |  | 1600 | 2.73 | 4368 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 1 | 3 | 4 |  | 18373.76 | 7500 | 3 | 20406.75 | 10000 | 3 | OH lines on each side of the bridge. Gas line is located at the end of the wings and identified by markers and flags |  |  | 89142 | 34946
392 | -- | 541 | 32045 | 35982 | 64003103302148 | 12 |  | Westmoreland | MT. PLEASANT & BULLSKIN T |  | JACOBS CREEK |  | 48 | 68 | 44.0 | 66 | [25 empty] | Urban Minor Arterial | 48 | 20 | 68 | 44.0 | 42 | 24 | 66 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 5400 | 3 |  |  | 1800 | 2.73 | 4914 | 3 |  | 1800 | 2.73 | 4914 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 22522.5 | 10000 | 3 | OH lines offset 10' from the edge of bridge and 40' back from the near abutment. |  |  | 98864 | 34949
393 | -- | 26 | 88201 | 9265 | 14004507902031 | 2 |  | Centre | WOODWARD |  | PINE CREEK |  | 49 | 69 | 46.6 | 62 | [25 empty] | Rural Minor Collector | 49 | 20 | 69 | 46.6 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 6 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0.5 | 0 |  |  | Noted by PennDOT, parallel to road, offset unknown | 0 | 120.88 | 0 | [13 empty] | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0.75 | 0 |  |  | Pedestal noted by PennDOT, parallel to road, distance unknown | 0 | 32.1 | 0 |  |  |  | 0.75 | 0 |  |  | Cabinets noted by PennDOT, parallel to road, distance unknown | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  | Moved to underground fiber | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3000 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 2 | 3890.25 | 7780.5 | 25 | 10 | -8.3 | OUT OF ROW |  |  | 0 | 2 | 2 |  | 0 | 7500 | 0 | 15970.5 | 10000 | 2 | COMPLETE, pole offsets not given in site visit notes, poles appear closer than 15' | Assumed outermost Pole offset on Right side is 10' based on pictures |  | 51507 | 34977
394 | -- | 212 | 81284 | 10497 | 15304401300000 | 6 |  | Chester | NEAR WEST GROVE 45F06 (3799E7) |  | MIDDLE BR WHITE CLAY CR |  | 33 | 53 | 19.5 | 50 | [25 empty] | Rural Local | 33 | 20 | 53 | 19.5 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 7200 | 3 |  |  | 1800 | 2.73 | 4914 | 5 |  | 3000 | 2.73 | 8190 | 3 |  | 1800 | 2.73 | 4914 | 1 |  | 600 | 2.73 | 1638 | 2 | 3890.25 | 7780.5 | [6 empty] | 0 | 2 | 2 |  | 0 | 7500 | 0 | 27436.5 | 10000 | 3 | COMPLETE, no pole offsets given in site visit notes, no utility sketch, poles appear closer than 15' in site visit photos |  |  | 31157 | 34980
395 | -- | 241 | 90739 | 13896 | 21203100100000 | 8 |  | Cumberland | Spanglers Mill over Yellow Breeches Ck |  | YELLOW BREECHES CREEK |  | 139 | 159 | 29.8 | 64 | [25 empty] | Urban Major Collector | 139 | 20 | 159 | 29.8 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 3 |  |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 2 | 3890.25 | 7780.5 | [5 empty] | 9 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 81841 | 34985
396 | -- | 564 | 102789 | 13897 | 21203100100187 | 8 |  | Cumberland | S. of Lisburn on Spangler Mill, mill race (Y.B.) |  | MILL RACE |  | 55 | 75 | [27 empty] | Urban Major Collector | 55 | 20 | 75 | [5 empty] | 1e-17 | 1e-28 | 1e-30 | 0 | 0 | 0 |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4200 | 3 |  |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 2 | 3890.25 | 7780.5 |  | 8 |  |  |  | 9 | 0 | 2 | 2 |  | 0 | 7500 | 0 | 19246.5 | 10000 | 2 | COMPLETE, pole offsets given in site visit notes |  |  | 30715 | 34996
397 | -- | 479 | 29525 | 22433 | 37300100300259 | 11 |  | Lawrence | 1/4 MI. SOUTH OF SR 0317 |  | BESSEMER HAUL ROAD |  | 123 | 143 | 48.4 | 56 | [25 empty] | Rural Minor Collector | 123 | 20 | 143 | 48.4 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  | Gas line identified in site visit pics - crosses near abutment | 56 | 120.88 | 6769.28 | [13 empty] | 56 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 8" Water | 1 | Yes | 143 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 2 | 0 | 2 |  | 6769.28 | 7500 | 1 | 0 | 10000 | 0 | 6" to 8" water line attached to the bridge. Gas line crosses the road near the abutment. OH lines offset 20'+ from the bridge |  |  | 30881 | 35090
398 | -- | 147 | 79572 | 32308 | 57026703202704 | 4 |  | Susquehanna | FRST LK TP 4.5M S SR 4014 |  | MIDDLE BR WYALUSING CR | 20143580177 | 63 | 83 | 26.0 | 54 | [25 empty] | Rural Minor Arterial | 63 | 20 | 83 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 5600 | 4 |  |  | 3200 | 2.73 | 8736 | 3 |  | 2400 | 2.73 | 6552 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [5 empty] | 6 | 0 | 3 | 3 |  | 0 | 7500 | 0 | 26958.75 | 10000 | 3 | COMPLETE, pole offset given in site visit notes |  |  | 31146 | 35103
399 | -- | 481 | 29549 | 22441 | 37300400600000 | 11 |  | Lawrence | 3/4 MILE W OF TR 551 |  | OVER BR OF HONEY CREEK |  | 25 | 45 | 26.5 | 46 | [25 empty] | Rural Local | 25 | 20 | 45 | 26.5 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  |  | 1 | 2" |  | Unknown poly line crosses under bridge | 46 | 56.12 | 2581.52 | 46 | [16 empty] | None | 0 | None | 0 |  |  | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 1 | 0 | 1 |  | 2581.52 | 7500 | 1 | 0 | 10000 | 0 | No utilities identified in site visit summary, but a 2" poly line appears to cross under the bridge in one of the site visit pics. Unknown utility |  |  | 30552 | 35171
400 | -- | 170 | 78889 | 4953 | 06100601100107 | 5 |  | Berks | CRYSTALCAVE RD,VIRGINVLLE |  | SACONY CREEK | 20143571648/20143571649 | 125 | 145 | 33.5 | 54 | [25 empty] | Rural Minor Collector | 125 | 20 | 145 | 33.5 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4000 | 4 |  |  | 3200 | 2.73 | 8736 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [5 empty] | 0 | 0 | 3 | 3 |  | 0 | 7500 | 0 | 22590.75 | 10000 | 3 | COMPLETE, power lines crosses directly over bridge |  |  | 30702 | 35178
401 | -- | 483 | 51503 | 16651 | 26016603900000 | 12 |  | Fayette | REDSTONE & LUZERNE TWPS. |  | DUNLAP CREEK | 20143571450/20143571452 | 42 | 62 | 30.3 | 54 | [25 empty] | Urban Minor Arterial | 42 | 20 | 62 | 30.3 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | Elevated on beam across creek - 10" - 12" line | 62 | 249.45 | 15465.9 | [13 empty] | 62 | [8 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  | Located 10' offset from bridge | 62 | 120.88 | 7494.56 | [13 empty] | 62 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 5400 | 5 |  |  | 3000 | 2.73 | 8190 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 22960.46 | 7500 | 4 | 22522.5 | 10000 | 3 | Water line elevated across channel with beams - 10"-12". Gas line crosses channel 10' offset from bridge. OH lines on one side of bridge near structure. |  |  | 81846 | 35201
402 | -- | 179 | 85811 | 26785 | 45020900401748 | 5 |  | Monroe | KRESGEVILLE |  | MIDDLE CREEK | 20143561422 | 50 | 70 | 43.0 | 62 | [25 empty] | Rural Principal Arterial | 50 | 20 | 70 | 43.0 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 10400 | 6 |  |  | 4800 | 2.73 | 13104 | 7 |  | 5600 | 2.73 | 15288 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [5 empty] | 3 | 0 | 3 | 3 |  | 0 | 7500 | 0 | 40062.75 | 10000 | 5 | COMPLETE, pole offsets given in site visit notes |  |  | 30635 | 35227
403 | -- | 233 | 87437 | 362 | 01400500101339 | 8 |  | Adams | 1/4 MI.N. OF BENDERSVILLE |  | OPOSSUM CREEK |  | 43 | 63 | 31.4 | 52 | [25 empty] | Rural Local | 43 | 20 | 63 | 31.4 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4000 | 4 |  |  | 3200 | 2.73 | 8736 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [5 empty] | 5 | 0 | 3 | 3 |  | 0 | 7500 | 0 | 22590.75 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes, 12' Left and 5' Right |  |  | 32045 | 35982
404 | -- | 486 | 74176 | 16720 | 26100300320000 | 12 |  | Fayette | SPRINGFIELD TOWNSHIP |  | LAUREL RUN |  | 39 | 59 | 14.0 | 46 | [25 empty] | Rural Minor Collector | 39 | 20 | 59 | 14.0 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  |  | 59 | 249.45 | 14717.55 | [13 empty] | 59 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1600 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 14717.55 | 7500 | 2 | 8258.25 | 10000 | 1 | OH lines over the wings on side of the bridge. FH identified near edge of road. |  |  | 76089 | 36002
405 | -- | 348 | 23410 | 31470 | 55052300701200 | 9 |  | Somerset | BEACHLY |  | LAUREL RUN | 20143571775 | 38 | 58 | 26.0 | 52 | [25 empty] | Rural Minor Arterial | 38 | 20 | 58 | 26.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 1 | 1 | 4800 | 5 |  |  | 4000 | 2.73 | 10920 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | 30 | [5 empty] | 0 | 3 | 3 |  | 0 | 7500 | 0 | 24774.75 | 10000 | 3 | OH lines run along the roadway and cross at an angle over the bridge. No other utilities identified in site visit. |  |  | 79402 | 36130
406 | -- | 384 | 83241 | 11049 | 16200902200128 | 10 |  | Clarion | ELDER ROAD |  | CHERRY RUN |  | 45 | 65 | 27.6 | 48 | [25 empty] | Rural Minor Collector | 45 | 20 | 65 | 27.6 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 2 |  |  | 1600 | 2.73 | 4368 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 0 | 3 | 3 |  | 0 | 7500 | 0 | 18222.75 | 10000 | 2 | 3 OH poles need to be relocated. One OH line crosses over the wings and OH E crosses at an angle over the bridge. |  |  | 31601 | 36168
407 | -- | 391 | 83282 | 19550 | 33003601701535 | 10 |  | Jefferson | CLOE NO.1 |  | CANOE CREEK |  | 67 | 87 | 35.5 | 56 | [25 empty] | Rural Minor Arterial | 67 | 20 | 87 | 35.5 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 6 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 |  |  |  | 1 |  |  |  |  | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 4-6" Conduit bank, 8" Unknown | 1 | Yes | 435 |  | 1 | 6400 | 2 |  |  | 1600 | 2.73 | 4368 | 6 |  | 4800 | 2.73 | 13104 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 1 | 3 | 4 |  | 0 | 7500 | 0 | 29142.75 | 10000 | 3 | OH utilities along edge of bridge and crossing. 4-4" conduit attached under bridge w/ Bell MH in roadway. 3" gas line attached to outside of bridge |  |  | 74418 | 36207
408 | -- | 5 | 97118 | 13128 | 20040805201643 | 1 |  | Crawford | HYDETOWN BOROUGH |  | OVER THOMPSON CREEK |  | 78 | 98 | 43.0 | 54 | [25 empty] | Urban Major Collector | 78 | 20 | 98 | 43.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 | 0 |  |  | Attached to bridge, not mentioned in site visit notes, PennDOT photos | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 4" Gas | 1 | Yes | 98 | 0 | 1 | 8800 | 4 |  |  | 3200 | 2.73 | 8736 | 5 |  | 4000 | 2.73 | 10920 | 2 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 1 | 3 | 4 |  | 0 | 7500 | 0 | 35694.75 | 10000 | 4 | COMPLETE, pole offsets not given in site visit, poles appear closer than 15' in PennDOT photos, attached gas line size estimated using PennDOT photos |  |  | 31826 | 36228
409 | -- | 33 | 88199 | 9451 | 14304003701668 | 2 |  | Centre | UNIONVILLE BORO |  | DEWITT RUN |  | 35 | 55 | 36.0 | 60 | [25 empty] | Rural Principal Arterial - Other | 35 | 20 | 55 | 36.0 | 36 | 24 | 60 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 8800 | 5 |  |  | 4000 | 2.73 | 10920 | 3 |  | 2400 | 2.73 | 6552 | 3 |  | 2400 | 2.73 | 6552 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [5 empty] | 3 | 0 | 3 | 3 |  | 0 | 7500 | 0 | 35694.75 | 10000 | 4 | COMPLETE, pole offsets given in site visit notes |  |  | 31614 | 36230
410 | -- | 78 | 85275 | 26595 | 44401300500000 | 2 |  | Mifflin | 1 MI NW STRODES MILLS |  | STRODES RUN |  | 33 | 53 | 26.8 | 52 | [25 empty] | Rural Principal Arterial - Other | 33 | 20 | 53 | 26.8 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3200 | 2 |  |  | 1600 | 2.73 | 4368 | 1 |  | 800 | 2.73 | 2184 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 0 | 3 | 3 |  | 0 | 7500 | 0 | 20406.75 | 10000 | 3 | COMPLETE, pole offsets not given in site visit, poles appear closer than 15' in photos |  |  | 76121 | 36248
411 | -- | 493 | 29820 | 16789 | 26105000101121 | 12 |  | Fayette | BULLSKIN TOWNSHIP |  | MOUNTS CREEK | 20143571183 | 39 | 59 | 24.2 | 52 | [25 empty] | Rural Minor Collector | 39 | 20 | 59 | 24.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  |  | 59 | 249.45 | 14717.55 | [13 empty] | 59 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 1 | 0 | 1 |  | 14717.55 | 7500 | 2 | 0 | 10000 | 0 | No OH lines affected by construction - 20'+ offset from bridge. Water line flagged near abutments. |  |  | 76122 | 36251
412 | -- | 494 | 90965 | 16794 | 26105002101302 | 12 |  | Fayette | SALTLICK TOWNSHIP |  | CHAMPION CREEK |  | 27 | 47 | 27.0 | 50 | [25 empty] | Rural Major Collector | 27 | 20 | 47 | 27.0 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | FH identified near road | 47 | 249.45 | 11724.15 | [13 empty] | 47 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 11724.15 | 7500 | 2 | 11056.5 | 10000 | 2 | OH telephone and cable lines cross over wings. OH E 20'+ offset from bridge. FH located near roadway - water line relocation anticipated. |  |  | 98633 | 36331
413 | -- | 495 | 89075 | 16806 | 26105103000845 | 12 |  | Fayette | BULLSKIN TOWNSHIP |  | BRANCH OF BREAKNECK RUN |  | 21 | 41 | 27.0 | 50 | [25 empty] | Rural Major Collector | 21 | 20 | 41 | 27.0 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | Flagged near bridge on both ends | 41 | 249.45 | 10227.45 | [13 empty] | 41 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1600 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 10227.45 | 7500 | 2 | 8258.25 | 10000 | 1 | OH lines cross over wings. Waterline flagged near the bridge on both ends. |  |  | 31972 | 36365
414 | -- | 106 | 91436 | 24511 | 41001500702198 | 3 |  | Lycoming | 8 MILES S OF WILLIAMSPORT |  | OVER BLACK HOLE CREEK |  | 45 | 65 | 56.2 | 78 | [25 empty] | Urban Principal Arterial | 45 | 20 | 65 | 56.2 | 54 | 24 | 78 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 6400 | 4 |  |  | 3200 | 2.73 | 8736 | 2 |  | 1600 | 2.73 | 4368 | 2 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | 50 |  |  |  |  | 14 | 0 | 3 | 3 |  | 0 | 7500 | 0 | 29142.75 | 10000 | 3 | COMPLETE, pole offset in site visit notes/sketches |  |  | 31611 | 36387
415 | -- | 497 | 29926 | 16840 | 26105801300142 | 12 |  | Fayette | SALTLICK & DONEGAL TWPS. |  | INDIAN CREEK | 20143580467/20143580470 | 63 | 83 | 24.3 | 54 | [25 empty] | Rural Major Collector | 63 | 20 | 83 | 24.3 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | Blue painted near bridge on both ends | 83 | 249.45 | 20704.35 | [13 empty] | 83 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 1 |  |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 20704.35 | 7500 | 3 | 14332.5 | 10000 | 2 | OH lines cross over wings. Water line identified by blue paint during site visit. |  |  | 89037 | 36389
416 | -- | 498 | 29893 | 16841 | 26105801300864 | 12 |  | Fayette | SALTLICK & DONEGAL TWPS. |  | INDIAN CREEK | 20143571250 | 45 | 65 | 26.0 | 54 | [25 empty] | Rural Major Collector | 45 | 20 | 65 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | Blue painted near bridge on both ends | 65 | 249.45 | 16214.25 | [13 empty] | 65 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 16214.25 | 7500 | 3 | 7166.25 | 10000 | 1 | OH line crosses bridge at an angle. Water line identified by blue paint during site visit. |  |  | 31304 | 36431
417 | -- | 108 | 6023 | 24591 | 41008700600000 | 3 |  | Lycoming | 0.1 MI N OF FARRAGUT |  | OVER TRIB TO LOYALSOCK C |  | 23 | 43 | 35.7 | 64 | [25 empty] | Rural Minor Arterial | 23 | 20 | 43 | 35.7 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 8000 | 4 |  | PPL | 3200 | 2.73 | 8736 | 4 |  | 3200 | 2.73 | 8736 | 2 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | 35 |  |  |  |  | 10 | 0 | 3 | 3 |  | 0 | 7500 | 0 | 33510.75 | 10000 | 4 | COMPLETE, pole offset in site visit notes/sketches |  |  | 79404 | 36481
418 | -- | 321 | 21957 | 5709 | 07101303601234 | 9 |  | Blair | 0.23 MILE NORTH FROM PA 453 |  | SINKING RUN |  | 56 | 76 | 26.0 | 54 | [25 empty] | Rural Local | 56 | 20 | 76 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 6400 | 3 |  |  | 2400 | 2.73 | 6552 | 3 |  | 2400 | 2.73 | 6552 | 2 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | 30 | [5 empty] | 0 | 3 | 3 |  | 0 | 7500 | 0 | 29142.75 | 10000 | 3 | OH lines run along the edge of the bridge and cross over the bridge at an angle. No other utilities identified. |  |  | 79418 | 36482
419 | -- | 458 | 70807 | 3722 | 04302700400000 | 11 |  | Beaver | .5 MILE NORTH OF SR 168 |  | MILL CREEK | 20143570586 | 40 | 60 | 32.2 | 54 | [25 empty] | Rural Minor Collector | 40 | 20 | 60 | 32.2 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  | 1 |  |  | Greene Township |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 8000 | 7 |  |  | 5600 | 2.73 | 15288 | 2 |  | 1600 | 2.73 | 4368 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 0 | 3 | 3 |  | 0 | 7500 | 0 | 33510.75 | 10000 | 4 | All site visit pics are rotated. OH lines cross over guardrail and wings |  |  | 79419 | 36493
420 | -- | 502 | 79328 | 16928 | 26301301900753 | 12 |  | Fayette | GERMAN TOWNSHIP |  | MIDDLE RUN |  | 44 | 64 | 26.2 | 48 | [25 empty] | Rural Minor Collector | 44 | 20 | 64 | 26.2 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  |  | 48 | 249.45 | 11973.6 | [13 empty] | 48 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 11973.6 | 7500 | 2 | 7166.25 | 10000 | 1 | Water line identified near the bridge in the site visit. OH line crosses over bridge at an angle. |  |  | 31699 | 36684
421 | -- | 477 | 29387 | 22396 | 37200100802619 | 11 |  | Lawrence | 100' SOUTH OF SR 2012 |  | MCKEE RUN |  | 24 | 44 | 20.0 | 46 | [25 empty] | Rural Minor Collector | 24 | 20 | 44 | 20.0 | 22 | 24 | 46 |  | 1e-17 | 1e-28 | 1e-30 | 0 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3200 | 2 |  |  | 1600 | 2.73 | 4368 | 1 |  | 800 | 2.73 | 2184 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 0 | 3 | 3 |  | 0 | 7500 | 0 | 20406.75 | 10000 | 3 | 2 OH lines cross over the bridge and will need to be relocated. |  |  | 91189 | 36750
422 | -- | 504 | 79340 | 18013 | 30001802400670 | 12 |  | Greene | CENTER TOWNSHIP |  | HOUSE RUN | 20143571263 | 40 | 60 | 26.2 | 54 | [25 empty] | Rural Major Collector | 40 | 20 | 60 | 26.2 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 114 | 120.88 | 13780.32 | [13 empty] | 114 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4800 | 2 |  |  | 1600 | 2.73 | 4368 | 2 |  | 1600 | 2.73 | 4368 | 2 |  | 1600 | 2.73 | 4368 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 1 | 3 | 4 |  | 13780.32 | 7500 | 2 | 24774.75 | 10000 | 3 | OH lines cross near bridge on both sides of the road with 2 poles location near abutments. Gas line cross the channel near the bridge then crosses the road near the abutment. |  |  | 89049 | 37037
423 | -- | 505 | 79342 | 18044 | 30001805800146 | 12 |  | Greene | MORRIS TOWNSHIP |  | BROWNS CREEK |  | 44 | 64 | 26.0 | 54 | [25 empty] | Rural Major Collector | 44 | 20 | 64 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [18 empty] | 1 |  |  | Drop down at a pole that is anticipated to be relocated | 54 | 32.1 | 1733.4 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 400 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 1733.4 | 7500 | 1 | 4982.25 | 10000 | 1 | OH telephone crosses near the edge of the bridge. UG fiber optic/telephone drops down from pole to be relocated - assume relocation to match width of roadway.
424 | -- | 506 | 30291 | 18154 | 30018800300000 | 12 |  | Greene | FRANKLIN TOWNSHIP |  | GRIMES RUN | 20143571273 | 28 | 48 | 33.7 | 56 | [25 empty] | Urban Minor Arterial | 28 | 20 | 48 | 33.7 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  | FH and meters located near roadway during site visit | 48 | 249.45 | 11973.6 | [13 empty] | 48 |  |  |  |  | 1 |  |  |  | 48 | 477.3 | 22910.4 | [13 empty] | 48 |  |  |  |  | 1 |  |  | Markers located in site visit | 48 | 120.88 | 5802.24 | [13 empty] | 48 | [8 empty] | 0 | 191.55 | 0 | [18 empty] | 1 |  |  | MH located near roadway | 48 | 32.1 | 1540.8 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 1" Water, 2" Unknown | 1 | Yes | 96 |  | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 5 | 2 | 7 |  | 42227.04 | 7500 | 6 | 11056.5 | 10000 | 2 | Not clear whether WW line goes under the bridge or just runs parallel. Unidentified orange conduit crudely tied under bridge.
425 | -- | 507 | 76037 | 18164 | 30018801800000 | 12 |  | Greene | JEFFERSON TOWNSHIP |  | BR SOUTH FORK TENMILE CK | 20143571371 | 35 | 55 | 28.3 | 54 | [25 empty] | Rural Minor Arterial | 35 | 20 | 55 | 28.3 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  |  | 55 | 249.45 | 13719.75 | [13 empty] | 55 | [8 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 54 | 120.88 | 6527.52 | [13 empty] | 54 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4800 | 2 |  |  | 1200 | 2.73 | 3276 | 3 |  | 1800 | 2.73 | 4914 | 3 |  | 1800 | 2.73 | 4914 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 20247.27 | 7500 | 3 | 20884.5 | 10000 | 3 | Water and gas lines identified near bridge in site visit. Numerous OH lines cross near the edge of the bridge.
426 | -- | 508 | 89031 | 18214 | 30101101500501 | 12 |  | Greene | JEFFERSON T & CLARKSVILLE |  | SOUTH FORK TENMILE CREEK | 20143580303/20143580304 | 151 | 171 | 29.5 | 55 | [25 empty] | Rural Major Collector | 151 | 20 | 171 | 29.5 | 31 | 24 | 55 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [18 empty] | 1 |  |  |  | 171 | 477.3 | 81618.3 | [13 empty] | 171 | [8 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 6" Gas | 1 | Yes | 171 |  | 1 | 4200 | 4 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 81618.3 | 7500 | 11 | 19246.5 | 10000 | 2 | 4" to 6" gas line attached to the bridge under railing. OH lines cross over the wings of the bridge. WW line also identified during the site visit.
427 | -- | 557 | 79419 | 36493 | 64202100601976 | 12 |  | Westmoreland | MOUNT PLEASANT TOWNSHIP |  | SEWICKLEY CREEK |  | 97 | 117 | 31.5 | 51 | [25 empty] | Urban Local | 97 | 20 | 117 | 31.5 | 27 | 24 | 51 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 7200 | 3 |  |  | 2400 | 2.73 | 6552 | 3 |  | 2400 | 2.73 | 6552 | 3 |  | 2400 | 2.73 | 6552 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 0 | 3 | 3 |  | 0 | 7500 | 0 | 31326.75 | 10000 | 4 | OH lines on both sides of the bridge. 5' offset on one side and 8' offset on the other side.
428 | -- | 510 | 30335 | 18261 | 30200303301330 | 12 |  | Greene | FRANKLIN TOWNSHIP |  | TENMILE CREEK (CROSSING @ LOW) |  | 133 | 153 | 23.7 | 50 | [25 empty] | Urban Collector | 133 | 20 | 153 | 23.7 | 26 | 24 | 50 |  | 1 | 20 | 200 | 2 | [5 empty] | 0 | 249.45 | 0 | [18 empty] | 1 |  |  | Cross the road and the channel | 203 | 477.3 | 96891.9 | [13 empty] | 203 | [8 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 3" Gas | 1 | Yes | 153 |  | 1 | 1200 | 2 |  |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 96891.9 | 7500 | 13 | 11056.5 | 10000 | 2 | 2" to 3" gas attached to the bridge under the railing. WW line crosses the road near the abutment then crosses the channel.
429 | -- | 511 | 79353 | 18279 | 30201103700000 | 12 |  | Greene | FRANKLIN TOWNSHIP |  | COAL LICK RUN |  | 28 | 48 | 26.3 | 50 | [25 empty] | Rural Major Collector | 28 | 20 | 48 | 26.3 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | Located within 6' of the edge of bridge | 48 | 249.45 | 11973.6 | [13 empty] | 48 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 0 |  |  | 0 | 2.73 | 0 | 2 |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 11973.6 | 7500 | 2 | 7166.25 | 10000 | 1 | OH lines cross over the edge of the bridge/wings. Water line identified with flags within 6' of the bridge end during the site visit.
430 | -- | 512 | 30289 | 18287 | 30201600701702 | 12 |  | Greene | MONOGAHELA TOWNSHIP |  | WHITELEY CREEK | 20143580312 | 129 | 149 | 24.1 | 52 | [25 empty] | Rural Major Collector | 129 | 20 | 149 | 24.1 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  |  | 149 | 249.45 | 37168.05 | [13 empty] | 149 | [8 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 149 | 120.88 | 18011.12 | [13 empty] | 149 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 800 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 2 | 1 | 3 |  | 55179.17 | 7500 | 8 | 6074.25 | 10000 | 1 | Water line and gas line located near the bridge during the site visit.
431 | -- | 513 | 79356 | 18315 | 30202600100590 | 12 |  | Greene | FRANKLIN TOWNSHIP |  | LAUREL RUN |  | 39 | 59 | 37.0 | 60 | [25 empty] | Urban Collector | 39 | 20 | 59 | 37.0 | 36 | 24 | 60 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  |  | 59 | 249.45 | 14717.55 | [13 empty] | 59 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 3" Gas | 1 | Yes | 59 |  | 1 | 6400 | 3 |  |  | 2400 | 2.73 | 6552 | 2 |  | 1600 | 2.73 | 4368 | 3 |  | 2400 | 2.73 | 6552 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 2 | 3 | 5 |  | 14717.55 | 7500 | 2 | 29142.75 | 10000 | 3 | Water line and gas line identified within 6' of the bridge on different sides. OH lines on each side of the bridge to be relocated.
432 | -- | 514 | 79357 | 18317 | 30202600501285 | 12 |  | Greene | FRANKLIN TOWNSHIP |  | BRADENS RUN |  | 24 | 44 | 38.5 | 60 | [25 empty] | Urban Collector | 24 | 20 | 44 | 38.5 | 36 | 24 | 60 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | FH and flags identified in site visit | 44 | 249.45 | 10975.8 | [13 empty] | 44 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2800 | 3 |  |  | 1200 | 2.73 | 3276 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 10975.8 | 7500 | 2 | 11534.25 | 10000 | 2 | OH lines cross over wings on one side of bridge. Water line identified with flags and FH near the bridge on one side.
433 | -- | 49 | 69088 | 15535 | 24021900201858 | 2 |  | Elk | BROCKPORT |  | MEAD RUN | 20143580336 | 27 | 47 | 41.5 | 62 | [25 empty] | Rural Principal Arterial - Other | 27 | 20 | 47 | 41.5 | 38 | 24 | 62 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1 | 0 |  |  | Noted in site visit, crosses road, distance unknown | 0 | 249.45 | 0 | [13 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1 | 0 |  |  | Noted in site visit, parallel to road, offset unknown | 0 | 120.88 | 0 | [13 empty] | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 10400 | 6 |  |  | 4800 | 2.73 | 13104 | 2 |  | 1600 | 2.73 | 4368 | 3 |  | 2400 | 2.73 | 6552 | 2 |  | 1600 | 2.73 | 4368 | 3 | 3890.25 | 11670.75 | 30 | 10 | -0.75 | OUT OF ROW |  |  | 0 | 3 | 3 |  | 0 | 7500 | 0 | 40062.75 | 10000 | 5 | COMPLETE, pole offsets not given in site visit notes | GAS APPEARS TO CROSS MORE THAN 15' AWAY FROM WINGS, WATER CAP AT OTHER SIDE OF INTERSECTION, CHANGING BOTH TO 0
434 | -- | 516 | 30231 | 18403 | 30301300900000 | 12 |  | Greene | WAYNE TOWNSHIP |  | BELLS RUN | 20143571401 | 26 | 46 | 28.3 | 50 | [25 empty] | Rural Major Collector | 26 | 20 | 46 | 28.3 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [18 empty] | 1 |  |  | Suspended on wire over the channel | 46 | 32.1 | 1476.6 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 1 | 0 | 1 |  | 1476.6 | 7500 | 1 | 0 | 10000 | 0 | No OH near the bridge. UG FO line is suspended across the channel on a wire approx. 12' from the bridge. Gas line identified 20'+ offset from the bridge.
435 | -- | 517 | 30975 | 34335 | 62001900400000 | 12 |  | Washington | AMWELL TOWNSHIP |  | BANE CREEK |  | 103 | 123 | 27.3 | 54 | [25 empty] | Rural Major Collector | 103 | 20 | 123 | 27.3 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | Near the road before the bridge. Turns away from the bridge before crossing. | 123 | 249.45 | 30682.35 | [13 empty] | 123 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 1 | 0 | 1 |  | 30682.35 | 7500 | 5 | 0 | 10000 | 0 | No OH near the bridge. Water line identified near the roadway as it approaches the bridge. Water line turns away from bridge then crosses channel.
436 | -- | 518 | 30639 | 34417 | 62005003300000 | 12 |  | Washington | CECIL TOWNSHIP |  | MILLER RUN |  | 66 | 86 | 32.5 | 54 | [25 empty] | Rural Minor Arterial | 66 | 20 | 86 | 32.5 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | Identified near the bridge in site visit | 86 | 249.45 | 21452.7 | [13 empty] | 86 | [8 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  |  | 86 | 120.88 | 10395.68 | [13 empty] | 86 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 2 | 0 | 2 |  | 31848.38 | 7500 | 5 | 0 | 10000 | 0 | No OH lines near the bridge. Water line and gas line identified in the site visit.
437 | -- | 519 | 30997 | 34609 | 62008804902545 | 12 |  | Washington | SPEERS & CHARLEROI BORO. |  | MAPLE CREEK |  | 76 | 96 | 39.6 | 54 | [25 empty] | Urban Principal Arterial | 76 | 20 | 96 | 39.6 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  | Water line identified with paint near bridge | 96 | 249.45 | 23947.2 | [13 empty] | 96 |  |  |  |  | 1 |  |  |  | 96 | 477.3 | 45820.8 | [13 empty] | 96 | [8 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [18 empty] | 1 |  |  |  | 96 | 32.1 | 3081.6 |  |  |  |  | 1 |  |  |  | 96 | 25.68 | 2465.28 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 8" Gas | 1 | Yes | 96 |  | 1 | 8800 | 6 |  |  | 4800 | 2.73 | 13104 | 1 |  | 800 | 2.73 | 2184 | 3 |  | 2400 | 2.73 | 6552 | 1 |  | 800 | 2.73 | 2184 | 3 | 3890.25 | 11670.75 | [6 empty] | 5 | 3 | 8 |  | 75314.88 | 7500 | 11 | 35694.75 | 10000 | 4 | 6" to 8" gas line attached to the bridge. Water line identified near the bridge. Numerous OH lines crossing road and bridge with an electric substation at one corner of bridge.
438 | -- | 520 | 73058 | 34623 | 62008807600000 | 12 |  | Washington | FINLEYVILLE BOROUGH |  | PETERS CREEK |  | 65 | 85 | 24.3 | 64 | [25 empty] | Urban Principal Arterial | 65 | 20 | 85 | 24.3 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | Water line identified near bridge | 85 | 249.45 | 21203.25 | [13 empty] | 85 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [18 empty] | 1 |  |  |  | 85 | 32.1 | 2728.5 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 600 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 23931.75 | 7500 | 4 | 9418.5 | 10000 | 1 | OH telephone line crosses over the wings on one side of the road. OH E 20'+ offset from the other side of bridge.
439 | -- | 521 | 89048 | 34650 | 62022100802172 | 12 |  | Washington | MORRIS TOWNSHIP |  | TENMILE CREEK |  | 72 | 92 | 26.0 | 52 | [25 empty] | Rural Major Collector | 72 | 20 | 92 | 26.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  | Markers near the roadway/bridge | 52 | 120.88 | 6285.76 | [13 empty] | 52 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  |  | 1 |  |  | Telephone | 92 | 56.12 | 5163.04 | [13 empty] | 92 |  |  |  | None | 0 | None | 0 |  | 1 | 1200 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 2 | 1 | 3 |  | 11448.8 | 7500 | 2 | 7166.25 | 10000 | 1 | OH line 6.5' from the edge of the bridge. Gas line identified within 8' of the edge of bridge. UG Telephone line from drop down of pole to be relocated.
440 | -- | 522 | 88078 | 34673 | 62023104300092 | 12 |  | Washington | BLAINE & INDEPENDENCE TWP |  | BRUSH RUN | 20143580124/20143580125 | 61 | 81 | 18.3 | 48 | [25 empty] | Rural Major Collector | 61 | 20 | 81 | 18.3 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  |  | 1 |  | Bell of Pennsylvania | Cable | 156 | 56.12 | 8754.72 | [13 empty] | 156 |  |  |  | None | 0 | None | 0 |  | 1 | 600 | 0 |  |  | 0 | 2.73 | 0 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 8754.72 | 7500 | 2 | 9418.5 | 10000 | 1 | OH lines over wings on one side of bridge. UG Cable connected to drop downs on each pole anticipated to be relocated on both ends of the bridge.
441 | -- | 523 | 76062 | 34692 | 62048100500000 | 12 |  | Washington | WEST PIKE RUN TOWNSHIP |  | PIKE RUN |  | 44 | 64 | 26.0 | 54 | [25 empty] | Rural Minor Arterial | 44 | 20 | 64 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  | Equitable Gas | 64 | 120.88 | 7736.32 | [13 empty] | 64 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2400 | 2 |  |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 7736.32 | 7500 | 2 | 14332.5 | 10000 | 2 | OH lines cross the channel over the wings and also across the road near one abutment. Gas line identified near the bridge in the site visit.
442 | -- | 524 | 30813 | 34702 | 62048102400990 | 12 |  | Washington | CARROLL TOWNSHIP |  | TAYLOR RUN |  | 50 | 70 | 23.2 | 54 | [25 empty] | Urban Collector | 50 | 20 | 70 | 23.2 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  | Identified in the roadway during site visit | 70 | 120.88 | 8461.6 | [13 empty] | 70 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1600 | 3 |  |  | 1200 | 2.73 | 3276 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 8461.6 | 7500 | 2 | 8258.25 | 10000 | 1 | OH lines cross over the wings of the bridge. Gas line located in the road during the site visit.
443 | -- | 525 | 31155 | 34847 | 62104900520000 | 12 |  | Washington | SOUTH STRABANE TOWNSHIP |  | BR. LITTLE CHARTIERS CK. |  | 27 | 47 | 22.8 | 52 | [25 empty] | Urban Local | 27 | 20 | 47 | 22.8 | 28 | 24 | 52 |  | 1 | 20 | 200 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 |  |  |  |  | 1 |  | Bell of Pennsylvania | Telephone | 47 | 56.12 | 2637.64 | [13 empty] | 47 |  |  |  | None | 0 | None | 0 |  | 1 | 3200 | 3 |  |  | 2400 | 2.73 | 6552 | 1 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 3 | 3890.25 | 11670.75 | [6 empty] | 1 | 3 | 4 |  | 2637.64 | 7500 | 1 | 20406.75 | 10000 | 3 | OH lines cross over the bridge at an angle. Drop down at one of the poles for UG T.
444 | -- | 215 | 102315 | 27513 | 46066302700894 | 6 |  | Montgomery | PERKIOMEN HEIGHTS 02D13 |  | BRCH PERKIOMEN CR/2916H1 |  | 52 | 72 | 29 | 64 | [25 empty] | Rural Principal Arterial | 52 | 20 | 72 | 29 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4000 | 2 |  |  | 1600 | 2.73 | 4368 | 1 |  | 800 | 2.73 | 2184 | 1 |  | 800 | 2.73 | 2184 | 1 |  | 800 | 2.73 | 2184 | 3 | 3890.25 | 11670.75 | [6 empty] | 0 | 3 | 3 |  | 0 | 7500 | 0 | 22590.75 | 10000 | 3 | COMPLETE, no pole offsets given in site visit notes, poles appear closer than 15' in photos
445 | -- | 527 | 76072 | 34901 | 62201102800165 | 12 |  | Washington | AMWELL TOWNSHIP |  | LITTLE TENMILE CREEK |  | 60 | 80 | 22.3 | 50 | [25 empty] | Rural Major Collector | 60 | 20 | 80 | 22.3 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  | Markers and flags near the bridge | 80 | 120.88 | 9670.4 | [13 empty] | 80 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 1 | 0 | 1 |  | 9670.4 | 7500 | 2 | 0 | 10000 | 0 | No OH utilities affected by construction. Gas line identified near the bridge by markers and flags.
446 | -- | 139 | 96689 | 20820 | 35401900200731 | 4 |  | Lackawanna | S ABINGTON TP OVER I-81 |  | SR 0081 I-81 | 20143521244 | 293 | 313 | 33.5 | 53 | [25 empty] | Urban Minor Collector | 293 | 20 | 313 | 33.5 | 29 | 24 | 53 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  | Attached to bridge | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 20" sewer line | 1 | Yes | 313 | 0 | 1 | 5000 | 4 |  |  | 4000 | 2.73 | 10920 | 1 |  | 1000 | 2.73 | 2730 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | [6 empty] | 1 | 4 | 5 |  | 0 | 7500 | 0 | 29211 | 10000 | 3 | COMPLETE, no pole offsets given in site visit notes, poles appear closer than 15' in photos, sewer line size estimated from site visit photos | LONG BRIDGE OVER ROUTE 81
447 | -- | 529 | 89142 | 34946 | 62202300800032 | 12 |  | Washington | FALLOWFIELD TOWNSHIP |  | BRANCH OF PIGEON CREEK | 20143580131 | 29 | 49 | 24.2 | 48 | [25 empty] | Urban Local | 29 | 20 | 49 | 24.2 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | Crosses road near abutment | 48 | 249.45 | 11973.6 | [13 empty] | 48 | [8 empty] | 0 | 477.3 | 0 | [18 empty] | 1 |  |  | Crosses channel near the edge of bridge - flags and markers | 49 | 120.88 | 5923.12 | [13 empty] | 49 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 6600 | 3 |  |  | 1800 | 2.73 | 4914 | 4 |  | 2400 | 2.73 | 6552 | 4 |  | 2400 | 2.73 | 6552 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 17896.72 | 7500 | 3 | 25798.5 | 10000 | 3 | OH crosses over the bridge. Water line identified in site visit crossing the road near abutment. Gas ling marked with flags crossing the channel near the bridge.
448 | -- | 530 | 98864 | 34949 | 62202301100756 | 12 |  | Washington | FALLOWFIELD TOWNSHIP |  | PIGEON CREEK |  | 94 | 114 | 27.0 | 50 | [25 empty] | Rural Minor Collector | 94 | 20 | 114 | 27.0 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  | Flagged near the bridge in site visit pics | 114 | 249.45 | 28437.3 | [13 empty] | 114 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4800 | 5 |  |  | 3000 | 2.73 | 8190 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 28437.3 | 7500 | 4 | 20884.5 | 10000 | 3 | OH lines cross over bridge at an angle. Water lie identified with flags near the bridge in the site visit pics.
449 | -- | 227 | 87434 | 148 | 01023403100000 | 8 |  | Adams | 2 MI.N.E. OF BIGLERVILLE |  | OPOSSUM CREEK |  | 79 | 99 | 32.8 | 64 | [25 empty] | Rural Minor Arterial | 79 | 20 | 99 | 32.8 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 7000 | 4 |  |  | 4000 | 2.73 | 10920 | 3 |  | 3000 | 2.73 | 8190 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | [5 empty] | 6 | 0 | 4 | 4 |  | 0 | 7500 | 0 | 34671 | 10000 | 4 | COMPLETE, pole offsets given in site visit notes, 7' Left and 6' Right
450 | -- | 243 | 90769 | 13948 | 21400100200000 | 8 |  | Cumberland | 2 MI.N. OF SHIPPENSBURG |  | MIDDLE SPRING CR. |  | 40 | 60 | 20.8 | 52 | [25 empty] | Rural Local | 40 | 20 | 60 | 20.8 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4000 | 2 |  |  | 2000 | 2.73 | 5460 | 2 |  | 2000 | 2.73 | 5460 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | [5 empty] | 3 | 0 | 4 | 4 |  | 0 | 7500 | 0 | 26481 | 10000 | 3 | COMPLETE, pole offsets given in site visit notes
451 | -- | 52 | 4194 | 20021 | 34007502501504 | 2 |  | Juniata | EAST WATERFORD |  | HORSE VALLEY RUN CREEK |  | 34 | 54 | 26.3 | 56 | [25 empty] | Rural Minor Arterial | 34 | 20 | 54 | 26.3 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 8000 | 5 |  |  | 5000 | 2.73 | 13650 | 2 |  | 2000 | 2.73 | 5460 | 1 |  | 1000 | 2.73 | 2730 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | 25 | 6 | 5.85 | IN ROW |  | 2 | 0 | 4 | 4 |  | 0 | 7500 | 0 | 37401 | 10000 | 4 | COMPLETE, pole offsets given in site visit notes | ELIMINATE 1 POLE NEAR PARKING LOT OF GAS/BANK PARKING LOT IF IT'S DETERMINED SHORING OF PARKING LOT IS NEEDED
452 | -- | 88 | 85402 | 30435 | 52402600220000 | 2 |  | Potter | ROULETTE |  | FISHING CREEK |  | 68 | 88 | 25.0 | 52 | [25 empty] | Rural Local | 68 | 20 | 88 | 25.0 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 4 | 1e-17 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 1e-17 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  | Gas line attached to bridge | 0 | 120.88 | 0 | [17 empty] | 0.5 |  |  |  | Noted in PennDOT notes, orientation/offset unknown | 88 | 191.55 | 16856.4 | [13 empty] | 88 |  |  |  | 1e-17 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 1e-17 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | 4" Gas | 1 | Yes | 88 | 0 | 1 | 11000 | 7 |  |  | 7000 | 2.73 | 19110 | 3 |  | 3000 | 2.73 | 8190 | 1 |  | 1000 | 2.73 | 2730 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | [5 empty] | 15 | 1 | 4 | 5 |  | 16856.4 | 7500 | 3 | 45591 | 10000 | 5 | COMPLETE, pole offsets in site visit notes, 15' Left, 2' Right, gas line size estimated from site visit photo
453 | -- | 111 | 6054 | 24751 | 41041400800000 | 3 |  | Lycoming | VILLAGE OF JERSEY MILLS |  | OVER CALLAHAN RUN |  | 23 | 43 | 25.7 | 52 | [25 empty] | Rural Major Collector | 23 | 20 | 43 | 25.7 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 8000 | 4 |  |  | 4000 | 2.73 | 10920 | 3 |  | 3000 | 2.73 | 8190 | 1 |  | 1000 | 2.73 | 2730 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | 25 | 10 | 2.15 | IN ROW |  | 10 | 0 | 4 | 4 |  | 0 | 7500 | 0 | 37401 | 10000 | 4 | COMPLETE, pole offset in site visit notes/sketches
454 | -- | 135 | 7542 | 33469 | 59100101101961 | 3 |  | Union | 2.5 MI W OF KELLY CROSSRD |  | OVER SPRUCE RUN |  | 35 | 55 | 24.5 | 52 | [25 empty] | Rural Major Collector | 35 | 20 | 55 | 24.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 5000 | 3 |  | PPL | 3000 | 2.73 | 8190 | 1 |  | 1000 | 2.73 | 2730 | 1 |  | 1000 | 2.73 | 2730 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | 25 |  |  |  |  | 0 | 0 | 4 | 4 |  | 0 | 7500 | 0 | 29211 | 10000 | 3 | COMPLETE, pole offset in site visit notes/sketch
455 | -- | 136 | 7542 | 33470 | 59100101102058 | 3 |  | Union | 2.5 MI W OF KELLY CROSSRD |  | OVER SPRUCE RUN |  | 32 | 52 | 25.5 | 52 | [25 empty] | Rural Major Collector | 32 | 20 | 52 | 25.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 4000 | 1 |  | PPL | 1000 | 2.73 | 2730 | 2 |  | 2000 | 2.73 | 5460 | 1 |  | 1000 | 2.73 | 2730 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | 25 |  |  |  |  | 7 | 0 | 4 | 4 |  | 0 | 7500 | 0 | 26481 | 10000 | 3 | COMPLETE, pole offset in site visit notes/sketch
456 | -- | 143 | 67514 | 29982 | 51200600100953 | 4 |  | Pike | DINGMAN TWP .2 M E TR 739 |  | DWARFKILL CREEK | 20143580171 | 28 | 48 | 23.7 | 52 | [25 empty] | Rural Local | 28 | 20 | 48 | 23.7 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 7000 | 4 |  |  | 4000 | 2.73 | 10920 | 1 |  | 1000 | 2.73 | 2730 | 2 |  | 2000 | 2.73 | 5460 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | 25 | 10 | 3.15 | IN ROW |  |  | 0 | 4 | 4 |  | 0 | 7500 | 0 | 34671 | 10000 | 4 | COMPLETE, pole offsets not given in site visit notes/sketch, poles appear to be further than 15' in photos
457 | -- | 222 | 87417 | 75 | 01003402700000 | 8 |  | Adams | IDAVILLE |  | BERMUDIAN CREEK |  | 26 | 46 | 25.9 | 64 | [25 empty] | Rural Minor Arterial | 26 | 20 | 46 | 25.9 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 8000 | 4 |  |  | 4000 | 2.73 | 10920 | 2 |  | 2000 | 2.73 | 5460 | 2 |  | 2000 | 2.73 | 5460 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | [5 empty] | 6 | 0 | 4 | 4 |  | 0 | 7500 | 0 | 37401 | 10000 | 4 | COMPLETE, pole offsets given in site visit notes, 6' Left and 7' Right
458 | -- | 255 | 87316 | 21196 | 36032201500954 | 8 |  | Lancaster | VILLAGE OF CLAY |  | MIDDLE CREEK |  | 35 | 55 | 45.0 | 64 | [25 empty] | Urban Principal Arterial | 35 | 20 | 55 | 45.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 8000 | 4 |  |  | 4000 | 2.73 | 10920 | 3 |  | 3000 | 2.73 | 8190 | 1 |  | 1000 | 2.73 | 2730 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | [6 empty] | 0 | 4 | 4 |  | 0 | 7500 | 0 | 37401 | 10000 | 4 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos
459 | -- | 313 | 21455 | 4044 | 05009602600000 | 9 |  | Bedford | MADLEY |  | WOLF CAMP RUN | 20143561445 | 54 | 74 | 25.8 | 54 | [25 empty] | Rural Major Collector | 54 | 20 | 74 | 25.8 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 3000 | 1 |  |  | 1000 | 2.73 | 2730 | 1 |  | 1000 | 2.73 | 2730 | 0 |  | 0 | 2.73 | 0 | 1 |  | 1000 | 2.73 | 2730 | 4 | 3890.25 | 15561 | 30 | [5 empty] | 0 | 4 | 4 |  | 0 | 7500 | 0 | 23751 | 10000 | 3 | No offsets given in site visit info. Poles appear to be near the end of wings based on pics.
460 | -- | 543 | 79402 | 36130 | 64013602502924 | 12 |  | Westmoreland | HEMPFIELD TOWNSHIP |  | BR. LITTLE SEWICKLEY CK. |  | 24 | 44 | 26.5 | 54 | [25 empty] | Urban Minor Arterial | 24 | 20 | 44 | 26.5 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | 2 |  | 1 |  |  |  | 44 | 249.45 | 10975.8 | [13 empty] | 44 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | 4" Consol Energy Gas OPS | 1 | Yes | 44 |  | 1 | 4200 | 3 |  |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 2 |  | 1200 | 2.73 | 3276 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 2 | 2 | 4 |  | 10975.8 | 7500 | 2 | 19246.5 | 10000 | 2 | OH lines offset 5' from the edge of bridge. Water line offset 10' from the edge of bridge. 4" to 6" gas line attached to the wings of the bridge on the same side as the water line.
461 | -- | 324 | 22626 | 8424 | 11016002000862 | 9 |  | Cambria | 0.2 MILE NORTH OF TR 869E |  | LAUREL RUN |  | 26 | 46 | 31.4 | 56 | [25 empty] | Rural Major Collector | 26 | 20 | 46 | 31.4 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 6000 | 2 |  |  | 2000 | 2.73 | 5460 | 2 |  | 2000 | 2.73 | 5460 | 2 |  | 2000 | 2.73 | 5460 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | 20 | [5 empty] | 0 | 4 | 4 |  | 0 | 7500 | 0 | 31941 | 10000 | 4 | OH lines on both sides of the bridge. No other utilities identified in site visit.
462 | -- | 550 | 98633 | 36331 | 64098201701219 | 12 |  | Westmoreland | UNITY TOWNSHIP |  | NINEMILE RUN | 20143571496 | 43 | 63 | 26.5 | 52 | [25 empty] | Rural Major Collector | 43 | 20 | 63 | 26.5 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  |  | 63 | 249.45 | 15715.35 | [13 empty] | 63 |  |  |  |  | 1 |  |  |  | 63 | 477.3 | 30069.9 | [13 empty] | 63 | [8 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1200 | 1 |  |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 2 | 1 | 3 |  | 45785.25 | 7500 | 7 | 7166.25 | 10000 | 1 | Water, WW, and OH lines located near the bridge in the site visit.
463 | -- | 331 | 22827 | 17832 | 29052202901545 | 9 |  | Fulton | 0.47 MILE NORTH FROM PA 928 |  | BIG COVE CREEK | 20143571746 | 75 | 95 | 26.0 | 54 | [25 empty] | Rural Minor Arterial | 75 | 20 | 95 | 26.0 | 30 | 24 | 54 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 6000 | 4 |  |  | 4000 | 2.73 | 10920 | 1 |  | 1000 | 2.73 | 2730 | 1 |  | 1000 | 2.73 | 2730 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | 30.00, 27.50 | [5 empty] | 0 | 4 | 4 |  | 0 | 7500 | 0 | 31941 | 10000 | 4 | OH on both sides of the roadway - 5' from edge of bridge on each side. No other utilities identified in site visit.
464 | -- | 553 | 89037 | 36389 | 64101700600042 | 12 |  | Westmoreland | LIGONIER TOWNSHIP |  | BRANCH OF HANNAS RUN |  | 23 | 43 | 27.0 | 48 | [25 empty] | Rural Major Collector | 23 | 20 | 43 | 27.0 | 24 | 24 | 48 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  |  | 43 | 249.45 | 10726.35 | [13 empty] | 43 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 1600 | 2 |  |  | 800 | 2.73 | 2184 | 1 |  | 400 | 2.73 | 1092 | 1 |  | 400 | 2.73 | 1092 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 1 | 1 | 2 |  | 10726.35 | 7500 | 2 | 8258.25 | 10000 | 1 | OH lines crossing over bridge at an angle. Water line identified by markers and FH in the site visit.
465 | -- | 555 | 79404 | 36481 | 64201201301481 | 12 |  | Westmoreland | MOUNT PLEASANT TOWNSHIP |  | BRINKER RUN |  | 24 | 44 | 26.4 | 50 | [25 empty] | Urban Collector | 24 | 20 | 44 | 26.4 | 26 | 24 | 50 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  |  | 44 | 249.45 | 10975.8 | [13 empty] | 44 | [8 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 3600 | 3 |  |  | 1800 | 2.73 | 4914 | 2 |  | 1200 | 2.73 | 3276 | 1 |  | 600 | 2.73 | 1638 | 0 |  | 0 | 2.73 | 0 | 2 | 3890.25 | 7780.5 | [6 empty] | 1 | 2 | 3 |  | 10975.8 | 7500 | 2 | 17608.5 | 10000 | 2 | OH lines located within 5' of the edge of bridge. Water line identified by markers within 5' of the edge of bridge during site visit.
466 | -- | 344 | 88158 | 45123 | 55003003602574 | 9 |  | Somerset | 2.44 MILE WEST FROM PA 160 |  | TRIB CALENDAR RUN |  | 12 | 32 | 26.0 | 64 | [25 empty] | Rural Principal Arterial | 12 | 20 | 32 | 26.0 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 | [6 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 5000 | 3 |  |  | 3000 | 2.73 | 8190 | 1 |  | 1000 | 2.73 | 2730 | 1 |  | 1000 | 2.73 | 2730 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | 25 | [5 empty] | 0 | 4 | 4 |  | 0 | 7500 | 0 | 29211 | 10000 | 3 | OH lines within 5' of edge of bridge. No other utilities identified.
467 | -- | 558 | 31699 | 36684 | 64400700200691 | 12 |  | Westmoreland | CITY OF JEANNETTE |  | BULL RUN |  | 28 | 48 | 33.5 | 56 | [25 empty] | Urban Collector | 28 | 20 | 48 | 33.5 | 32 | 24 | 56 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  |  | 48 | 249.45 | 11973.6 | [13 empty] | 48 |  |  |  |  | 1 |  |  |  | 48 | 477.3 | 22910.4 | [13 empty] | 48 | [8 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 2800 | 3 |  |  | 1200 | 2.73 | 3276 | 2 |  | 800 | 2.73 | 2184 | 2 |  | 800 | 2.73 | 2184 | 0 |  | 0 | 2.73 | 0 | 1 | 3890.25 | 3890.25 | [6 empty] | 2 | 1 | 3 |  | 34884 | 7500 | 5 | 11534.25 | 10000 | 2 | Water and WW lines identified in the roadway during the site visit. OH lines cross over the bridge at an angle.
468 | -- | 560 | 89049 | 37037 | 64801105100448 | 12 |  | Westmoreland | ROSTRAVER TOWNSHIP |  | POLLOCK RUN |  | 22 | 42 | 43.6 | 64 | [25 empty] | No Classification | 22 | 20 | 42 | 43.6 | 40 | 24 | 64 |  | 1e-17 | 1e-28 | 1e-30 |  |  | 1 |  |  |  | 42 | 249.45 | 10476.9 | [13 empty] | 42 |  |  |  |  | 1 |  |  |  | 42 | 477.3 | 20046.6 | [13 empty] | 42 |  |  |  |  | 1 |  | Peoples Natural Gas | Sitting on wings | 42 | 120.88 | 5076.96 | [13 empty] | 42 | [8 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 0 | 0 | 0 |  |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 |  | 0 | 2.73 | 0 | 0 | 3890.25 | 0 | [6 empty] | 3 | 0 | 3 |  | 35600.46 | 7500 | 5 | 0 | 10000 | 0 | 4" to 6" gas line sits on wings. Water and WW lines located near the bridge. No OH line identified near the bridge during the site visit.
469 | -- | 361 | 24000 | 3169 | 03200101402192 | 10 |  | Armstrong | RURAL VALLEY NO.3 |  | COWANSHANNOCK CREEK |  | 116 | 136 | 31.2 | 52 | [25 empty] | Rural Local | 116 | 20 | 136 | 31.2 | 28 | 24 | 52 |  | 1e-17 | 1e-28 | 1e-30 | 2 | [5 empty] | 0 | 249.45 | 0 | [22 empty] | 0 | 477.3 | 0 | [22 empty] | 0 | 120.88 | 0 | [22 empty] | 0 | 191.55 | 0 | [22 empty] | 0 | 32.1 | 0 | [8 empty] | 0 | 25.68 | 0 | [8 empty] | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 |  | 1 | 4000 | 1 |  |  | 1000 | 2.73 | 2730 | 2 |  | 2000 | 2.73 | 5460 | 1 |  | 1000 | 2.73 | 2730 | 0 |  | 0 | 2.73 | 0 | 4 | 3890.25 | 15561 | [6 empty] | 0 | 4 | 4 |  | 0 | 7500 | 0 | 26481 | 10000 | 3 | OH lines on each side of the bridge. Water line located 40'+ offset from the bridge - no impact.
470 | -- | 140 | 67364 | 23795 | 40011501200000 | 4 |  | Luzerne | BEAR CR TW 1.2M S SR 2038 |  | SHADES CREEK |  | 27 | 47 | 40.0 | 60 | [25 empty] | Rural Minor Arterial | 27 | 20 | 47 | 40.0 | 36 | 24 | 60 |  | 1e-17 | 1e-28 | 1e-30 | 2 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 12000 | 5 |  |  | 5000 | 2.73 | 13650 | 4 |  | 4000 | 2.73 | 10920 | 1 |  | 1000 | 2.73 | 2730 | 2 |  | 2000 | 2.73 | 5460 | 4 | 3890.25 | 15561 | 50 |  |  |  |  | 4 | 0 | 4 | 4 |  | 0 | 7500 | 0 | 48321 | 10000 | 5 | COMPLETE, pole offsets in site visit notes/sketch
471 | -- | 254 | 87315 | 21043 | 36003004802322 | 8 |  | Lancaster | LEAMAN PLACE |  | ESHELMAN'S RUN |  | 67 | 87 | 56.8 | 76 | [25 empty] | Urban Principal Arterial | 67 | 20 | 87 | 56.8 | 52 | 24 | 76 |  | 1e-17 | 1e-28 | 1e-30 | 0 | 0 |  |  |  |  | 0 | 249.45 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 477.3 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 120.88 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 |  |  |  |  | 0 | 32.1 | 0 |  |  |  | 0 |  |  |  |  | 0 | 25.68 | 0 |  |  |  | 0 |  |  |  |  | 0 | 56.12 | 0 | [17 empty] | None | 0 | None | 0 | 0 | 1 | 14000 | 5 |  |  | 5000 | 2.73 | 13650 | 4 |  | 4000 | 2.73 | 10920 | 4 |  | 4000 | 2.73 | 10920 | 1 |  | 1000 | 2.73 | 2730 | 4 | 3890.25 | 15561 | [6 empty] | 0 | 4 | 4 |  | 0 | 7500 | 0 | 53781 | 10000 | 6 | COMPLETE, pole offsets not given in site visit notes, no sketch, poles appear closer than 15' in photos
| R | 105 | #N/A | 12745 | 19403600120000 | 3 |  | Columbia | TOWN OF BLOOMSBURG |  | OVER HEMLOCK CREEK |  | 0 | 0 | 0 | 0 | [25 empty] | Urban Major Collector | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [5 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [5 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | N/A | N/A | N/A | N/A | 0 | 1e-17 | 1e-30 | 1e-17 | N/A | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 |  |  | N/A |  |  |  | N/A |  | 0 | 0 | 0 | N/A
| R | 193 | #N/A | 27022 | 45301500201644 | 5 |  | Monroe | ROLLING HILLS ROAD |  | AQUASHICOLA CREEK |  | 0 | 0 | 0 | 0 | [25 empty] | Rural Local | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [5 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [5 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | N/A | N/A | N/A | N/A | 0 | 1e-17 | 1e-30 | 1e-17 | N/A | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 |  |  | N/A |  |  |  | N/A |  | 0 | 0 | 0 | N/A
| R | 199 | #N/A | 42278 | 48003301200000 | 5 |  | Northampton | 0.5 MI S OF PA 191 EXIT |  | BUSHKILL CREEK |  | 0 | 0 | 0 | 0 | [25 empty] | Urban Freeways/Expressways/Interstates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [5 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [5 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | N/A | N/A | N/A | N/A | 0 | 1e-17 | 1e-30 | 1e-17 | N/A | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 |  |  | N/A |  |  |  | N/A |  | 0 | 0 | 0 | N/A
| R | 200 | #N/A | 42446 | 48003301210000 | 5 |  | Northampton | 0.5MI S OF PA 191 EXIT |  | BUSHKILL CREEK |  | 0 | 0 | 0 | 0 | [25 empty] | Urban Freeways/Expressways/Interstates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [5 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [5 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | N/A | N/A | N/A | N/A | 0 | 1e-17 | 1e-30 | 1e-17 | N/A | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 |  |  | N/A |  |  |  | N/A |  | 0 | 0 | 0 | N/A
| R | 400 | #N/A | 41065 | 02013000420000 | 11 |  | Allegheny | 1 1/2 MILES E. OF PA 8 |  | ABANDONED RR |  | 0 | 0 | 0 | 0 | [25 empty] | Urban Principal Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [5 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [5 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | N/A | N/A | N/A | N/A | 0 | 1e-17 | 1e-30 | 1e-17 | N/A | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 |  |  | N/A |  |  |  | N/A |  | 0 | 0 | 0 | N/A
| R | 401 | #N/A | 41066 | 02013000420165 | 11 |  | Allegheny | 1 1/2 MILES E. OF PA 8 |  | ABANDONED RR |  | 0 | 0 | 0 | 0 | [25 empty] | Urban Principal Arterial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | 0 | 0 | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [5 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [5 empty] | 1e-17 | 0 | N/A | N/A | N/A | 1e-30 | [19 empty] | N/A | N/A | N/A | N/A | 0 | 1e-17 | 1e-30 | 1e-17 | N/A | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 | N/A | 1e-30 |  |  | 1e-17 |  |  | N/A |  |  |  | N/A |  | 0 | 0 | 0 | N/A
#N/A
|  |  | #N/A | [39 empty] | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | [5 empty] | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ | [5 empty] | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ | [5 empty] | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  |  | ~~~~~~~~~~~~ |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | [19 empty] | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~
|  |  | #N/A | [5 empty] | TOTAL | [33 empty] | 28724 | 11500 | 40224 | [5 empty] | 13 | 500 | 5000 | 634 | 41.5 | 92 |  |  |  | 5498 |  |  | 0 | 0 | 50 | 0 | 338 | 50 | 0 | 98 | 0 | 38 | 0 | 0 | 0 | 4924 |  |  |  | 24.75 | 60 |  |  |  | 4139 |  | 1975544.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 109 | 3995 |  |  |  | 69.75 | 100 |  |  |  | 6130 |  |  | 61 | 45 | 493 | 0 | 122 | 360 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 4950 |  |  |  | 4.5 | 4 |  |  |  | 368 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 |  |  |  | 0.75 | 22 |  |  |  | 1432 | [5 empty] | 3.25 | 9 |  |  |  | 548 | [5 empty] | 12.5 | 9 |  |  |  | 614 |  |  | 46 | 0 | 52 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466 |  |  |  |  | 65 |  | 6541 | 5 | 421.5 | 1363600 | 1026 |  |  | 630400 |  |  | 753 |  | 441200 |  |  | 442 |  | 258400 |  |  | 45 |  | 33600 |  |  | 829 | [18 empty] | 0 | 0 | 0 | 198551 | 0 | 0 | 0
#N/A
|  |  | #N/A | [5 empty] | ECB's | [33 empty] | 5134 | 2080 | 7214 | [5 empty] | 2 | 65 | 650 | 135 | 18.5 | 10 |  |  |  | 537 |  |  | 0 | 0 | 50 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187 |  |  |  | 11 | 9 |  |  |  | 857 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 857 |  |  |  | 15.5 | 22 |  |  |  | 1111 |  |  | 61 | 0 | 350 | 0 | 50 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 |  |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 1 |  |  |  | 45 | [5 empty] | 0 | 1 |  |  |  | 50 | [5 empty] | 0.5 | 1 |  |  |  | 50 |  |  | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 21 |  | 1748 | 1 | 73.5 | 126800 | 95 |  |  | 40800 |  |  | 108 | 0 | 46000 |  |  | 93 | 0 | 39600 |  |  | 1 | 0 | 400 |  |  | 152
|  |  | #N/A | [5 empty] | REMAINING BRIDGES | [33 empty] | 23530 | 9380 | 32910 | [5 empty] | 11 | 435 | 4350 | 493 | 23 | 82 |  |  |  | 4961 |  |  | 0 | 0 | 0 | 0 | 38 | 50 | 0 | 98 | 0 | 38 | 0 | 0 | 0 | 4737 |  |  |  | 13.75 | 50 |  |  |  | 3202 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 109 | 3058 |  |  |  | 53.25 | 77 |  |  |  | 4969 |  |  | 0 | 45 | 143 | 0 | 72 | 110 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 4500 |  |  |  | 4.5 | 4 |  |  |  | 368 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 |  |  |  | 0.75 | 21 |  |  |  | 1387 | [5 empty] | 3.25 | 8 |  |  |  | 498 | [5 empty] | 12 | 8 |  |  |  | 564 |  |  | 46 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466 |  |  |  |  | 43 |  | 4737 | 4 | 346 | 1230000 | 927 |  |  | 587600 |  |  | 640 | 0 | 392800 |  |  | 344 | 0 | 216400 |  |  | 44 | 0 | 33200 |  |  | 673
|  |  | #N/A | [39 empty] | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | [5 empty] | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ | [5 empty] | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ | [5 empty] | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  |  |  | ~~~~~~~~~~~~ |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ | ~~~~~~~~~~~~ |  |  | ~~~~~~~~~~~~
|  |  | #N/A | [5 empty] | TOTAL | [33 empty] | 28664 | 11460 | 40124 | [5 empty] | 13 | 500 | 5000 | 628 | 41.5 | 92 |  |  |  | 5498 |  | 1371476.1 | 0 | 0 | 50 | 0 | 338 | 50 | 0 | 98 | 0 | 38 | 0 | 0 | 0 | 4924 |  |  |  | 24.75 | 59 |  |  |  | 4059 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 109 | 3915 |  |  |  | 68.75 | 99 |  |  |  | 6080 |  | 740994.4 | 61 | 45 | 493 | 0 | 122 | 310 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 4950 |  |  |  | 4.5 | 4 |  |  |  | 368 |  | 70490.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 |  |  |  | 0.75 | 22 |  |  |  | 1432 |  | 45967.2 |  |  |  | 3.25 | 9 |  |  |  | 548 |  | 14072.64 |  |  |  | 12.5 | 9 |  |  |  | 614 |  | 34457.68 | 46 | 0 | 52 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466 |  |  |  |  | 64 |  | 6485 | 5 | 419.5 | 1356800 | 1022 |  |  | 628400 |  | 1720992 | 748 | 0 | 438800 |  | 1204476 | 437 | 0 | 256000 |  | 705432 | 45 | 0 | 33600 |  | 91728 | 825 |  | 3225017.25
[14 empty] | Final D-419 |  |  | Conditional D-419
MPMS |  |  |  |  | Bridge ID | [8 empty] | MPMS | DATE
97120 |  |  |  |  | 20000604100000 | [5 empty] | 35401900200731 | 20143521244 |  | 99281 | 2014-06-23 |  | 98939 | 41813
90155 |  |  |  |  | 20000608400273 | [5 empty] | 57010601220638 | 20143561405 |  | 5093 | 2014-06-24 |  | 78822 | 41810
97121 |  |  |  |  | 20028501000629 | [5 empty] | 45020900401748 | 20143561422 |  | 76863 | 2014-04-09 |  | 6057 | 41810
97117 |  |  |  |  | 20040801800428 | [5 empty] | 36105500202673 | 20143561430 |  | 5210 | 2014-06-19 |  | 96726 | 41816
97118 |  |  |  |  | 20040805201643 | [5 empty] | 05005600901305 | 20143561437 |  | 5039 | 2014-02-20 |  | 96727 | 41814
89176 |  |  |  |  | 20088601600750 | [5 empty] | 05009602600000 | 20143561445 |  | 5208 | 2014-05-23 |  | 68927 | 41814
97124 |  |  |  |  | 20401100200000 | [5 empty] | 05086901201328 | 20143561454 |  | 5215 | 2014-05-01 |  | 79580 | 41815
1140 |  |  |  |  | 25401100800860 | [5 empty] | 11016002200000 | 20143561462 |  | 5578 | 2014-04-23 |  | 85724 | 41815
74663 |  |  |  |  | 27006201302194 | [5 empty] | 29052201600330 | 20143561474 |  | 7021 | 2014-06-24 |  | 79606 | 41814
1370 |  |  |  |  | 27066600700000 | [5 empty] | 02100102101194 | 20143580503 |  | 74043 | 2014-06-04 |  | 24153 | 41815
93595 |  |  |  |  | 27066600900000 | [5 empty] | 04302700400000 | 20143570586 |  | 83478 | 2014-04-07 |  | 24667 | 41820
1398 |  |  |  |  | 27066601100240 | [5 empty] | 37301500201288 | 20143571138 |  | 7347 | 2014-06-24 |  | 27419 | 41817
97328 |  |  |  |  | 43017304703518 | [5 empty] | 26105000101121 | 20143571183 |  | 7136 | 2014-05-28 |  | 63343 | 41817
1686 |  |  |  |  | 43031801500622 | [5 empty] | 26105801300864 | 20143571250 |  | 79055 | 2014-05-20 |  | 63513 | 41816
58092 |  |  |  |  | 43302001700000 | [5 empty] | 30001802400670 | 20143571263 |  | 7251 | 2014-01-08 |  | 63324 | 41815
93160 |  |  |  |  | 60042702200000 | [5 empty] | 30018800300000 | 20143571273 |  | 74037 | 2014-06-05 |  | 63356 | 41816
2251 |  |  |  |  | 60201301000000 | [5 empty] | 30018801800000 | 20143571371 |  | 74022 | 2014-06-04 |  | 63547 | 41814
97457 |  |  |  |  | 61000603502233 | [5 empty] | 30300600100674 | 20143571385 |  | 6049 | 2014-06-25 |  | 28446 | 41817
2438 |  |  |  |  | 61000603900000 | [5 empty] | 30301300900000 | 20143571401 |  | 98939 | 2014-09-25 |  | 74338 | 41820
2546 |  |  |  |  | 61000608200000 | [5 empty] | 17005306400000 | 20143580396 |  | 78822 | 2014-09-17 |  | 27287 | 41817
2580 |  |  |  |  | 61002705203359 | [5 empty] | 42077001400000 | 20143580408 |  | 6057 | 2014-09-17 |  | 63344 | 41820
2548 |  |  |  |  | 61012700902381 | [5 empty] | 31065505400533 | 20143580408 |  | 96726 | 2014-12-15 |  | 78223 | 41820
84954 |  |  |  |  | 61095701700981 | [5 empty] | 31091301901896 | 20143580425 |  | 96727 | 2014-12-15
97452 |  |  |  |  | 61301000600428 | [5 empty] | 55052300301840 | 20143580432 |  | 68927 | 2014-12-15
85095 |  |  |  |  | 12012000400000 | [5 empty] | 10301000600000 | 20143571422 |  | 79580 | 2014-12-15
88201 |  |  |  |  | 14004507902031 | [5 empty] | 26016603900000 | 20143571450/20143571452 |  | 68917 | 2014-06-19
88155 |  |  |  |  | 14014403400099 | [5 empty] | 64098201701219 | 20143571496 |  | 56752 | 2014-06-19
85135 |  |  |  |  | 14100200501555 | [5 empty] | 02204500300840 | 20143571433 |  | 68786 | 2014-06-19
81359 |  |  |  |  | 14100200801726 | [5 empty] | 46404200341011 | 20143571505 |  | 68806 | 2014-06-19
2893 |  |  |  |  | 14201300100000 | [5 empty] | 36101900500000 | 20143571514 |  | 85782 | 2014-06-19
85125 |  |  |  |  | 14304001301062 | [5 empty] | 38402000800000 | 20143571525 |  | 9719 | 2014-06-19
85128 |  |  |  |  | 14304001500701 | [5 empty] | 61301000600428 | 20143571624 |  | 85724 | 2014-11-05
88199 |  |  |  |  | 14304003701668 | [5 empty] | 47025400200000 | 20143571637 |  | 79157 | 2014-04-11
91413 |  |  |  |  | 14400200702338 | [5 empty] | 06100601100107 | 20143571648/20143571649 |  | 11649 | 2014-06-06
3195 |  |  |  |  | 14400600100000 | [5 empty] | 36202000100000 | 20143571656 |  | 79170 | 2014-04-24
69443 |  |  |  |  | 17005306400000 | [5 empty] | 36204500700000 | 20143571667/20143571668 |  | 96447 | 2014-06-19
91508 |  |  |  |  | 17021902800000 | [5 empty] | 66012402502532 | 20143571677 |  | 91680 | 2014-05-08
85076 |  |  |  |  | 17021904201459 | [5 empty] | 29052201601370 | 20143571735 |  | 79606 | 2014-12-19
85079 |  |  |  |  | 17021904602606 | [5 empty] | 29052202901545 | 20143571746 |  | 24153 | 2014-12-02
93323 |  |  |  |  | 17021904700185 | [5 empty] | 31002604900654 | 20143571761 |  | 24667 | 2014-09-25
93372 |  |  |  |  | 17025502200000 | [5 empty] | 31469 | 20143571775 |  | 83335 | 2014-06-23
88626 |  |  |  |  | 17025503200000 | [5 empty] | 55201301000000 | 20143580119 |  | 27419 | 2014-12-19
89978 |  |  |  |  | 17100900401885 | [5 empty] | 62023104300092 | 20143580124/20143580125 |  | 63343 | 2014-11-21
3571 |  |  |  |  | 17200703101047 | [5 empty] | 62202300800032 | 20143580131 |  | 63513 | 2014-11-14
85119 |  |  |  |  | 17300902501042 | [5 empty] | M | 20143580136 |  | 63324 | 2014-10-17
91510 |  |  |  |  | 18015000701624 | [5 empty] | 01200600400591 | 20143580152 |  | 63356 | 2014-10-07
69040 |  |  |  |  | 18047700300000 | [5 empty] | 51200600100953 | 20143580171 |  | 63547 | 2014-12-03
85152 |  |  |  |  | 24012002801546 | [5 empty] | 02013600500000 | 20143580439 |  | 28446 | 2014-12-17
69088 |  |  |  |  | 24021900201858 | [5 empty] | 02013601202172 | 20143580328 |  | 74338 | 2014-11-24
88185 |  |  |  |  | 24021904900000 | [5 empty] | 02097800300000 | 20143580332 |  | 27287 | 2014-12-23
88195 |  |  |  |  | 34003507200000 | [5 empty] | 02200100800335 | 20143580442 |  | 63344 | 2014-11-04
4194 |  |  |  |  | 34007502501504 | [5 empty] | 02201000102238 | 20143580340 |  | 78223 | 2014-11-13
4214 |  |  |  |  | 34100200200000 | [5 empty] | 20040801800428 | 20143580160 |  | 76089 | 2014-06-03
4218 |  |  |  |  | 34100400300549 | [5 empty] | 08022001301099 | 20143580167 |  | 31601 | 2014-05-29
81508 |  |  |  |  | 34200601501696 | [5 empty] | 57026703202704 | 20143580177 |  | 74418 | 2014-06-03
91518 |  |  |  |  | 34200701400000 | [5 empty] | 57070602700000 | 20143580198 |  | 31826 | 2014-06-09
78606 |  |  |  |  | 42000605100562 | [5 empty] | 05102000500880 | 20143580298 |  | 31614 | 2014-06-09
78605 |  |  |  |  | 42000605800309 | [5 empty] | 07101302500908 | 20143580307 |  | 76122 | 2014-06-16
4344 |  |  |  |  | 42004600600000 | [5 empty] | 55201800600000 | 20143580311 |  | 31611 | 2014-06-16
88664 |  |  |  |  | 42005904500000 | [5 empty] | 03205700100245 | 20143580317 |  | 31304 | 2014-05-29
88183 |  |  |  |  | 42015500200000 | [5 empty] | 03300900800000 | 20143580322 |  | 79418 | 2014-07-08
85215 |  |  |  |  | 42015501900182 | [5 empty] | 26104300200093 | 20143580347/20143580348 |  | 91189 | 2014-06-09
4341 |  |  |  |  | 42015502701162 | [5 empty] | 17200703101047 | 20143580324
85259 |  |  |  |  | 42015502900238 | [5 empty] | 18047700300000 | 20143580327
85234 |  |  |  |  | 42034604101617 | [5 empty] | 24021900201858 | 20143580336
4336 |  |  |  |  | 42034604201811 | [5 empty] | 42200100100806 | 20143580345
85237 |  |  |  |  | 42064602900000 | [5 empty] | 52004904300530 | 20143580428
4340 |  |  |  |  | 42077001300784 | [5 empty] | 36002300301231 | 20143580433/20143580434
88630 |  |  |  |  | 42077001400000 | [5 empty] | 36077204500174 | 20143580443
68965 |  |  |  |  | 42101500100472 | [5 empty] | 26038100801000 | 20143580452
4486 |  |  |  |  | 42200100100806 | [5 empty] | 26105801300142 | 20143580467/20143580470
78611 |  |  |  |  | 42200200320000 | [5 empty] | 57101801302350 | 20143580483
93322 |  |  |  |  | 42401100102339 | [5 empty] | 63019106701296 | 20143580183
4642 |  |  |  |  | 44065502201820 | [5 empty] | 39204900302189 | 20143580203
85297 |  |  |  |  | 44065502300022 | [5 empty] | 09203701900000 | 20143580217
4676 |  |  |  |  | 44100200800896 | [5 empty] | 28027400200000 | 20143580224
4677 |  |  |  |  | 44100201200618 | [5 empty] | 10400201302768 | 20143580231
85275 |  |  |  |  | 44401300500000 | [5 empty] | 32095403700000 | 20143580238
88640 |  |  |  |  | 52000602300000 | [5 empty] | 04302500701409 | 20143580299
69501 |  |  |  |  | 52004402700000 | [5 empty] | 30101101500501 | 20143580303/20143580304
93375 |  |  |  |  | 52004408101925 | [5 empty] | 30201600701702 | 20143580312
85309 |  |  |  |  | 52004409500000 | [5 empty] | 55052300801065 | 20143580320
4805 |  |  |  |  | 52004410100000
4897 |  |  |  |  | 52004904300530
4898 |  |  |  |  | 52004904400406
4899 |  |  |  |  | 52044900501401
93373 |  |  |  |  | 52200201302331
85402 |  |  |  |  | 52402600220000
83457 |  |  |  |  | 08001403400602
99281 |  |  |  |  | 08018704000000
5038 |  |  |  |  | 08022001301099
5093 |  |  |  |  | 08036700101794
79247 |  |  |  |  | 08041403800000
76863 |  |  |  |  | 08046700100052
5210 |  |  |  |  | 08046702700000
5039 |  |  |  |  | 08051402000863
5208 |  |  |  |  | 08070601701340
5215 |  |  |  |  | 08070602601160
98535 |  |  |  |  | 08105900700582
5218 |  |  |  |  | 08401302501496
5589 |  |  |  |  | 19004402401397
98939 |  |  |  |  | 19025402500486
5578 |  |  |  |  | 19048703700177
78822 |  |  |  |  | 19403101120000
91436 |  |  |  |  | 41001500702198
6049 |  |  |  |  | 41004403440880
6023 |  |  |  |  | 41008700600000
6145 |  |  |  |  | 41011801700622
6045 |  |  |  |  | 41041400100417
6054 |  |  |  |  | 41041400800000
6057 |  |  |  |  | 41200200320000
6052 |  |  |  |  | 41201501720000
74022 |  |  |  |  | 41205000120000
6144 |  |  |  |  | 41206101702204
6387 |  |  |  |  | 47025400200000
6381 |  |  |  |  | 47100600100570
74037 |  |  |  |  | 47100600500000
97586 |  |  |  |  | 49102700400616
6669 |  |  |  |  | 49200100200000
79230 |  |  |  |  | 49402000301775
6603 |  |  |  |  | 49402200101591
88047 |  |  |  |  | 49402600100165
88799 |  |  |  |  | 54102300401962
89977 |  |  |  |  | 56008701100148
7021 |  |  |  |  | 56008705202440
7009 |  |  |  |  | 56015401501564
7326 |  |  |  |  | 58004901400434
7251 |  |  |  |  | 58024903220000
87929 |  |  |  |  | 58054902602539
79055 |  |  |  |  | 58300103901413
7136 |  |  |  |  | 58300500400000
7347 |  |  |  |  | 58401702800000
83470 |  |  |  |  | 58403501300426
7542 |  |  |  |  | 59100101101961
7542 |  |  |  |  | 59100101102058
83478 |  |  |  |  | 59100300200000
74043 |  |  |  |  | 59300202000501
96689 |  |  |  |  | 35401900200731
67364 |  |  |  |  | 40011501200000
97506 |  |  |  |  | 40800500201030
96726 |  |  |  |  | 51100700301853
67514 |  |  |  |  | 51200600100953
96737 |  |  |  |  | 57001104601461
89023 |  |  |  |  | 57010601220638
9719 |  |  |  |  | 57026703200000
79572 |  |  |  |  | 57026703202704
9656 |  |  |  |  | 57037400502476
96729 |  |  |  |  | 57070602700000
100550 |  |  |  |  | 57085800500000
85782 |  |  |  |  | 57100700500000
96734 |  |  |  |  | 57101801302350
96727 |  |  |  |  | 57200800203639
9679 |  |  |  |  | 57202100501583
96736 |  |  |  |  | 57400201300000
68876 |  |  |  |  | 63019106701296
9969 |  |  |  |  | 63029601800000
68917 |  |  |  |  | 63101801602046
68927 |  |  |  |  | 63200700301844
67584 |  |  |  |  | 63300601600000
56752 |  |  |  |  | 63401401300733
79580 |  |  |  |  | 63403302600090
9978 |  |  |  |  | 63403703303161
10230 |  |  |  |  | 65026700100659
10243 |  |  |  |  | 65029201500354
68786 |  |  |  |  | 65100100500000
68806 |  |  |  |  | 65200100500596
79078 |  |  |  |  | 06062501301318
78877 |  |  |  |  | 06100400100619
78889 |  |  |  |  | 06100601100107
85635 |  |  |  |  | 06100800300000
79081 |  |  |  |  | 06300900701675
85764 |  |  |  |  | 13020902602676
85762 |  |  |  |  | 13401000501489
85693 |  |  |  |  | 39022202103224
89633 |  |  |  |  | 39100400202044
85683 |  |  |  |  | 39204900302189
89639 |  |  |  |  | 39622200303519
85811 |  |  |  |  | 45020900401748
91680 |  |  |  |  | 45020903110000
79157 |  |  |  |  | 45031401101750
79158 |  |  |  |  | 45039000300932
11649 |  |  |  |  | 45061105100000
11730 |  |  |  |  | 45071500201751
96445 |  |  |  |  | 45090300200000
85879 |  |  |  |  | 45094000701313
89628 |  |  |  |  | 45094001400882
79204 |  |  |  |  | 45094003900000
79170 |  |  |  |  | 45100400300941
76368 |  |  |  |  | 45200900101729
96447 |  |  |  |  | 45300900220000
11758 |  |  |  |  | 45301100300000
79185 |  |  |  |  | 45302301202040
85849 |  |  |  |  | 45400300702976
79187 |  |  |  |  | 45400600200000
99555 |  |  |  |  | 48003300200000
99555 |  |  |  |  | 48003300210000
85947 |  |  |  |  | 48051202101582
67256 |  |  |  |  | 48100400601655
12098 |  |  |  |  | 48101500801677
12717 |  |  |  |  | 53033902000276
12710 |  |  |  |  | 53033902400902
12710 |  |  |  |  | 53033902401098
85810 |  |  |  |  | 53092400702725
85724 |  |  |  |  | 53401600100000
47695 |  |  |  |  | 53403600300000
12522 |  |  |  |  | 53403900200000
56830 |  |  |  |  | 09203701900000
81284 |  |  |  |  | 15304401300000
86306 |  |  |  |  | 15400800402407
15232 |  |  |  |  | 23042000701072
102315 |  |  |  |  | 46066302700894
102218 |  |  |  |  | 46201300320000
86343 |  |  |  |  | 46202700500209
67373 |  |  |  |  | 46304400500389
81290 |  |  |  |  | 46404200341011
87428 |  |  |  |  | 1003003000000
87427 |  |  |  |  | 01003402200745
87417 |  |  |  |  | 01003402700000
87673 |  |  |  |  | 01009701000240
18051 |  |  |  |  | 01011601100000
99774 |  |  |  |  | 01019402401689
87436 |  |  |  |  | 01023401202343
87434 |  |  |  |  | 01023403100000
18146 |  |  |  |  | 01039400600526
87676 |  |  |  |  | 01101400501701
87671 |  |  |  |  | 01101601101587
74951 |  |  |  |  | 01200600400591
87675 |  |  |  |  | 01301301000061
87437 |  |  |  |  | 01400500101339
87438 |  |  |  |  | 01400601202897
90784 |  |  |  |  | 01401100101013
90694 |  |  |  |  | 21001105202844
87424 |  |  |  |  | 21003400700827
90695 |  |  |  |  | 21023300900266
89274 |  |  |  |  | 21023303801454
74054 |  |  |  |  | 21099702601555
90739 |  |  |  |  | 21203100100000
102789 |  |  |  |  | 21203100100187
74055 |  |  |  |  | 21301900100000
90769 |  |  |  |  | 21400100200000
90770 |  |  |  |  | 21400800302148
100078 |  |  |  |  | 22101800101692
47519 |  |  |  |  | 22201200100356
87457 |  |  |  |  | 22400400202505
87686 |  |  |  |  | 28023302000092
63173 |  |  |  |  | 28027400200000
87683 |  |  |  |  | 28099706500000
78710 |  |  |  |  | 28400801900060
78708 |  |  |  |  | 28400802301142
19965 |  |  |  |  | 36002300301231
87315 |  |  |  |  | 36003004802322
87316 |  |  |  |  | 36032201500954
87536 |  |  |  |  | 36034003700000
87554 |  |  |  |  | 36034003801674
19915 |  |  |  |  | 36037204240000
87505 |  |  |  |  | 36046202200000
91194 |  |  |  |  | 36062501302573
78868 |  |  |  |  | 36077204500174
91266 |  |  |  |  | 36101900500000
87521 |  |  |  |  | 36102100420000
74958 |  |  |  |  | 36102402100000
19927 |  |  |  |  | 36102500801639
100523 |  |  |  |  | 36103400200000
63230 |  |  |  |  | 36103501500846
20124 |  |  |  |  | 36103702100000
87706 |  |  |  |  | 36103900500000
91323 |  |  |  |  | 36104800500000
87515 |  |  |  |  | 36105300200000
87566 |  |  |  |  | 36105500202673
91324 |  |  |  |  | 36200200602329
87516 |  |  |  |  | 36200500300000
20123 |  |  |  |  | 36201000560000
87562 |  |  |  |  | 36201200320000
91108 |  |  |  |  | 36201500400000
19964 |  |  |  |  | 36202000100000
87518 |  |  |  |  | 36202000200000
87501 |  |  |  |  | 36204500700000
19812 |  |  |  |  | 36300400200000
63229 |  |  |  |  | 36301702401388
20151 |  |  |  |  | 36303201100000
91352 |  |  |  |  | 38402000800000
87462 |  |  |  |  | 50001100300893
93582 |  |  |  |  | 50001701101051
79054 |  |  |  |  | 50001707600000
73961 |  |  |  |  | 50007401900530
87465 |  |  |  |  | 50085002201839
90716 |  |  |  |  | 50085002501777
87491 |  |  |  |  | 50101502002360
101098 |  |  |  |  | 50300600100014
79042 |  |  |  |  | 50301700100000
79047 |  |  |  |  | 50400701001472
91353 |  |  |  |  | 66012401400000
87693 |  |  |  |  | 66012402502532
91191 |  |  |  |  | 66042504600314
78860 |  |  |  |  | 66061601000255
87551 |  |  |  |  | 66061601001014
78878 |  |  |  |  | 66092100900000
78896 |  |  |  |  | 66202800800249
87695 |  |  |  |  | 66202900902536
91367 |  |  |  |  | 66304500800853
87596 |  |  |  |  | 66305100200000
87595 |  |  |  |  | 66307100100000
74944 |  |  |  |  | 66400102102301
83428 |  |  |  |  | 66401200602478
90222 |  |  |  |  | 66403300403136
91192 |  |  |  |  | 66405100300581
88114 |  |  |  |  | 05003001000907
21558 |  |  |  |  | 05003001100000
21563 |  |  |  |  | 05005600901305
21455 |  |  |  |  | 05009602600000
88121 |  |  |  |  | 05086901201328
21596 |  |  |  |  | 05101100400000
21552 |  |  |  |  | 05101200400000
21600 |  |  |  |  | 05102000500880
74424 |  |  |  |  | 05403101601407
22107 |  |  |  |  | 07101302400000
74376 |  |  |  |  | 07101302500908
21957 |  |  |  |  | 07101303601234
21961 |  |  |  |  | 07300500100050
21967 |  |  |  |  | 07403100301171
22626 |  |  |  |  | 11016002000862
22627 |  |  |  |  | 11016002200000
22444 |  |  |  |  | 11102601101804
22797 |  |  |  |  | 29048400101102
22798 |  |  |  |  | 29052201401573
22825 |  |  |  |  | 29052201600330
22826 |  |  |  |  | 29052201601370
22827 |  |  |  |  | 29052202901545
22832 |  |  |  |  | 29065503900454
88142 |  |  |  |  | 29065504501203
22837 |  |  |  |  | 29100100100266
74433 |  |  |  |  | 31002202300000
23030 |  |  |  |  | 31002604900654
22980 |  |  |  |  | 31002605100972
23039 |  |  |  |  | 31065505400533
23038 |  |  |  |  | 31091301901896
23058 |  |  |  |  | 31100800400000
23114 |  |  |  |  | 31101900100185
74449 |  |  |  |  | 31101900600000
23116 |  |  |  |  | 31400900200000
88158 |  |  |  |  | 55003003602574
92698 |  |  |  |  | 55003003702626
23517 |  |  |  |  | 55003104200000
23586 |  |  |  |  | 55052300301840
23410 |  |  |  |  | 55052300701200
74446 |  |  |  |  | 55052300801065
23516 |  |  |  |  | 55100400101850
23571 |  |  |  |  | 55100700300000
23588 |  |  |  |  | 55100701800000
74467 |  |  |  |  | 55200500300000
23428 |  |  |  |  | 55201301000000
23549 |  |  |  |  | 55201800600000
23454 |  |  |  |  | 55202600300000
23601 |  |  |  |  | 55401900700000
83197 |  |  |  |  | 03006600600000
24085 |  |  |  |  | 03083901001927
79606 |  |  |  |  | 03103900600000
24000 |  |  |  |  | 03200101402192
83252 |  |  |  |  | 03200500500000
74202 |  |  |  |  | 03204701200000
24023 |  |  |  |  | 03205700100245
24018 |  |  |  |  | 03300900800000
24153 |  |  |  |  | 03301300602401
83284 |  |  |  |  | 03301702501033
98070 |  |  |  |  | 03301702801869
24806 |  |  |  |  | 10006800200616
24757 |  |  |  |  | 10030800801195
24667 |  |  |  |  | 10035603000333
24779 |  |  |  |  | 10102500100211
78002 |  |  |  |  | 10200700101196
83332 |  |  |  |  | 10300400300433
24703 |  |  |  |  | 10301000600000
83335 |  |  |  |  | 10301200500000
77989 |  |  |  |  | 10302700500194
89967 |  |  |  |  | 10400201302768
24710 |  |  |  |  | 10800505000898
83229 |  |  |  |  | 16032201801102
83232 |  |  |  |  | 16086100421587
83234 |  |  |  |  | 16086100620656
25221 |  |  |  |  | 16200900100000
83241 |  |  |  |  | 16200902200128
83256 |  |  |  |  | 16401500301431
83293 |  |  |  |  | 32028601500520
95851 |  |  |  |  | 32055302000620
25780 |  |  |  |  | 32095403700000
25584 |  |  |  |  | 32300701200000
78120 |  |  |  |  | 32401000100530
83282 |  |  |  |  | 33003601701535
83312 |  |  |  |  | 33200300700000
26151 |  |  |  |  | 33200802100200
26069 |  |  |  |  | 33300302500000
83343 |  |  |  |  | 33400100700000
62523 |  |  |  |  | 02000804101108
27272 |  |  |  |  | 02003001202263
28154 |  |  |  |  | 02003001901870
73522 |  |  |  |  | 02005100802710
37590 |  |  |  |  | 02013600500000
28597 |  |  |  |  | 02013601202172
63321 |  |  |  |  | 02091002400485
63324 |  |  |  |  | 02091003000000
78185 |  |  |  |  | 02097800300000
27185 |  |  |  |  | 02100102101194
27188 |  |  |  |  | 02100103502537
28128 |  |  |  |  | 02100103601567
78220 |  |  |  |  | 02100600402405
89100 |  |  |  |  | 02101100101018
63342 |  |  |  |  | 02101100102295
28603 |  |  |  |  | 02101200602013
63343 |  |  |  |  | 02101300202226
63344 |  |  |  |  | 02101300300428
78223 |  |  |  |  | 02101300400000
99687 |  |  |  |  | 02101500702617
27287 |  |  |  |  | 02101600801980
63356 |  |  |  |  | 02102801801751
63513 |  |  |  |  | 02103400501321
28607 |  |  |  |  | 02200100800335
62174 |  |  |  |  | 02200101300130
26417 |  |  |  |  | 02200800100053
73045 |  |  |  |  | 02201000102238
27451 |  |  |  |  | 02201701301248
99665 |  |  |  |  | 02201701400112
78224 |  |  |  |  | 02201800400721
99670 |  |  |  |  | 02202200102622
63529 |  |  |  |  | 02204500300840
78271 |  |  |  |  | 02204600401678
63547 |  |  |  |  | 02204600800256
74324 |  |  |  |  | 02204600801088
27419 |  |  |  |  | 02206500402452
89124 |  |  |  |  | 02207500900000
27275 |  |  |  |  | 02207501900000
63557 |  |  |  |  | 02211800203544
27436 |  |  |  |  | 02300800420000
28446 |  |  |  |  | 02301400302259
27386 |  |  |  |  | 02301800260000
28136 |  |  |  |  | 02302100300941
27454 |  |  |  |  | 02304801200000
27430 |  |  |  |  | 02309800500762
27429 |  |  |  |  | 02309800601125
89079 |  |  |  |  | 02310800100174
78407 |  |  |  |  | 02310800301395
74338 |  |  |  |  | 02401700500880
78413 |  |  |  |  | 02403200902202
78414 |  |  |  |  | 02403600701676
78416 |  |  |  |  | 02403601303135
78417 |  |  |  |  | 02403601400961
70804 |  |  |  |  | 04016803300983
28944 |  |  |  |  | 04016805001748
93613 |  |  |  |  | 04100500202450
80062 |  |  |  |  | 04101400700193
69069 |  |  |  |  | 04300500800933
67378 |  |  |  |  | 04300900600000
70805 |  |  |  |  | 04302500701409
70807 |  |  |  |  | 04302700400000
89058 |  |  |  |  | 04302700460000
99793 |  |  |  |  | 04401201000519
29062 |  |  |  |  | 04401201100256
78310 |  |  |  |  | 04401201500926
99794 |  |  |  |  | 04401900500000
78313 |  |  |  |  | 04403400200000
29374 |  |  |  |  | 37020800700000
78362 |  |  |  |  | 37020801000000
29534 |  |  |  |  | 37020802201379
78318 |  |  |  |  | 37022400601429
89094 |  |  |  |  | 37022401100412
78370 |  |  |  |  | 37095601200542
69103 |  |  |  |  | 37095601501187
78374 |  |  |  |  | 37095601900000
69231 |  |  |  |  | 37100501501309
78378 |  |  |  |  | 37100900603315
99796 |  |  |  |  | 37101200700000
29321 |  |  |  |  | 37101200900000
29387 |  |  |  |  | 37200100802619
99798 |  |  |  |  | 37201200103494
29525 |  |  |  |  | 37300100300259
99797 |  |  |  |  | 37300300800000
29549 |  |  |  |  | 37300400600000
80677 |  |  |  |  | 37301500201288
51503 |  |  |  |  | 26016603900000
51484 |  |  |  |  | 26038100801000
74174 |  |  |  |  | 26100100200639
74176 |  |  |  |  | 26100300320000
81961 |  |  |  |  | 26100700300000
29781 |  |  |  |  | 26101800100206
69229 |  |  |  |  | 26103100100053
74345 |  |  |  |  | 26103100601336
76009 |  |  |  |  | 26103100700299
76012 |  |  |  |  | 26104300200093
29820 |  |  |  |  | 26105000101121
90965 |  |  |  |  | 26105002101302
89075 |  |  |  |  | 26105103000845
29823 |  |  |  |  | 26105501401377
29926 |  |  |  |  | 26105801300142
29893 |  |  |  |  | 26105801300864
74184 |  |  |  |  | 26201500300000
74189 |  |  |  |  | 26301100900000
81636 |  |  |  |  | 26301301601348
79325 |  |  |  |  | 26301301700955
79326 |  |  |  |  | 26301301701416
79328 |  |  |  |  | 26301301900753
74190 |  |  |  |  | 26301301901171
79337 |  |  |  |  | 26404400201593
79340 |  |  |  |  | 30001802400670
79342 |  |  |  |  | 30001805800146
30291 |  |  |  |  | 30018800300000
76037 |  |  |  |  | 30018801800000
89031 |  |  |  |  | 30101101500501
74203 |  |  |  |  | 30101400803315
30335 |  |  |  |  | 30200303301330
79353 |  |  |  |  | 30201103700000
30289 |  |  |  |  | 30201600701702
79356 |  |  |  |  | 30202600100590
79357 |  |  |  |  | 30202600501285
88079 |  |  |  |  | 30300600100674
30231 |  |  |  |  | 30301300900000
30975 |  |  |  |  | 62001900400000
30639 |  |  |  |  | 62005003300000
30997 |  |  |  |  | 62008804902545
73058 |  |  |  |  | 62008807600000
89048 |  |  |  |  | 62022100802172
88078 |  |  |  |  | 62023104300092
76062 |  |  |  |  | 62048100500000
30813 |  |  |  |  | 62048102400990
31155 |  |  |  |  | 62104900520000
98374 |  |  |  |  | 62200700200048
76072 |  |  |  |  | 62201102800165
98377 |  |  |  |  | 62201500200805
89142 |  |  |  |  | 62202300800032
98864 |  |  |  |  | 62202301100756
51507 |  |  |  |  | 62203400500000
31157 |  |  |  |  | 62203600101601
81841 |  |  |  |  | 62203600500000
30715 |  |  |  |  | 62203700403160
30881 |  |  |  |  | 62303700801515
31146 |  |  |  |  | 62400300701841
30552 |  |  |  |  | 62402300200000
30702 |  |  |  |  | 62402700100687
81846 |  |  |  |  | 62403900701840
30635 |  |  |  |  | 62406100401960
32045 |  |  |  |  | 64003103302148
76089 |  |  |  |  | 64005600501506
79402 |  |  |  |  | 64013602502924
31601 |  |  |  |  | 64025900700000
74418 |  |  |  |  | 64036601720000
31826 |  |  |  |  | 64038102400504
31614 |  |  |  |  | 64038103000000
76121 |  |  |  |  | 64071102601107
76122 |  |  |  |  | 64071103000565
98633 |  |  |  |  | 64098201701219
31972 |  |  |  |  | 64100400200165
31611 |  |  |  |  | 64101700400238
89037 |  |  |  |  | 64101700600042
31304 |  |  |  |  | 64103400500000
79404 |  |  |  |  | 64201201301481
79418 |  |  |  |  | 64201300201727
79419 |  |  |  |  | 64202100601976
31699 |  |  |  |  | 64400700200691
91189 |  |  |  |  | 64405300120000
89049 |  |  |  |  | 64801105100448

## Sheet2 (hidden)
JV # | BR Key | BMS # | District
1 | 12879 | 20000604100000 | 01
9 | 17195 | 27006201302194 | 01
18 | 33956 | 61000603502233 | 01
25 | 8831 | 12012000400000 | 02
26 | 9265 | 14004507902031 | 02
27 | 9360 | 14014403400099 | 02
28 | 9576 | 14100200501555 | 02
29 | 9577 | 14100200801726 | 02
31 | 9431 | 14304001301062 | 02
32 | 9434 | 14304001500701 | 02
33 | 9451 | 14304003701668 | 02
36 | 11245 | 17005306400000 | 02
37 | 11390 | 17021902800000 | 02
38 | 11399 | 17021904201459 | 02
39 | 11403 | 17021904602606 | 02
40 | 11404 | 17021904700185 | 02
41 | 11454 | 17025502200000 | 02
42 | 11461 | 17025503200000 | 02
46 | 12163 | 18015000701624 | 02
48 | 15531 | 24012002801546 | 02
49 | 15535 | 24021900201858 | 02
50 | 15560 | 24021904900000 | 02
51 | 19992 | 34003507200000 | 02
57 | 25213 | 42000605100562 | 02
58 | 25216 | 42000605800309 | 02
59 | 25243 | 42004600600000 | 02
60 | 25281 | 42005904500000 | 02
61 | 25297 | 42015500200000 | 02
62 | 25308 | 42015501900182 | 02
63 | 25313 | 42015502701162 | 02
64 | 25314 | 42015502900238 | 02
65 | 25418 | 42034604101617 | 02
66 | 25420 | 42034604201811 | 02
68 | 25461 | 42077001300784 | 02
69 | 25462 | 42077001400000 | 02
71 | 25495 | 42200100100806 | 02
72 | 25500 | 42200200320000 | 02
74 | 26468 | 44065502201820 | 02
75 | 26469 | 44065502300022 | 02
79 | 30090 | 52000602300000 | 02
80 | 30144 | 52004402700000 | 02
81 | 30156 | 52004408101925 | 02
83 | 30166 | 52004410100000 | 02
84 | 30190 | 52004904300530 | 02
85 | 30191 | 52004904400406 | 02
86 | 30233 | 52044900501401 | 02
87 | 30348 | 52200201302331 | 02
89 | 6074 | 08001403400602 | 03
90 | 6104 | 08018704000000 | 03
91 | 6136 | 08022001301099 | 03
92 | 6164 | 08036700101794 | 03
93 | 6191 | 08041403800000 | 03
94 | 6193 | 08046700100052 | 03
97 | 6224 | 08070601701340 | 03
98 | 6227 | 08070602601160 | 03
100 | 6476 | 08401302501496 | 03
102 | 12555 | 19025402500486 | 03
103 | 12592 | 19048703700177 | 03
106 | 24511 | 41001500702198 | 03
107 | 24566 | 41004403440880 | 03
108 | 24591 | 41008700600000 | 03
109 | 24603 | 41011801700622 | 03
110 | 24748 | 41041400100417 | 03
111 | 24751 | 41041400800000 | 03
112 | 24850 | 41200200320000 | 03
116 | 28361 | 47025400200000 | 03
125 | 31948 | 56008701100148 | 03
126 | 31966 | 56008705202440 | 03
127 | 31981 | 56015401501564 | 03
128 | 32822 | 58004901400434 | 03
129 | 32843 | 58024903220000 | 03
131 | 33080 | 58300103901413 | 03
132 | 33083 | 58300500400000 | 03
133 | 33180 | 58401702800000 | 03
140 | 23795 | 40011501200000 | 04
141 | 24493 | 40800500201030 | 04
143 | 29982 | 51200600100953 | 04
144 | 32153 | 57001104601461 | 04
173 | 8994 | 13020902602676 | 05
175 | 23144 | 39022202103224 | 05
176 | 23228 | 39100400202044 | 05
178 | 23136 | 39622200303519 | 05
179 | 26785 | 45020900401748 | 05
180 | 26795 | 45020903110000 | 05
186 | 26904 | 45094000701313 | 05
187 | 26907 | 45094001400882 | 05
188 | 26914 | 45094003900000 | 05
190 | 26962 | 45200900101729 | 05
196 | 27059 | 45400600200000 | 05
197 | 28493 | 48003300200000 | 05
198 | 28494 | 48003300210000 | 05
199 | 42278 | 48003301200000 | 05
200 | 42446 | 48003301210000 | 05
201 | 28606 | 48051202101582 | 05
207 | 30730 | 53092400702725 | 05
211 | 7262 | 09203701900000 | 06
215 | 27513 | 46066302700894 | 06
217 | 27643 | 46202700500209 | 06
220 | 47 | 01003003000000 | 08
223 | 87 | 01009701000240 | 08
236 | 13564 | 21001105202844 | 08
237 | 13616 | 21003400700827 | 08
239 | 13741 | 21023303801454 | 08
254 | 21043 | 36003004802322 | 08
255 | 21196 | 36032201500954 | 08
259 | 21277 | 36046202200000 | 08
284 | 22812 | 38402000800000 | 08
285 | 29426 | 50001100300893 | 08
295 | 37488 | 66012401400000 | 08
312 | 4010 | 05005600901305 | 09
313 | 4044 | 05009602600000 | 09
317 | 4196 | 05102000500880 | 09
343 | 18881 | 31400900200000 | 09
358 | 2992 | 03006600600000 | 10
359 | 3097 | 03083901001927 | 10
366 | 3282 | 03301300602401 | 10
368 | 3294 | 03301702801869 | 10
369 | 7834 | 10006800200616 | 10
370 | 7925 | 10030800801195 | 10
371 | 7935 | 10035603000333 | 10
372 | 8016 | 10102500100211 | 10
373 | 8025 | 10200700101196 | 10
377 | 8104 | 10302700500194 | 10
380 | 10975 | 16032201801102 | 10
381 | 10997 | 16086100421587 | 10
382 | 10996 | 16086100620656 | 10
383 | 11042 | 16200900100000 | 10
386 | 19087 | 32028601500520 | 10
387 | 19183 | 32055302000620 | 10
391 | 19550 | 33003601701535 | 10
396 | 505 | 02000804101108 | 11
397 | 659 | 02003001202263 | 11
398 | 664 | 02003001901870 | 11
399 | 709 | 02005100802710 | 11
401 | 954 | 02013600500000 | 11
403 | 961 | 02013601202172 | 11
404 | 1334 | 02091002400485 | 11
406 | 1346 | 02097800300000 | 11
407 | 1365 | 02100102101194 | 11
408 | 1372 | 02100103502537 | 11
409 | 1373 | 02100103601567 | 11
410 | 1390 | 02100600402405 | 11
411 | 1397 | 02101100101018 | 11
417 | 1424 | 02101500702617 | 11
429 | 1559 | 02204500300840 | 11
431 | 1567 | 02204600800256 | 11
433 | 1600 | 02206500402452 | 11
437 | 1704 | 02300800420000 | 11
441 | 1776 | 02304801200000 | 11
442 | 1859 | 02309800500762 | 11
447 | 1974 |  | 11
448 | 1976 |  | 11
468 | 22277 |  | 11
477 | 22396 | 37200100802619 | 11
479 | 22433 |  | 11
483 | 16651 | 26016603900000 | 12
484 | 16673 | 26038100801000 | 12
486 | 16720 | 26100300320000 | 12
493 | 16789 | 26105000101121 | 12
496 | 16827 | 26105501401377 | 12
497 | 16840 | 26105801300142 | 12
498 | 16841 | 26105801300864 | 12
500 | 16910 | 26301100900000 | 12
501 | 16922 | 26301301700955 | 12
502 | 16928 | 26301301900753 | 12
503 | 17052 | 26404400201593 | 12
504 | 18013 | 30001802400670 | 12
505 | 18044 | 30001805800146 | 12
506 | 18154 | 30018800300000 | 12
507 | 18164 | 30018801800000 | 12
509 | 18222 | 30101400803315 | 12
511 | 18279 | 30201103700000 | 12
513 | 18315 | 30202600100590 | 12
514 | 18317 | 30202600501285 | 12
515 | 18351 | 30300600100674 | 12
516 | 18403 | 30301300900000 | 12
517 | 34335 | 62001900400000 | 12
518 | 34417 | 62005003300000 | 12
519 | 34609 | 62008804902545 | 12
520 | 34623 | 62008807600000 | 12
521 | 34650 | 62022100802172 | 12
523 | 34692 | 62048100500000 | 12
525 | 34847 | 62104900520000 | 12
530 | 34949 | 62202301100756 | 12
531 | 34977 | 62203400500000 | 12
542 | 36002 | 64005600501506 | 12
543 | 36130 | 64013602502924 | 12
545 | 36207 | 64036601720000 | 12
546 | 36228 | 64038102400504 | 12
549 | 36251 | 64071103000565 | 12
550 | 36331 | 64098201701219 | 12
551 | 36365 | 64100400200165 | 12
556 | 36482 | 64201300201727 | 12
559 | 36750 | 64405300120000 | 12
Phased Construction
421 | 1479 | 02200100800335 | 11
423 | 1496 | 02200800100053 | 11
424 | 1498 | 02201000102238 | 11
425 | 1519 | 02201701301248 | 11
426 | 1520 | 02201701400112 | 11
427 | 1523 | 02201800400721 | 11
428 | 1527 | 02202200102622 | 11
430 | 1562 | 02204600401678 | 11
432 | 1568 | 02204600801088 | 11
434 | 1620 | 02207500900000 | 11
435 | 1626 | 02207501900000 | 11
439 | 1727 | 02301800260000 | 11
443 | 1860 | 02309800601125 | 11
444 | 1881 | 02310800100174 | 11
445 | 1882 | 02310800301395 | 11
449 | 1980 | 02403601303135 | 11
450 | 1982 | 02403601400961 | 11
451 | 3599 | 04016803300983 | 11
452 | 3602 | 04016805001748 | 11
453 | 3647 | 04100500202450 | 11
454 | 3654 | 04101400700193 | 11
455 | 3693 | 04300500800933 | 11
456 | 3695 | 04300900600000 | 11
457 | 3717 | 04302500701409 | 11
458 | 3722 | 04302700400000 | 11
459 | 3723 | 04302700460000 | 11
460 | 3747 | 04401201000519 | 11
461 | 3749 | 04401201100256 | 11
462 | 3750 | 04401201500926 | 11
To Be Determined
2 | 12902 | 20000608400273 | 01
3 | 13084 | 20028501000629 | 01
4 | 13122 | 20040801800428 | 01
5 | 13128 | 20040805201643 | 01
6 | 13027 | 20088601600750 | 01
7 | 13367 | 20401100200000 | 01
8 | 16373 | 25401100800860 | 01
10 | 17207 | 27066600700000 | 01
11 | 17208 | 27066600900000 | 01
12 | 17209 | 27066601100240 | 01
13 | 25833 | 43017304703518 | 01
14 | 25858 | 43031801500622 | 01
15 | 26008 | 43302001700000 | 01
16 | 33765 | 60042702200000 | 01
17 | 33788 | 60201301000000 | 01
21 | 34001 | 61002705203359 | 01
22 | 34056 | 61012700902381 | 01
23 | 34077 | 61095701700981 | 01
24 | 34169 | 61301000600428 | 01
30 | 9679 | 14201300100000 | 02
34 | 9778 | 14400200702338 | 02
35 | 9790 | 14400600100000 | 02
43 | 11658 | 17100900401885 | 02
44 | 11698 | 17200703101047 | 02
45 | 11807 | 17300902501042 | 02
47 | 12239 | 18047700300000 | 02
52 | 20021 | 34007502501504 | 02
53 | 20106 | 34100200200000 | 02
54 | 20118 | 34100400300549 | 02
55 | 20137 | 34200601501696 | 02
56 | 20147 | 34200701400000 | 02
67 | 25459 |  | 02
70 | 25489 |  | 02
73 | 25535 | 42401100102339 | 02
76 | 26472 |  | 02
77 | 26477 |  | 02
78 | 26595 |  | 02
82 | 30162 | 52004409500000 | 02
88 | 30435 | 52402600220000 | 02
95 | 6203 | 8046702700000 | 03
96 | 6216 | 8051402000863 | 03
99 | 6348 | 8105900700582 | 03
101 | 12486 | 19004402401397 | 03
104 | 12738 | 19403101120000 | 03
105 | 12745 | 19403600120000 | 03
113 | 24881 | 41201501720000 | 03
114 | 24928 | 41205000120000 | 03
115 | 24938 | 41206101702204 | 03
117 | 28387 |  | 03
118 | 28389 |  | 03
119 | 29174 |  | 03
120 | 29178 |  | 03
121 | 29303 |  | 03
122 | 29306 |  | 03
123 | 29311 |  | 03
124 | 31169 |  | 03
130 | 32931 | 58054902602539 | 03
134 | 33209 |  | 03
135 | 33469 |  | 03
136 | 33470 |  | 03
137 | 33478 |  | 03
138 | 33543 |  | 03
139 | 20820 |  | 04
142 | 29947 | 51100700301853 | 04
145 | 32244 |  | 04
146 | 32307 | 57026703200000 | 04
147 | 32308 |  | 04
148 | 32327 |  | 04
149 | 32365 |  | 04
150 | 32378 |  | 04
151 | 32401 | 57100700500000 | 04
152 | 32437 |  | 04
153 | 32478 | 57200800203639 | 04
154 | 32507 | 57202100501583 | 04
155 | 32647 | 57400201300000 | 04
156 | 35471 | 63019106701296 | 04
157 | 35508 | 63029601800000 | 04
158 | 35624 | 63101801602046 | 04
159 | 35654 | 63200700301844 | 04
160 | 35675 | 63300601600000 | 04
161 | 35765 | 63401401300733 | 04
162 | 35802 | 63403302600090 | 04
163 | 35810 | 63403703303161 | 04
164 | 37163 | 65026700100659 | 04
165 | 37172 | 65029201500354 | 04
166 | 37192 | 65100100500000 | 04
167 | 37222 | 65200100500596 | 04
168 | 4900 | 06062501301318 | 05
169 | 4946 | 06100400100619 | 05
170 | 4953 | 06100601100107 | 05
171 | 4957 | 06100800300000 | 05
172 | 5147 | 06300900701675 | 05
174 | 9104 | 13401000501489 | 05
177 | 23330 | 39204900302189 | 05
181 | 26811 | 45031401101750 | 05
182 | 26832 | 45039000300932 | 05
183 | 26887 | 45061105100000 | 05
184 | 26888 | 45071500201751 | 05
185 | 26901 | 45090300200000 | 05
189 | 26924 | 45100400300941 | 05
191 | 27011 | 45300900220000 | 05
192 | 27017 | 45301100300000 | 05
193 | 27022 | 45301500201644 | 05
194 | 27042 | 45302301202040 | 05
195 | 27055 | 45400300702976 | 05
202 | 28660 |  | 05
203 | 28672 |  | 05
204 | 30678 | 53033902000276 | 05
205 | 30679 | 53033902400902 | 05
206 | 30680 | 53033902401098 | 05
208 | 30832 | 53401600100000 | 05
209 | 30856 | 53403600300000 | 05
210 | 30862 | 53403900200000 | 05
212 | 10497 | 15304401300000 | 06
213 | 10599 | 15400800402407 | 06
214 | 15002 | 23042000701072 | 06
216 | 27605 | 46201300320000 | 06
218 | 27757 | 46304400500389 | 06
219 | 27868 | 46404200341011 | 06
221 | 71 | 01003402200745 | 08
222 | 75 | 01003402700000 | 08
224 | 98 | 01011601100000 | 08
225 | 128 | 01019402401689 | 08
226 | 135 | 01023401202343 | 08
227 | 148 | 01023403100000 | 08
228 | 160 | 01039400600526 | 08
229 | 185 | 01101400501701 | 08
230 | 198 | 01101601101587 | 08
231 | 229 | 01200600400591 | 08
232 | 319 | 01301301000061 | 08
233 | 362 | 01400500101339 | 08
234 | 364 | 01400601202897 | 08
235 | 381 | 01401100101013 | 08
238 | 13735 | 21023300900266 | 08
240 | 13824 | 21099702601555 | 08
241 | 13896 | 21203100100000 | 08
242 | 13946 | 21301900100000 | 08
243 | 13948 | 21400100200000 | 08
244 | 13961 | 21400800302148 | 08
245 | 14441 | 22101800101692 | 08
246 | 14481 | 22201200100356 | 08
247 | 14578 | 22400400202505 | 08
248 | 17407 | 28023302000092 | 08
249 | 17408 | 28027400200000 | 08
250 | 17471 | 28099706500000 | 08
251 | 17592 | 28400801900060 | 08
252 | 17593 | 28400802301142 | 08
253 | 20976 | 36002300301231 | 08
256 | 21237 | 36034003700000 | 08
257 | 21238 | 36034003801674 | 08
258 | 21251 | 36037204240000 | 08
260 | 21292 | 36062501302573 | 08
261 | 21326 | 36077204500174 | 08
262 | 21403 | 36101900500000 | 08
263 | 21409 | 36102100420000 | 08
264 | 21415 | 36102402100000 | 08
265 | 21417 | 36102500801639 | 08
266 | 21439 | 36103400200000 | 08
267 | 21446 | 36103501500846 | 08
268 | 21454 | 36103702100000 | 08
269 | 21459 | 36103900500000 | 08
270 | 21474 | 36104800500000 | 08
271 | 21482 | 36105300200000 | 08
272 | 21487 | 36105500202673 | 08
273 | 21514 | 36200200602329 | 08
274 | 21518 | 36200500300000 | 08
275 | 21533 | 36201000560000 | 08
276 | 21536 | 36201200320000 | 08
277 | 21545 | 36201500400000 | 08
278 | 21558 | 36202000100000 | 08
279 | 21559 | 36202000200000 | 08
280 | 21595 | 36204500700000 | 08
281 | 21601 | 36300400200000 | 08
282 | 21637 | 36301702401388 | 08
283 | 21662 | 36303201100000 | 08
286 | 29451 | 50001701101051 | 08
287 | 29468 | 50001707600000 | 08
288 | 29518 | 50007401900530 | 08
289 | 29565 | 50085002201839 | 08
290 | 29566 | 50085002501777 | 08
291 | 29605 | 50101502002360 | 08
292 | 29651 | 50300600100014 | 08
293 | 29673 | 50301700100000 | 08
294 | 29693 | 50400701001472 | 08
296 | 37491 | 66012402502532 | 08
297 | 37590 | 66042504600314 | 08
298 | 37607 | 66061601000255 | 08
299 | 37608 | 66061601001014 | 08
300 | 37641 | 66092100900000 | 08
301 | 37725 | 66202800800249 | 08
302 | 37726 | 66202900902536 | 08
303 | 37878 | 66304500800853 | 08
304 | 37890 | 66305100200000 | 08
305 | 37921 | 66307100100000 | 08
306 | 37946 | 66400102102301 | 08
307 | 37976 | 66401200602478 | 08
308 | 38007 | 66403300403136 | 08
309 | 38023 | 66405100300581 | 08
310 | 3954 | 05003001000907 | 09
311 | 3955 | 05003001100000 | 09
314 | 4122 | 05086901201328 | 09
315 | 4174 | 05101100400000 | 09
316 | 4177 | 05101200400000 | 09
318 | 4386 | 05403101601407 | 09
319 | 5699 | 07101302400000 | 09
320 | 5702 | 07101302500908 | 09
321 | 5709 | 07101303601234 | 09
322 | 5763 | 07300500100050 | 09
323 | 5883 | 07403100301171 | 09
324 | 8424 | 11016002000862 | 09
325 | 8425 | 11016002200000 | 09
326 | 8580 | 11102601101804 | 09
327 | 17813 | 29048400101102 | 09
328 | 17826 | 29052201401573 | 09
329 | 17827 | 29052201600330 | 09
330 | 17828 | 29052201601370 | 09
331 | 17832 | 29052202901545 | 09
332 | 17850 | 29065503900454 | 09
333 | 17853 | 29065504501203 | 09
334 | 17873 | 29100100100266 | 09
335 | 18576 | 31002202300000 | 09
336 | 18601 | 31002604900654 | 09
337 | 18603 | 31002605100972 | 09
338 | 18703 | 31065505400533 | 09
339 | 18742 | 31091301901896 | 09
340 | 18773 | 31100800400000 | 09
341 | 18784 | 31101900100185 | 09
342 | 18785 | 31101900600000 | 09
344 | 45123 | 55003003602574 | 09
345 | 41517 | 55003003702626 | 09
346 | 31343 | 55003104200000 | 09
347 | 31469 | 55052300301840 | 09
348 | 31470 | 55052300701200 | 09
349 | 31471 | 55052300801065 | 09
350 | 31521 | 55100400101850 | 09
351 | 31528 | 55100700300000 | 09
352 | 31532 | 55100701800000 | 09
353 | 31588 | 55200500300000 | 09
354 | 31608 | 55201301000000 | 09
355 | 31630 | 55201800600000 | 09
356 | 31651 | 55202600300000 | 09
357 | 31758 | 55401900700000 | 09
360 | 3160 | 03103900600000 | 10
361 | 3169 | 03200101402192 | 10
362 | 3176 | 03200500500000 | 10
363 | 3232 | 03204701200000 | 10
364 | 3245 | 03205700100245 | 10
365 | 3278 | 03300900800000 | 10
367 | 3293 | 03301702501033 | 10
374 | 8061 | 10300400300433 | 10
375 | 8071 | 10301000600000 | 10
376 | 8073 | 10301200500000 | 10
378 | 8113 | 10400201302768 | 10
379 | 8334 | 10800505000898 | 10
384 | 11049 | 16200902200128 | 10
385 | 11088 | 16401500301431 | 10
388 | 19200 | 32095403700000 | 10
389 | 19320 | 32300701200000 | 10
390 | 19392 | 32401000100530 | 10
392 | 19699 | 33200300700000 | 10
393 | 19708 | 33200802100200 | 10
394 | 19737 | 33300302500000 | 10
395 | 19807 | 33400100700000 | 10
400 | 41065 | 02013000420000 | 11
401 | 41066 | 02013000420165 | 11
405 | 1339 | 02091003000000 | 11
412 | 1400 | 02101100102295 | 11
413 | 1404 | 02101200602013 | 11
414 | 1405 | 02101300202226 | 11
415 | 1406 | 02101300300428 | 11
416 | 42177 | 02101300400000 | 11
418 | 1435 | 02101600801980 | 11
419 | 1455 | 02102801801751 | 11
420 | 1471 | 02103400501321 | 11
422 | 1481 | 02200101300130 | 11
436 | 1671 | 02211800203544 | 11
438 | 1715 | 02301400302259 | 11
440 | 1733 | 02302100300941 | 11
446 | 1950 | 02401700500880 | 11
463 | 3755 | 04401900500000 | 11
464 | 3769 | 04403400200000 | 11
465 | 22262 | 37020800700000 | 11
466 | 22265 | 37020801000000 | 11
467 | 22269 | 37020802201379 | 11
469 | 22281 | 37022401100412 | 11
470 | 22358 | 37095601200542 | 11
471 | 22359 | 37095601501187 | 11
472 | 22362 | 37095601900000 | 11
473 | 22369 | 37100501501309 | 11
474 | 22374 | 37100900603315 | 11
475 | 22378 | 37101200700000 | 11
476 | 22379 | 37101200900000 | 11
478 | 22416 | 37201200103494 | 11
480 | 22439 | 37300300800000 | 11
481 | 22441 | 37300400600000 | 11
482 | 22455 | 37301500201288 | 11
485 | 16713 | 26100100200639 | 12
487 | 16725 | 26100700300000 | 12
488 | 16736 | 26101800100206 | 12
489 | 16752 | 26103100100053 | 12
490 | 16757 | 26103100601336 | 12
491 | 16758 | 26103100700299 | 12
492 | 16782 | 26104300200093 | 12
494 | 16794 | 26105002101302 | 12
495 | 16806 | 26105103000845 | 12
499 | 16868 | 26201500300000 | 12
508 | 18214 | 30101101500501 | 12
510 | 18261 | 30200303301330 | 12
512 | 18287 | 30201600701702 | 12
522 | 34673 | 62023104300092 | 12
524 | 34702 | 62048102400990 | 12
526 | 34879 | 62200700200048 | 12
527 | 34901 | 62201102800165 | 12
528 | 34907 | 62201500200805 | 12
529 | 34946 | 62202300800032 | 12
532 | 34980 | 62203600101601 | 12
533 | 34985 | 62203600500000 | 12
534 | 34996 | 62203700403160 | 12
535 | 35090 | 62303700801515 | 12
536 | 35103 | 62400300701841 | 12
537 | 35171 | 62402300200000 | 12
538 | 35178 | 62402700100687 | 12
539 | 35201 | 62403900701840 | 12
540 | 35227 | 62406100401960 | 12
541 | 35982 | 64003103302148 | 12
544 | 36168 | 64025900700000 | 12
547 | 36230 | 64038103000000 | 12
548 | 36248 | 64071102601107 | 12
552 | 36387 | 64101700400238 | 12
553 | 36389 | 64101700600042 | 12
554 | 36431 | 64103400500000 | 12
555 | 36481 | 64201201301481 | 12
557 | 36493 | 64202100601976 | 12
558 | 36684 | 64400700200691 | 12
560 | 37037 | 64801105100448 | 12
Total closure with detour
19 | 33957 | 61000603900000 | 01
20 | 33982 | 61000608200000 | 01
Total closure with temporary roadway
SUMMARY
Phased Construction
To Be Determined
Total closure with detour
Total closure with temporary roadway

## Sheet3 (hidden)
Early Completion Bridge | 5A03 BRKEY | 5A04 DISTRICT | 5A05 COUNTY | 5B07 deck_width | existing out to outwidth | proposed curb to curb | assumed parapet | assumed new out to out width | delta
- | 12879 | 01 | Crawford | 69.5 | 25.5 | 30 | 3.375 | 33.375 | 7.875
- | 12902 | 01 | Crawford | 30 | 25.7 | 28 | 3.375 | 31.375 | 5.675
- | 13084 | 01 | Crawford | 43.0 | 33.5 | 52 | 3.375 | 55.375 | 21.875
- | 13122 | 01 | Crawford | 26.0 | 26.6 | 32 | 3.375 | 35.375 | 8.775
- | 13128 | 01 | Crawford | 43.0 | 24.4 | 28 | 3.375 | 31.375 | 6.975
- | 13027 | 01 | Crawford | 43.0 | 26.0 | 32 | 3.375 | 35.375 | 9.375
- | 13367 | 01 | Crawford | 24.5 | 26.2 | 32 | 3.375 | 35.375 | 9.175
- | 16373 | 01 | Erie | 33.0 | 33.0 | 32 | 3.375 | 35.375 | 2.375
- | 17195 | 01 | Forest | 35.1 | 25.8 | 34 | 3.375 | 37.375 | 11.575
- | 17207 | 01 | Forest | 27.0 | 17.9 | 24 | 3.375 | 27.375 | 9.475
- | 17208 | 01 | Forest | 25.5 | 29.5 | 28 | 3.375 | 31.375 | 1.875
- | 17209 | 01 | Forest | 27.5 | 24.5 | 32 | 3.375 | 35.375 | 10.875
- | 25833 | 01 | Mercer | 40.8 | 18.0 | 24 | 3.375 | 27.375 | 9.375
- | 25858 | 01 | Mercer | 35.0 | 16.4 | 24 | 3.375 | 27.375 | 10.975
- | 26008 | 01 | Mercer | 16.5 | 26.2 | 24 | 3.375 | 27.375 | 1.175
- | 33765 | 01 | Venango | 26.0 | 33.0 | 32 | 3.375 | 35.375 | 2.375
- | 33788 | 01 | Venango | 26.7 | 26.1 | 33 | 3.375 | 36.375 | 10.275
- | 33956 | 01 | Warren | 39.0 | 24.5 | 30 | 3.375 | 33.375 | 8.875
- | 33957 | 01 | Warren | 39.5 | 23.6 | 24 | 3.375 | 27.375 | 3.775
- | 33982 | 01 | Warren | 42.0 | 26.3 | 28 | 3.375 | 31.375 | 5.075
- | 34001 | 01 | Warren | 26.0 | 20.2 | 28 | 3.375 | 31.375 | 11.175
- | 34056 | 01 | Warren | 37.0 | 22.1 | 30 | 3.375 | 33.375 | 11.275
- | 34077 | 01 | Warren | 39.3 | 29.8 | 28 | 3.375 | 31.375 | 1.575
- | 34169 | 01 | Warren | 33.0 | 25.4 | 30 | 3.375 | 33.375 | 7.975
- | 8831 | 02 | Cameron | 41.6 | 28.0 | 24 | 3.375 | 27.375 | -0.625
- | 9265 | 02 | Centre | 46.6 | 31.0 | 30 | 3.375 | 33.375 | 2.375
- | 9360 | 02 | Centre | 44.0 | 18.3 | 22 | 3.375 | 25.375 | 7.075
- | 9576 | 02 | Centre | 23.4 | 24.5 | 24 | 3.375 | 27.375 | 2.875
- | 9577 | 02 | Centre | 26.5 | 24.0 | 22 | 3.375 | 25.375 | 1.375
- | 9679 | 02 | Centre | 14.1 | 33.0 | 30 | 3.375 | 33.375 | 0.375
- | 9431 | 02 | Centre | 50.0 | 29.0 | 26 | 3.375 | 29.375 | 0.375
- | 9434 | 02 | Centre | 45.0 | 27.6 | 24 | 3.375 | 27.375 | -0.225
- | 9451 | 02 | Centre | 36.0 | 43.7 | 40 | 3.375 | 43.375 | -0.325
- | 9778 | 02 | Centre | 25.0 | 54.0 | 52 | 3.375 | 55.375 | 1.375
- | 9790 | 02 | Centre | 28.0 | 33.9 | 30 | 3.375 | 33.375 | -0.525
- | 11245 | 02 | Clearfield | 42.7 | 40.0 | 40 | 3.375 | 43.375 | 3.375
- | 11390 | 02 | Clearfield | 43.0 | 71.7 | 68 | 3.375 | 71.375 | -0.325
- | 11399 | 02 | Clearfield | 41.7 | 24.8 | 32 | 3.375 | 35.375 | 10.575
- | 11403 | 02 | Clearfield | 41.1 | 31.0 | 32 | 3.375 | 35.375 | 4.375
- | 11404 | 02 | Clearfield | 41.7 | 59.3 | 40 | 3.375 | 43.375 | -15.925
- | 11454 | 02 | Clearfield | 33.2 | 43.3 | 40 | 3.375 | 43.375 | 0.075
- | 11461 | 02 | Clearfield | 36.0 | 42.0 | 40 | 3.375 | 43.375 | 1.375
- | 11658 | 02 | Clearfield | 24.9 | 30.5 | 28 | 3.375 | 31.375 | 0.875
- | 11698 | 02 | Clearfield | 25.9 | 33.7 | 32 | 3.375 | 35.375 | 1.675
- | 11807 | 02 | Clearfield | 24.0 | 26.1 | 28 | 3.375 | 31.375 | 5.275
- | 12163 | 02 | Clinton | 34.0 | 25.8 | 26 | 3.375 | 29.375 | 3.575
- | 12239 | 02 | Clinton | 25.0 | 43.0 | 40 | 3.375 | 43.375 | 0.375
- | 15531 | 02 | Elk | 44.0 | 26.8 | 30 | 3.375 | 33.375 | 6.575
- | 15535 | 02 | Elk | 41.5 | 30.3 | 32 | 3.375 | 35.375 | 5.075
- | 15560 | 02 | Elk | 52.3 | 24.0 | 24 | 3.375 | 27.375 | 3.375
- | 19992 | 02 | Juniata | 34.0 | 25.0 | 24 | 3.375 | 27.375 | 2.375
- | 20021 | 02 | Juniata | 26.3 | 34.8 | 32 | 3.375 | 35.375 | 0.575
- | 20106 | 02 | Juniata | 24.2 | 69.7 | 70 | 3.375 | 73.375 | 3.675
- | 20118 | 02 | Juniata | 27.4 | 26.0 | 28 | 3.375 | 31.375 | 5.375
- | 20137 | 02 | Juniata | 26.1 | 20.7 | 22 | 3.375 | 25.375 | 4.675
- | 20147 | 02 | Juniata | 26.3 | 18.2 | 22 | 3.375 | 25.375 | 7.175
- | 25213 | 02 | McKean | 43.0 | 40.0 | 34 | 3.375 | 37.375 | -2.625
- | 25216 | 02 | McKean | 42.5 | 25.0 | 38 | 3.375 | 41.375 | 16.375
- | 25243 | 02 | McKean | 26.8 | 26.6 | 24 | 3.375 | 27.375 | 0.775
- | 25281 | 02 | McKean | 39.3 | 26.3 | 32 | 3.375 | 35.375 | 9.075
- | 25297 | 02 | McKean | 41.1 | 41.0 | 24 | 3.375 | 27.375 | -13.625
- | 25308 | 02 | McKean | 41.6 | 34.0 | 24 | 3.375 | 27.375 | -6.625
- | 25313 | 02 | McKean | 36.0 | 34.0 | 24 | 3.375 | 27.375 | -6.625
- | 25314 | 02 | McKean | 35.7 | 20.8 | 26 | 3.375 | 29.375 | 8.575
- | 25418 | 02 | McKean | 37.0 | 70.0 | 58 | 3.375 | 61.375 | -8.625
- | 25420 | 02 | McKean | 36.5 | 33.0 | 30 | 3.375 | 33.375 | 0.375
- | 25459 | 02 | McKean | 33.3 | 50.0 | 40 | 3.375 | 43.375 | -6.625
- | 25461 | 02 | McKean | 25.8 | 28.0 | 30 | 3.375 | 33.375 | 5.375
- | 25462 | 02 | McKean | 26.0 | 25.8 | 30 | 3.375 | 33.375 | 7.575
- | 25489 | 02 | McKean | 31.0 | 28.0 | 30 | 3.375 | 33.375 | 5.375
- | 25495 | 02 | McKean | 26.2 | 28.0 | 30 | 3.375 | 33.375 | 5.375
- | 25500 | 02 | McKean | 35.8 | 34.5 | 30 | 3.375 | 33.375 | -1.125
- | 25535 | 02 | McKean | 24.0 | 26.5 | 26 | 3.375 | 29.375 | 2.875
- | 26468 | 02 | Mifflin | 42.0 | 35.0 | 30 | 3.375 | 33.375 | -1.625
- | 26469 | 02 | Mifflin | 44.7 | 34.5 | 28 | 3.375 | 31.375 | -3.125
- | 26472 | 02 | Mifflin | 18.2 | 29.0 | 28 | 3.375 | 31.375 | 2.375
- | 26477 | 02 | Mifflin | 18.2 | 62.6 | 52 | 3.375 | 55.375 | -7.225
- | 26595 | 02 | Mifflin | 26.8 | 39.4 | 32 | 3.375 | 35.375 | -4.025
- | 30090 | 02 | Potter | 45.0 | 29.0 | 32 | 3.375 | 35.375 | 6.375
- | 30144 | 02 | Potter | 26.0 | 32.0 | 32 | 3.375 | 35.375 | 3.375
- | 30156 | 02 | Potter | 32.9 | 22.0 | 24 | 3.375 | 27.375 | 5.375
- | 30162 | 02 | Potter | 34.0 | 25.5 | 26 | 3.375 | 29.375 | 3.875
- | 30166 | 02 | Potter | 34.0 | 26.8 | 80 | 3.375 | 83.375 | 56.575
- | 30190 | 02 | Potter | 30.5 | 25.0 | 24 | 3.375 | 27.375 | 2.375
- | 30191 | 02 | Potter | 32.3 | 43.0 | 38 | 3.375 | 41.375 | -1.625
- | 30233 | 02 | Potter | 26.3 | 20.2 | 26 | 3.375 | 29.375 | 9.175
- | 30348 | 02 | Potter | 27.0 | 20.7 | 24 | 3.375 | 27.375 | 6.675
- | 30435 | 02 | Potter | 25.0 | 34.0 | 34 | 3.375 | 37.375 | 3.375
- | 6074 | 03 | Bradford | 43.0 | 31.5 | 24 | 3.375 | 27.375 | -4.125
Y | 6104 | 03 | Bradford | 25.5 | 24.2 | 24 | 3.375 | 27.375 | 3.175
- | 6136 | 03 | Bradford | 26.0 | 26.7 | 30 | 3.375 | 33.375 | 6.675
Y | 6164 | 03 | Bradford | 25.7 | 32.0 | 30 | 3.375 | 33.375 | 1.375
- | 6191 | 03 | Bradford | 35.1 | 69.5 | 71 | 3.375 | 74.375 | 4.875
Y | 6193 | 03 | Bradford | 33.5 | 30 | 32 | 3.375 | 35.375 | 5.375
Y | 6203 | 03 | Bradford | 26.6 | 43.0 | 40 | 3.375 | 43.375 | 0.375
Y | 6216 | 03 | Bradford | 24.4 | 26.0 | 28 | 3.375 | 31.375 | 5.375
Y | 6224 | 03 | Bradford | 26.0 | 43.0 | 30 | 3.375 | 33.375 | -9.625
Y | 6227 | 03 | Bradford | 26.2 | 43.0 | 28 | 3.375 | 31.375 | -11.625
- | 6348 | 03 | Bradford | 16.4 | 24.5 | 26 | 3.375 | 29.375 | 4.875
- | 6476 | 03 | Bradford | 25.5 | 33.0 | 34 | 3.375 | 37.375 | 4.375
- | 12486 | 03 | Columbia | 33.3 | 35.1 | 40 | 3.375 | 43.375 | 8.275
Y | 12555 | 03 | Columbia | 33.0 | 27.0 | 24 | 3.375 | 27.375 | 0.375
Y | 12592 | 03 | Columbia | 25.8 | 25.5 | 24 | 3.375 | 27.375 | 1.875
Y | 12738 | 03 | Columbia | 17.9 | 27.5 | 24 | 3.375 | 27.375 | -0.125
Y | 12745 | 03 | Columbia | 29.5 | 40.8 | 38 | 3.375 | 41.375 | 0.575
- | 24511 | 03 | Lycoming | 56.2 | 35.0 | 32 | 3.375 | 35.375 | 0.375
Y | 24566 | 03 | Lycoming | 24.5 | 16.5 | 24 | 3.375 | 27.375 | 10.875
- | 24591 | 03 | Lycoming | 35.7 | 26.0 | 28 | 3.375 | 31.375 | 5.375
- | 24603 | 03 | Lycoming | -- | 26.7 | 30 | 3.375 | 33.375 | 6.675
- | 24748 | 03 | Lycoming | 26.2 | 39.0 | 40 | 3.375 | 43.375 | 4.375
- | 24751 | 03 | Lycoming | 25.7 | 39.5 | 40 | 3.375 | 43.375 | 3.875
Y | 24850 | 03 | Lycoming | 18.0 | 42.0 | 40 | 3.375 | 43.375 | 1.375
- | 24881 | 03 | Lycoming | 20.0 | 26.0 | 32 | 3.375 | 35.375 | 9.375
Y | 24928 | 03 | Lycoming | 16.4 | 37.0 | 33 | 3.375 | 36.375 | -0.625
- | 24938 | 03 | Lycoming | 26.0 | 39.3 | 28 | 3.375 | 31.375 | -7.925
- | 28361 | 03 | Montour | 27.5 | 33.0 | 26 | 3.375 | 29.375 | -3.625
- | 28387 | 03 | Montour | 19.1 | 41.6 | 42 | 3.375 | 45.375 | 3.775
Y | 28389 | 03 | Montour | 26.2 | 46.6 | 38 | 3.375 | 41.375 | -5.225
- | 29174 | 03 | Northumberland | 32.9 | 44.0 | 44 | 3.375 | 47.375 | 3.375
- | 29178 | 03 | Northumberland | 26.3 | 23.4 | 24 | 3.375 | 27.375 | 3.975
- | 29303 | 03 | Northumberland | 26.7 | 26.5 | 28 | 3.375 | 31.375 | 4.875
- | 29306 | 03 | Northumberland | 26.4 | 14.1 | 28 | 3.375 | 31.375 | 17.275
- | 29311 | 03 | Northumberland | 20.4 | 50.0 | 50 | 3.375 | 53.375 | 3.375
- | 31169 | 03 | Snyder | 39.5 | 45.0 | 40 | 3.375 | 43.375 | -1.625
- | 31948 | 03 | Sullivan | 25.8 | 36.0 | 36 | 3.375 | 39.375 | 3.375
Y | 31966 | 03 | Sullivan | 33.0 | 25.0 | 28 | 3.375 | 31.375 | 6.375
- | 31981 | 03 | Tioga | 25.8 | 28.0 | 28 | 3.375 | 31.375 | 3.375
- | 32822 | 03 | Tioga | 47.5 | 42.7 | 44 | 3.375 | 47.375 | 4.675
Y | 32843 | 03 | Tioga | 26.1 | 43.0 | 44 | 3.375 | 47.375 | 4.375
- | 32931 | 03 | Tioga | 26.4 | 41.7 | 38 | 3.375 | 41.375 | -0.325
Y | 33080 | 03 | Tioga | 24.5 | 41.1 | 42 | 3.375 | 45.375 | 4.275
Y | 33083 | 03 | Tioga | 23.6 | 41.7 | 42 | 3.375 | 45.375 | 3.675
Y | 33180 | 03 | Tioga | 26.3 | 33.2 | 32 | 3.375 | 35.375 | 2.175
- | 33209 | 03 | Tioga | 27.3 | 36.0 | 32 | 3.375 | 35.375 | -0.625
- | 33469 | 03 | Union | 24.5 | 24.9 | 28 | 3.375 | 31.375 | 6.475
- | 33470 | 03 | Union | 25.5 | 25.9 | 28 | 3.375 | 31.375 | 5.475
Y | 33478 | 03 | Union | 20.2 | 24.0 | 28 | 3.375 | 31.375 | 7.375
Y | 33543 | 03 | Union | 22.1 | 34.0 | 34 | 3.375 | 37.375 | 3.375
- | 20820 | 04 | Lackawanna | 33.5 | 25.0 | 32 | 3.375 | 35.375 | 10.375
- | 23795 | 04 | Luzerne | 40.0 | 44.0 | 42 | 3.375 | 45.375 | 1.375
- | 24493 | 04 | Luzerne | 35.5 | 41.5 | 38 | 3.375 | 41.375 | -0.125
Y | 29947 | 04 | Pike | 29.8 | 52.3 | 40 | 3.375 | 43.375 | -8.925
- | 29982 | 04 | Pike | 23.7 | 34.0 | 34 | 3.375 | 37.375 | 3.375
- | 32153 | 04 | Susquehanna | 49.0 | 26.3 | 32 | 3.375 | 35.375 | 9.075
- | 32244 | 04 | Susquehanna | 29.0 | 24.2 | 28 | 3.375 | 31.375 | 7.175
Y | 32307 | 04 | Susquehanna | 25.4 | 27.4 | 28 | 3.375 | 31.375 | 3.975
- | 32308 | 04 | Susquehanna | 26.0 | 26.1 | 28 | 3.375 | 31.375 | 5.275
- | 32327 | 04 | Susquehanna | 28.0 | 26.3 | 28 | 3.375 | 31.375 | 5.075
- | 32365 | 04 | Susquehanna | 37.5 | 43.0 | 40 | 3.375 | 43.375 | 0.375
- | 32378 | 04 | Susquehanna | 37.5 | 42.5 | 40 | 3.375 | 43.375 | 0.875
Y | 32401 | 04 | Susquehanna | 28.0 | 26.8 | 32 | 3.375 | 35.375 | 8.575
- | 32437 | 04 | Susquehanna | 26.2 | 39.3 | 40 | 3.375 | 43.375 | 4.075
Y | 32478 | 04 | Susquehanna | 31.0 | 41.1 | 38 | 3.375 | 41.375 | 0.275
- | 32507 | 04 | Susquehanna | 33.5 | 41.6 | 40 | 3.375 | 43.375 | 1.775
- | 32647 | 04 | Susquehanna | 30.3 | 36.0 | 40 | 3.375 | 43.375 | 7.375
- | 35471 | 04 | Wayne | 26.0 | 35.7 | 40 | 3.375 | 43.375 | 7.675
- | 35508 | 04 | Wayne | 26.0 | 37.0 | 40 | 3.375 | 43.375 | 6.375
Y | 35624 | 04 | Wayne | 18.3 | 36.5 | 40 | 3.375 | 43.375 | 6.875
Y | 35654 | 04 | Wayne | 24.5 | 33.3 | 32 | 3.375 | 35.375 | 2.075
- | 35675 | 04 | Wayne | 24.3 | 25.8 | 32 | 3.375 | 35.375 | 9.575
Y | 35765 | 04 | Wayne | 24.0 | 26.0 | 32 | 3.375 | 35.375 | 9.375
Y | 35802 | 04 | Wayne | 33.0 | 31.0 | 32 | 3.375 | 35.375 | 4.375
- | 35810 | 04 | Wayne | 21.0 | 26.2 | 26 | 3.375 | 29.375 | 3.175
- | 37163 | 04 | Wyoming | 31.0 | 35.8 | 24 | 3.375 | 27.375 | -8.425
- | 37172 | 04 | Wyoming | 27.5 | 24.0 | 24 | 3.375 | 27.375 | 3.375
Y | 37192 | 04 | Wyoming | 29.0 | 42.0 | 40 | 3.375 | 43.375 | 1.375
Y | 37222 | 04 | Wyoming | 27.6 | 44.7 | 40 | 3.375 | 43.375 | -1.325
- | 4900 | 05 | Berks | 25.0 | 18.2 | 28 | 3.375 | 31.375 | 13.175
- | 4946 | 05 | Berks | 23.2 | 18.2 | 28 | 3.375 | 31.375 | 13.175
- | 4953 | 05 | Berks | 33.5 | 26.8 | 28 | 3.375 | 31.375 | 4.575
- | 4957 | 05 | Berks | 27.5 | 45.0 | 44 | 3.375 | 47.375 | 2.375
- | 5147 | 05 | Berks | 26.0 | 26.0 | 30 | 3.375 | 33.375 | 7.375
Y | 8994 | 05 | Carbon | 43.7 | 32.9 | 34 | 3.375 | 37.375 | 4.475
- | 9104 | 05 | Carbon | 26.2 | 34.0 | 34 | 3.375 | 37.375 | 3.375
- | 23144 | 05 | Lehigh | 63.0 | 34.0 | 34 | 3.375 | 37.375 | 3.375
- | 23228 | 05 | Lehigh | 41.4 | 30.5 | 34 | 3.375 | 37.375 | 6.875
- | 23330 | 05 | Lehigh | 25.8 | 32.3 | 34 | 3.375 | 37.375 | 5.075
- | 23136 | 05 | Lehigh | 45.0 | 26.3 | 34 | 3.375 | 37.375 | 11.075
- | 26785 | 05 | Monroe | 43.0 | 27.0 | 24 | 3.375 | 27.375 | 0.375
Y | 26795 | 05 | Monroe | 54.0 | 25.0 | 28 | 3.375 | 31.375 | 6.375
Y | 26811 | 05 | Monroe | 33.9 | 43.0 | 34 | 3.375 | 37.375 | -5.625
Y | 26832 | 05 | Monroe | 40.0 | 26.0 | 40 | 3.375 | 43.375 | 17.375
Y | 26887 | 05 | Monroe | 71.7 | 35.1 | 32 | 3.375 | 35.375 | 0.275
Y | 26888 | 05 | Monroe | 24.8 | 16.4 | 24 | 3.375 | 27.375 | 10.975
Y | 26901 | 05 | Monroe | 31.0 | 25.5 | 32 | 3.375 | 35.375 | 9.875
Y | 26904 | 05 | Monroe | 59.3 | 33.3 | 32 | 3.375 | 35.375 | 2.075
Y | 26907 | 05 | Monroe | 43.3 | 56.2 | 54 | 3.375 | 57.375 | 1.175
Y | 26914 | 05 | Monroe | 42.0 | 35.7 | 40 | 3.375 | 43.375 | 7.675
Y | 26924 | 05 | Monroe | 30.5 | 34 | 37 | 3.375 | 40.375 | 6.375
Y | 26962 | 05 | Monroe | 33.7 | 26.2 | 28 | 3.375 | 31.375 | 5.175
Y | 27011 | 05 | Monroe | 26.1 | 25.7 | 28 | 3.375 | 31.375 | 5.675
Y | 27017 | 05 | Monroe | 25.8 | 20.0 | 24 | 3.375 | 27.375 | 7.375
Y | 27042 | 05 | Monroe | 43.0 | 26.0 | 26 | 3.375 | 29.375 | 3.375
Y | 27055 | 05 | Monroe | 26.8 | 27.5 | 36 | 3.375 | 39.375 | 11.875
Y | 27059 | 05 | Monroe | 30.3 | 19.1 | 24 | 3.375 | 27.375 | 8.275
- | 28493 | 05 | Northampton | 56.5 | 32.9 | 24 | 3.375 | 27.375 | -5.525
- | 28494 | 05 | Northampton | 56.5 | 26.3 | 24 | 3.375 | 27.375 | 1.075
R | 42278 | 05 | Northampton | 45.4 | 26.7 | 24 | 3.375 | 27.375 | 0.675
R | 42446 | 05 | Northampton | 45.4 | 26.4 | 24 | 3.375 | 27.375 | 0.975
- | 28606 | 05 | Northampton | 26.2 | 20.4 | 28 | 3.375 | 31.375 | 10.975
- | 28660 | 05 | Northampton | 26.0 | 39.5 | 38 | 3.375 | 41.375 | 1.875
- | 28672 | 05 | Northampton | 30.5 | 25.8 | 32 | 3.375 | 35.375 | 9.575
Y | 30678 | 05 | Schuylkill | 24.0 | 25.8 | 30 | 3.375 | 33.375 | 7.575
Y | 30679 | 05 | Schuylkill | 25.0 | 47.5 | 38 | 3.375 | 41.375 | -6.125
Y | 30680 | 05 | Schuylkill | 34.8 | 26.4 | 30 | 3.375 | 33.375 | 6.975
Y | 30730 | 05 | Schuylkill | 69.7 | 27.3 | 32 | 3.375 | 35.375 | 8.075
Y | 30832 | 05 | Schuylkill | 26.0 | 24.5 | 28 | 3.375 | 31.375 | 6.875
Y | 30856 | 05 | Schuylkill | 20.7 | 25.5 | 28 | 3.375 | 31.375 | 5.875
Y | 30862 | 05 | Schuylkill | 18.2 | 33.5 | 29 | 3.375 | 32.375 | -1.125
- | 7262 | 06 | Bucks | 62.5 | 40.0 | 36 | 3.375 | 39.375 | -0.625
- | 10497 | 06 | Chester | 19.5 | 35.5 | 40 | 3.375 | 43.375 | 7.875
- | 10599 | 06 | Chester | 24.0 | 23.7 | 28 | 3.375 | 31.375 | 7.675
- | 15002 | 06 | Delaware | 30.2 | 49.0 | 46 | 3.375 | 49.375 | 0.375
- | 27513 | 06 | Montgomery | 29 | 29.0 | 40 | 3.375 | 43.375 | 14.375
- | 27605 | 06 | Montgomery | 48.5 | 26.0 | 30 | 3.375 | 33.375 | 7.375
- | 27643 | 06 | Montgomery | 26.0 | 28.0 | 30 | 3.375 | 33.375 | 5.375
- | 27757 | 06 | Montgomery | 34.6 | 37.5 | 36 | 3.375 | 39.375 | 1.875
- | 27868 | 06 | Montgomery | 31.5 | 37.5 | 32 | 3.375 | 35.375 | -2.125
- | 47 | 08 | Adams | 46.8 | 26.2 | 24 | 3.375 | 27.375 | 1.175
- | 71 | 08 | Adams | 26.0 | 33.5 | 28 | 3.375 | 31.375 | -2.125
- | 75 | 08 | Adams | 25.9 | 30.3 | 28 | 3.375 | 31.375 | 1.075
- | 87 | 08 | Adams | 41.3 | 26.0 | 30 | 3.375 | 33.375 | 7.375
- | 98 | 08 | Adams | 26.2 | 26.0 | 33 | 3.375 | 36.375 | 10.375
- | 128 | 08 | Adams | 28.4 | 24.3 | 24 | 3.375 | 27.375 | 3.075
- | 135 | 08 | Adams | 26.0 | 21.0 | 27 | 3.375 | 30.375 | 9.375
- | 148 | 08 | Adams | 32.8 | 31.0 | 26 | 3.375 | 29.375 | -1.625
- | 160 | 08 | Adams | 25.2 | 27.5 | 26 | 3.375 | 29.375 | 1.875
- | 185 | 08 | Adams | 25.7 | 25.0 | 30 | 3.375 | 33.375 | 8.375
- | 198 | 08 | Adams | 26.0 | 23.2 | 30 | 3.375 | 33.375 | 10.175
- | 229 | 08 | Adams | 27.6 | 33.5 | 30 | 3.375 | 33.375 | -0.125
- | 319 | 08 | Adams | 13.8 | 27.5 | 28 | 3.375 | 31.375 | 3.875
- | 362 | 08 | Adams | 31.4 | 26.0 | 30 | 3.375 | 33.375 | 7.375
- | 364 | 08 | Adams | 26.0 | 26.2 | 30 | 3.375 | 33.375 | 7.175
- | 381 | 08 | Adams | 27.2 | 63.0 | 54 | 3.375 | 57.375 | -5.625
- | 13564 | 08 | Cumberland | 75.5 | 41.4 | 32 | 3.375 | 35.375 | -6.025
- | 13616 | 08 | Cumberland | 28.0 | 25.8 | 32 | 3.375 | 35.375 | 9.575
- | 13735 | 08 | Cumberland | 25.6 | 45.0 | 41 | 3.375 | 44.375 | -0.625
- | 13741 | 08 | Cumberland | 24.4 | 43.0 | 38 | 3.375 | 41.375 | -1.625
- | 13824 | 08 | Cumberland | 25.9 | 56.5 | 56 | 3.375 | 59.375 | 2.875
- | 13896 | 08 | Cumberland | 29.8 | 56.5 | 56 | 3.375 | 59.375 | 2.875
- | 13946 | 08 | Cumberland | 18.0 | 26.2 | 32 | 3.375 | 35.375 | 9.175
- | 13948 | 08 | Cumberland | 20.8 | 26.0 | 28 | 3.375 | 31.375 | 5.375
- | 13961 | 08 | Cumberland | 24.3 | 30.5 | 32 | 3.375 | 35.375 | 4.875
- | 14441 | 08 | Dauphin | 20.0 | 62.5 | 64 | 3.375 | 67.375 | 4.875
- | 14481 | 08 | Dauphin | 29.7 | 19.5 | 26 | 3.375 | 29.375 | 9.875
- | 14578 | 08 | Dauphin | 26.9 | 24.0 | 22 | 3.375 | 25.375 | 1.375
- | 17407 | 08 | Franklin | 37.4 | 30.2 | 32 | 3.375 | 35.375 | 5.175
- | 17408 | 08 | Franklin | 26.0 | 29 | 40 | 3.375 | 43.375 | 14.375
- | 17471 | 08 | Franklin | 32.6 | 48.5 | 36 | 3.375 | 39.375 | -9.125
- | 17592 | 08 | Franklin | 27.4 | 26.0 | 32 | 3.375 | 35.375 | 9.375
- | 17593 | 08 | Franklin | 30.2 | 34.6 | 26 | 3.375 | 29.375 | -5.225
- | 20976 | 08 | Lancaster | 26.8 | 31.5 | 28 | 3.375 | 31.375 | -0.125
- | 21043 | 08 | Lancaster | 56.8 | 46.8 | 48 | 3.375 | 51.375 | 4.575
- | 21196 | 08 | Lancaster | 45.0 | 26.0 | 40 | 3.375 | 43.375 | 17.375
- | 21237 | 08 | Lancaster | 32.8 | 25.9 | 40 | 3.375 | 43.375 | 17.475
- | 21238 | 08 | Lancaster | 32.6 | 41.3 | 40 | 3.375 | 43.375 | 2.075
- | 21251 | 08 | Lancaster | 36.0 | 26.2 | 40 | 3.375 | 43.375 | 17.175
- | 21277 | 08 | Lancaster | 52.3 | 28.4 | 40 | 3.375 | 43.375 | 14.975
- | 21292 | 08 | Lancaster | 34.5 | 26.0 | 28 | 3.375 | 31.375 | 5.375
- | 21326 | 08 | Lancaster | 30.5 | 32.8 | 40 | 3.375 | 43.375 | 10.575
- | 21403 | 08 | Lancaster | 17.8 | 25.2 | 40 | 3.375 | 43.375 | 18.175
- | 21409 | 08 | Lancaster | 22.9 | 25.7 | 28 | 3.375 | 31.375 | 5.675
- | 21415 | 08 | Lancaster | 22.7 | 26.0 | 28 | 3.375 | 31.375 | 5.375
- | 21417 | 08 | Lancaster | 20.2 | 27.6 | 28 | 3.375 | 31.375 | 3.775
- | 21439 | 08 | Lancaster | 27.2 | 13.8 | 28 | 3.375 | 31.375 | 17.575
- | 21446 | 08 | Lancaster | 18.1 | 31.4 | 28 | 3.375 | 31.375 | -0.025
- | 21454 | 08 | Lancaster | 23.0 | 26.0 | 28 | 3.375 | 31.375 | 5.375
- | 21459 | 08 | Lancaster | 21.7 | 27.2 | 28 | 3.375 | 31.375 | 4.175
- | 21474 | 08 | Lancaster | 26.2 | 75.5 | 74 | 3.375 | 77.375 | 1.875
- | 21482 | 08 | Lancaster | 19.0 | 28.0 | 40 | 3.375 | 43.375 | 15.375
- | 21487 | 08 | Lancaster | 26.0 | 25.6 | 30 | 3.375 | 33.375 | 7.775
- | 21514 | 08 | Lancaster | 27.3 | 24.4 | 40 | 3.375 | 43.375 | 18.975
- | 21518 | 08 | Lancaster | 26.2 | 25.9 | 28 | 3.375 | 31.375 | 5.475
- | 21533 | 08 | Lancaster | 24.0 | 29.8 | 40 | 3.375 | 43.375 | 13.575
- | 21536 | 08 | Lancaster | 25.7 | 18.0 | 28 | 3.375 | 31.375 | 13.375
- | 21545 | 08 | Lancaster | 24.6 | 20.8 | 28 | 3.375 | 31.375 | 10.575
- | 21558 | 08 | Lancaster | 23.0 | 24.3 | 28 | 3.375 | 31.375 | 7.075
- | 21559 | 08 | Lancaster | 18.5 | 20.0 | 24 | 3.375 | 27.375 | 7.375
- | 21595 | 08 | Lancaster | 20.2 | 29.7 | 32 | 3.375 | 35.375 | 5.675
- | 21601 | 08 | Lancaster | 25.0 | 26.9 | 28 | 3.375 | 31.375 | 4.475
- | 21637 | 08 | Lancaster | 26.0 | 37.4 | 32 | 3.375 | 35.375 | -2.025
- | 21662 | 08 | Lancaster | 28.0 | 26.0 | 28 | 3.375 | 31.375 | 5.375
- | 22812 | 08 | Lebanon | 66.2 | 32.6 | 38 | 3.375 | 41.375 | 8.775
- | 29426 | 08 | Perry | 42 | 27.4 | 28 | 3.375 | 31.375 | 3.975
- | 29451 | 08 | Perry | 27.1 | 30.2 | 28 | 3.375 | 31.375 | 1.175
- | 29468 | 08 | Perry | 33.3 | 26.8 | 40 | 3.375 | 43.375 | 16.575
- | 29518 | 08 | Perry | 27.7 | 56.8 | 52 | 3.375 | 55.375 | -1.425
- | 29565 | 08 | Perry | 26.4 | 45.0 | 40 | 3.375 | 43.375 | -1.625
- | 29566 | 08 | Perry | 23.0 | 32.8 | 34 | 3.375 | 37.375 | 4.575
- | 29605 | 08 | Perry | 44.3 | 32.6 | 36 | 3.375 | 39.375 | 6.775
- | 29651 | 08 | Perry | 15.0 | 36.0 | 24 | 3.375 | 27.375 | -8.625
- | 29673 | 08 | Perry | 24.4 | 52.3 | 52 | 3.375 | 55.375 | 3.075
- | 29693 | 08 | Perry | 27.7 | 34.5 | 30 | 3.375 | 33.375 | -1.125
- | 37488 | 08 | York | 25.8 | 30.5 | 40 | 3.375 | 43.375 | 12.875
- | 37491 | 08 | York | 26.0 | 17.8 | 28 | 3.375 | 31.375 | 13.575
- | 37590 | 08 | York | 25.7 | 22.9 | 28 | 3.375 | 31.375 | 8.475
- | 37607 | 08 | York | 26.1 | 22.7 | 28 | 3.375 | 31.375 | 8.675
- | 37608 | 08 | York | 26.5 | 20.2 | 28 | 3.375 | 31.375 | 11.175
- | 37641 | 08 | York | 27.5 | 27.2 | 28 | 3.375 | 31.375 | 4.175
- | 37725 | 08 | York | 42.6 | 18.1 | 28 | 3.375 | 31.375 | 13.275
- | 37726 | 08 | York | 27.5 | 23.0 | 28 | 3.375 | 31.375 | 8.375
- | 37878 | 08 | York | 25.6 | 21.7 | 28 | 3.375 | 31.375 | 9.675
- | 37890 | 08 | York | 20.0 | 26.2 | 24 | 3.375 | 27.375 | 1.175
- | 37921 | 08 | York | 26.3 | 19.0 | 28 | 3.375 | 31.375 | 12.375
- | 37946 | 08 | York | 26.0 | 26.0 | 32 | 3.375 | 35.375 | 9.375
- | 37976 | 08 | York | 24.6 | 27.3 | 28 | 3.375 | 31.375 | 4.075
- | 38007 | 08 | York | 19.5 | 26.2 | 28 | 3.375 | 31.375 | 5.175
- | 38023 | 08 | York | 25.3 | 24.0 | 28 | 3.375 | 31.375 | 7.375
- | 3954 | 09 | Bedford | 32.4 | 25.7 | 28 | 3.375 | 31.375 | 5.675
- | 3955 | 09 | Bedford | 43.1 | 24.6 | 28 | 3.375 | 31.375 | 6.775
- | 4010 | 09 | Bedford | 39.8 | 23.0 | 28 | 3.375 | 31.375 | 8.375
- | 4044 | 09 | Bedford | 25.8 | 18.5 | 28 | 3.375 | 31.375 | 12.875
- | 4122 | 09 | Bedford | 24.1 | 20.2 | 30 | 3.375 | 33.375 | 13.175
- | 4174 | 09 | Bedford | 18.2 | 25.0 | 28 | 3.375 | 31.375 | 6.375
- | 4177 | 09 | Bedford | 19.6 | 26.0 | 32 | 3.375 | 35.375 | 9.375
- | 4196 | 09 | Bedford | 28.3 | 28.0 | 32 | 3.375 | 35.375 | 7.375
- | 4386 | 09 | Bedford | 25.0 | 66.2 | 66 | 3.375 | 69.375 | 3.175
- | 5699 | 09 | Blair | 33.0 | 42 | 52 | 3.375 | 55.375 | 13.375
- | 5702 | 09 | Blair | 32.9 | 27.1 | 28 | 3.375 | 31.375 | 4.275
- | 5709 | 09 | Blair | 26.0 | 33.3 | 34 | 3.375 | 37.375 | 4.075
- | 5763 | 09 | Blair | 25.8 | 27.7 | 32 | 3.375 | 35.375 | 7.675
- | 5883 | 09 | Blair | 30.0 | 26.4 | 28 | 3.375 | 31.375 | 4.975
- | 8424 | 09 | Cambria | 31.4 | 23.0 | 28 | 3.375 | 31.375 | 8.375
- | 8425 | 09 | Cambria | 28.1 | 44.3 | 32 | 3.375 | 35.375 | -8.925
- | 8580 | 09 | Cambria | 26.0 | 15.0 | 28 | 3.375 | 31.375 | 16.375
- | 17813 | 09 | Fulton | 25.9 | 24.4 | 24 | 3.375 | 27.375 | 2.975
- | 17826 | 09 | Fulton | 33.3 | 27.7 | 28 | 3.375 | 31.375 | 3.675
- | 17827 | 09 | Fulton | 26.0 | 25.8 | 40 | 3.375 | 43.375 | 17.575
- | 17828 | 09 | Fulton | 26.1 | 26.0 | 30 | 3.375 | 33.375 | 7.375
- | 17832 | 09 | Fulton | 26.0 | 25.7 | 30 | 3.375 | 33.375 | 7.675
- | 17850 | 09 | Fulton | 24.4 | 26.1 | 32 | 3.375 | 35.375 | 9.275
- | 17853 | 09 | Fulton | 24.5 | 26.5 | 32 | 3.375 | 35.375 | 8.875
- | 17873 | 09 | Fulton | 28.0 | 27.5 | 40 | 3.375 | 43.375 | 15.875
- | 18576 | 09 | Huntingdon | 65.0 | 42.6 | 26 | 3.375 | 29.375 | -13.225
- | 18601 | 09 | Huntingdon | 33.0 | 27.5 | 28 | 3.375 | 31.375 | 3.875
- | 18603 | 09 | Huntingdon | 33.8 | 25.6 | 32 | 3.375 | 35.375 | 9.775
- | 18703 | 09 | Huntingdon | 32.9 | 20.0 | 24 | 3.375 | 27.375 | 7.375
- | 18742 | 09 | Huntingdon | 29.4 | 26.3 | 28 | 3.375 | 31.375 | 5.075
- | 18773 | 09 | Huntingdon | 20.1 | 26.0 | 40 | 3.375 | 43.375 | 17.375
- | 18784 | 09 | Huntingdon | 25.0 | 24.6 | 28 | 3.375 | 31.375 | 6.775
- | 18785 | 09 | Huntingdon | 27.0 | 19.5 | 28 | 3.375 | 31.375 | 11.875
- | 18881 | 09 | Huntingdon | 25.0 | 25.3 | 28 | 3.375 | 31.375 | 6.075
- | 45123 | 09 | Somerset | 26.0 | 32.4 | 40 | 3.375 | 43.375 | 10.975
- | 41517 | 09 | Somerset | 26.0 | 43.1 | 40 | 3.375 | 43.375 | 0.275
- | 31343 | 09 | Somerset | 40.0 | 39.8 | 40 | 3.375 | 43.375 | 3.575
- | 31469 | 09 | Somerset | 34.0 | 25.8 | 30 | 3.375 | 33.375 | 7.575
- | 31470 | 09 | Somerset | 26.0 | 24.1 | 28 | 3.375 | 31.375 | 7.275
- | 31471 | 09 | Somerset | 25.0 | 18.2 | 24 | 3.375 | 27.375 | 9.175
- | 31521 | 09 | Somerset | 40.0 | 19.6 | 26 | 3.375 | 29.375 | 9.775
- | 31528 | 09 | Somerset | 23.7 | 28.3 | 28 | 3.375 | 31.375 | 3.075
- | 31532 | 09 | Somerset | 20.0 | 25.0 | 30 | 3.375 | 33.375 | 8.375
- | 31588 | 09 | Somerset | 24.1 | 33.0 | 30 | 3.375 | 33.375 | 0.375
- | 31608 | 09 | Somerset | 14.0 | 32.9 | 30 | 3.375 | 33.375 | 0.475
- | 31630 | 09 | Somerset | 24.2 | 26.0 | 30 | 3.375 | 33.375 | 7.375
- | 31651 | 09 | Somerset | 18.7 | 25.8 | 26 | 3.375 | 29.375 | 3.575
- | 31758 | 09 | Somerset | 31.5 | 30.0 | 30 | 3.375 | 33.375 | 3.375
- | 2992 | 10 | Armstrong | 37.6 | 31.4 | 32 | 3.375 | 35.375 | 3.975
Y | 3097 | 10 | Armstrong | 40.0 | 28.1 | 32 | 3.375 | 35.375 | 7.275
Y | 3160 | 10 | Armstrong | 25.0 | 26.0 | 30 | 3.375 | 33.375 | 7.375
- | 3169 | 10 | Armstrong | 31.2 | 25.9 | 24 | 3.375 | 27.375 | 1.475
- | 3176 | 10 | Armstrong | 24.0 | 33.3 | 30 | 3.375 | 33.375 | 0.075
- | 3232 | 10 | Armstrong | 19.7 | 26.0 | 30 | 3.375 | 33.375 | 7.375
- | 3245 | 10 | Armstrong | 23.7 | 26.1 | 30 | 3.375 | 33.375 | 7.275
- | 3278 | 10 | Armstrong | 28.0 | 26.0 | 30 | 3.375 | 33.375 | 7.375
Y | 3282 | 10 | Armstrong | 26.6 | 24.4 | 28 | 3.375 | 31.375 | 6.975
Y | 3293 | 10 | Armstrong | 26.3 | 24.5 | 28 | 3.375 | 31.375 | 6.875
- | 3294 | 10 | Armstrong | 48.0 | 28.0 | 28 | 3.375 | 31.375 | 3.375
Y | 7834 | 10 | Butler | 41.0 | 65.0 | 62 | 3.375 | 65.375 | 0.375
- | 7925 | 10 | Butler | 33.4 | 33.0 | 32 | 3.375 | 35.375 | 2.375
Y | 7935 | 10 | Butler | 34.0 | 33.8 | 32 | 3.375 | 35.375 | 1.575
- | 8016 | 10 | Butler | 33.0 | 32.9 | 32 | 3.375 | 35.375 | 2.475
Y | 8025 | 10 | Butler | 34.0 | 29.4 | 32 | 3.375 | 35.375 | 5.975
- | 8061 | 10 | Butler | 19.0 | 20.1 | 24 | 3.375 | 27.375 | 7.275
- | 8071 | 10 | Butler | 24.0 | 25.0 | 24 | 3.375 | 27.375 | 2.375
Y | 8073 | 10 | Butler | 20.8 | 27.0 | 24 | 3.375 | 27.375 | 0.375
- | 8104 | 10 | Butler | 35.6 | 25.0 | 24 | 3.375 | 27.375 | 2.375
- | 8113 | 10 | Butler | 31.0 | 26.0 | 40 | 3.375 | 43.375 | 17.375
- | 8334 | 10 | Butler | 35.3 | 26.0 | 40 | 3.375 | 43.375 | 17.375
- | 10975 | 10 | Clarion | 41.6 | 40.0 | 40 | 3.375 | 43.375 | 3.375
- | 10997 | 10 | Clarion | 41.8 | 34.0 | 28 | 3.375 | 31.375 | -2.625
- | 10996 | 10 | Clarion | 37.8 | 26.0 | 28 | 3.375 | 31.375 | 5.375
- | 11042 | 10 | Clarion | 24.5 | 25.0 | 28 | 3.375 | 31.375 | 6.375
- | 11049 | 10 | Clarion | 27.6 | 40.0 | 32 | 3.375 | 35.375 | -4.625
- | 11088 | 10 | Clarion | 36.4 | 23.7 | 28 | 3.375 | 31.375 | 7.675
- | 19087 | 10 | Indiana | 43.0 | 20.0 | 28 | 3.375 | 31.375 | 11.375
- | 19183 | 10 | Indiana | 33.5 | 24.1 | 24 | 3.375 | 27.375 | 3.275
- | 19200 | 10 | Indiana | 26.6 | 14.0 | 24 | 3.375 | 27.375 | 13.375
- | 19320 | 10 | Indiana | 26.0 | 24.2 | 24 | 3.375 | 27.375 | 3.175
- | 19392 | 10 | Indiana | 33.5 | 18.7 | 24 | 3.375 | 27.375 | 8.675
- | 19550 | 10 | Jefferson | 35.5 | 31.5 | 30 | 3.375 | 33.375 | 1.875
- | 19699 | 10 | Jefferson | 33.2 | 37.6 | 26 | 3.375 | 29.375 | -8.225
- | 19708 | 10 | Jefferson | 29.5 | 31.2 | 28 | 3.375 | 31.375 | 0.175
- | 19737 | 10 | Jefferson | 22.0 | 24.0 | 40 | 3.375 | 43.375 | 19.375
- | 19807 | 10 | Jefferson | 25.1 | 19.7 | 38 | 3.375 | 41.375 | 21.675
Y | 505 | 11 | Allegheny | 70.0 | 23.7 | 32 | 3.375 | 35.375 | 11.675
- | 659 | 11 | Allegheny | 42.0 | 28.0 | 40 | 3.375 | 43.375 | 15.375
- | 664 | 11 | Allegheny | 75.0 | 48.0 | 30 | 3.375 | 33.375 | -14.625
- | 709 | 11 | Allegheny | 73.0 | 33.4 | 30 | 3.375 | 33.375 | -0.025
- | 954 | 11 | Allegheny | 40.0 | 33.0 | 28 | 3.375 | 31.375 | -1.625
- | 961 | 11 | Allegheny | 26.0 | 19.0 | 28 | 3.375 | 31.375 | 12.375
- | 1334 | 11 | Allegheny | 26.8 | 24.0 | 24 | 3.375 | 27.375 | 3.375
Y | 1339 | 11 | Allegheny | 33.0 | 35.6 | 44 | 3.375 | 47.375 | 11.775
- | 1346 | 11 | Allegheny | 31.5 | 31.0 | 30 | 3.375 | 33.375 | 2.375
- | 1365 | 11 | Allegheny | 48.0 | 35.3 | 32 | 3.375 | 35.375 | 0.075
- | 1372 | 11 | Allegheny | 48.0 | 41.6 | 38 | 3.375 | 41.375 | -0.225
Y | 1373 | 11 | Allegheny | 50.0 | 41.8 | 38 | 3.375 | 41.375 | -0.425
- | 1390 | 11 | Allegheny | 45.0 | 37.8 | 38 | 3.375 | 41.375 | 3.575
Y | 1397 | 11 | Allegheny | 28.0 | 24.5 | 26 | 3.375 | 29.375 | 4.875
Y | 1400 | 11 | Allegheny | 25.8 | 27.6 | 24 | 3.375 | 27.375 | -0.225
- | 1404 | 11 | Allegheny | 21.0 | 36.4 | 30 | 3.375 | 33.375 | -3.025
Y | 1405 | 11 | Allegheny | 28.0 | 43.0 | 40 | 3.375 | 43.375 | 0.375
Y | 1406 | 11 | Allegheny | 28.0 | 33.5 | 30 | 3.375 | 33.375 | -0.125
Y | 42177 | 11 | Allegheny | 34.5 | 26.6 | 24 | 3.375 | 27.375 | 0.775
- | 1424 | 11 | Allegheny | 22.5 | 26.0 | 24 | 3.375 | 27.375 | 1.375
Y | 1435 | 11 | Allegheny | 26.5 | 33.5 | 28 | 3.375 | 31.375 | -2.125
Y | 1455 | 11 | Allegheny | 35.0 | 35.5 | 32 | 3.375 | 35.375 | -0.125
Y | 1471 | 11 | Allegheny | 34.5 | 33.2 | 32 | 3.375 | 35.375 | 2.175
- | 1479 | 11 | Allegheny | 26.7 | 29.5 | 30 | 3.375 | 33.375 | 3.875
Y | 1481 | 11 | Allegheny | 29.0 | 22.0 | 24 | 3.375 | 27.375 | 5.375
- | 1496 | 11 | Allegheny | 23.0 | 25.1 | 24 | 3.375 | 27.375 | 2.275
- | 1498 | 11 | Allegheny | 29.6 | 42.0 | 30 | 3.375 | 33.375 | -8.625
- | 1519 | 11 | Allegheny | 33.0 | 75.0 | 66 | 3.375 | 69.375 | -5.625
- | 1520 | 11 | Allegheny | 38.0 | 73.0 | 76 | 3.375 | 79.375 | 6.375
- | 1523 | 11 | Allegheny | 28.0 | 40.0 | 30 | 3.375 | 33.375 | -6.625
- | 1527 | 11 | Allegheny | 28.0 | 26.0 | 30 | 3.375 | 33.375 | 7.375
Y | 1559 | 11 | Allegheny | 62.6 | 26.8 | 30 | 3.375 | 33.375 | 6.575
- | 1562 | 11 | Allegheny | 39.0 | 31.5 | 28 | 3.375 | 31.375 | -0.125
Y | 1567 | 11 | Allegheny | 39.4 | 48.0 | 36 | 3.375 | 39.375 | -8.625
- | 1568 | 11 | Allegheny | 40.0 | 48.0 | 36 | 3.375 | 39.375 | -8.625
Y | 1600 | 11 | Allegheny | 29.0 | 45.0 | 30 | 3.375 | 33.375 | -11.625
- | 1620 | 11 | Allegheny | 34.6 | 21.0 | 24 | 3.375 | 27.375 | 6.375
- | 1626 | 11 | Allegheny | 26.0 | 22.5 | 28 | 3.375 | 31.375 | 8.875
Y | 1671 | 11 | Allegheny | 32.0 | 26.7 | 28 | 3.375 | 31.375 | 4.675
- | 1704 | 11 | Allegheny | 27.8 | 23.0 | 28 | 3.375 | 31.375 | 8.375
Y | 1715 | 11 | Allegheny | 22.0 | 29.6 | 28 | 3.375 | 31.375 | 1.775
- | 1727 | 11 | Allegheny | 26.0 | 33.0 | 28 | 3.375 | 31.375 | -1.625
- | 1733 | 11 | Allegheny | 26.0 | 38.0 | 28 | 3.375 | 31.375 | -6.625
- | 1776 | 11 | Allegheny | 26.6 | 28.0 | 28 | 3.375 | 31.375 | 3.375
- | 1859 | 11 | Allegheny | 29.0 | 28.0 | 28 | 3.375 | 31.375 | 3.375
- | 1860 | 11 | Allegheny | 27.5 | 39.0 | 32 | 3.375 | 35.375 | -3.625
- | 1881 | 11 | Allegheny | 26.1 | 40.0 | 30 | 3.375 | 33.375 | -6.625
- | 1882 | 11 | Allegheny | 26.0 | 34.6 | 30 | 3.375 | 33.375 | -1.225
Y | 1950 | 11 | Allegheny | 25.5 | 26.0 | 34 | 3.375 | 37.375 | 11.375
- | 1974 | 11 | Allegheny | 28.0 | 27.8 | 28 | 3.375 | 31.375 | 3.575
- | 1976 | 11 | Allegheny | 32.6 | 26.0 | 24 | 3.375 | 27.375 | 1.375
- | 1980 | 11 | Allegheny | 35.0 | 26.0 | 26 | 3.375 | 29.375 | 3.375
- | 1982 | 11 | Allegheny | 32.0 | 26.6 | 26 | 3.375 | 29.375 | 2.775
- | 3599 | 11 | Beaver | 43.0 | 29.0 | 30 | 3.375 | 33.375 | 4.375
- | 3602 | 11 | Beaver | 22.0 | 27.5 | 30 | 3.375 | 33.375 | 5.875
- | 3647 | 11 | Beaver | 27.5 | 26.1 | 30 | 3.375 | 33.375 | 7.275
- | 3654 | 11 | Beaver | 40.0 | 26.0 | 30 | 3.375 | 33.375 | 7.375
- | 3693 | 11 | Beaver | 28.0 | 28.0 | 28 | 3.375 | 31.375 | 3.375
- | 3695 | 11 | Beaver | 29.5 | 32.6 | 32 | 3.375 | 35.375 | 2.775
- | 3717 | 11 | Beaver | 26.5 | 35.0 | 32 | 3.375 | 35.375 | 0.375
- | 3722 | 11 | Beaver | 32.2 | 32.0 | 32 | 3.375 | 35.375 | 3.375
- | 3723 | 11 | Beaver | 32.0 | 43.0 | 34 | 3.375 | 37.375 | -5.625
- | 3747 | 11 | Beaver | 26.0 | 22.0 | 30 | 3.375 | 33.375 | 11.375
- | 3749 | 11 | Beaver | 36.7 | 27.5 | 32 | 3.375 | 35.375 | 7.875
- | 3750 | 11 | Beaver | 36.7 | 40.0 | 30 | 3.375 | 33.375 | -6.625
- | 3755 | 11 | Beaver | 20.5 | 28.0 | 38 | 3.375 | 41.375 | 13.375
- | 3769 | 11 | Beaver | 14.0 | 29.5 | 32 | 3.375 | 35.375 | 5.875
- | 22262 | 11 | Lawrence | 37.5 | 26.5 | 30 | 3.375 | 33.375 | 6.875
- | 22265 | 11 | Lawrence | 31.0 | 32.2 | 30 | 3.375 | 33.375 | 1.175
- | 22269 | 11 | Lawrence | 42.0 | 32.0 | 30 | 3.375 | 33.375 | 1.375
- | 22277 | 11 | Lawrence | 43.6 | 26.0 | 30 | 3.375 | 33.375 | 7.375
- | 22281 | 11 | Lawrence | 42.0 | 36.7 | 30 | 3.375 | 33.375 | -3.325
- | 22358 | 11 | Lawrence | 38.5 | 36.7 | 32 | 3.375 | 35.375 | -1.325
- | 22359 | 11 | Lawrence | 26.0 | 20.5 | 26 | 3.375 | 29.375 | 8.875
- | 22362 | 11 | Lawrence | 24.2 | 14.0 | 22 | 3.375 | 25.375 | 11.375
- | 22369 | 11 | Lawrence | 26.5 | 37.5 | 28 | 3.375 | 31.375 | -6.125
- | 22374 | 11 | Lawrence | 18.2 | 31.0 | 28 | 3.375 | 31.375 | 0.375
- | 22378 | 11 | Lawrence | 27.5 | 42.0 | 34 | 3.375 | 37.375 | -4.625
- | 22379 | 11 | Lawrence | 27.5 | 43.6 | 40 | 3.375 | 43.375 | -0.225
- | 22396 | 11 | Lawrence | 20.0 | 42.0 | 38 | 3.375 | 41.375 | -0.625
- | 22416 | 11 | Lawrence | 24.0 | 38.5 | 28 | 3.375 | 31.375 | -7.125
- | 22433 | 11 | Lawrence | 48.4 | 26.0 | 28 | 3.375 | 31.375 | 5.375
- | 22439 | 11 | Lawrence | 25.0 | 24.2 | 28 | 3.375 | 31.375 | 7.175
- | 22441 | 11 | Lawrence | 26.5 | 26.5 | 26 | 3.375 | 29.375 | 2.875
- | 22455 | 11 | Lawrence | 27.0 | 18.2 | 22 | 3.375 | 25.375 | 7.175
- | 16651 | 12 | Fayette | 30.3 | 27.5 | 24 | 3.375 | 27.375 | -0.125
- | 16673 | 12 | Fayette | 25.0 | 27.5 | 24 | 3.375 | 27.375 | -0.125
- | 16713 | 12 | Fayette | 15.7 | 20.0 | 22 | 3.375 | 25.375 | 5.375
- | 16720 | 12 | Fayette | 14.0 | 24.0 | 28 | 3.375 | 31.375 | 7.375
- | 16725 | 12 | Fayette | 35.0 | 48.4 | 32 | 3.375 | 35.375 | -13.025
- | 16736 | 12 | Fayette | 24.0 | 25.0 | 22 | 3.375 | 25.375 | 0.375
- | 16752 | 12 | Fayette | 28.3 | 26.5 | 22 | 3.375 | 25.375 | -1.125
- | 16757 | 12 | Fayette | 25.7 | 27.0 | 30 | 3.375 | 33.375 | 6.375
- | 16758 | 12 | Fayette | 22.3 | 30.3 | 30 | 3.375 | 33.375 | 3.075
- | 16782 | 12 | Fayette | 25.0 | 25.0 | 26 | 3.375 | 29.375 | 4.375
- | 16789 | 12 | Fayette | 24.2 | 15.7 | 22 | 3.375 | 25.375 | 9.675
- | 16794 | 12 | Fayette | 27.0 | 14.0 | 22 | 3.375 | 25.375 | 11.375
- | 16806 | 12 | Fayette | 27.0 | 35.0 | 28 | 3.375 | 31.375 | -3.625
- | 16827 | 12 | Fayette | 29.5 | 24.0 | 26 | 3.375 | 29.375 | 5.375
- | 16840 | 12 | Fayette | 24.3 | 28.3 | 30 | 3.375 | 33.375 | 5.075
- | 16841 | 12 | Fayette | 26.0 | 25.7 | 24 | 3.375 | 27.375 | 1.675
- | 16868 | 12 | Fayette | 25.0 | 22.3 | 24 | 3.375 | 27.375 | 5.075
- | 16910 | 12 | Fayette | 26.0 | 25.0 | 26 | 3.375 | 29.375 | 4.375
- | 16922 | 12 | Fayette | 26.3 | 24.2 | 28 | 3.375 | 31.375 | 7.175
- | 16928 | 12 | Fayette | 26.2 | 27.0 | 26 | 3.375 | 29.375 | 2.375
- | 17052 | 12 | Fayette | 26.8 | 27.0 | 26 | 3.375 | 29.375 | 2.375
- | 18013 | 12 | Greene | 26.2 | 29.5 | 26 | 3.375 | 29.375 | -0.125
- | 18044 | 12 | Greene | 26.0 | 24.3 | 30 | 3.375 | 33.375 | 9.075
- | 18154 | 12 | Greene | 33.7 | 26.0 | 30 | 3.375 | 33.375 | 7.375
- | 18164 | 12 | Greene | 28.3 | 25.0 | 24 | 3.375 | 27.375 | 2.375
- | 18214 | 12 | Greene | 29.5 | 26.0 | 24 | 3.375 | 27.375 | 1.375
- | 18222 | 12 | Greene | 16.0 | 26.3 | 24 | 3.375 | 27.375 | 1.075
- | 18261 | 12 | Greene | 23.7 | 26.2 | 24 | 3.375 | 27.375 | 1.175
- | 18279 | 12 | Greene | 26.3 | 26.8 | 26 | 3.375 | 29.375 | 2.575
- | 18287 | 12 | Greene | 24.1 | 26.2 | 30 | 3.375 | 33.375 | 7.175
- | 18315 | 12 | Greene | 37.0 | 26.0 | 30 | 3.375 | 33.375 | 7.375
- | 18317 | 12 | Greene | 38.5 | 33.7 | 32 | 3.375 | 35.375 | 1.675
- | 18351 | 12 | Greene | 14.0 | 28.3 | 30 | 3.375 | 33.375 | 5.075
- | 18403 | 12 | Greene | 28.3 | 29.5 | 31 | 3.375 | 34.375 | 4.875
- | 34335 | 12 | Washington | 27.3 | 16.0 | 22 | 3.375 | 25.375 | 9.375
- | 34417 | 12 | Washington | 32.5 | 23.7 | 26 | 3.375 | 29.375 | 5.675
- | 34609 | 12 | Washington | 39.6 | 26.3 | 26 | 3.375 | 29.375 | 3.075
- | 34623 | 12 | Washington | 24.3 | 24.1 | 28 | 3.375 | 31.375 | 7.275
- | 34650 | 12 | Washington | 26.0 | 37.0 | 36 | 3.375 | 39.375 | 2.375
- | 34673 | 12 | Washington | 18.3 | 38.5 | 36 | 3.375 | 39.375 | 0.875
- | 34692 | 12 | Washington | 26.0 | 14.0 | 22 | 3.375 | 25.375 | 11.375
- | 34702 | 12 | Washington | 23.2 | 28.3 | 26 | 3.375 | 29.375 | 1.075
- | 34847 | 12 | Washington | 22.8 | 27.3 | 30 | 3.375 | 33.375 | 6.075
- | 34879 | 12 | Washington | 24.0 | 32.5 | 30 | 3.375 | 33.375 | 0.875
- | 34901 | 12 | Washington | 22.3 | 39.6 | 30 | 3.375 | 33.375 | -6.225
- | 34907 | 12 | Washington | 20.8 | 24.3 | 40 | 3.375 | 43.375 | 19.075
- | 34946 | 12 | Washington | 24.2 | 26.0 | 28 | 3.375 | 31.375 | 5.375
- | 34949 | 12 | Washington | 27.0 | 18.3 | 24 | 3.375 | 27.375 | 9.075
- | 34977 | 12 | Washington | 22.3 | 26.0 | 30 | 3.375 | 33.375 | 7.375
- | 34980 | 12 | Washington | 24.0 | 23.2 | 30 | 3.375 | 33.375 | 10.175
- | 34985 | 12 | Washington | 23.0 | 22.8 | 28 | 3.375 | 31.375 | 8.575
- | 34996 | 12 | Washington | 25.0 | 24.0 | 24 | 3.375 | 27.375 | 3.375
- | 35090 | 12 | Washington | 17.0 | 22.3 | 26 | 3.375 | 29.375 | 7.075
- | 35103 | 12 | Washington | 15.5 | 20.8 | 26 | 3.375 | 29.375 | 8.575
- | 35171 | 12 | Washington | 13.5 | 24.2 | 24 | 3.375 | 27.375 | 3.175
- | 35178 | 12 | Washington | 21.5 | 27.0 | 26 | 3.375 | 29.375 | 2.375
- | 35201 | 12 | Washington | 18.7 | 22.3 | 22 | 3.375 | 25.375 | 3.075
- | 35227 | 12 | Washington | 15.0 | 24.0 | 24 | 3.375 | 27.375 | 3.375
- | 35982 | 12 | Westmoreland | 44.0 | 23.0 | 24 | 3.375 | 27.375 | 4.375
Y | 36002 | 12 | Westmoreland | 26.8 | 25.0 | 24 | 3.375 | 27.375 | 2.375
- | 36130 | 12 | Westmoreland | 26.5 | 17.0 | 22 | 3.375 | 25.375 | 8.375
Y | 36168 | 12 | Westmoreland | 25.0 | 15.5 | 22 | 3.375 | 25.375 | 9.875
Y | 36207 | 12 | Westmoreland | 43.0 | 13.5 | 24 | 3.375 | 27.375 | 13.875
Y | 36228 | 12 | Westmoreland | 20.2 | 21.5 | 24 | 3.375 | 27.375 | 5.875
Y | 36230 | 12 | Westmoreland | 20.7 | 18.7 | 24 | 3.375 | 27.375 | 8.675
- | 36248 | 12 | Westmoreland | 36.0 | 15.0 | 22 | 3.375 | 25.375 | 10.375
Y | 36251 | 12 | Westmoreland | 34.0 | 44.0 | 42 | 3.375 | 45.375 | 1.375
- | 36331 | 12 | Westmoreland | 26.5 | 26.5 | 30 | 3.375 | 33.375 | 6.875
- | 36365 | 12 | Westmoreland | 15.1 | 36.0 | 34 | 3.375 | 37.375 | 1.375
Y | 36387 | 12 | Westmoreland | 31.5 | 26.5 | 28 | 3.375 | 31.375 | 4.875
- | 36389 | 12 | Westmoreland | 27.0 | 15.1 | 22 | 3.375 | 25.375 | 10.275
Y | 36431 | 12 | Westmoreland | 24.2 | 27.0 | 24 | 3.375 | 27.375 | 0.375
- | 36481 | 12 | Westmoreland | 26.4 | 26.4 | 26 | 3.375 | 29.375 | 2.975
Y | 36482 | 12 | Westmoreland | 26.7 | 31.5 | 27 | 3.375 | 30.375 | -1.125
- | 36493 | 12 | Westmoreland | 31.5 | 33.5 | 32 | 3.375 | 35.375 | 1.875
- | 36684 | 12 | Westmoreland | 33.5 | 43.6 | 40 | 3.375 | 43.375 | -0.225
Y | 36750 | 12 | Westmoreland | 32.0
- | 37037 | 12 | Westmoreland | 43.6
- | 16920 | 12 | Fayette | 24.0
- | 16923 | 12 | Fayette | 26.3
- | 16930 | 12 | Fayette | 16.8 | 189.3

## FOR RICH (hidden)
| UTILITIES01 |  | Early Completion Bridges - 2015 |  |  | 88 | EACH | 8/26 - 1397 changed to REB | OVER ROADWAY | IF "UNKNOWN", RANK AS 0.25 | [99 empty] | IF "UNKNOWN", RANK AS 0.25
|  |  |  | TBD AS OF 06/03/14 |  | 32 | EACH |  |  |  | inspection | inspection |  | inspection | [17 empty] | Bridge |  |  |  | inspection | inspection |  | inspection | [17 empty] | Bridge |  |  |  | inspection | inspection |  | inspection | [17 empty] | Bridge |  |  |  | inspection | inspection |  | inspection | [17 empty] | Bridge |  |  |  | inspection | inspection |  | inspection |  |  |  | Bridge |  |  |  | inspection | inspection |  | inspection |  |  |  | Bridge |  |  |  | inspection | inspection |  | inspection | [17 empty] | Bridge |  |  | Structure | Structure | Structure | Structure
[32 empty] | Extremity to | [24 empty] | Extremity to | [24 empty] | Extremity to | [24 empty] | Extremity to | [10 empty] | Extremity to | [10 empty] | Extremity to | [24 empty] | Extremity to |  |  | Attached | Attached | Attached | Attached
|  |  | 2 WEEK SCHEDULE |  | STRUCTURE ATTACHED UTILITY |  |  |  |  | No. of | No. of |  | Company |  | Total |  |  | 2" | 3" | 4" | 5" | 6" | 8" | 10" | 12" | 14" | 16" | 18" | 20" | 24" | Unknown | Pole/Line | In or Out | In or Out | No. of | No. of |  | Company |  | Total |  |  | 2" | 3" | 4" | 5" | 6" | 8" | 10" | 12" | 14" | 16" | 18" | 20" | 24" | Unknown | Pole/Line | In or Out | In or Out | No. of | No. of |  | Company |  | Total |  |  | 2" | 3" | 4" | 5" | 6" | 8" | 10" | 12" | 14" | 16" | 18" | 20" | 24" | Unknown | Pole/Line | In or Out | In or Out | No. of | No. of |  | Company |  | Total |  |  | 2" | 3" | 4" | 5" | 6" | 8" | 10" | 12" | 14" | 16" | 18" | 20" | 24" | Unknown | Pole/Line | In or Out | In or Out | No. of | No. of |  | Company |  | Total |  |  | Pole/Line | In or Out | In or Out | No. of | No. of |  | Company |  | Total |  |  | Pole/Line | In or Out | In or Out | No. of | No. of |  | Company |  | Total |  |  | 2" | 3" | 4" | 5" | 6" | 8" | 10" | 12" | 14" | 16" | 18" | 20" | 24" | Unknown | Pole/Line | In or Out | In or Out |  | Temporary |  |  | Grand Total Cost
[10 empty] | Relocate | Relocate | Diameter | Owner |  | Relocate | [15 empty] | Dia. | offset | of ROW Calc | of ROW | Relocate | Relocate | Diameter | Owner |  | Relocate | [15 empty] | Dia. | offset | of ROW Calc | of ROW | Relocate | Relocate | Diameter | Owner |  | Relocate | [15 empty] | Dia. | offset | of ROW Calc | of ROW | Relocate | Relocate | Diameter | Owner |  | Relocate | [15 empty] | Dia. | offset | of ROW Calc | of ROW | Relocate | Relocate | Diameter | Owner |  | Relocate |  |  | offset | of ROW Calc | of ROW | Relocate | Relocate | Diameter | Owner |  | Relocate |  |  | offset | of ROW Calc | of ROW | Relocate | Relocate | Diameter | Owner | Underground | Relocate | [15 empty] | Dia. | offset | of ROW Calc | of ROW |  | Support | Temporary |  | Aerial | Approx. Crew Cost | Aerial
|  | Early | [7 empty] | Underground | Underground | Underground | Underground | Underground | Underground | Avg. Unit Price | Total Cost | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Avg. Unit Cost | Total Cost | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground |  |  | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground |  |  | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground |  |  | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground |  |  | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground |  |  | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Underground | Relocate | across | Support | Relocate | Conflicts | Per Day | # Schedule Days | HDR Notes | Notes by Walsh
Utility |  | Completion |  | Bridge | [5 empty] | Water | Water | Water | Water | Water | Water |  |  | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Water | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary |  |  | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Sanitary | Gas | Gas | Gas | Gas | Gas | Gas | Avg. Unit Cost | Total Cost | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Oil | Oil | Oil | Oil | Oil | Oil | Avg. Unit Cost | Total Cost | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Oil | Fiber Optic | Fiber Optic | Fiber Optic | Fiber Optic | Fiber Optic | Fiber Optic | Avg. Unit Cost | Total Cost | Fiber Optic | Fiber Optic | Fiber Optic | Electric | Electric | Electric | Electric | Electric | Electric | Avg. Unit Cost | Total Cost | Electric | Electric | Electric | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Avg. Unit Cost | Total Cost | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Unspecified | Utility | waterway |  | Utility |  |  |  |  | As of 5/29/14
Clearance | Count | (Y / N) | JV # | Key | BMS # | District | County | Location | Feature Intersected | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (FEET) | (FEET) |  | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (FEET) | (FEET) |  | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (FEET) | (FEET) |  | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (FEET) | (FEET) |  | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (FEET) | (FEET) |  | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (FEET) | (FEET) |  | (EACH) | (EACH) | (INCH) | Name | Notes | (LF) |  |  | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (LF) | (FEET) | (FEET) |  | (Type - i.e. waterline) | (Y = 1, N = 0) | Required | (LF)
COORDINATED, ATTACHED | 5 | Y | 415 | 1406 | 02101300300428 | 11 | Allegheny | 1 MI. N.E. OF SR 0008 | LITTLE PINE CREEK | 1 | 1 |  |  |  | 50 | 249.45 | 12472.5 |  |  | 50 | [39 empty] | 0 | 1 |  |  |  | 50 | 120.88 | 6044 | [5 empty] | 50 | [11 empty] | 0 | 0 |  |  |  | 0 | 191.55 | 0 | [17 empty] | 0 | 0 |  |  |  | 1e-30 | 32.1 | 3.21e-29 |  |  |  | 0 | 0 |  |  |  | 1e-30 | 25.68 | 2.568e-29 |  |  |  | 0 | 0 |  |  |  | 0 | 56.12 | 0 | [17 empty] | 4" Water, 8" Gas (asbestos wrapped) | 1 | Yes | 98 | 12148.5 | 10000 | 2 | Existing gas line (asbestos wrapped) is 8' off existing bridge