## Sheet1
FMEA ID# | Process Map Element | Potential Failure Mode
84 | Hot Mix Production | Cross contamination of aggregate in stockpile
85 | Hot Mix Production | Segregation of aggregate in stockpile
86 | Hot Mix Production | Stockpile becomes contaminated
88 | Hot Mix Production | High moisture content in the delivered or stored aggregate
89 | Hot Mix Production | High variability in the gradation of delivered aggregate
90 | Hot Mix Production | Delivery truck brings wrong aggregate or it is identified incorrectly
91 | Hot Mix Production | Delivered aggregate is dumped in the wrong place
92 | Hot Mix Production | Putting the delivered PG grade in wrong tank
93 | Hot Mix Production | Contaminating asphalt cement when switching PG grade in the same storage tank
94 | Hot Mix Production | Asphalt cement delivery doesn’t arrive on time
95 | Hot Mix Production | Asphalt delivered at too high or too low a temperature (Polymer Modified)
96 | Hot Mix Production | Tank heating system fails
97 | Hot Mix Production | Temperature control system fails to control the tank temperature
98 | Hot Mix Production | Delivered RAP is contaminated
99 | Hot Mix Production | RAP stockpile run low during production
100 | Hot Mix Production | Putting the incorrect aggregate into the plant cold feed bin
101 | Hot Mix Production | Correct gradation of aggregate, but incorrect skid factor materials put into bin
102 | Hot Mix Production | (Drum/Batch) Flow from cold bin is restricted
103 | Hot Mix Production | Cold feed belt goes out of calibration (Drum/Batch)
104 | Hot Mix Production | Mechanical failure of cold feed belt to dryer (Drum/Batch)
105 | Hot Mix Production | Weighing mechanism on weigh bridge malfunctions (Drum)
106 | Hot Mix Production | Synchronization of feed belt system malfunctions – Aggregate (Drum)
107 | Hot Mix Production | Plant operator does not react properly to an alarm – Aggregate (Drum/Batch)
108 | Hot Mix Production | System monitoring devices malfunction – Aggregate (Drum/Batch)
109 | Hot Mix Production | Scalper malfunctions at cold feed bins (Drum)
110 | Hot Mix Production | Wrong screen placed in scalper (Drum)
111 | Hot Mix Production | High moisture content in the fine aggregate (Drum/Batch)
113 | Hot Mix Production | Bag House Auger Failure
114 | Hot Mix Production | Bag House Fan Failure
115 | Hot Mix Production | Bag House Holes in Bags
116 | Hot Mix Production | Bag House Cleaning System Failure
117 | Hot Mix Production | Incorrect asphalt cement drawn into delivery system
118 | Hot Mix Production | Tank valves malfunction
119 | Hot Mix Production | Asphalt delivery pump malfunctions
120 | Hot Mix Production | Asphalt delivery pump sensing system malfunctions (Drum)
121 | Hot Mix Production | Feed line heating malfunctions
122 | Hot Mix Production | (Asphalt Injection) Feed line nozzle malfunctions Drum only
123 | Hot Mix Production | Feed line purging system malfunctions
126 | Hot Mix Production | System monitoring devices malfunction - Asphalt
127 | Hot Mix Production | Asphalt storage tank runs dry
128 | Hot Mix Production | RAP crusher malfunctions
129 | Hot Mix Production | RAP crusher runs empty
130 | Hot Mix Production | RAP Scalper screen becomes worn or broken
131 | Hot Mix Production | RAP bin clogs
132 | Hot Mix Production | RAP Feed belt malfunctions
133 | Hot Mix Production | Dryer Flighting Alignment Problems
134 | Hot Mix Production | Dryer Flighting Wear
135 | Hot Mix Production | Improper Mixing Temperature
136 | Hot Mix Production | Burner Adjustment Problems
137 | Hot Mix Production | Burner Mechanical Problems
138 | Hot Mix Production | Temperature Sensing System
139 | Hot Mix Production | Drum Drive Failure
140 | Hot Mix Production | Power Failure
146 | Hot Mix Production | Mechanical Failure on Slat Conveyor
147 | Hot Mix Production | Failure of Cross Conveyor
148 | Hot Mix Production | Silo Batcher Mechanical Failure
149 | Hot Mix Production | Batcher Operator Error
150 | Hot Mix Production | Failure to Unload the Silo in a held or timely manner (Materials stored beyond approved holding time)
151 | Hot Mix Production | Silo Doors Won’t Operate
152 | Hot Mix Production | Wrong Silo is Unloaded
153 | Hot Mix Production | Failure of Silo Heating System
154 | Hot Mix Delivery | Improper sequencing of load into truck
155 | Hot Mix Delivery | Using of release agents improperly
156 | Hot Mix Delivery | Variation in temperature while loading (too high or too low)
157 | Hot Mix Delivery | Improper tarping of truck bed for the environmental conditions
158 | Hot Mix Delivery | Improper bed heating
159 | Hot Mix Delivery | Improper bed insulation
160 | Hot Mix Delivery | Delays in transporting of HMA to job site (traffic)
161 | Hot Mix Delivery | Queuing of trucks at paving paver
162 | Hot Mix Delivery | An interruption of flow of trucks to the paver (plant breakdown)
163 | Hot Mix Delivery | Inadequate planning for delivery of HMA to job site (# of trucks, route)
201 | Pavement Preparation | Surface to be paved not clean
202 | Pavement Preparation | Improper or inadequate patching
203 | Pavement Preparation | Improper sub-grade preparation (Overlay projects and shoulders)
204 | Pavement Preparation | Inadequate drainage design
164 | Hot Mix Placement | Breakdown of the Materials transfer vehicle (MTV)
165 | Hot Mix Placement | Truck Missing the hopper when dumping HMA
166 | Hot Mix Placement | Truck bumps the paver (no MTV)
167 | Hot Mix Placement | Running the hopper too low
168 | Hot Mix Placement | Hopper wings improperly used
169 | Hot Mix Placement | Running with hopper too full
170 | Hot Mix Placement | Improper heating of screed
171 | Hot Mix Placement | Screed vibration not turned on
172 | Hot Mix Placement | Improper height of materials at auger
173 | Hot Mix Placement | Auger extensions improperly used
174 | Hot Mix Placement | Improper material feed at gear box
175 | Hot Mix Placement | Improper manual adjustment of screws
176 | Hot Mix Placement | Improper use of MTV (not keeping paver moving)
177 | Hot Mix Placement | Improper function of automated controls
178 | Hot Mix Placement | Improper use or non-use of joint matcher
179 | Hot Mix Placement | Improper speed of paver (not keeping paver moving)
180 | Hot Mix Placement | Improper steering of paver
181 | Hot Mix Placement | Improper screed angle (Lead crown)
182 | Hot Mix Placement | Worn screed plate
183 | Hot Mix Placement | Improper hand work
184 | Hot Mix Placement | Physical or Chemical contamination of the asphalt mat
185 | HMA Compaction | Inadequate number of rollers
186 | HMA Compaction | Improper vibratory settings on roller
187 | HMA Compaction | Improper roller operation
188 | HMA Compaction | Mechanical failure of roller
189 | HMA Compaction | Improper operational setup of roller
190 | HMA Compaction | Rolling at improper temperature
191 | HMA Compaction | Improper rolling of joints
192 | HMA Compaction | Accommodating traffic needs
193 | HMA Compaction | Improper calibration and standardization of nuclear gauge (and testing and frequency)
194 | HMA Compaction | Improper operation of nuclear gauge (operator error)
196 | HMA Compaction | Improper number of rolling passes
197 | HMA Tack | Improper application and protection of tack coats
198 | HMA Compaction | Improper sampling methods (coring)
199 | HMA Compaction | Adverse changes in weather during paving
200 | HMA Compaction | Paving under adverse weather conditions
205 | HMA Delivery | Mechanical problem – truck leaking oil
206 | HMA Delivery | Driver not properly educated
207 | Pavement Preparation | Milling uneven
208 | Pavement Preparation | Joint location wrong
209 | Pavement Preparation | Milling depth wrong
210 | Pavement Preparation | Milling just to get millings
211 | Tack | Not waiting for tack to break
212 | Tack | Joint tack material wrong
213 | Tack | Improper tack of butt joint
214 | Tack | Improper tack of wedge joint
215 | QC | Improper sampling of loose boxes
216 | QC | Cores handled improperly
217 | QC | Sample taken in wrong location
218 | QC | Sample handled improperly
219 | QC | Variance between person taking samples
220 | QC | Conflict between sample location required and a spec that says do not take a non-representative sample. Sample location called for is not representative of the mat.
221 | QC | Size of sample box (everything over 19mm)
222 | QC | Timing of sample. Do not sample first or last load Allow equipment and plant to get up and running
223 | QC | Sample misidentification
224 | QC | Sample results not received in a timely manner This could be for a whole list of reasons
225 | QC | Not taking adequate companion samples
226 | QC | Core Samples Many of the same FEMA’s from the boxes apply plus These additional ones Mishandling of cores prior to packaging
227 | QC | Correlation between nuclear gage results and actual core results Not known
228 | QC | Core not packaged in a manner to prevent damage during shipment and storage
229 | QC | Field QC placing mix with wrong mix design
230 | QC | Temperature out of spec.
231 | QC | Failure of QC tech to make necessary corrections or notify Appropriate person of problems
232 | QC | Tech notifies appropriate person of problem and no corrective action is taken.
233 | QC | Placing traffic on mat too quickly
235 | QC | Using incorrect data to determine nuclear gage readings
236 | QC | Rollers failing to adhere to prescribed rolling pattern
237 | QC | Breakdown in communication between QC tech, Plant and paving super
238 | QC | Improper monitoring of joint construction
239 | QC | QC tech provides inadequate instructions as to Setting of amplitudes and frequencies of rollers As well instructions as to temperature windows and speeds
240 | QC | Not monitoring above failure mode
241 | QC | Insufficient nuclear readings
242 | QC | QC tech not having sufficient authority to direct quality aspects of operation
243 | QC | Gage out of calibration or daily standardization done incorrectly
244 | QC | Tech. using gage they’re not familiar with
245 | QC | Failure to account for underlying base conditions
246 | QC | Failure to address changing weather conditions to insure proper placement and compaction of mix as well as taking appropriate action when weather forces suspension of operations.
247 | QC | Failure to address mat contamination
248 | QC | Failure to properly clean and maintain nuclear gage
249 | QC | Failure of thermometers to operate properly because of calibration or breakage